## Front
Name: Jack Keenan
Module: Principles of Measurement and Estimating
Module code: ACB5003
Elemental cost Plan

## Information Used
Information Used & Assumptions
1 | Information Used
Spring Design Drawings;
Proposed Ground Floor Plan
Proposed First Floor Plan
Proposed Second Floor Plan
Proposed Third Floor Plan
Proposed Fourth Floor Plan
Proposed Elevations 2316 (02) 300
Proposed Elevations 2316 (02) 301
Proposed Views towards the development
Proposed Site Plan
Information as provided by Coastal;
Multi-Utility Infrastructure Feasibility Study
2 | General assumptions;
FF&E is excluded unless specifically identified within the cost plan.
Costs are based upon the information as provided.
We have assumed a project bank account will not be required for this scheme.
We have assumed that the area of works will be decanted for the project. No allowance is made for throughways or dealing with building occupants.
The exact nature of specification for internal doors, screens, folding partitions and finishes is assumed.
All costs are provisional awaiting design development.
3 | General notes and exclusions;
All included costs are subject to variation following design development.
Risks associated with BREXIT are not considered.
A risk allowance of 10% is included for this estimate.
VAT is excluded from the estimate.
Works will be undertaken in a single phase.

## Summary Original
Cost Plan for UWTSD Library
NRM 1 phaseologies
Elemental Cost Plan |  |  |  | Jack Keenan - 1908062
Module: Principles of Measurement and Estimating
Module Code: ACB5003
Elements in red are NRM1 Phraseologies
Cost
Building works estimate |  |  |  |  | 2189
| Group element 0 | #REF! | #REF! |  | #REF!
| Group element 1 | SUBSTRUCTURE | 533180 |  | 243.5724
| Group element 2 | SUPERSTRUCTURE | 3618185.16 |  | 1652.8941
| Group element 3 | INTERNAL FINISHES | 249447.35 | 0 | 113.9549
| Group element 4 | FITTINGS AND FURNISHINGS | 0 |  | 0
| Group element 5 | Internal Services | 1560000 | 0 | 712.6542 | #REF!
| Group element 8 | EXTERNAL WORKS | 0 |  | 0
| Group element 9 | MAIN CONTRACTOR'S PRELIMINARIES | 814144.8765 |  | 371.9255
Works cost estimate (sub total A) |  |  | #REF! | 0
Project design team fees and other development costs (sub total B)
0
Base cost estimate A + B (sub total C) |  |  | #REF!
| Group element 13 | Risk allowance @
Total Risk allowances (sub total D) |  |  | 0
0
Total Construction Cost (C + D) |  |  | #REF!
0
0
0
0
0
0
0
0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0

## NRM1 CP template
Cost Plan for UWTSD Library
NRM 1 phaseologies
Elemental Cost Plan |  |  | Jack Keenan - 1908062
Module: Principles of Measurement and Estimating
Module Code: ACB5003
Elements in red are NRM1 Phraseologies
Ref. | Element | Quantity / unit |  |  | Rate | Sub-Total | Group-Total | Notes
1 | SUBSTRUCTURE | [5 empty] | 533180
1.1 | Foundations
| Ground floor slab including substructure blockwork, shutter course blockwork, insulation, DPM and concrete slab. |  | 1442 | m2 | 190 | 273980
| Reinforced concrete piles |  | 1728 | m3 | 150 | 259200 |  | Piles at an average depth of 18 to 20 meters. Assumsed diameter is 750mm
2 | SUPERSTRUCTURE | [5 empty] | 3618185.16
2.1 | Frame
| Concrete Frame including concrete columns and beamns |  | 15700 | m2 | 150 | 2355000
Scaffolding
| Scaffolding in conjunction with the above works |  | 16632 | m2 | 0 |  |  | Scaffolding has been included within the prelimns.
2.2 | Upper Floors
| FF Concrete Floor |  | 854.067 | m2 | 140 | 119569.38
| SF Concrete Floor |  | 955.152 | m2 | 140 | 133721.28
2.3 | Roof
Roof structure - pitched roofs: details, including design loads (kN/M2), spans (m) and angle of pitch (degtrees). To be stated
| Construction of new pitched roof - metal standing seam roof covering |  | 1321 | m2 | 90 | 118890
| Solar PV panels |  | 185 | m2 | 725 | 134125 |  | Solar PV panels are placed on south facing side of the building only.
| PPC Aluminium roof light |  | 4 | no | 2244.6 | 8978.4 |  | Roof lights are on the north facing side of the building.
| Allowance for gutters |  | 95.4 | item | 26 | 2480.4
| Allowance for down pipes |  | 44 | item | 21 | 924
| Allowance for trims and flashings |  | 0 | item |  | 0
2.4 | Stairs & Ramps
| Precaste concrete stairs ground to second floor, planting deck, including finshes, balustrading and hand railing. |  | 2 | no | 22000 | 44000
2.5 | External Walls
External walls: Details to be stated.
| Cladding to elevations |  | 294 | m2 | 54 | 15876 |  | Rainscreen aluminium cladding
| External Facing Brickwork |  | 408 | m2 | 180 | 73440
2.6 | Windows and external doors
Windows : details, including overall size of opening (mm) to be stated.
Windows
| Window Type 1 |  | 4.4 | m2 | 490 | 2156
| Window Type 2 |  | 45.64 | m2 | 490 | 22363.6
| Window Type 2a |  | 16.23 | m2 | 490 | 7952.7
| Window Type 3 |  | 9.78 | m2 | 490 | 4792.2
| Window Type 3a |  | 3.26 | m2 | 490 | 1597.4
| Window Type 4 |  | 3.26 | m2 | 490 | 1597.4
| Window Type 5 |  | 30.73 | m2 | 490 | 15057.7
| Window Type 6 |  | 13.17 | m2 | 490 | 6453.3
| Window Type 7 |  | 45.06 | m2 | 490 | 22079.4
Curtain Wall System
| Total area |  | 760.58 | m2 | 450 | 342261
| Turnstill doors to entrance screens |  | 2 | nr | 5000 |  |  | Rate to include for power supply and operator to turnstill doors also.
External doors: details, including type, number of door leaves (nr) size of each door leaf (mm) and overall size of opening (mm) to be stated.
External doors
| External Door Type 1 |  | 4 | no | 1900 | 7600 |  | External doors include ones that are not included in the curtain wall areas.
2.7 | Internal walls
Internal walls:details, including thickness, to be stated
| 140mm block wall |  | 1498 | m2 | 65 | 97370 |  | Walls surronding the liftshafts and stairwells are included in the concrete frame element.
2.8 | Internal doors & screens
Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated.
Fire resisting doors: details, including type, number of door leaves (nr), fire rating (hours), size of each door leaf (mm), and overall size of opening (mm), to be stated.
| Internal door Type 1 |  | 19 | Nr | 925 | 17575
| Internal door Type 2 |  | 13 | Nr | 1125 | 14625
| Internal door Type 4 |  | 10 | Nr | 1125 | 11250
| Internal door Type 5 |  | 9 | Nr | 1600 | 14400
| Internal door Type 5b |  | 5 | Nr | 1600 | 8000
| Internal door Type 5c |  | 2 | Nr | 1600 | 3200
| Internal door Type 6 |  | 7 | Nr | 1550 | 10850
3 | INTERNAL FINISHES | [5 empty] | 249447.35
3.1 | Wall finishes
Finishes to walls and columns: details to be stated.
| Dot and Dab Walls including plasterboard and universal compound adhesive |  | 4487 | m2 | 8.31 | 37286.97
| Skim Finish to walls - 3mm skim coat |  | 4487 | m2 | 6.16 | 27639.92
| Paint finish - 1 mist coat and 2 coats of emulsion |  | 4487 | m2 | 9 | 40383
| Skirtings - Supply and fit of 3inch bullnose skirting |  | 1282 | lm | 16 | 20512
| Skirting - Decoration of skirting (1 primer and 2no gloss) |  | 1282 | lm | 11.86 | 15204.52
3.2 | Floor finishes | [6 empty] | Vinyl floors to bathrooms/stairwell areas. Timber laminate floor to downstairs area and carpet everywhere else.
Finishes to floors: details to be stated.
| Vinyl to floors |  | 193.99 | m2 | 100 | 19399
| Carpet Floor covering |  | 2105.28 | m2 | 35 | 73684.8
| Laminate timber flooring |  | 289.38 | m2 | 53 | 15337.14
3.3 | Ceiling finishes
| Finishes to ceilings: details to be stated. | [6 empty] | Concrete Ceilings with exposed surfaces. Rate for slabs will cover this.
4 | FITTINGS AND FURNISHINGS | [5 empty] | 0
4.1 | General fittings, furnishings and equipment
Kitchen units: details to be stated.
| Toilets |  | 0 | no | 0 | 0
5 | Internal Services | [5 empty] | 1560000
5.1 | mechanical and electrical services: including heating, air treatment, ventilation, power, lighting, protective installations, communications and special installations. |  | 2600 | m2 | 530 | 1378000 |  | Internal finishes have been shown as a lump sum.
| Statutory signage |  | 1 | no | 5600 | 5600
| Builders work in conjunction with the works. |  | 2600 | no | 14 | 36400
5.1 | Lift and Conveyor installations
Passenger lifts: details, including capacity (i.e. number of persons), speed (in m/sec), number of doors (nr), door heights and number of levels serviced (nr), to be stated.
| Passenger lift |  | 2 | no | 70000 | 140000 |  | 8 person lift - Operating from ground to second floor.
5.11 | Fire and lightning protection - Included above
| Fire alarms |  | 0 | no | 0 | 0 |  | Included within the M&E cost.
5.12 | Communication, security and control systems - Included above
| Telecommunication systems: details of each type of system to be stated. | [6 empty] | Included within the M&E cost.
Data transmission systems: details of each type of system to be stated.
8 | EXTERNAL WORKS | [5 empty] | 0 | External services have been worked out as a lump sum.
8.7 | External Services
Electrical
Connections to statutory undertaker's electricity main: details to be stated.
| Main electrical supply to building |  | 0 | item | 0 | 0 |  | All included within M&E Cost.
| Disconnections |  | 0 | item | 0 | 0
| Electrical substation |  | 0 | item | 0 | 0
Water
Connections to statutory undertaker's water main: details to be stated.
| Mains layout cost |  | 0 | item | 0 | 0
| Service costs |  | 0 | item | 0 | 0
| Water/sewerage infrastructure costs |  | 0 | item | 0 | 0
| Disconnections of water mains |  | 0 | item | 0 | 0
Gas
Connections to statutory undertaker's gas main: details to be stated.
| Works Allowance |  | 0 | item | 0 | 0
9 | MAIN CONTRACTOR'S PRELIMINARIES | [5 empty] | 814144.8765
| Main contractors preliminaries & OHP |  | 15 | % | 5427632.51 | 814144.8765
| SECTION SUB-TOTAL | [5 empty] | 6774957.3865