Project Management - Waterfall

Stage 1 – Research & Diagnosis

- External analysis

- Internal analysis

- Evidence gathering

- Literature review

Stage 2 – Strategic Options

- Develop at least three coherent options

- Test alignment with industry realities

- Compare feasibility

Stage 3 – Financial & Operational Testing

- Basic financial logic

- Resource implications

- Risk identification

- Implementation feasibility

Stage 4 – Implementation Plan

- Timeline

- Governance

- Risk mitigation

- Leadership implications

Stage 5 – Presentation & Rehearsal

- Slide consolidation

- Visual refinement

- Executive summary

- Board-level questioning practice

Project Management – Agile

Sprint 1 (Weeks - ) – Initial Hypothesis

Goal: Develop an early strategic direction quickly.

Tasks:

- Rapid external analysis

- Identify likely strategic themes

- Draft 2–3 early hypotheses

- Create rough slide outline

End of Sprint Review:

- Are we solving the right problem?

- What assumptions need testing?

Sprint 2 (Weeks - ) – Evidence & Testing

Goal: Stress-test early ideas.

Tasks:

- Deeper research

- Challenge assumptions

- Refine strategic options

- Identify financial implications

Sprint Review:

- Does evidence support our direction?

- Should we pivot?

Sprint 3 (Weeks - ) – Financial & Risk Refinement

Goal: Make the strategy robust.

Tasks:

- Financial modelling

- Risk register development

- Sustainability alignment

- Slide prototype v1

Sprint Review:

- Is the strategy coherent?

- Does finance contradict our idea?

Sprint 4 (Weeks - ) – Presentation Iteration

Goal: Improve communication.

Tasks:

- Draft slides

- Practice explaining logic

- Identify weak arguments

- Tighten narrative

Sprint Review:

- Is this board-ready?

- Are we persuasive?

Sprint 5 (Weeks - ) – Final Refinement

Goal: Polish and strengthen.

Tasks:

- Improve visuals

- Strengthen weak sections

- Anticipate board questions

- Run timed rehearsals

Sprint Review:

- What would the board attack first?

- Fix it.