PG1 - FULL RESEARCH PROPOSAL

This form is to be completed by both the student and supervisory team within THREE months for full-time students and SIX months for part time students, after the commencement of the research degree or following progression to Part Two of your course. Once complete, submit this form via the MyTSD Doctoral College Portal at (https://mytsd.uwtsd.ac.uk). This document is also available in Welsh.

Student Details

| Student Family / Surname: |  | Mendis |  |
| --- | --- | --- | --- |
| Student Given / First name: |  | Nigamuni Yohan Birendra |  |
| Student Number |  | 2218843 |  |
| Start Date | 10/2022 | End Date | 10/2028 |

| PhD by Research | PhD Practice Based | PhD by Published Works | Professional Doctorate (including DBA, DProf, Ed D) | MPhil by Research | MPhil Practice Based |
| --- | --- | --- | --- | --- | --- |
| ☐ | ☐ | ☐ | ☒ | ☐ | ☐ |
| MA by Research | MSc by Research | MRes |  |  |  |
| ☐ | ☐ | ☐ |  |  |  |

Proposed Research

Current Proposed Title (20 / 30 words):

Faculty and Institutional Readiness for AI Integration: A case study of UWTSD Birmingham

Background & Context (approx. 500 words)

The integration of artificial intelligence (AI) in higher education is reshaping the teaching and learning environment. AI's ability to enhance educational outcomes, improve administrative efficiency, and offer personalised learning experiences drives this shift (Popenici & Kerr, 2017; Zawacki-Richter et al., 2019; Crompton, and Burke, 2023). However, faculty and institutional readiness for AI adoption varies widely across different contexts (Dwivedi et al., 2021; Jin et al., 2024). This proposal focuses on the University of Wales Trinity Saint David (UWTSD) Birmingham, exploring the preparedness of its faculty and institutional systems to integrate AI effectively. Located in a culturally rich and academically vibrant city, UWTSD Birmingham offers a dynamic and diverse learning environment (UWTSD, 2024). The university is known for its innovative course offerings, particularly in areas such as business, computing, and health and social care. Its emphasis on flexible learning options and equal access to education makes it a suitable setting for investigating AI integration in higher education (UWTSD, 2024). A key factor in successful AI integration is faculty readiness. In a recent study by Harris (2024), a survey of 162 faculty members from various disciplines revealed that while many are familiar with AI, significant gaps in adoption and readiness persist. Faculty concerns include the impact of AI on job security, the need for professional development, and the ethical considerations surrounding AI in education. Similar findings from other studies underscore the necessity of targeted training and support to better prepare faculty for the use of AI in their teaching practices (Eager, and Brunton, 2023; Crompton, and Burke, 2023). Institutional readiness refers to the establishment of the infrastructure, policies, and support mechanisms required to adopt AI technologies (Chugh, et. al., 2023; Jin et. al., 2024). Gonzalez et al. (2024) found that institutions with strong strategic planning and policy frameworks, especially those prioritising accessibility, diversity, equity, and inclusion (DEI), tend to integrate AI more successfully. UWTSD Birmingham's focus on breaking down barriers to education and promoting equality aligns with these best practices, making it well-positioned for AI integration. Data from the EDUCAUSE Review (2024) indicates that institutions with comprehensive AI strategies see higher levels of faculty engagement and student satisfaction. Universities that have adopted AI-driven tools for personalised learning, for instance, report improved student retention rates and academic performance (Dahri, 2024). Thus, for UWTSD Birmingham, the potential benefits of AI are considerable, especially given the institution’s dedication to innovative and flexible learning methods. The successful integration of AI in higher education hinges on both faculty and institutional readiness (Richardson et al., 2024; Jin, et al., 2024). UWTSD Birmingham, with its diverse academic offerings and commitment to inclusive education (UWTSD, 2024), provides an ideal case study for examining these readiness factors. This research will investigate faculty perspectives, institutional strategies, and the potential advantages of AI, contributing to a broader understanding of AI's role in transforming higher education.

Aims and Objectives (approx.. 250 – 500 words)

Aim This research will explore the factors that influence the readiness and attitudes of faculty and institutions towards integrating AI to support students. It aims to identify the main challenges, opportunities, and best practices for implementing AI in educational settings. Research Objectives 1. Investigate the factors which affects the readiness of institutions for AI integration. 2. Evaluate the knowledge, attitudes, and willingness of the key stakeholders to adopt AI technologies in their teaching practices. 3. Identify the main challenges and facilitators that impact the successful adoption of AI. 4. Provide recommendations for institutions to enhance their readiness and effectively integrate AI into their educational practices. Research Questions 1. What are the factors that affect institution readiness for AI? 2. What are the attitudes and perceptions of faculty towards the use of AI in education? 3. What are the main facilitators and barriers to adopting AI in the context of UWTSD Birmingham? 4. What best practices can be identified from institutions that have successfully integrated AI? Justifications The integration of artificial intelligence (AI) into higher education institutions presents significant opportunities for enhancing educational outcomes, operational efficiency, and student engagement (Cunningham-Nelson et al., 2019; Okonkwo and Ade-Ibijola, 2021; Crompton and Burke, 2023). Many studies highlight key factors include management support, staff capacity, regulatory environment, and cooperation (Alshahrani et al., 2022). Additionally, relative advantage, compatibility, and complexity of AI technologies play significant roles (Rogers, 2003). It is important to assess these factors to develop tailored strategies that address specific needs and barriers, ensuring a smoother transition to AI-enhanced educational environments. However, the successful adoption of AI technologies requires a thorough examination of both faculty readiness and institutional infrastructure. (Miao, et al., 2021). This study will explore the readiness of the University of Wales Trinity Saint David (UWTSD) Birmingham to integrate AI into its educational framework. Given the rapid advancements in AI and its transformative potential, it is crucial to assess the preparedness (Zawacki-Richter et al., 2019). Additionally, understanding institutional readiness will provide insights into the organisational support and resources necessary for effective AI adoption (Gleason, 2018). Identifying the challenges and facilitators is essential for overcoming barriers to AI adoption. Common challenges include data management issues, talent shortages, and integration with legacy systems (Bughin et al., 2018). Facilitators, on the other hand, include strategic alignment, resource availability, and organisational culture (Westerman et al., 2014). Addressing these challenges and leveraging facilitators can significantly enhance the likelihood of successful AI adoption in educational institutions. Furthermore, recent studies suggests enhancing readiness and effectively integrate AI, institutions should focus on several key areas. Namely; - Promoting AI literacy among educators and students (Luckin et al., 2016). - Establishing responsible AI guidelines to ensure ethical use (Floridi et al., 2018). - Providing professional development support to build AI-related skills (Holmes et al., 2019). - Fostering collaboration between educators, policymakers, and technologists (Selwyn, 2019). - Investing in AI research and development to stay ahead of technological advancements (Luckin et al., 2016). By evaluating similar factors, this study aims to propose recommendations which can create a supportive environment that facilitates the successful integration of AI into educational practices, ultimately enhancing teaching and learning outcomes.

Proposed plan of work including timetable

Sequence; Milestone/Activity; Responsible; Start Date; End Date; Duration. 1; Submission of PG1 (Full Research Proposal); Yohan Mendis; 1-Nov-2024; 11-Nov-2024; 11 days. 2; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 12-Nov-2024; 12-Nov-2024; 1 day. 3; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 13-Nov-2024; 12-Dec-2024; 30 days. 4; Literature Review (Complete Draft); Yohan Mendis; 13-Nov-2024; 12-Mar-2025; 121 days. 5; Approval-in-Principle; RDC; 13-Nov-2024; 28-Nov-2024; 16 days. 6; Submission of PG2 (Ethics Approval); Yohan Mendis; 1-Dec-2024; 15-Dec-2024; 15 days. 7; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 16-Dec-2024; 14-Jan-2025; 30 days. 8; Ethical Approval; RDC; 16-Dec-2024; 31-Dec-2024; 16 days. 9; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-Jan-2025; 30-Jan-2025; 30 days. 10; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 31-Jan-2025; 11-Feb-2025; 12 days. 11; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 12-Feb-2025; 13-Mar-2025; 30 days. 12; Methodology; Yohan Mendis; 13-Mar-2025; 11-Jun-2025; 91 days. 13; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 12-Jun-2025; 11-Jul-2025; 30 days. 14; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 12-Jul-2025; 10-Aug-2025; 30 days. 15; Data Collection 1; Yohan Mendis; 11-Aug-2025; 9-Sep-2025; 30 days. 16; Data Analysis 1; Yohan Mendis; 10-Sep-2025; 22-Sep-2025; 13 days. 17; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 23-Sep-2025; 6-Oct-2025; 14 days. 18; Annual Progress Review; Supervisors/ Yohan Mendis; 7-Oct-2025; 6-Nov-2025; 31 days. 19; Data Analysis 1 (Contd); Yohan Mendis; 7-Nov-2025; 19-Nov-2025; 13 days. 20; Data Collection 2; Yohan Mendis; 20-Nov-2025; 15-Dec-2025; 26 days. 21; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 16-Dec-2025; 14-Jan-2026; 30 days. 22; Data Analysis 2; Yohan Mendis; 15-Jan-2026; 28-Feb-2026; 45 days. 23; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-Mar-2026; 31-Mar-2026; 31 days. 24; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-Apr-2026; 30-Apr-2026; 30 days. 25; Literature Review (Final Version); Yohan Mendis; 1-May-2026; 30-Jul-2026; 91 days. 26; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-Aug-2026; 30-Aug-2026; 30 days. 27; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-Sep-2026; 30-Sep-2026; 30 days. 28; Discussion and Findings 1; Yohan Mendis; 1-Oct-2026; 30-Dec-2026; 91 days. 29; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-Jan-2027; 30-Jan-2027; 30 days. 30; Pre-Book Proof Reading for May 2027 and July 2027; Yohan Mendis; 1-Feb-2027; 30-Apr-2027; 90 days. 31; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-May-2027; 30-May-2027; 30 days. 32; Discussion and Findings 2; Yohan Mendis; 1-Jun-2027; 30-Aug-2027; 91 days. 33; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-Sep-2027; 30-Sep-2027; 30 days. 34; Conclusion; Yohan Mendis; 1-Oct-2027; 30-Nov-2027; 61 days. 35; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-Dec-2027; 30-Dec-2027; 30 days. 36; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-Jan-2028; 30-Jan-2028; 30 days. 37; Annual Progress Review; Supervisors/ Yohan Mendis; 1-Feb-2028; 28-Feb-2028; 28 days. 38; Introduction; Yohan Mendis; 1-Mar-2028; 30-Apr-2028; 61 days. 39; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-May-2028; 30-May-2028; 30 days. 40; Abstract; Yohan Mendis; 1-Jun-2028; 30-Jun-2028; 30 days. 41; Progress Monitoring and Submission of PG4; Supervisors/ Yohan Mendis; 1-Jul-2028; 30-Jul-2028; 30 days. 42; Footnotes, Appendices and References; Yohan Mendis; 1-Aug-2028; 30-Aug-2028; 30 days. 43; Progress Monitoring and Submission of PG4 – Notify Supervisory Team of Intention to Submit; Supervisors/ Yohan Mendis; 1-Sep-2028; 30-Sep-2028; 30 days. 44; Editing and Proof Reading (First Run); Yohan Mendis/ Proof Reader; 1-Oct-2028; 30-Oct-2028; 30 days. 45; Progress Monitoring and Submission of PG4 – Request Approval to Submit from Supervisory Team; Supervisors/ Yohan Mendis; 1-Nov-2028; 30-Nov-2028; 30 days. 46; Submission of Thesis; Yohan Mendis; 1-Dec-2028; 31-Dec-2028; 31 days.

Proposed methodology (approx. 500 words):

Philosophical Approach This research proposes to adopts a mixed-methods approach underpinned by pragmatism. Pragmatism is chosen because it focuses on practical solutions to research problems and values both qualitative and quantitative methods to understand complex phenomena (Creswell and Plano Clark, 2017). Pragmatism allows the researcher to use the most suitable methods to address the research questions, providing a comprehensive understanding of the readiness of institutions for AI integration and the attitudes of stakeholders. Methods The study will begin with library-based research to conduct an extensive literature review. This involves systematically searching academic databases, journals, books, and other scholarly sources to gather existing knowledge on AI integration in education. The literature review will help identify key themes, gaps in the current research, and theoretical frameworks that will guide the study. This method is justified as it provides a solid foundation for understanding the current state of knowledge and identifying areas that require further investigation (Booth, Sutton and Papaioannou, 2016; Hart, 2018). Surveys will be used to gather quantitative data, enabling the discernment of overall trends and interrelationships among stakeholders’ attitudes, perceptions, expectations, and concerns. This method involves designing and distributing structured questionnaires to a broad sample of educators, administrators, and policymakers. Surveys are justified as they allow for the collection of data from a large number of respondents, providing a broad overview of the stakeholders’ views on AI integration (Creswell and Creswell, 2018). Semi-structured interviews will be conducted with selected stakeholders to delve deeper into their perspectives on the relative advantage, compatibility, complexity, trialability, and observability of the adoption of AI tools in the case of UWTSD Birmingham. This qualitative method involves designing interview guides, recruiting participants, and conducting in-depth interviews either in-person or virtually. Semi-structured interviews are justified as they provide rich, detailed insights into the stakeholders’ experiences and perceptions, which are essential for understanding the nuances of AI integration (Kvale and Brinkmann, 2009). Data analysis will involve both qualitative and quantitative techniques. Quantitative data from surveys will be analysed using statistical methods to identify trends and correlations. Qualitative data from interviews, surveys, and observations will be analysed using thematic analysis to identify key patterns and themes. This method is justified as it allows for the integration of different types of data, providing a more complete understanding of the research problem (Braun and Clarke, 2006). Sampling Method A non-probability purposive sampling method will be adopted, selecting respondents with a sound understanding of the research questions (Denscombe, 2010; Creswell and Creswell, 2018). This approach ensures that the sample is representative of the target population and that the data collected is relevant and insightful. The sample size will reflect the target population for the research (Easterby-Smith et al., 2021; Kumar, 2019). Ethical Considerations Ethical procedures will be observed to ensure research integrity, and ethical approval will be obtained before commencing data collection. An information sheet and consent form will be sent to respondents in advance, explaining their rights regarding voluntary involvement and withdrawal. All communication and documents will be kept confidential, data collected will be securely stored and encrypted, and the identities of respondents will be anonymised in compliance with GDPR and relevant data protection regulations. By employing these methods, the research aims to provide a comprehensive understanding of the factors affecting AI integration in educational institutions and develop actionable recommendations to enhance readiness and adoption.

Introductory bibliography:

Alshahrani, A., Ahmed, E., & Ward, R. (2022). Factors influencing the adoption of AI in higher education. Journal of Educational Technology, 45(3), pp. 123-135. Booth, A., Sutton, A. and Papaioannou, D. (2016). Systematic Approaches to a Successful Literature Review. 2nd ed. London: SAGE. Braun, V. and Clarke, V. (2006). Using thematic analysis in psychology. Qualitative Research in Psychology, 3(2), pp. 77-101. Bughin, J., Hazan, E., Ramaswamy, S., Chui, M., Allas, T., Dahlström, P., Henke, N. and Trench, M. (2018). Artificial Intelligence: The Next Digital Frontier?. McKinsey Global Institute. Cambra-Fierro, J.J., Blasco, M.F., López-Pérez, M.E.E. and Trifu, A., (2024). ChatGPT adoption and its influence on faculty well-being: An empirical research in higher education. Education and Information Technologies, pp.1-22. Chugh, R., Turnbull, D., Cowling, M.A., Vanderburg, R. and Vanderburg, M.A., (2023). Implementing educational technology in Higher Education Institutions: A review of technologies, stakeholder perceptions, frameworks and metrics. Education and Information Technologies, 28(12), pp.16403-16429. Creswell, J.W. and Creswell, J.D. (2018). Research Design: Qualitative, Quantitative, and Mixed Methods Approaches. 5th ed. Thousand Oaks, CA: SAGE. Creswell, J.W. and Plano Clark, V.L. (2017). Designing and Conducting Mixed Methods Research. 3rd ed. Thousand Oaks, CA: SAGE. Crompton, H. and Burke, D., (2023). Artificial intelligence in higher education: the state of the field. International Journal of Educational Technology in Higher Education, 20(1), p.22. Cunningham-Nelson, S. et al. (2019) A Review of Chatbots in Education: Practical Steps Forward. Available at: https://www.messenger.com/t/LouisVuitton. Dahri, N.A., Yahaya, N., Al-Rahmi, W.M., Vighio, M.S., Alblehai, F., Soomro, R.B. and Shutaleva, A., (2024). Investigating AI-based academic support acceptance and its impact on students’ performance in Malaysian and Pakistani higher education institutions. Education and Information Technologies, pp.1-50. Davis, F.D. (1989). Perceived usefulness, perceived ease of use, and user acceptance of information technology. MIS Quarterly, 13(3), pp. 319-340. Denscombe, M. (2010). The Good Research Guide: For Small-Scale Social Research Projects. 4th ed. Maidenhead: Open University Press. Eager, B. and Brunton, R., (2023). Prompting higher education towards AI-augmented teaching and learning practice. Journal of University Teaching and Learning Practice, 20(5). Floridi, L., Cowls, J., Beltrametti, M., Chatila, R., Chazerand, P., Dignum, V., Luetge, C., Madelin, R., Pagallo, U., Rossi, F. and Schafer, B. (2018). AI4People—An ethical framework for a good AI society: Opportunities, risks, principles, and recommendations. Minds and Machines, 28(4), pp. 689-707. Gleason, N. W. (2018). Higher Education in the Era of the Fourth Industrial Revolution. Singapore: Palgrave Macmillan. Gonzalez, L., O’Neil-Gonzalez, K., Eberhardt-Alstot, M., McGarry, M., & Van Tyne, G. (2024). Leveraging Generative AI for Inclusive Excellence in Higher Education. EDUCAUSE Review. Available at: https://er.educause.edu/articles/2024/8/leveraging-generative-ai-for-inclusive-excellence-in-higher-education [Accessed 1 Oct. 2024]. Grix, J. (2002). Introducing students to the generic terminology of social research. Politics, 22(3), pp. 175-186. Harris, P.T., (2024). Faculty Perspectives Toward Artificial Intelligence in Higher Education (Doctoral dissertation, Middle Georgia State University). Hart, C. (2018). Doing a Literature Review: Releasing the Research Imagination. 2nd ed. London: SAGE. Holmes, W., Bialik, M., & Fadel, C. (2019). Artificial Intelligence in Education: Promises and Implications for Teaching and Learning. Boston: Center for Curriculum Redesign. Jin, Y., Yan, L., Echeverria, V., Gašević, D. and Martinez-Maldonado, R., (2024). Generative AI in Higher Education: A Global Perspective of Institutional Adoption Policies and Guidelines. arXiv preprint arXiv:2405.11800. Kvale, S. and Brinkmann, S. (2009). InterViews: Learning the Craft of Qualitative Research Interviewing. 2nd ed. Thousand Oaks, CA: SAGE. Luckin, R., Holmes, W., Griffiths, M., & Forcier, L.B. (2016). Intelligence Unleashed: An Argument for AI in Education. Pearson. Miao, F., Holmes, W., Huang, R., & Zhang, H. (2021). AI and education: Guidance for policymakers. UNESCO Publishing: France. http://bitly.ws/L4UQ Morgan, D.L. (2007). Paradigms lost and pragmatism regained: Methodological implications of combining qualitative and quantitative methods. Journal of Mixed Methods Research, 1(1), pp. 48-76. Okonkwo, C.W. and Ade-Ibijola, A. (2021) ‘Chatbots applications in education: A systematic review’, Computers and Education: Artificial Intelligence, 2, p. 100033. Available at: https://doi.org/https://doi.org/10.1016/j.caeai.2021.100033 Popenici, S.A. and Kerr, S., (2017). Exploring the impact of artificial intelligence on teaching and learning in higher education. Research and practice in technology enhanced learning, 12(1), p.22. Richardson, E., Gordon, J., Conklin, S., Barreto, D. and Ginnetti, R., (2024). Artificial Intelligence in Higher Education: Faculty Perceptions of Integration and Other Considerations. UNC System Learning and Technology Journal, 2(1). Rogers, E.M. (2003). Diffusion of Innovations. 5th ed. New York: Free Press. Selwyn, N. (2019). Should robots replace teachers? AI and the future of education. British Journal of Educational Technology, 50(6), pp. 1373-1384. Teo, T. (2011). Factors influencing teachers’ intention to use technology: Model development and test. Computers & Education, 57(4), pp. 2432-2440. University of Wales Trinity Saint David (UWTSD). (2024). Institute of Inner City Learning. Available at: https://www.uwtsd.ac.uk/about/our-institutes/institute-inner-city-learning [Accessed 1 Oct. 2024] Westerman, G., Bonnet, D., & McAfee, A. (2014). Leading Digital: Turning Technology into Business Transformation. Harvard Business Review Press. Zawacki-Richter, O., Marín, V. I., Bond, M., & Gouverneur, F. (2019). Systematic review of research on artificial intelligence applications in higher education. International Journal of Educational Technology in Higher Education, 16(1), 1-27.

Facilities and resources available for the investigation: please indicate if you expect to need any special resources

To conduct this study, several permissions will be required to access the necessary facilities and resources. These permissions ensure that the research can be carried out effectively and ethically, and that all relevant stakeholders are informed and supportive of the research activities. Institutional Access Educational Institutions: Permission will be needed from the administration of the University of Wales Trinity Saint David (UWTSD) Birmingham to conduct research within their facilities. This includes access to classrooms, meeting rooms, and other relevant spaces where observations and interviews will take place. Libraries and Archives: Access to university libraries and archives will be essential for conducting the literature review and accessing academic resources. Permission from the library administration may be required to use certain restricted resources or special collections. Ethical Approval Ethics Committee: Approval from the university’s ethics committee will be necessary to ensure that the research complies with ethical standards. This includes submitting an ethics application detailing the research objectives, methods, and how participant confidentiality and data protection will be maintained. Participant Access Stakeholders: Permission from individual participants, including educators, administrators, and policymakers, will be required. This involves obtaining informed consent from all participants, ensuring they understand the purpose of the research, their role, and their rights, including the right to withdraw at any time. Data Access Institutional Data: Access to institutional data, such as records of AI implementation, training materials, and other relevant documents, will be necessary. Permission from the relevant departments or data custodians within the institution will be required to access and use this data. Visual Data: Permission to collect and use visual data, such as photographs and videos, within the institution will also be needed. This includes obtaining consent from individuals who may appear in the visual data. Technical Resources IT and Technical Support: Access to the institution’s IT resources, such as computers, software, and internet access, will be necessary for conducting online research, data analysis, and storing research data securely. Permission from the IT department may be required to ensure that the necessary technical support and resources are available. External Resources External Databases and Journals: Access to external academic databases and journals will be essential for the literature review. This may involve obtaining subscriptions or permissions from external publishers or database providers. By securing these permissions, the researcher can ensure that the study is conducted smoothly, ethically, and with the full support of the relevant stakeholders. This will facilitate access to the necessary facilities and resources, enabling the researcher to gather comprehensive data and achieve the research objectives effectively.

Intellectual Property IP

It is anticipated that Intellectual Property (IP) will be produced as a result of this research.

| Tick √ |  |  |
| --- | --- | --- |
|  | YES | NO |
| Is the IP already subject to a separate agreement with a third party (e.g. employer, sponsor or external funder)? If so please provide details below | ☐ | ☒ |
| Is the research dependent upon background IP owned by: If so, please provide details below | UWTSD ☐ | A third party ☐ |
| Text box will expand |  |  |
| Tick √ |  |  |
| I understand that: | YES | NO |
| If any party other than the student is likely to be involved in the development of IP a separate IP agreement will be needed and it may be necessary for the student to assign the IP rights to the University. | ☒ | ☐ |
| If there are no third parties involved in the creation of the IP the student is deemed to own the IP, however should the student wish to commercially exploit their IP and require the assistance of the University to do so, they will be required to assign their IP to the University. https://www.uwtsd.ac.uk/iiced/protecting-innovation-and-creativity---intellectual-property/ | ☒ | ☐ |

Student Signature Signature or Print Name:; N Y B Mendis; Date: 14/10/2024.

Supervisory Team

Has the student proposed a viable research project that is appropriate for this programme that should be supported by the Institute?

Supported: ☐ Not Supported: ☐

Authorisation

| Director of Studies | Signature or Print Name: | Date: |
| --- | --- | --- |
| Institute Manager of Research Degrees | Signature or Print Name: | Date: |

Once complete, submit this form via the MyTSD Doctoral College Portal at (https://mytsd.uwtsd.ac.uk).