## Sheet1
Task Name | Duration | Start | Finish | Cost
GCC SA1 Student Accomodation | 476 d | Mon 04/10/21 | Mon 31/07/23 | 8353207.12
Pre-Construction | 60 d | Mon 04/10/21 | Fri 24/12/21 | 111200
Pre-Construction Documentation & Surveys | 4 w | Mon 04/10/21 | Fri 29/10/21 | 47200
Procurement of Materials | 10 w | Mon 18/10/21 | Fri 24/12/21 | 64000
Site Set Up | 35 d | Mon 15/11/21 | Fri 31/12/21 | 109871.2
Site Clearance / Grading Works | 3 w | Mon 15/11/21 | Fri 03/12/21 | 63699.6
Set Layout | 1 w | Mon 06/12/21 | Fri 10/12/21 | 7609.6
Stone & Compact Temp Roadways, Storage and Parking Areas | 2 w | Mon 13/12/21 | Fri 24/12/21 | 14860.8
Site Boundary Hoarding Installation | 2 w | Mon 13/12/21 | Fri 24/12/21 | 10860.8
Site Offices & Welfare | 3 w | Mon 13/12/21 | Fri 31/12/21 | 7410
Set up designated Pedestrian Access Routes | 1 w | Mon 27/12/21 | Fri 31/12/21 | 5430.4
Substructure | 66 d | Mon 03/01/22 | Mon 04/04/22 | 256412.72
Setting Out Foundations | 2 w | Mon 03/01/22 | Fri 14/01/22 | 10890.4
Foundation & Drainage Excavation | 3 w | Thu 06/01/22 | Wed 26/01/22 | 16291.2
Excavation of Pits for Lift Shafts | 2 w | Mon 17/01/22 | Fri 28/01/22 | 10860.8
CFA Piling & Removal of Soil | 4 w | Thu 27/01/22 | Wed 23/02/22 | 137729.2
Installation of Pre-Cast Lift Shaft to Pit | 3 d | Mon 31/01/22 | Wed 02/02/22 | 2259.12
Position Services and Drainage | 3 w | Thu 27/01/22 | Wed 16/02/22 | 13780.8
Prepare Excavation, Install Shuttering & Reinforcement for Pile Caps | 4 w | Tue 08/02/22 | Mon 07/03/22 | 35801.6
Pour Concrete for Pile Caps | 1 w | Tue 08/03/22 | Mon 14/03/22 | 10218.8
Curing of Concrete Foundations | 3 w | Tue 15/03/22 | Mon 04/04/22 | 0
Surveying, Laying & Connecting Services & Drainage | 3 w | Tue 22/02/22 | Mon 14/03/22 | 18580.8
Superstructure | 345 d | Tue 15/03/22 | Mon 10/07/23 | 7795190
Ground Floor (Retail Units) | 300 d | Tue 15/03/22 | Mon 08/05/23 | 1653268.8
Lay Out Reinforcement for Ground Floor Slab | 4 w | Tue 15/03/22 | Mon 11/04/22 | 29419.2
Pour Ground Floor Concrete slab | 2 w | Tue 05/04/22 | Mon 18/04/22 | 43510.4
Curing of Ground Floor Concrete | 3 w | Tue 19/04/22 | Mon 09/05/22 | 0
Installation of Pre-Cast Lift Shaft & Stairs to Underside of 1st Floor | 5 d | Tue 10/05/22 | Mon 16/05/22 | 6457.2
Erect Formwork & Reinforcement for Ground Floor to 1st Floor Columns | 3 w | Tue 26/04/22 | Mon 16/05/22 | 22125.6
Pour Concrete for Ground Floor to 1st Floor Columns | 2 w | Tue 10/05/22 | Mon 23/05/22 | 44489.6
Installation of Formwork to Underside of 1st Floor | 3 w | Tue 17/05/22 | Mon 06/06/22 | 52437.6
Install Reinforcment for 1st Floor Slab | 4 w | Tue 31/05/22 | Mon 27/06/22 | 35584
Pouring of Concrete Slab to 1st Floor | 2 w | Tue 21/06/22 | Mon 04/07/22 | 43510.4
Install SFS Panels to Exterior Elevations | 8 w | Tue 28/06/22 | Mon 22/08/22 | 21916.8
Install Cement Particle Board & Insulation to SFS Panels | 12 w | Tue 12/07/22 | Mon 03/10/22 | 180748.8
Install Windows & Doors to Exterior Elevations | 10 w | Tue 06/09/22 | Mon 14/11/22 | 38476
Lay Brickwork for External Skin | 16 w | Tue 19/07/22 | Mon 07/11/22 | 49478.4
Erect Scaffolding to 1st Floor Level | 3 w | Tue 15/11/22 | Mon 05/12/22 | 48852
Set Out Internal Layout & Service Requirements | 3 w | Tue 28/06/22 | Mon 18/07/22 | 17107.2
Erect Partitions Between Retail Units | 6 w | Tue 12/07/22 | Mon 22/08/22 | 12216
1st Fix Mechanical (Support System (Unistrut)) | 10 w | Tue 26/07/22 | Mon 03/10/22 | 31876
1st Fix Mechanical (Ventilation) | 10 w | Tue 26/07/22 | Mon 03/10/22 | 31876
1st Fix Mechanical (Pipework & Sprinklers) | 12 w | Tue 26/07/22 | Mon 17/10/22 | 98188.8
1st Fix Mechanical (Lifts) | 6 w | Tue 26/07/22 | Mon 05/09/22 | 16888.8
1st Fix Electrical | 8 w | Tue 26/07/22 | Mon 19/09/22 | 21244.8
1st Fix Carpentry | 5 w | Tue 26/07/22 | Mon 29/08/22 | 10844
Firestopping | 4 w | Tue 26/07/22 | Mon 22/08/22 | 9880
Insulating & Boarding Internal Walls | 8 w | Tue 23/08/22 | Mon 17/10/22 | 24438.4
Install Suspended Ceiling Framework & Pattresses | 12 w | Tue 20/09/22 | Mon 12/12/22 | 24115.2
2nd Fix Mechanical (Ventilation) | 6 w | Tue 15/11/22 | Mon 26/12/22 | 75772.8
2nd Fix Mechanical (Pipework & Sprinklers) | 7 w | Tue 15/11/22 | Mon 02/01/23 | 95463.2
2nd Fix Mechanical (Lifts) | 3 w | Tue 15/11/22 | Mon 05/12/22 | 26625.6
2nd Fix Electrical | 8 w | Tue 15/11/22 | Mon 09/01/23 | 98764.8
2nd Fix Carpentry | 8 w | Tue 15/11/22 | Mon 09/01/23 | 70012.8
Phase 1 Painting & Finishes | 3 w | Tue 27/12/22 | Mon 16/01/23 | 9285.6
Install Flooring | 10 w | Tue 20/12/22 | Mon 27/02/23 | 25524
Install Ceiling Tiles | 6 w | Tue 27/12/22 | Mon 06/02/23 | 30144
Electrical Final Fix | 8 w | Tue 10/01/23 | Mon 06/03/23 | 98764.8
Carpentry Final Fix | 9 w | Tue 10/01/23 | Mon 13/03/23 | 78764.4
Final Phase Painting & Finishes | 10 w | Tue 14/02/23 | Mon 24/04/23 | 106944
GCC Inspection & Snagging | 2 w | Tue 18/04/23 | Mon 01/05/23 | 12551.2
Cleaning & Removal of Equipment | 2 w | Tue 25/04/23 | Mon 08/05/23 | 5370.4
Client Inspection & Snagging | 1 w | Tue 02/05/23 | Mon 08/05/23 | 3600
1st Floor (Residential Units) | 250 d | Tue 26/07/22 | Mon 10/07/23 | 2873097.2
Installation of Pre-Cast Lift Shaft & Stairs to Underside of 2nd Floor | 5 d | Tue 26/07/22 | Mon 01/08/22 | 6088
Erect Formwork & Reinforcament for 1st Floor to 2nd Floor Columns | 3 w | Tue 26/07/22 | Mon 15/08/22 | 52437.6
Pour Concrete for 1st Floor to 2nd Floor Columns | 2 w | Tue 09/08/22 | Mon 22/08/22 | 77444
Crane Bathroom Pods & Materials onto 1st Floor Slab | 1 w | Tue 26/07/22 | Mon 01/08/22 | 10970.4
Installation of Formwork to Underside of 2nd Floor | 4 w | Tue 16/08/22 | Mon 12/09/22 | 69916.8
Installation of Concrete Reinforcement to 2nd Floor | 4 w | Tue 23/08/22 | Mon 19/09/22 | 97193.6
Pouring of Concrete Slab to 2nd Floor | 2 w | Tue 20/09/22 | Mon 03/10/22 | 43510.4
Concrete Curing and Formwork Removal | 3 w | Tue 04/10/22 | Mon 24/10/22 | 0
Install Canti-Deck system to 1st Floor (3no. locations) | 6 d | Tue 25/10/22 | Tue 01/11/22 | 6091.2
Install Handrailing to Balcony Areas | 3 w | Tue 25/10/22 | Mon 14/11/22 | 16597.2
Install SFS Panels to Exterior Elevations | 8 w | Tue 25/10/22 | Mon 19/12/22 | 120499.2
Install Cement Particle Board & Insulation to SFS Panels | 14 w | Tue 15/11/22 | Mon 20/02/23 | 210873.6
Install Windows & Doors to Exterior Elevations | 10 w | Tue 15/11/22 | Mon 23/01/23 | 176288
Erect Scaffolding to 2nd Floor Level (Including from Balcony) | 3 w | Tue 06/12/22 | Mon 26/12/22 | 48852
Lay Brickwork for External Skin | 16 w | Tue 06/12/22 | Mon 27/03/23 | 246643.2
Set Out Internal Layout & Service Requirements for Rooms | 3 w | Tue 25/10/22 | Mon 14/11/22 | 17107.2
Position Bathroom Pods in Required Locations | 2 w | Tue 08/11/22 | Mon 21/11/22 | 8010.4
Erect Partition Walls | 8 w | Tue 08/11/22 | Mon 02/01/23 | 93481.6
1st Fix Mechanical (Support System (Unistrut)) | 8 w | Tue 01/11/22 | Mon 26/12/22 | 134707.2
1st Fix Mechanical (Ventilation) | 8 w | Tue 01/11/22 | Mon 26/12/22 | 134707.2
1st Fix Mechanical (Pipework & Sprinklers) | 12 w | Tue 01/11/22 | Mon 23/01/23 | 206716.8
1st Fix Mechanical (Lifts) | 4 w | Tue 01/11/22 | Mon 28/11/22 | 39464
1st Fix Electrical | 8 w | Tue 01/11/22 | Mon 26/12/22 | 98764.8
1st Fix Carpentry | 6 w | Tue 01/11/22 | Mon 12/12/22 | 52509.6
Firestopping | 6 w | Tue 22/11/22 | Mon 02/01/23 | 14820
Insulating & Boarding Walls & Ceilings | 8 w | Tue 20/12/22 | Mon 13/02/23 | 100985.6
Tape & Joint Walls & Ceilings | 4 w | Tue 24/01/23 | Mon 20/02/23 | 29427.2
2nd Fix Mechanical (Ventilation) | 6 w | Tue 10/01/23 | Mon 20/02/23 | 75772.8
2nd Fix Mechanical (Pipework & Sprinklers) | 6 w | Tue 10/01/23 | Mon 20/02/23 | 81825.6
2nd Fix Mechanical (Lifts) | 2 w | Tue 31/01/23 | Mon 13/02/23 | 17750.4
2nd Fix Electrical | 8 w | Tue 31/01/23 | Mon 27/03/23 | 98764.8
2nd Fix Carpentry | 8 w | Tue 31/01/23 | Mon 27/03/23 | 70012.8
Phase 1 Painting & Finishes | 6 w | Tue 14/03/23 | Mon 24/04/23 | 64166.4
Install Flooring | 8 w | Tue 28/02/23 | Mon 24/04/23 | 59500.8
Electrical Final Fix | 8 w | Tue 04/04/23 | Mon 29/05/23 | 98764.8
Carpentry Final Fix | 8 w | Tue 04/04/23 | Mon 29/05/23 | 70012.8
Final Phase Painting & Finishes | 6 w | Tue 02/05/23 | Mon 12/06/23 | 64166.4
GCC Inspection & Snagging | 4 w | Tue 30/05/23 | Mon 26/06/23 | 35912
Cleaning & Removal of Equipment | 2 w | Tue 13/06/23 | Mon 26/06/23 | 15140.8
Client Inspection & Snagging | 2 w | Tue 27/06/23 | Mon 10/07/23 | 7200
2nd Floor (Residential Units) | 185 d | Tue 25/10/22 | Mon 10/07/23 | 3016414
Installation of Pre-Cast Lift Shaft & Stairs to Underside of Roof Level | 5 d | Tue 25/10/22 | Mon 31/10/22 | 6088
Erect Formwork & Reinforcement for 2nd Floor to Roof Columns | 3 w | Tue 25/10/22 | Mon 14/11/22 | 52437.6
Pour Concrete for 2nd Floor to Roof Level Columns | 2 w | Thu 03/11/22 | Thu 17/11/22 | 77444
Crane Bathroom Pods & Materials onto 2nd Floor Slab | 1 w | Tue 25/10/22 | Mon 31/10/22 | 10970.4
Installation of Formwork to Underside of Roof Level | 3 w | Thu 17/11/22 | Thu 08/12/22 | 52437.6
Installation of Concrete Reinforcement to Roof Level | 4 w | Tue 29/11/22 | Mon 26/12/22 | 97193.6
Pouring Concrete Slab to Roof Level | 2 w | Tue 20/12/22 | Mon 02/01/23 | 43510.4
Curing of Concrete & Removal of Formwork | 3 w | Tue 03/01/23 | Mon 23/01/23 | 0
Install Canti-Deck system to 2nd Floor | 5 d | Tue 24/01/23 | Mon 30/01/23 | 5076
Install SFS Panels to Exterior Elevations | 7 w | Tue 24/01/23 | Mon 13/03/23 | 105436.8
Install Cement Particle Board & Insulation to SFS Panels | 12 w | Tue 31/01/23 | Mon 24/04/23 | 180748.8
Install Windows & Doors to Exterior Elevations | 12 w | Tue 31/01/23 | Mon 24/04/23 | 211545.6
Erect Scaffolding to Roof Level | 3 w | Tue 28/02/23 | Mon 20/03/23 | 48852
Lay Brickwork for External Skin | 16 w | Tue 21/02/23 | Mon 12/06/23 | 246643.2
Set Out Internal Layout & Service Requirements for Rooms | 2 w | Tue 24/01/23 | Mon 06/02/23 | 11404.8
Position Bathroom Pods in Required Locations | 2 w | Tue 31/01/23 | Mon 13/02/23 | 8010.4
Position all Equipment in Plant Room | 1 w | Tue 31/01/23 | Mon 06/02/23 | 6576.8
Erect Partition Walls | 6 w | Tue 31/01/23 | Mon 13/03/23 | 70111.2
1st Fix Mechanical (Support System (Unistrut)) (Plant Room Inculded) | 14 w | Tue 07/02/23 | Mon 15/05/23 | 235737.6
1st Fix Mechanical (Ventilation)(Plant Room Inculded) | 10 w | Tue 31/01/23 | Mon 10/04/23 | 168384
1st Fix Mechanical (Pipework & Sprinklers)(Plant Room Inculded) | 12 w | Tue 31/01/23 | Mon 24/04/23 | 206716.8
1st Fix Mechanical (Lifts) | 4 w | Tue 31/01/23 | Mon 27/02/23 | 39464
1st Fix Electrical (Plant Room Inculded) | 13 w | Tue 31/01/23 | Mon 01/05/23 | 160492.8
1st Fix Carpentry | 6 w | Tue 31/01/23 | Mon 13/03/23 | 52509.6
Firestopping | 4 w | Tue 14/02/23 | Mon 13/03/23 | 9880
Insulating & Boarding Walls & Ceilings | 5 w | Tue 28/02/23 | Mon 03/04/23 | 63116
Tape & Joint Walls & Ceilings | 4 w | Tue 21/03/23 | Mon 17/04/23 | 29427.2
2nd Fix Mechanical (Ventilation)(Plant Room Inculded) | 8 w | Tue 21/03/23 | Mon 15/05/23 | 101030.4
2nd Fix Mechanical (Pipework & Sprinklers)(Plant Room Inculded) | 8 w | Tue 21/03/23 | Mon 15/05/23 | 109100.8
2nd Fix Mechanical (Lifts) | 2 w | Tue 21/03/23 | Mon 03/04/23 | 17750.4
2nd Fix Electrical (Plant Room Inculded) | 10 w | Tue 21/03/23 | Mon 29/05/23 | 123456
2nd Fix Carpentry | 8 w | Tue 21/03/23 | Mon 15/05/23 | 70012.8
Phase 1 Painting & Finishes | 6 w | Tue 04/04/23 | Mon 15/05/23 | 64166.4
Install Flooring | 7 w | Tue 25/04/23 | Mon 12/06/23 | 52063.2
Electrical Final Fix (Plant Room Inculded) | 8 w | Thu 13/04/23 | Thu 08/06/23 | 98764.8
Carpentry Final Fix | 8 w | Thu 13/04/23 | Thu 08/06/23 | 70012.8
Final Phase Painting & Finishes | 6 w | Tue 25/04/23 | Mon 05/06/23 | 64166.4
GCC Inspection & Snagging | 3 w | Tue 13/06/23 | Mon 03/07/23 | 26934
Cleaning & Removal of Equipment | 2 w | Tue 13/06/23 | Mon 26/06/23 | 15140.8
Client Inspection & Snagging | 1 w | Tue 04/07/23 | Mon 10/07/23 | 3600
Inverted Roof | 92.5 d | Tue 24/01/23 | Thu 01/06/23 | 252410
Install Single Ply Waterproof Membrane | 5 w | Tue 24/01/23 | Mon 27/02/23 | 18826
Install Geotextile Layer | 2 w | Thu 16/02/23 | Thu 02/03/23 | 17046.4
1st Fix Electrical for PVPV | 1 w | Tue 21/02/23 | Mon 27/02/23 | 1650.8
Lay Polystyrene Insulation | 4 w | Tue 28/02/23 | Mon 27/03/23 | 34092.8
Install Water Infiltration Layer | 3 w | Tue 07/03/23 | Mon 27/03/23 | 25569.6
Lay Open-Jointed Ballast System | 3 w | Thu 16/03/23 | Thu 06/04/23 | 25569.6
Lay Concrete Paving Slabs for PV | 1 w | Thu 06/04/23 | Thu 13/04/23 | 8523.2
Install PV panels to Paving Slabs | 2 w | Thu 13/04/23 | Thu 27/04/23 | 7736.8
Final Fix Electrical | 1 w | Thu 13/04/23 | Thu 20/04/23 | 2584
GCC Inspection & Snagging | 3 w | Thu 13/04/23 | Thu 04/05/23 | 26934
Cleaning & Removal of Equipment | 2 w | Thu 13/04/23 | Thu 27/04/23 | 15140.8
Client Inspection & Snagging | 1 w | Thu 04/05/23 | Thu 11/05/23 | 3600
Scaffolding Dismantle | 4 w | Thu 04/05/23 | Thu 01/06/23 | 65136
Commissioning | 57.5 d | Tue 04/04/23 | Thu 22/06/23 | 15094.8
Install & Commission Lifts | 2 w | Tue 04/04/23 | Mon 17/04/23 | 3994.4
Final Testing & Callibrating of Plant Room Equipment | 1 w | Thu 08/06/23 | Thu 15/06/23 | 3935.2
Power On & Test | 1 w | Thu 08/06/23 | Thu 15/06/23 | 2584
Water On & Test | 1 w | Tue 16/05/23 | Mon 22/05/23 | 2584
Comms Connections On & Test | 1 w | Thu 15/06/23 | Thu 22/06/23 | 1997.2
Exterior | 147.5 d | Tue 06/12/22 | Thu 29/06/23 | 20093.2
Exterior Drainage | 2 w | Tue 06/12/22 | Mon 19/12/22 | 7112
Paving / Tarmac / Surfacing | 2 w | Thu 25/05/23 | Thu 08/06/23 | 4342.4
Install Facilities (Exercise Eqpt., Benches, etc) | 3 w | Thu 08/06/23 | Thu 29/06/23 | 6548.4
Landscaping | 2 w | Thu 08/06/23 | Thu 22/06/23 | 2090.4
Completion | 160 d | Tue 20/12/22 | Mon 31/07/23 | 45345.2 | ,
Disconnecting & Clearing of Site Set Up | 3 w | Tue 20/12/22 | Mon 09/01/23 | 14300.4
Cleaning of Windows / Doors & Paving | 2 w | Thu 08/06/23 | Thu 22/06/23 | 10048
Snagging | 2 w | Tue 11/07/23 | Mon 24/07/23 | 15396.8
Handover | 1 w | Tue 25/07/23 | Mon 31/07/23 | 5600 | Total | 8353207.12
£