## Example Project Journey
BMHP6020 Independent Project – Example Project Journey Gantt Chart 2026–27
Illustrative example only: a sensible route through the project. Individual plans may differ and should be discussed with the Project Supervisor.
PLAN → UNDERTAKE → REFLECT ¦ Dissertation: WHY? → HOW? → WHAT? → SO WHAT? → NOW WHAT?
Project stage / activity | 28 Sep | 05 Oct | 12 Oct | 19 Oct | 26 Oct | 02 Nov | 09 Nov | 16 Nov | 23 Nov | 30 Nov | 07 Dec | 14 Dec | 21 Dec | 28 Dec | 04 Jan | 11 Jan | 18 Jan | 25 Jan | 01 Feb | 08 Feb | 15 Feb | 22 Feb | 01 Mar | 08 Mar | 15 Mar | 22 Mar | 29 Mar | 05 Apr | 12 Apr | 19 Apr | 26 Apr | 03 May
COMPONENT 1 – PLAN
Identify/refine Health & Social Care issue | bar: 28 Sep to 05 Oct
Background reading and project justification | bar: 28 Sep to 02 Nov
Develop/refine research question, aim & objectives | bar: 12 Oct to 09 Nov
Prepare/refine project Gantt chart | bar: 28 Sep to 09 Nov
COMPONENT 1 SUBMISSION – Fri 13 Nov 2026 | bar: 28 Sep to 03 May
COMPONENT 2 – UNDERTAKE
Chapter 1 – Introduction: WHY? | bar: 16 Nov to 21 Dec
Chapter 2 – Methods/Search Strategy: HOW? | bar: 19 Oct to 18 Jan
Literature searching and search documentation | bar: 19 Oct to 25 Jan
Screen/select evidence + CASP/CRAAP appraisal | bar: 26 Oct to 25 Jan
Organise evidence and develop themes | bar: 09 Nov to 08 Feb
Chapter 3 – Literature Review: WHAT? | bar: 16 Nov to 22 Feb
Synthesis across themes + broader gaps | bar: 25 Jan to 01 Mar
Chapter 4 – Discussion: SO WHAT? | bar: 01 Feb to 08 Mar
Chapter 5 – Conclusion & Recommendations: NOW WHAT? | bar: 22 Feb to 08 Mar
Whole dissertation review, edit, proofread & final checks | bar: 01 Mar to 15 Mar
COMPONENT 2 SUBMISSION – Fri 19 Mar 2027 | bar: 28 Sep to 03 May
COMPONENT 3 – REFLECT
Review Gantt chart and project journey | bar: 22 Mar to 26 Apr
Review supervision record and key learning | bar: 22 Mar to 26 Apr
Prepare for Viva: findings, implications & recommendations | bar: 12 Apr to 03 May
SUPERVISION RECORD SUBMISSION – Fri 30 Apr 2027 | bar: 28 Sep to 03 May
COMPONENT 3 VIVA – w/c 3 May 2027 | bar: 28 Sep to 03 May
Fixed academic milestones / breaks
Reading Week | 28 Sep: w/c 26 October 2026
Final week of taught module delivery | 28 Sep: w/c 23 November 2026
Christmas holidays | 28 Sep: 14 December 2026 – 8 January 2027
Reading Week | 28 Sep: w/c 8 February 2027
Easter holidays | 28 Sep: 22 March – 9 April 2027
◆ = suggested period of activity. Overlap is intentional: searching, appraisal, writing and refinement are iterative rather than strictly linear.