BA (Hons) Leadership and Management Skills for the Workplace

Assignment Title: Managing Projects in the Organisation

Task 1: Project Management plan

Task 2: Evaluation of the project Management plan

Module code: BMSW5104

Lecturer: Rexon Nting

Student name: Samata Khatoon

Student number: 1919228

Contents

Task 1: Project Management plan

Introduction & background ………………………………………………….3

Task 1: Project management methodology ………………………………..4

Task 2: Stakeholder analysis ………………………………………………..6

Task 3: Project Network Diagram ………………………………………….12

Critical Path……………………………………………………………………14

Shortest time possible calculation…………………………………………..15

Task 4: Work breakdown structure …………………………………………18

Organisational chart…………………………………………………………..18

Task 5: Costs………………………………………………………………….19

Task 6: Consideration of Resources………………………………………..21

Task 7: Project Schedule …………………………………………………….21

Task 8: Risk Analysis ………………………………………………………..24

Task 9: Benefits of this project ………………………………………………24

Conclusion …………………………………………………………………….26

Reference list………………………………………………………………….26

Appendix lecture notes ………………………………………………………28

Task 2: Evaluation of the project management plan…….34-44

Task 1: Project Management plan

Introduction

Background

The WM College was established in the United Kingdom, within the London Borough of Camden. It was founded in 1854. It had over 4,100 students enrolled in the college in 2018. https://www.wmcollege.ac.uk

Working Men's Institute is one of the first adult learning school systems in the United Kingdom, as well as Europe's earliest surviving adult education centre. It was founded by Christian socialists and was at the vanguard of higher learning thought at the time of its creation. In the London Borough of Camden, the college now has two locations. The institute was constructed in 1854 by Christian Socialists to provide a liberal education for Victorian skilled artisans in order to combat what its creators viewed as the failures in reality with Associationism's social philosophy. Concerns over the Chartist Group's revolutionary praxis prompted the establishment of the institution in portion. Its early proponents were also heavily involved with the Co-operative Movement and labour unions. According to a survey, as college attendance and fees have climbed, and the majority of working pupils has risen (Wikipedia, 2021).

The aim of this project is to identify the main challenges Working Men College faces during the Pandemic  and how to overcome the problem. This report begins with a detail project management plan includes the total estimated budget, estimated timeline, goals, and so many things related to the project.

Every small, medium and big companies have to launch different ad campaigns and so on to achieve their objectives. Before launching the campaign, they try to figure out the overall budget, time, and overall plan for the campaign (Steinfort, 2017). That is why project management is an essential tool for every company. In this report, there will be a project management plan for the Working Men’s College. The governing board ( I am a trustee for WMC) discussed the top challenges faced such as - Covid-safe, Testing, Vaccines and plan B if thing’s get worse. In this report, there will be a stakeholder analysis, discuss how Prince2 project management methodologies is applicable in this project.

In this project management plan, the risk of this project will be assessed. After the end of this report, there will be a report about the effectiveness of the project management plan. In this report, the reader can understand the effectiveness of the project management plan.

# Task 1: Project management methodology

In the given case, it has been mentioned that because of the covid-19, a lot of things have been changed. Before the pandemic, people were not used to wearing masks. But during the pandemic, people are used to wearing face masks. Due to the coronavirus, lots of small and medium sized companies were shut down. But big companies have taken proper strategies to overcome this situation. The government has posed a lockdown in every country. That is why every company is maintaining a home office. Employees are communicating with each other through Zoom, Google meets, teams, and so on. That is why the government is trying to provide vaccines to the mass to help control outbreaks.. Schools, colleges, and universities are shut down. Due to the coronavirus, students are staying and studying from home. They are attending in online classes. But after a certain period last year, academic institutions opened. And the students are getting back to class. Administrations of academic institutes are being very careful about the health and safety issues of everyone. Based on the case, this project management has been done for making advertising by the Working Men’s College.

This ad campaign will be launched to create awareness in student’s minds to use hand wash properly (Stanley, 2018). The governor of the Working Men’s college will make corporate social responsibility. That is why he will hire a project management team who will make a hand wash advertisement to make the students aware about health and safety. Normally, a method is a combination of different methods, practices, processes, and techniques. Project management’s methodologies are specific and strict. There are different project management methodologies. These are the Scrum methodology, the waterfall methodology, the lean and six sigma methodologies. For this project management plan, prince2 methodology will be applied.

Prince2 project management indicates projects in a controlled environment. This project management method is a management methodology that is based on process, and that aims to the improvement of the overall organisation, management, and control of the project from the very beginning to the end. There are seven principles for this prince2 project management methodology. These are:

- Justification of the project.

- Continuous learning.

- Clear roles and responsibilities of each employee who are under the project.

- Step by step approach.

- Manage by exception.

- Focusing on the quality of the product.

- Customised approach to the project.

Like the other methods, Prince2 methodology has advantages and disadvantages also. Here are the advantages and disadvantages of Prince2 methodology:

| Advantages | Disadvantages |
| --- | --- |
| - Prince2 methodology is a widely known methodology for project management. - It is an easy way to recruit people with certification. - It is based on the best practices of project management. - This methodology for project management is full. That means there is no gap in this method. - It can be used in any project for any size and any type. - This method can be used anywhere. - For this method, the team members can be selected based on the project. | - It has only two tools and techniques. - It does not cover soft skills. - To run this project, there are needs of skilled people. - This project is divided into different phases that is why it needs a lot of time. So, it can be said that it is time-consuming. |

Prince2 is one of the best practices for project management. It is well recognized and it is approved by all. This is a generic project management method. It can be used in any project and sector. Project management can be reduced (Rose, 2019). That means it can be cost-effective. So, it can be used widely by any project manager.

Working Man college will implement the project plan for their students as well as for their stakeholders. This project will help everyone to be careful about the importance of being hygiene in the time of coronavirus. Through this advertisement, Working Man college can make the event successful. They will show this advertisement in their auditorium and different types of college cultural functions.

# Task 2: Stakeholder analysis

| - Senior management - Shareholders - Government board of the construction company. - National media | - Suppliers - Special interest group - Government - Local Authority |
| --- | --- |
| - Employees - Local schools | - Students - Local community - Competitors - Environmental activists. |

This stakeholder analysis chart shows the Interest and power of four different groups. On the top left, this group indicates high power and low interest. On the top right, this group indicates high power and high interest. The bottom left corner is consisting the group which has low power along with low interest. And the last one is in the bottom right corner. In this group, they have high interest and low power. Senior management of the company, shareholders of the company who have shares in the company, government board of the construction company who deals with governmental issues, and the national media who make the people informed about the company have low interest and huge power about the company (Rose, 2019). They can make some decisions about the company and they have a lot of interest. That is why these groups work actively for this company. Then the suppliers who provide instruments, the raw materials to that company, special interest groups like different referencing groups, the government of the country in which it operates have high power and they have high interest in this company. Then, the employees who work in the organisation, local schools who are affected positively or negatively both have low interest and they have low power to make any decisions about the company. And the final group of students, local community, competitors, and environmental activists have a high interest in the company but they have low power. They cannot be able to take any kind of decisions about the company.

Stakeholder analysis:

| Stakeholders | Internal/External | Influence | How will they influence this project? | Communication method |
| --- | --- | --- | --- | --- |
| Senior management | Internal | High influence | They can make any decisions regarding this project. Along with this, they can make the project manager influenced to change his strategy. | The communication method will be straight that is why the senior management will communicate through e-mail, and they can call meetings to communicate with the project management team after a certain time. |
| Shareholders | Internal | High influence | They can influence the project by making decisions or giving their opinion. | The communication of this stakeholder is also meeting. Senior management can call meetings and invite the shareholders to express their opinions. |
| Students | External | Low influence | They cannot influence the project directly. But they can influence this project indirectly through their buying decisions. | They can communicate through their buying decisions with the company. Moreover, they can express their opinions when companies will try to get students’ opinions. |
| Employees | Internal | High influence | They can make the project manager and the senior management team of the company influenced through their decisions. | They can communicate through e-mails and meetings. |
| Suppliers | External | High | They are the suppliers and without them the company is nothing. The raw materials of Working Men College are supplied by their suppliers. They can make an influence. | They can communicate through phone calls, and texts. |
| Government | External | High | They can influence Working Men College through laws and regulations. | The government can be communicated indirectly. They can communicate with the Government through media conferences for some time. |

There are many kinds of stakeholders in a company. Among them, some are very important. They are students, employees, investors, communities, and governments. Each of the stakeholders has different power of influence. Like, the consumer has no direct power to influence a company’s decision. They can make indirect decisions. As an example, if the price of a company’s products is so high, students cannot influence this decision of the company. But if they stop buying those products of the company, the company will be forced to decrease its product’s price (Joslin and Müller, 2015). Each stakeholder is very crucial for a company. The company needs to take care of every stakeholder.

Power: Different types of groups have different types of power. WM College will take care of those parties who have high power to control this project.

Validity: Because this event is important for the people, and through this, they can make the people aware. So, it is valid.

Necessity: The necessity of this project is high. Because it will help the people to stay safe in the time of coronavirus.

# Task 3: Project Network Diagram

| No | Activities | Duration (Days) | Dependency (No.) | EST | LST | EFT | LFT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Budget Approval | 1 | - | 0 | 9 | 1 | 10 |
| 2. | Hire publicity director | 14 | 1 | 1 | 10 | 15 | 24 |
| 3. | Hire set designer | 14 | 1 | 1 | 45 | 15 | 59 |
| 4. | Hire place for auditions | 7 | 2 | 15 | 24 | 22 | 31 |
| 5. | Ad to hire cast and crew | 7 | 2 | 15 | 24 | 22 | 31 |
| 6. | Hire production and publicity crew | 28 | 4,5 | 22 | 31 | 50 | 59 |
| 7. | Set design and built | 42 | 3, 6 | 50 | 59 | 92 | 101 |
| 8. | Train production crew | 12 | 3, 6 | 92 | 94 | 104 | 106 |
| 9. | Audition to hire cast | 2 | 4, 5 | 22 | 64 | 24 | 66 |
| 10. | Cast rehearsal | 84 | 9 | 24 | 22 | 106 | 106 |
| 11. | Hire orchestra | 7 | 1 | 1 | 59 | 18 | 66 |
| 12. | Music | 7 | 11 | 18 | 95 | 25 | 102 |
| 13. | Photograph cast and review | 35 | 6, 9, 11 | 50 | 66 | 85 | 101 |
| 14. | Enter info to computer | 1 | 13 | 85 | 101 | 86 | 102 |
| 15. | Printing | 5 | 14 | 86 | 102 | 91 | 107 |
| 16. | Developing and Plan | 7 | 6 | 50 | 79 | 57 | 86 |
| 17. | Ad media | 21 | 16 | 57 | 86 | 78 | 107 |
| 18. | Orchestra Rehearsal | 4 | 12 | 25 | 102 | 29 | 106 |
| 19. | Order costumes | 7 | 9 | 24 | 94 | 31 | 101 |
| 20. | Costume Parade & alterations | 5 | 7, 19 | 92 | 101 | 97 | 106 |
| 21. | Dress rehearsal | 1 | 8, 10, 18, 20 | 106 | 106 | 107 | 107 |
| 22. | Performance | 10 | 15, 17, 21 | 107 | 107 | 117 | 117 |

Figure 1: Project network Diagram.

EST: Early start time.

LST: Late start time.

EFT: Early finish time.

Figure 2: Shortest time Calculation.

## Critical Path:

Because this program's EFT and LFT are, all the same, its critical path for such a project is 10-21- 22. If only one of the project's operations is postponed by a single day, the entire project will be affected by the same amount of time. As a result, this essential path was picked for the celebration.

## Shortest time possible calculation

| 1 | 2 | 4 | 6 | 8 | 21 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 28 | 12 | 1 | 10 | 73 |

| 1 | 2 | 4 | 6 | 13 | 14 | 15 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 28 | 35 | 1 | 5 | 10 | 101 |

| 1 | 2 | 4 | 6 | 7 | 21 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 28 | 42 | 1 | 10 | 103 |

| 1 | 2 | 4 | 6 | 16 | 17 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 28 | 7 | 21 | 10 | 88 |

| 1 | 2 | 4 | 9 | 10 | 21 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 2 | 84 | 1 | 10 | 119 |

| 1 | 2 | 4 | 9 | 13 | 14 | 15 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 2 | 35 | 1 | 5 | 10 | 75 |

| 1 | 2 | 4 | 9 | 19 | 20 | 21 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 2 | 7 | 5 | 1 | 10 | 47 |

| 1 | 2 | 5 | 6 | 8 | 21 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 28 | 12 | 1 | 10 | 73 |

| 1 | 2 | 5 | 6 | 13 | 14 | 15 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 28 | 35 | 1 | 5 | 10 | 101 |

| 1 | 2 | 5 | 6 | 16 | 17 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 28 | 7 | 21 | 10 | 88 |

| 1 | 2 | 5 | 9 | 10 | 21 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 2 | 84 | 1 | 10 | 119 |

| 1 | 2 | 5 | 9 | 13 | 14 | 15 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 2 | 35 | 1 | 5 | 10 | 75 |

| 1 | 2 | 5 | 9 | 19 | 20 | 21 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 7 | 2 | 7 | 5 | 1 | 10 | 47 |

| 1 | 3 | 7 | 20 | 21 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 14 | 42 | 5 | 1 | 10 | 73 |

| 1 | 3 | 8 | 21 | 22 | Total |
| --- | --- | --- | --- | --- | --- |

| 1 | 11 | 12 | 18 | 21 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 7 | 7 | 4 | 1 | 10 | 30 |

| 1 | 11 | 13 | 14 | 15 | 22 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 7 | 35 | 1 | 5 | 10 | 59 |

Figure 3: Shortest time possible calculation (Kononenko and Aghaee, 2016)

Every project manager is trying to be effective. That is why he always tries to choose the effective path through which he will run the project. For this project management, the shortest possible time is 30 days. The rest of the critical path is more time-consuming rather than this path. So, it can be said that the shortest time possible is 30 days and it will be used by the project manager.

# Task 4: Work breakdown structure

This event is making people aware of using hand wash. The project has been broken into five stages. The first one is the initiation of the project. In this part, there will be set design and build, develop advertising plan, Budget approval. The second one is planning, and it has advertised to hire crew and casts, order the costumes. The third one is execution which has an audition to hire cast, hire set designer, hire the place for auditions, hire production and publicity crew, hire publicity director, hire an orchestra, costume parade, and alteration, train production crew, etc. The fourth one is the control which includes cast rehearsal, orchestra rehearsal, dress rehearsal, advertising media, and music (Indelicato, 2012). The final one is closeout which has photograph cast and crew and collects biographies, enters information into computer, printing, and performance.

This project will be done one by one. First of all-

Commencement: The project management has to plan how to start the project.

Planning: In this phase, the team will plan for everything. They will take the necessary steps to start the like buying the necessary projects.

Execution: In this phase, the project management team will execute the planning.

Control: In this phase, the team will control the ongoing process.

Closeout: In this phase, the management team will complete the project.

## Organisational chart

For this project, there will be a project manager. Under the project manager, there are more managers. They are finance manager, HR manager, purchasing manager, Service manager, and patient manager. Under all of these managers, so many staff are controlled by the manager.

# Task 5: Costs

Project on making advertising by the Working Men’s College

| Cost description | The cost in (£) |
| --- | --- |
| Project conception and initiation |  |
| Getting project approval | 120,000 |
| Certification of the project | 80,000 |
|  | 2 00,000 |
| Project planning and definition |  |
| Project personal selection | 200,000 |
| Project team development | 300,000 |
| Identifying resources and allocation of financial budget | 300,000 |
| Communicate with related local authority | 150,000 |
| Setting required tasks | 250,000 |
| Visiting targeted place in the local area | 200,000 |
| Identifying underserved community or target people | 150,000 |
| Identifying major social problems in the local area | 250,000 |
|  | 1.8 million |
| Project launch and execution |  |
| Communicate with local people to deeply understand the cause of those problems | 800,000 |
| Analysing the cause of those problems | 900,000 |
| Designing probable solutions to solve those problems | 800,000 |
| Experimenting probable solution in the local area | 700,000 |
|  | 3.2 million |
| Project performance and control |  |
| Preparing a report on the project | 900,000 |
| Presenting and communicating the project | 400,000 |
| Post-project adjustment and correction | 500,000 |
|  | 1.8 million |
| Project closer |  |
| Project handover | 500,000 |
| Project closure | 300,000 |
|  | 800,000 |
| Contingency fund | 200,000 |
| Total | £8 million |

# Task 6: Consideration of Resources

As a project management plan developer, there needs to invest time, effort, devices, and has to bear some costs for carrying the project.

| Resources Name | Resources Requirements |
| --- | --- |
| Time | The project is an 18-months long project. Through time, to observe the project development to progress and till the closure of the project will require a lot of time investment in this project. |
| Financial capital (costs) | The costs that can be needed to invest in this project development are the internet bill, mobile costs, transportation costs, etc. |
| Human capital | Throughout the project has to give mental and physical efforts. |
| Communication tool | There needs to use some devices such as mobile, telephone, etc. for communication. |
| Project making devices | Laptop, PC, etc. |

# Task 7: Project Schedule

Project on making advertising by the Working Men’s College

| Cost description | Budgeted time |
| --- | --- |
| Project conception and initiation |  |
| Getting project approval | 9 days |
| Certification of the project | 6 days |
|  | 15 days |
| Project planning and definition |  |
| Project personal selection | 1 month |
| Project team development | 15 days |
| Identifying resources and allocation of financial budget | 1 month |
| Communicate with related local authority | 15 days |
| Setting required tasks | 15 days |
| Visiting targeted place in the local area | 1 month |
| Identifying underserved community or target people | 1 month |
| Identifying major social problems in the local area | 1 month |
|  | 6.5 months |
| Project launch and execution |  |
| Communicate with local people to deeply understand the cause of those problems | 1 month |
| Analysing the cause of those problems | 1.5 months |
| Designing probable solutions to solve those problems | 1 month |
| Experimenting probable solution in the local area | 2.5 months |
|  | 6 months |
| Project performance and control |  |
| Preparing a report on the project | 1 month |
| Presenting and communicating the project | 2 months |
| Post-project adjustment and correction | 1 month |
|  | 4 months |
| Project closer |  |
| Project handover | 20 days |
| Project closure | 10 days |
|  | 1 month |
| Total | 18 months |

# Task 8: Risk Analysis

Risk means uncertainty. There is nothing that can be gone according to the plan. If there is a plan, it may not be done properly. Lack of competency, lack of proper teamwork can lead a project to uncertainty. Here are the risk factors and their impacts on the project.

| Risk factors | Impact on the project | Strategies need |
| --- | --- | --- |
| Weak leadership | High risk | Mitigate |
| Poor team management skill | Medium risk | Accept |
| Lack of effectiveness | High risk | Mitigate |
| Lack of adequate fund | High risk | Enhance |
| Staff training | Low | Arrange training |
| Nurse training | Medium | Arrange training |
| Authority | High | Accept |
| Social Activists | High | Mitigate |
| Local people | Medium | Enhance |
| Weak employee performance | Medium | Mitigate |
| Lack of expertise people | High | Mitigate |
| Poor communication skill | Medium | Mitigate |
| Less staff | High | enhance |
| Poor critical thinking skill | Medium | Mitigate |
| Regulatory impacts | Medium | Accept |
| Public response | Low | Accept |
| Project success rate | Medium | Mitigate |
| Stakeholder’s impact | Low | Mitigate |
| Collaborative working | High | Mitigate |
| Project completion | Medium | Mitigate |

# Task 9: Benefits of This project

| SL no. | Benefits |
| --- | --- |
| 1 | Students will be aware about the effect of coronavirus. |
| 2 | They will understand the drawbacks of coronavirus. |
| 3 | They will be careful about being hygienic. |
| 4 | The virus will not be able to spread so much. |
| 5 | The total condition of the country will remain good. |
| 6 | Other institutions will be motivated to do the same project. |

# Conclusion

This prince2 project management will be applicable for this WM College project. This methodology will help the project to be successful (Pace, 2019). This project will need only 30 days to complete. If WM College can appropriately convince the students and make them aware of the impact of hand wash, and if they can be able to increase their sales, then the project will be successful.

# Reference list

Indelicato, G. (2012). Book Review: Project Management Fundamentals: Key Concepts and Methodology, Second Edition. Project Management Journal, 43(1), pp.92–92.

Joslin, R. and Müller, R. (2015). Relationships between a project management methodology and project success in different project governance contexts. International Journal of Project Management, 33(6), pp.1377–1392.

Kononenko, I.V. and Aghaee, A. (2016). Model and Method for Synthesis of Project Management Methodology with Fuzzy Input Data. Bulletin of NTU “KhPI”. Series: Strategic Management, Portfolio, Program and Project Management, 5(1(1173)), p.9.

Pace, M. (2019). A Correlational Study on Project Management Methodology and Project Success. Journal of Engineering, Project, and Production Management, 9(2), pp.56–65.

Rasnacis, A. and Berzisa, S. (2015). Adaptation of Agile Project Management Methodology for Project Team. Information Technology and Management Science, 18(1).

Rose, K.H. (2019). Book Review: The Complete Project Management Methodology and Toolkit. Project Management Journal, 41(2), pp.82–82.

Stanley, F.J. (2018). Establishing a Project Management Methodology. Journal of Information Systems Management, 5(4), pp.15–24.

Steinfort, P. (2017). Community and post-disaster Program Management Methodology. International Journal of Project Management, 35(5), pp.788–801.

https://www.wmcollege.ac.uk/information-advice/how-to-enrol/

https://www.wmcollege.ac.uk

Wikipedia, 2021 - https://en.wikipedia.org/wiki/Working_Men%27s_College

Lecture notes; by Rexon Nting

Appendix’s lecture notes

Task 2: Evaluation of the project management plan

Speaker notes

Introduction

This report is about the evaluation of the project management plan of Working Men College. This is the time of the pandemic. Due to the coronavirus, a lot of people are getting affected. This project is for the people who should be aware of handwashing (Rose, 2015). That is why Working Men College will go for a project through Prince2 methodology. The main reason for this project management is promoting their products and making the customers aware of the hand wash. In this report, there will be an evaluation of the effectiveness of this project.

Speaker notes

The WM College was established in the United Kingdom. It was founded in 1854. Statistics have said that it has 4,100 students in the college in 2018. It is located in England. In this report, there will be a stakeholder analysis. Working Men's Institute is one of the first adult learning school systems in the United Kingdom, as well as Europe's earliest surviving adult education centre. It was founded by Christian socialists and was at the vanguard of higher learning thought at the time of its creation.

Speaker notes

The aims of this project plan are-

- To make the students aware of the effects of coronavirus.

- To make them understand the drawbacks of coronavirus.

- To make them care about being hygienic (Milosevic and Ozbay, 2020).

- To make the other institutions motivated to do so.

Speaker notes

This event is making people aware of using hand-wash. The project has been broken into five stages. The first one is the initiation of the project. In this part, there will be set design and build, develop advertising plan, Budget approval. The second one is planning, and it has advertised to hire crew and casts, order the costumes. The third one is execution which has an audition to hire cast, hire set designer, hire the place for auditions, hire production and publicity crew, hire publicity director, hire an orchestra, costume parade, and alteration, train production crew, etc. The fourth one is the control which includes cast rehearsal, orchestra rehearsal, dress rehearsal, advertising media, and music (Indelicato, 2012). The final one is closeout which has photograph cast and crew and collects biographies, enters information into computer, printing, and performance.  This project will be done one by one. First of all-

Commencement: The project management has to plan how to start the project.

Planning: In this phase, the team will plan for everything. They will take the necessary steps to start the like buying the necessary projects.

Execution: In this phase, the project management team will execute the planning.

Control: In this phase, the team will control the ongoing process.

Closeout: In this phase, the management team will complete the project.

Evaluation of the effectiveness of the project management of Working Men College.

It is known that promotion is the best way to make the customers aware of a brand. Effective promotion can make it happen to make the customers properly aware. If there is an effective promotion, there will be a good amount of response. Though people are using a lot of hand wash and sanitiser. But the Working Men College wants to make the customers informed that, their hand wash can kill 99.9 percent of germs. Through their project, they also want to promote that, the importance of washing hands in time of pandemic is essential. During this pandemic, a lot of people are being affected by the Novel coronavirus (Patanakul, 2015). People are now afraid of this virus. This virus can affect a lot of people at a time. It can travel from person to person through an object. That is why people are maintaining distance from others. At that time, when Working Men College tries to say that, their hand wash can make people safe from affecting by this virus, people will get interested in their product. Moreover, Working Men College is performing CSR also through this project. CSR means corporate social responsibility. Through this project, Working Men College is showing that they are socially responsible. They are helping the people by making them aware. It is known that the success of any project depends on its contents, how a project has approached the customers, how much information the project has, how much help the project is. All of these are performed by Working Men College properly. These things will help the project to be successful and effective.

Here are the four criteria to make a project effective. The effectiveness of the Working Men College project will be measured through these criteria. These are:

Clearly define the problem: First of all, in the ad campaign of Working Men College, they will make the people introduced with the problem. Though people already know that, the coronavirus is an alarming issue. But at the starting of this ad campaign, they will inform the customers about the seriousness of this pandemic.

Productive collaboration: To make the problem solved, there should be an idea that will make the customers interested.

Use tool to monitor progress: Working Men College can use different types of tools to monitor progress. Through this, they can understand whether the project should be run or not.

Effective Project management: Through effective management one can make the project successful.

Quality Expectations: The quality expectations for this venture are typically more prominent since the undertaking chief directs movements of every sort as indicated by sufficient arrangement. The organization expects a more elevated level of undertaking execution (Milosevic and Ozbay, 2020). The organization ought to talk with general society to take in what they expect from such music occasions. The artists in this undertaking are generally VIPs and cross-country artists. They are specialists in their fields. Without a doubt, venture planning is advancing great, and the melodic program will fulfil general society. In that case, directors should focus on the necessities of the general population just as the ability of the entertainers.

Acknowledgement Criteria: As it is an immense music project, certain missteps just as misusing may happen. A few of them appear to be passable, and others are not. In that case, minor blames or missteps would be endured, yet no considerable blunders would be endured.

Quality Specification: The clinic administration strategy will give the most significant level of value. The emergency clinic specialists would give the best help conceivable through preparing doctors and other clinic labourers. Every single fundamental stockpile and gear are as of now given and carried out (Hyväri, 2016). Subsequently, this business might be expected to offer unrivalled assistance. Control Measures for Occurrences: Because the organization is coming up short on faculty, extra people ought to be recruited to assist with overseeing this program. Labourers will be accountable for keeping the feeling quiet. On such occasions, the board might assess and offer remarks on the exhibition.

Speaker notes

Every project manager is trying to be effective. That is why he always tries to choose the effective path through which he will run the project. For this project management, the shortest possible time is 30 days. The rest of the critical path is more time-consuming rather than this path. So, it can be said that the shortest time possible is 30 days and it will be used by the project manager.

Speaker notes

Conclusion

The coronavirus is a concerning issue for this time. This pandemic is affecting not only a single country but also the whole world. People are trying to get rid of this pandemic. They are maintaining home quarantine, home office, and so on to avoid this problem. As Working Men College is solving the problem, they can be able to make the project successful (Clarke, 2019). If they can make this project successful, they can make both the consumers aware and increase the demand for their products.