Planning and Delivering an International Meeting/Event

Name: Valentina Stoian

Student No: 2209627

Module Title: International Meetings Management BMIH6007

Lecturer Name: Christopher Wilkin

Table of Contents

Introduction	3

The Event Cycle	3

Event Concept	4

Aim and Objectives of the Meeting / Event	5

Event Management	6

Event Budget	7

Industry Trends / Issues / Impacts	8

Situational and Cultural Considerations	10

Conclusion	11

References	12

Appendices	13

Appendix 1: Assessment 1 PowerPoint Slides	13

# Introduction

North Pole Adventure Experience is a unique family entertainment event that brings people into Santa’s world and gives a view of Santa’s workshop. Including fun, creativity and an exciting holiday atmosphere, this vibrant themed party is a mix of fun and games, art, and musical performance (Berridge, 2020). It has been chosen for the purpose of being able to entertain families with children from 3 to 12 years, thus offering them a wonderful experience that will make it a holiday season for all. The main reason for choosing this event theme is the snowy weather in the UK in the month of December. The geographical location is stated as Ash Barton Estate - Ash Road, Braunton, North Devon, UK. The event makes it possible to try Christmas practices by oneself. The event location is very good for arranging the snow winter Christmas party with adorable guest experience. The families can visit themed zones where children can make toys and paint ornaments or play with them and watch performers dressed as holiday characters like real Santa Claus. This delightful situation makes families develop recreation time together to be spent working on art forms (Bladen et al., 2022).

North Pole Adventure Experience will be held in a large ball room at Ash Barton Estate and it accommodate large numbers of guests with comfort and safety. The choice of this location is particularly important because it offers enablement factors such as accessibility, safety, and space to meet the need for one or many related activities. This event is designed to turn into one of those cherished family holidays in the community.

# The Event Cycle

Event Cycle can be described as a process map that defines the steps in organizing and conducting an event. It typically involves of six key stages which involve Initiation, Planning, Implementation, Monitoring, Evaluation, and Closure. This cycle aids in finding out details related to events and organize the stages properly (Altschwager et al., 2024).

In case of the North Pole Adventure Experience, Beginning of the Event Cycle is when the event initiative is commenced through an investigation of consumer trends looking for an active holiday. This process requires recognizing venues and arranging marketing approaches along with other factors that will guarantee delivery of best vacations (González-Granadillo et al., 2021).

The Implementation stage contains activities, incorporating a comfortable environment for children and the assembly of performers. During the event, Monitoring takes place to measure guest satisfaction and to check that all is well.

After that comes the Evaluation stage where the views of the attendees are taken about the event’s success or tournament performance. Last is the closure phase during which an event is decommissioned, and financial accounts are closed (Horta, 2024). This systematic approach lets the North Pole Adventure Experience not only be fun for the participants but also possible for future experiences as well.

# Event Concept

Itinerary

10:00 AM – Event Opening: Families get to enter at Ash Barton Estate, the system plays loud music embracing the holiday mood, and beautiful enhancements greet visitors.

10:30 AM – Santa Workshop Tour: Before entering the Ash Barton Estate, children are provided with a glimpse of a life-like set-up of a 'Santa's workshop', and they get a chance to assist in demonstrative making of toys followed by a turn in each child making own toy.

11:30 AM – Decoration of ornaments: People then go for ornament decorating and children are allowed to decorate their ornaments for home Christmas ornaments.

12:30 PM – Lunch Break: Holiday meals such as sandwiches, chips, and cooked beans are provided for the attendees to have time and make new friends to share some jokes.

1:30 - Live Performances: The performers will be singing and dancing as fairies and taking photos with Santa Clause at Ash Barton Estate.

3:00 PM – Crafting Activities: During the afternoon, there are card-creating cookies designing and other types of crafts and all can join and have a suitable time.

4:30 PM – Final performance and Closing Ceremony: The last event of the day also incorporates families to enjoy the creative presentation, have some fun with the shows of the day, and get some gifts as well.

Ash Barton Estate itinerary ensures that all participants equally enjoy a wonderful, creative, and carefree day up to the end of the event.

# Aim and Objectives of the Meeting / Event

Aim

To organize an extraordinary holiday event which promotes children and families’ interaction and feeling of community and excitement at the North Pole Adventure Experience at Ash Barton Estate facility by performing entertaining and engaging activities and shows.

SMART Objectives

| Objective | Specific | Measurable | Achievable | Relevant | Time-bound |
| --- | --- | --- | --- | --- | --- |

| Increase Attendance | To reach at least 500+ guests who are present throughout the duration of the event. | Monitor all kinds of tickets available for sale and the number of people attending the event. | Choosing the specific advertisement approach (social networks, cooperation with local businesses). | Attracting families improves appeal to the community. | 1 month. |
| --- | --- | --- | --- | --- | --- |

| Enhance Guest Satisfaction | Get a guest satisfaction rate of not less than 90% as captured in post-event feedback surveys. | Assessment of survey and feedback. | Offering captivating tasks and ensuring elevated levels of service delivery. | Making sure learners are satisfied to attend the class in the future. | Immediately after the event. |
| --- | --- | --- | --- | --- | --- |

| Generate Revenue | Target at selling tickets, sponsoring and merchandise to an amount of £25,500. | Supervising the ticketing revenue, sponsorship, and merchandise. | Fixing ticket prices at £40 and signing contracts with companies within the area. | Financial success is conducive to future events. | Immediately after the event. |
| --- | --- | --- | --- | --- | --- |

# Event Management

The success of the North Pole Adventure Experience plan at Ash Barton Estate focuses on the need to acquire a variety of operational, planning, and marketing competencies.

Operational Skills and Resources

- Event Coordination: It always requires skilled professionals with good project management abilities within event coordinators to capture the complete event cycle (Hancock, 2023). This comprises of developing a calendar/timeline, overseeing the timeline, and guaranteeing everything runs as planned.

- Logistics Management: Coordinators will require professional knowledge to organize venue and equipment, assign locations, and manage a location. This also encompasses the redesigning and staffing of spaces for making art, putting up shows, and stealing food (Mason, 2020).

- Safety and Compliance: Readiness regarding health and safety norms is important. Event managers should abide by the law on matters concerning the assembly of people, and laws regarding hygiene, especially in the preparation of foods for consumption.

Planning Skills and Resources

- Budget Management: Mastery of the principles of controlling the financial resources in an organization is also critical to the development of the event budget (Graham, 2023). It entails issues to do with expenditure, including assessing expenses, handling of suppliers' payments, and revenue.

- Scheduling: Strong organisation ability is required to produce a full timetable of activities, shows, and gaps between them to ensure continuity.

- Vendor Management: It would be important to manage and negotiate relationships with suppliers such as caterers, decorators, and entertainers in a bid to ensure all their services are satisfactory to the event (Larsen, 2020).

Marketing Activities

- Digital Marketing Skills: Facebook and Instagram are two of the most important target resources for sharing information about the event, so it is crucial to have the appropriate level of digital marketing (Broeckerhoff and Galalae, 2022).

- Content Creation: Proficiency in designing texts and graphics will be required to create attractive advertisement materials also in electronic form such as flyers, posts, and releases (Davey et al., 2024).

- Public Relations: It is important to develop effective communication and public relations skills to engage local merchants and media thus increasing visibility and sponsorship.

# Event Budget

Breakdown of Income and Expenditure

| Item | Estimated Cost (£) | Estimated Revenue (£) |
| --- | --- | --- |
| Ash Barton Estate Venue Rent | 5,000 |  |
| Ash Barton Estate Staff Wages | 4,000 |  |
| Ash Barton Estate Decorations and Set Design | 2,500 |  |
| Ash Barton Estate Catering | 3,000 |  |
| Marketing and Promotion | 1,500 |  |
| Equipment and Supplies | 1,000 |  |
| Miscellaneous Expenses | 500 |  |
| Total Costs | 17,500 |  |
| Ticket Sales (500 tickets @ £40) |  | 20,000 |
| Sponsorships |  | 3,000 |
| Merchandise Sales |  | 2,500 |
| Total Revenue |  | 25,500 |
| Profit |  | 8,000 |

Analysis of Costs

Venue Rental (£5,000): This expense includes the hiring of a large, enclosed ball room area at Ash Barton Estate, which is suitable for winter recreation and shows.

Staff Wages (£4,000): This comprises allowances to event organizers, performers, chefs, receptionists, door attendants and caretakers.

Decorations and Set Design (£2,500): This budget provides for an entertaining factor such as character-projected pillar lighting, fibreglass antlers and inlaid polar bear tree toppers, and the like which appears in photos of the finished set.

Catering (£3,000): Ash Barton Estate accommodation services will consist of food and beverages during the holidays such as hot cocoa that will be consumed during such festivities.

Marketing and Promotion (£1,500): This cost includes advertising through computerization promotions of the events, and promotions on social media to ensure high family attendance.

Equipment and Supplies (£1,000): Expenditures are provided for the construction of controversial equipment, powering of necessary instruments, construction of material and any other requisites requisite for engagement in joint activities.

Miscellaneous Expenses (£500): This is a reserve for emergencies that are likely to happen in the planning as well as the implementation of the event.

Organisation Funding and Revenue Acquisition

Ticket Sales (£20,000): Income derived from ticket receipts, based on 500 tickets which cost £40 each, proving that there is much business in family-oriented spending during the holiday.

Sponsorships (£3,000): The event may be funded by local businesses that will attract their logos and company information to the festive products and services associated with it.

Merchandise Sales (£2,500): Offering logo products like, holiday souvenirs, and memorabilia, means more sales to boost company income as well as more value added to guests’ experiences.

# Industry Trends / Issues / Impacts

Currently, the events industry in the UK is going through several trends and challenges that impact the planning of such events as the North Pole Adventure Experience.

Trends

Sustainability and Eco-friendliness: Globally, there has been a rise in expectations for sustainability within event management, particularly with pending policy changes. This includes the endurance index for sustainability event performance measurements, attendee expectations for items used in an event should be sustainably sourced or green, reduction in waste and carbon offsetting (Gierl, 2021). Introducing the North Pole Adventure Experience at Ash Barton Estate into this trend is a way to achieve this by adopting environmentally friendly decorations should also practising proper waste management.

Hybrid Events: The change towards hybrid events that have both live and online components has become popular after the pandemic. Although the North Pole Adventure Experience can also be operated physically, the inclusion of other platforms such as online visits by Santa or the selling of tickets online serves to increase the experience reach (Marshall et al., 2023).

Experience-driven Events: Self-organized events are also getting more popular, which can be explained by the desire of spectators to engage in active work during events rather than follow passive patterns (Mingazova and Gbadamosi, 2022). The concept of the North Pole Adventure experience was based on this concept where direct interaction of families with specific 'holiday' zones and apparatuses was encouraged.

Issues

Economic Uncertainty: Availability now depends on its sensitivity to the current economic factors such as inflation as well as higher cost of living (Bamford et al., 2024). Families are likely to be more particular with their attendance at events therefore meaning that the North Pole Adventure Experience must offer valuable and memorable experiences to highlight the crowds.

Health and Safety Regulations: One must implement safety regulations because of continuing issues that relate to the well-being of the public. Schulenkorf et al., (2024) have stressed the need to protect the guests by adopting sanitation measures and regulating the size of gatherings to produce safe events that guests will find enjoyable.

Concisely, the current trends of sustainability and immersive experiences may be harnessed to make the North Pole Adventure Experience fit the unsettled economic situations and health regulations to thrive appropriately in the Ash Barton Estate event ground of the UK.

# Situational and Cultural Considerations

Several situational and cultural contingency factors must be considered when designing the North Pole Adventure Experience. Collectively using SWOT, PESTEL, and SOAR tools, one can analyse the internal core of the event as well as the outside world.

SWOT Analysis

Strengths: The idea that the event is an interactive one can be mentioned as one of the most effective features of such an event. Some of the factors include the Santa's workshop, and crafting areas, where families get to participate physically in activities, they consider seasonal (Rogers and Wynn-Moylan, 2022). Thus, getting value for their money, hence making many trips.

Weaknesses: The high fixed costs of equipment, stage and script, and the wages of cast and crew members are serious issues. Further, the event primarily generates its revenues seasonally, hence relatively restricted income.

Opportunities: Partnerships with local businesses or sponsorships are possible thus decreasing costs and increasing utility for attendees (MURPHY and ANNE, 2022). The event can be hosted at other centres or include virtual tours - that can broaden the reach of the event.

Threats: Some degree of competition could come from the fact that there may be other events appealing to the target demographic during the same period, such as Christmas markets and seasonal festivals (Allen et al., 2022). Also, contingencies such as unfavourable weather may affect the experience especially if the activities to be undertaken are outdoor related.

PESTEL Analysis

Political: Local government policies and restrictions due to permits and eventualities act as key elements of consideration when it comes to planning for the functions (Bamford et al., 2024). Government support during the holidays especially when it comes to organizing and hosting community-friendly events presents a plus.

Economic: High inflation and soaring costs mean that families may not afford to spend as much on other things could be a hindrance (Burnside et al., 2024). This can be balanced by promotions like early bird discounts, or family discounts.

Social: They target the family-oriented segment as people who prefer family activities together with friends and relatives. To achieve that, one must know the social structure of the identified community to ensure maximum attendance.

Technological: Promotion through social sites, online ticket-selling services, and application schedules or maps of events would be in context with technological advancement which will enhance the satisfaction level of the customers (Rogers and Wynn-Moylan, 2022).

Environmental: Other approaches like the use of environmentally friendly ornaments and focal control of waste discharges throughout the occasion will go along with green tendencies that consumers are demanding today.

Legal: It is crucial to meet the set health and safety regulations, especially after the Covid-19 pandemic to prevent legal repercussions and safeguard attendees (Burnside et al., 2024).

SOAR framework

Strengths: The idea for the North Pole Adventure Experience should have a definite potential to establish many clients within the community since it should provide a personalized and exciting adventure. The family event's strategic and distinctive theme sets it apart from other holiday celebrations.

Opportunities: The event can be expanded to different cities, or it can be a travelling show, and these options will increase the audience base (MURPHY and ANNE, 2022). Food with merchandise and themed souvenir items are other sources of revenue for these facilities.

Aspirations: The event may turn into a tradition where people would visit the event every year during the season. Increasing relationships of cooperation with local retailers and sponsors would promote stable development.

Results: The success will be assessed based on ticket sales, more sponsorship initiatives, and the need to develop this event into something that is not just regional (Marshall et al., 2023).

# Conclusion

Hence, it is to conclude that The North Pole Adventure Experience at Ash Barton Estate ssis best described as a holiday event that is designed to depict a special moment of joy that families associate with their holidays. Analyzing the situation analysis with reference to SWOT PESTEL and the SOAR tool, it is possible to identify the strengths and weaknesses of the event and identify the external factors. Stressing community engagement, the need for new, fresh, and unique approaches to marketing and endeavours related to green production and environmentally friendly actions led the event to strive to create family-fun and significant experiences. It also tends to ensure family attendance year after year making the event a part of the seasonal family traditions. This event strategic management guarantees the event's success and sustainability in the competition of the holiday events.

# References

Allen, J., Harris, R. and Jago, L. (2022) Festival & special event management. John Wiley & Sons.

Altschwager, T., Conduit, J., Karpen, I.O. and Goodman, S. (2024) Event engagement: Using event experiences to build brands.

Bamford, D., Reid, I., Forrester, P., Dehe, B., Bamford, J. and Papalexi, M. (2024) An empirical investigation into UK university-industry collaboration: the development of an impact framework. The Journal of Technology Transfer, 49(4), pp.1411-1443.

Berridge, G. (2020) Designing event experiences. In The Routledge Handbook of events (pp. 378-395). Routledge.

Bladen, C., Kennell, J., Abson, E. and Wilde, N. (2022) Events management: An introduction. Routledge.

Broeckerhoff, A. and Galalae, C. (2022) Christmas markets–marketplace icon. Consumption Markets & Culture, 25(1), pp.79-90.

Burnside, G., Cheyne, C.P., Leeming, G., Humann, M., Darby, A., Green, M.A., Crozier, A., Maskell, S., O’Halloran, K., Musi, E. and Carmi, E. (2024) COVID-19 risk mitigation in reopening mass cultural events: population-based observational study for the UK Events Research Programme in Liverpool City Region. Journal of the Royal Society of Medicine, 117(1), pp.11-23.

Davey, A., Sung, B. and Butcher, L. (2024) Revisiting experiential marketing: a Delphi study. Journal of Brand Management, 31(1), pp.16-37.

Gierl, H. (2021) Christmas is Coming: Exploring the Effectiveness of Christmas Commercials.

González-Granadillo, G., González-Zarzosa, S. and Diaz, R. (2021) Security information and event management (SIEM): analysis, trends, and usage in critical infrastructures.

Graham, N. (2023) Project Management for Dummies-UK. John Wiley & Sons.

Hancock, P. (2023) Organizing Christmas. Routledge.

Horta, P. (2024) ‘Tis the Season for warm, fuzzy emotion: visual storytelling and nostalgia in Christmas adverts.

Larsen, T. ed. (2020) The Oxford Handbook of Christmas. Oxford Handbooks.

Marshall, H., Johnson, J., and Brown, A.E. (2023) Going alone: The experience of solo eventgoers at music events in the UK. Event Management, 27(4), pp.591-606.

Mason, P. (2020) Tourism impacts, planning, and management. Routledge.

Mingazova, D. and Gbadamosi, A. (2022) Young Consumers, Deprivation, and Christmas Commercialisation. In Critical Perspectives on Diversity, Equity, and Inclusion in Marketing (pp. 177-195). IGI Global.

MURPHY, L. and ANNE, C. (2022) The Varieties of Christmas Magic: An ethnography of festivity, identity, and worldview in British life.

Rogers, T. and Wynn-Moylan, P. (2022) Conferences and conventions: A global industry. Routledge.

Schulenkorf, N., Welty Peachey, J., Chen, G. and Hergesell, A. (2024) Event leverage: A systematic literature review and new research agenda. European Sport Management Quarterly, 24(3), pp.785-809.

# Appendices

## Appendix 1: Assessment 1 PowerPoint Slides