## Slide 1: Project Management LCBB5005 Project Management Tools and Techniques Week 4 Session 2
"Everything should be made as simple as possible, but not simpler."
Attributed to Albert Einstein ,1879 – 1955

## Slide 2: Recap
Last week we looked at the project Management Knowledge Areas and their relevance within the project phases.

## Slide 3: Risk Management Tool
Risk management tools are used to assist in risk identification, establish root/cause effect analysis and enable effective decision making.
The steps involved in a risk management process.
    Evaluated
    Exposure
    Reduce
    Exploit

## Slide 4: Risk Management Process
  Risk management is an on-going process:
    Identify
    Prioritise
    Plan response
    Monitor
    Control

## Slide 5: Risk Management Cycle
Plan and Resource
Monitor and Report
Risk Management
Identify the risks
Evaluate the risks
Identify suitable responses to risks
Select Response

## Slide 6: Risk Identification
Assumption checking
  Identify all assumptions, if they cannot be confirmed they represent a risk
Dependency identification
  Identify all external, internal, and key resource dependencies
Reference to the WBS
  Use the WBS to brainstorm risks specific to an activity
Checklists
  Use checklists of common risk areas to identify potential risks that apply to the project

## Slide 7: Risk Prioritisation
In order to prioritise risk it is necessary to evaluate the
  Probability or likelihood of the risk occurring
  Impact or severity of the risk if it occurs
Probability can be assessed
  Qualitatively using a scale such as ‘High’, ‘Medium’, ‘Low’
  Quantitatively using actual probability values such as ‘30%’ or ‘0.5’
Impact can be assessed
  Qualitatively using a scale such as ‘High’, ‘Medium’, ‘Low’
  Quantitatively using actual monetary values such as ‘£10,000

## Slide 8: Risks Response Planning
After prioritisation the Project Manager should seek to identify suitable, cost effective responses to each priority risk
Responses to priority risks are pre-emptive
Any response should look to reduce either the probability or impact of the risk or both probability and impact.

## Slide 9: Risk Response Strategies
Avoid/Exploit
  Eliminate a negative risk or the impact by doing things differently.
  Ensure that a positive risk occurs and realise the opportunity
Reduce/Enhance
  Reduce the probability/impact of a negative risk to acceptable levels
  Increase the probability/impact of a positive risk
Transfer/Share
  Pass the management or impact of a negative risk to a third party to reduce or avoid the risk , i.e. an insurance policy or penalty clause
  As above for positive risks to exploit or enhance the risk, i.e form a an alliance or joint venture
Acceptance
  Tolerate, but monitor the risk
Contingency
  Do nothing now, but devise a risk response which will be initiated should the risk occur

## Slide 10: Risk Priority Graph
Low Medium High
Impact
6
5, 10
8
1, 9, 11, 12
2, 3
4
7
Probability
High
Medium
Low
Risk Tolerance Line

## Slide 11: Cost Management Tool
All projects are constrained by cost and time; hence, having robust cost and time estimates are essential to ensure that the project meets it’s objectives.
There are different types of estimating cost and time in projects: Analogous, Expert Judgement, Parametric and Three-Points estimating.

## Slide 12: Project Budget
Meredith and Mantel (2009, p.293) “A budget is a plan for allocating resources”.
It can be determined by the top-down and bottom-up approach:
  Top Down: Pre-determined by management based on what it is considered worth spending on the project to achieve the desired benefit.
  Bottom Up: Determined by estimating the cost of activities on the work breakdown structure.
  It is also important to plan for the contingency, which is the sum kept aside to cover any unforeseen cost related risks.

## Slide 13: Developing a Bottom-up Budget
Bottom-up budgets are determined by estimating the cost of each individual WBS activity.
The cost estimates are developed using:
  Direct Costs
  Indirect Costs (Overheads)
  Resource Costs
  Capital Costs
  Material Costs
Notes: Meridith and Mantel have changed the terminology used. What used to be referred to as ‘indirect costs’ are now referred to as ‘overheads’

## Slide 14: Analogous Estimating
According to PMI (2006), “analogous duration estimating utilises the actual duration of a previous or similar schedule as the basis of estimating the duration of a future schedule activity”
It relies on previous experience and knowledge of similar task.

## Slide 15: Expert Judgement Estimating
Expert judgement estimating deploys experts in related field to assist determine the estimate.
It is often adopted in radical innovation or cutting edge technology projects.
For instance:
Aircraft designers
Astronauts
Rocket scientist

## Slide 16: Parametric Estimating
Meridith and Mantel (2009)“an estimating technique that uses a statistical relationship between historical data and other variables (square footage in construction, lines of code in software development) to calculate an estimate for activity parameters, such as scope, cost, budget, and duration”
It relies on:
  Previous experience
  Accurate metrics
  Scaling metrics
  Often referred to as ‘count and compute

## Slide 17: Time Management Tools and Techniques
Identify project activities in groups and the possible sequence within and between the activity groups.
There different dependencies:
  Mandatory: Inherent in nature of the work to be done.
  Discretional: Established based on best practice and methodology.
  External: Relationship to other non project activities.

## Slide 18: Dependency: Rules of Precedence
Finish to Start (FS)
  Task B must not start before task A has completed
Start to Start (SS)
  Task B must not start before task A has started
Finish to Finish (FF)
  Task B must not complete before task A has completed
Start to Finish (SF)
  Task B must not complete before task A has started
A
B
A
B
A
B
A
B
Adapted from Meridith and Mantel, 2009, pp 350-351

## Slide 19: Dependency: Lead and Lag Time
Task precedence can be subject to a time differential
  Activity B cannot start until two days after activity A has completed
  Activity B may start five days after activity A has completed
SS, FF and SF all have implied time differentials
  although these may be agreed at zero
FS has an optional time differential
  the default assumption is a zero time differential
The time differential may be defined as a:
  Lead time – if allows for the acceleration of a subsequent activity
  Lag time – if imposes a delay in a subsequent activity

## Slide 20: Precedence Relationships Diagramming
A key aspect of project planning to organise activities into the correct sequence for completion.
The primary tool used to accomplish this and present the sequence is the Project Network Diagram which is defined as:
“The arrangement of all activities (and in some cases, events) in a project arrayed in their logical sequence and represented by arcs and nodes” (Meridith and Mantel, 2009, p338).

## Slide 21: Network Diagrams: Activity-on-Arrow (AOA)
Under this convention the following rules apply:
  Time and activities flow from left to right
  Activities are represented by arrows and link events
    Such as ‘Start Activity’ and ‘Finish Activity’ or ‘1’ and ‘2’ etc.
  Events and activities are given unique identifiers or labels
  Activity durations are also shown
Start
Finish
Write user requirements
25 days

## Slide 22: Calculating the Critical Path Terms Explained
Early Start (ES): earliest time an activity can begin
  Without interfering with the completion of preceding activities
Early Finish (EF): earliest time an activity can finish
  Early start + activity duration
Late Finish (LF): latest time an activity can finish
  Without delaying the completion of the project
Late Start (LS): latest time an activity can start
  Late finish – activity duration

## Slide 23: Calculating the Critical Path Terms Explained: Float
Float (aka Slack)
  Total Float: The time by which an activity can be delayed without impacting the project end date
    LF-EF or LS-LS can be used to derive total float
  Free Float: The time by which an activity can be delayed without impacting the start time of any successor activity
Notes: Float is the standard UK term, Slack is the standard US term.
Also, Independent Float - not covered here may refer learners to it

## Slide 24: Gantt Chart
A Gantt chart is a form of bar chart
Project activities are listed vertically
Time is measured horizontally from left to right
Each activity is plotted as a bar against time
  The bar starts on the correct start day according to the sequence of activities determined using the precedence network
  The length of the bar corresponds to the duration of the task
Gantt charts can be built manually or can be automated within a tool such as Microsoft Project

## Slide 25: Conclusion
Effective application of the tools and techniques fosters success and ensures that the project meets it’s objective.

## Slide 26: Reference
Meredith, J. and Mantel, S. (2009) Project Management: A Managerial Approach, Asia: John Wiley and Sons.
Wysocki, R.K (2003) Effective Project Management, Traditional, Extreme, Indianapolis: Wiley Publishing Inc.