EXERCISE 3
We had some delay in the previous activities of this job. For this reason we have to reduce the total duration of works in the last part of our arrow diagram shown below. We talked with all subcontractors and calculated normal time, normal cost, crash time and crash cost for every activity as shown in table below. We also know that indirect costs are estimated in £200/week.
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	Normal time
	Normal cost
	Crash time
	Crash cost

	10-11
	6 weeks
	£10,000
	5 weeks
	£15,000

	10-12
	10 weeks
	£25,000
	8 weeks
	£28,000

	11-13
	5 weeks
	£15,000
	4 weeks
	£16,000

	11-14
	8 weeks
	£12,000
	7 weeks
	£15,000

	12-14
	6 weeks
	£25,000
	4 weeks
	£29,000

	13-15
	9 weeks
	£30,000
	7 weeks
	£38,000

	14-15
	5 weeks
	£20,000
	4 weeks
	£20,500



Answer the following questions:
1. The project manager is convinced the cheapest way to reduce the total duration for 2 weeks is with activities 11-13 and 14-15. Do you agree with him?

2. We need to reduce the total duration for 3 weeks. Which activities would you choose?


3. How much is the total project cost?
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