## Slide 1: Vintner’s antiques

## Slide 2: Avengers Project Management Group
Iftey Jewel
Mahmud Akbar
Suraya Begum
Project Managers
Nurunneher Begum
Rena Begum
Notes: Good afternoon everyone. My name is Iftey Jewel. I have been bestowed as the project manager by the Avengers Project Management Group. I would like to introduce my project management team Mr Akbar Ali, Mrs Nurunneher Begum, Mrs Rena Begum, Mrs Suraya Begum.
This is a very prestigious assignment for our company and I greatly appreciate how excited and optimistic the Vintners Antiques group are about relocating their premises to Sparkhill and making a bold and spectacular start. I, along with my talented team will endeavour to meet your expectations to the best of our prowess. After our initial meeting with your team a few weeks ago, I would first of all like to enlighten yourselves about the Project Overview, then afterwards we can discuss and confirm the commencement of the project.

## Slide 3: Project Overview
The Vintner family manages the business
Currently, the 3rd generation is
working for the business
The family has traditional high
street shop at Shirley and a warehouse
in Sparkhill
Denis and Doreen are thinking to
shift all the activities to the warehouse
Both Denis and Doreen want to
utilize their knowledge of modern business
concepts to increase the profits
Both are inspired by the show –
Salvage Hunters
Notes: The purpose of this project is to give a makeover to Vintner Antiques and make the transition from Shirley to Sparkhill as smooth and efficient as possible. The Vintner family manages the business of selling quality antiques in the market. They have been very successful in managing the business for decades. Currently, the 3rd generation is running the business. The family has traditional high street shop at Shirley and a warehouse in Sparkhill. Denis and Doreen are thinking to shift all the activities to the warehouse. They are huge fans of Salvage Hunters. Both Denis and Doreen want to utilize their knowledge of modern business concepts to enhance the trade and increase the profits. Both of them want to transform their business using the concept of Salvage Hunters.

## Slide 4: Project Overview
Fierce competition forcing Vintners to come up with innovative ideas
The space in the warehouse is practically useless for the company
Online retail is a very exciting prospect for Vintners
Through the redesigning and renovating the warehouse, the company can gain plenty of benefits
It will require excellent team work
Digital marketing will play a crucial role in promotion of the company
Notes: There is intense competition in almost every industry and the Vintners feel they are ready for the challenge ahead. There has been an upsurge of interest in antiques collections and people are exploring new ways of buying antiques and artefacts.
There is no doubt that the strong competition has inspired the Vintners to come up with innovative ideas. The company is feeling the heat of competition. The space in the warehouse is practically useless for the company.
Online retail is a very exciting prospect for Vintners. People are buying and selling various kinds of items through online retailing. Growth in technology has made it easy for retailers to sell things online. Through the redesigning and renovating the warehouse, the company can gain plenty of benefits. Customers can either purchase antique items online or they can simply visit the newly designed warehouse. It will require excellent team- work. The company will need to promote its products on various platforms. The company can promote its products using various social media platforms such as Facebook, Instagram, etc.

## Slide 5: Sponsor
Denis Vintner
Steering Group
Commercial
Specialist
User
Doreen Vintner
Omar King
Suha Madani
Paul Ranson
Adviser
Notes: The relationship between sponsors, stakeholders, and project steering group can be explained with the help of a diagram. The diagram employed, illustrated the focus on project management team and project sponsor. Both these parties need to have good communication with customers and resources owner. Project team consisting all the five members of Vintner will try to understand the needs of customers. They will also interact with resource owner. Similarly, project sponsor will interact with customers and resources owners. The project sponsor will need to have better coordination with the management of Vintner Antiques. On the other hand, project team will build a strong reference network. It is necessary for the success of this project that every stakeholder plays their role effectively. There is no point moving ahead in the project without considering the needs of all stakeholders.

## Slide 6: User Stories

## Slide 7: Brown Paper Planning
Notes: Here we talk about the user stories that have been compiled at the start of the project. At the initiation stage of the project which is like a brain storming session, we discussed about fire extinguisher and fire exit door are required by Health & Safety. Firstly, we discussed about the structure in which the Vintner would be transferring the merchandises. The main aspects of the basic necessities have been discussed and prioritised. The insurance would of course be important because the premises and the stocks lying in the premises can be prone to different disastrous situation and since the future is uncertain, insurance is a necessity. Staff toilet is an essential component because the staff working in the warehouse will need the convenience of the toilet indeed. Warehouse employees would also require a kitchen for cooking purpose and there is a need for office room for the completion of the official work.

## Slide 8: User Stories
1
2
3
Notes: Apart from this, there is a need for the installation of roof, because the building is old where the roof needs to be replaced and it is important to have a new roof. Advertising is also essential for publicising the warehouse, via social media and other platforms. Business cards are important to promote the business identity and brand. Also, a loading and unloading bay will be required for shelfing and unloading bay for the premises.
To proficiently operate the warehouse, the firm will require telephone and broadband connection for handling day to day tasks. A new heating system will be required to keep the place warm. Working in good lighting conditions is also important, hence it is essential to have good lighting, and of course electricity would be required to run all these systems.
Moreover, the firm will require a new log on a flex-board to develop and boost company’s image. Personal protective equipment will be required for maintaining safety at the warehouse. The installation of signboards will be important to notify the customers about the direction. The company will require a proper showroom for promotional purposes and display some of the attractive goods to lure the prospective customers. Ventilation is a part of health and safety, and in order to keep the warehouse ventilated the company would need to install the air conditioning system. Also, the aspects that would be nice to have, were discussed which provides for a television for entertainment of staff, canteen room for having meals, tannoy system, sandwich maker, new van and a coffee machine.

## Slide 9
4
5

## Slide 10: The CHEVRON
Notes: The chevron chart is a way of categorizing the user stories into columns where we discussed and organized in the group which jobs need to be carried out as a listing of importance, such as must have, should have and nice to have. This listing will give us a better view of organising our project in to time management and cost.

## Slide 11: The Iron Triangle
Shifting to warehouse
The Iron triangle talks about the constraints which are likely to occur
in the project. Here the main task is to shift
the material to the warehouse and in this respect
the time, costs and the scope are the basic constraints.
Notes: The Iron Triangle defines the triple constrains of time, cost and quality that must be overseen in the project delivery. The triangle illustrates that the three essential factors of time, scope and cost are interrelated, and each point’s functioning or changes impacts the other two aspects. For example the cost focuses on the financial restrains, which is the project budget. The funding determines the hallmarks of the success that can be attained with financial resources. Insufficient funding will be a huge drawback, meaning not all the objectives will be achieved and compromises need to be made.
Here the main tasks are to prepare the warehouse appropriately and to transfer the merchandises to the warehouse safely and efficiently. In this respect the time, costs and the scope are the basic constraints. Considering the different aspects, it seems that the time of 30 days would be enough to handle the aspects that have been identified here and the costs seem to be relevant. Moreover, the scope covers most of the aspects which are under the control of the firm. However, there are some aspects which may be beyond the control of the company and cannot be assessed here, for example adverse weather conditions may delay the installation of the new roof. Therefore having a few days in hand, gives us a bit of leeway.

## Slide 12: Gannt Chart
The Gantt chart is prepared in order to conclude the time required for executing the whole process.
Notes: The Gantt chart is prepared in order to conclude the time required for executing the whole process. The total project is expected to be completed in within 30 days. The Gantt Chart has been prepared for 27 days, and 3 days has been kept as reserved. The major tasks have been compiled under important tasks which include the necessities, then the aspect related to Managing Facility, Organizing the warehouse, fixtures and the equipment.

## Slide 13: Gantt Chart
 | Project Lead: | [ John Doe ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Project Start Date: | 1/27/2020 (Monday) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Today's Date: | 2/18/2020 (Tuesday) |  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
 | Display Week: | 1 |  | Week 1 |  |  |  |  |  |  | Week 2 |  |  |  |  |  |  | Week 3 |  |  |  |  |  |  | Week 4 |  |  |  |  |  | 
 |  |  |  | 1 / 27 / 20 |  |  |  |  |  |  | 2 / 3 / 20 |  |  |  |  |  |  | 2 / 10 / 20 |  |  |  |  |  |  | 2 / 17 / 20 |  |  |  |  |  | 
WBS | Task | Start | End | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su
1 | Important Aspects | Mon 1/27/20 | Sat 2/01/20 | x | x | x | x | x | x | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 
1.1 | Building and Content insurance | Mon 1/27/20 | Mon 1/27/20 | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 
1.2 | Staff Toilet | Tue 1/28/20 | Wed 1/29/20 |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 
1.3 | Staff Kitchen | Thu 1/30/20 | Fri 1/31/20 |  |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 
1.4 | Office Room | Sat 2/01/20 | Sat 2/01/20 |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 
2 | Managing Facility | Fri 2/07/20 | Mon 2/17/20 |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x |  |  |  | t |  |  |  |  | 
2.1 | Folk Lift | Fri 2/07/20 | Fri 2/07/20 |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 
2.2 | Installation of new Roof | Mon 2/10/20 | Wed 2/12/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |  | t |  |  |  |  | 
2.3 | Shutters | Thu 2/13/20 | Thu 2/13/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  | t |  |  |  |  | 
2.4 | Loading Unloading Bay | Fri 2/14/20 | Sat 2/15/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  | t |  |  |  |  | 
2.5 | van | Mon 2/17/20 | Mon 2/17/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | t |  |  |  |  | 
3 | Organizing the Warehouse | Fri 2/14/20 | Mon 2/17/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x | t |  |  |  |  | 
3.1 | Decoration and Shelvings | Fri 2/14/20 | Fri 2/14/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  | t |  |  |  |  | 
3.2 | Safety Equipment | Sat 2/15/20 | Sat 2/15/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  | t |  |  |  |  | 
3.3 | New Sign | Mon 2/17/20 | Mon 2/17/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | t |  |  |  |  | 
4 | Fixtures | Tue 2/18/20 | Wed 2/19/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t | x |  |  |  | 
4.1 | Telephone and Broadband | Tue 2/18/20 | Tue 2/18/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 
4.2 | Good Lighting | Tue 2/18/20 | Tue 2/18/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 
4.3 | Equipment | Tue 2/18/20 | Tue 2/18/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 
4.4 | Gas+Lighting | Tue 2/18/20 | Tue 2/18/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 
4.5 | Health+Safety | Tue 2/18/20 | Wed 2/19/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t | x |  |  |  | 
5 | Equipment | Thu 2/20/20 | Sun 2/23/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  | x | x | x | x
5.1 | Television & Tannoy system | Thu 2/20/20 | Thu 2/20/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  | x |  |  | 
5.2 | Canteen Equipment | Fri 2/21/20 | Fri 2/21/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  | x |  | 
5.3 | Sandwich and Coffee Machine | Sat 2/22/20 | Sat 2/22/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  | x | 
5.4 | Van | Sun 2/23/20 | Sun 2/23/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | x
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | t |  |  |  |  | 

## Slide 14: Estimate using Product Project techniques
Complexity Size | Low | Medium | High
Small | 1 | 3 | 4
Medium | 3 | 5 | 10
Large | 5 | 8 | 10
Roberts2012
Notes: For any business cost and time are very significant factors that can impact the performance of the business as well as its revenue or profit. In the long run the shifting from store to warehouse will be a very cost- effective decision for the Vintner’s family. The warehouses can help in reducing various expenses such as the logistics cost, labour-related cost, etc. The Vintner’s family can also implement some cost-reducing energy within the warehouse. The transportation efforts from transporting the objects from warehouse top stores will also be omitted. The logistics cost will be reduced. The processes of identifying the stocks will also be easier. The better communication flow will be helpful in attaining the tasks at less expense and in short time. All in all, this project has a lot of potential to take Vintner to the next level.

## Slide 15: Cost of the Project
The Estimated Cost for this project will be:£66,000
Total Expected Time: 30 days
Roof Cost | 15,000 | Shutters | 4,500
Gas+Electric | 5,000 | Building &Content Insur | 300
Kitchen&Toilet | 5,000 | Decoration + Shelvings | 10,000
PC/Printer | 3,000 | New sign | 2,000
Lighting | 1,500 | Photographer | 800
Manual Handling Equipment | 8,000 | Car park | 2,000
Van | 3,000 | Health & Safety | 1,400
CCTV Wifi | 1,500 | Office Room | 3,000
Notes: Time has come that the company adopts new ideas to make more profits and become more sustainable. The total costs that have been expected to be incurred for this project would be almost 66,000 GBP and it will take almost 30 days to accomplish the project. Please bear in mind the costs are an estimate and may increase due to new demands or unforeseen circumstances.

## Slide 16: End of Presentation