## Cover
0
FEASIBILITY BUDGET ESTIMATE
STAGE COACH THEARTRE SCHOOL – MERTHYR TYDFIL
(PHASE 1 OF MASTERPLAN CONCEPT)
Client: Ace Capital Projects Ltd
M.E.S.S Construction Services Ref: SCT001
Version: 1
Date: December 2024

## QA
Quality Information
Prepared by |  |  | Checked by |  | Verified by |  |  | Approved by
Max James |  |  | Project Team |  | Project Team |  |  | Project Team
Revision History
Revision | Date |  | Details | Authorised |  | Name |  | Position
1 | 2024-11-01 |  |  | MJ |  | Max James | Commercial Manager
Distribution List
# Hard Copies |  | PDF Required |  | Association / Company Name
1 |  | Yes |  | ACE Capital Projects Ltd
P

## Contents
Table of Contents
1 | Basis for Estimate
2 | Stage Coach Budget Estimate
3 | Car Park Area Budget Estimate
PROJECT NAME Stage Coach Theartre

## Basis for Estimate
1. Basis For Estimate
1.01 | This estimate is based on BCIS figures and indicies for the construction of a theartre within Merthyr Tydfil, on the Glebeland site as per the brief provided by the client
1.03 | The contractor ihas been appointed
1.04 | Specifications and security standards are assumed and to be confirmed.
2. Assumptions and Exclusions
2.01 | VAT is excluded, unless stated otherwise
2.02 | The estimate has been prepared as an assessment of the potential final cost of the intended Works, based on the information noted, and will be subject to change as the design develops and more information becomes available as to the condition of the existing site and buildings
2.03 | Allowances for Design Team fees & surveys are included in the Summary
2.04 | Allowance included for upgrading the existing electrical supply to the site
2.05 | Assumed water and gas supplies have sufficient capacity for the proposed development.
2.06 | An allowance of 15% has been included as part of a contigency to form part of the overall works, this could potentially be reduced upon issue of information provided by the client
2.07 | Where provisional allowances have been made, they have been stated as provisional items. Costs will be firmed up upon recipet of information from the client
2.08 | No allowance for upgrade of district network operator infrastructure
2.09 | Assumed start on site of 3Q2025, based on BCIS Tender Price Indicies an inflation allowance of 3% has been included within the summary
2.1 | This estimate is for estimation purposes only and only includes Phase 1 of the developtment. An allowance has also been made for a provisional car park as the car park provided within the basement does not seem sufficient. This could be valued engineered if the spaces required were to decrease.
3. Areas (SOA)
#REF!
3.1 | Areas (GIFA) |  | m2 | sq. ft
|  | Reception | - | -
|  | Waiting | 59.2 | 637
|  | Café | 138.2 | 1488
|  | Kitchen | 35.5 | 382
|  | Dance Studios | 394.8 | 4250
|  | Offices | 146 | 1572
|  | Theatre | 379 | 4080
|  | Toilets | 78.9 | 849
|  | Storage | 197.6 | 2127
|  | Breakout Spaces | 189.5 | 2040
|  | Dressing Rooms | - | -
|  | Control Room | 31.6 | 340
|  | Bar | 118.4 | 1274
|  | Circulation | 1342.3 | 14449
|  | Atrium | Not Included | Not Included
|  | Plant | 592.2 | 6374
|  | Parking | 244.8 | 2635
|  |  | 3948 | 42497
PROJECT NAME: Stage Coach Theartre

## StageCoach
Project Name: Stage Coach Theartre
Estimate Title: Budget Estimate |  | GIFA | 3948 | m2
Date of issue: November 2024
Ref | Description | Quantity | Unit | Rate £ | Total £
A | BCIS rate for new build theartres | 3948 | m2 | 5389 | 21275772
Type of Work
| Ancillary Works | [5 empty] | Building function
[9 empty] | Sub-Class |  |  | Cut-off years | Sample | Mean | Standard deviation | Decile 0 (lowest) | Decile 1 | Decile 2 | Decile 3 | Decile 4 | Decile 5 (median) | Decile 6 | Decile 7 | Decile 8 | Decile 9 | Decile 10 (highest) | Lower quartile | Upper quartile
B | Schedule of Surveys allowance | item |  |  | 350000 | New build
[7 empty] | 524. | Theatres |  |  |  | 20 | 6 | 3613 | 1210 | 1877 |  |  |  |  | 3639 |  |  |  |  | 5389 | 2993 | 4177
C | Ground clearance allowance | Item |  |  | 200000
D | Upgrade incoming electrical supplies including sub-station | Item |  |  | 250000
E | BWIC with above - trenches etc | Item |  |  | 50000
F | Sprinkler protection | Item |  |  | 250000
G | Fire Officer hydrant tank | Item |  |  | 100000
H | Compound for fire hydrant tanks, including fencing | Item |  |  | 20000
I | BMS controls | Item |  |  | 236880
J | Asbestos removal allowance | Item |  |  | 250000
| Carried Forward |  |  |  | 22982652
| Brought Forward |  |  |  | 22982652
A | Preliminaries | 3% |  |  | 689479.56
| Sub-total |  |  |  | 23672131.56
B | Contractors OHP | 8% |  |  | 1893770.5248
| Sub-total |  |  |  | 25565902.0848
C | Framework Fee / Levy (Provisional) | 1% |  |  | 255659.0208
| Sub-total |  |  |  | 25821561.1056 |  | BCIS Prices |  |  | 2023-05-01 | 444.5
[10 empty] | 2024-08-01 | 472.1
D | Cost Plan & Design Development Contingency | 15% |  |  | 3873234.1658 | [5 empty] | 6.209%
| Sub-total |  |  |  | 29694795.2715 |  | BCIS - TPI |  |  | 4Q24 | 396
[10 empty] | 3Q25 | 407
E | Inflation - mid-point of construction 3Q25 | 3% |  |  | 890843.8581 | [5 empty] | 2.778%
| Sub-total |  |  |  | 30585639.1296
F | Design Team Fees | 5% |  |  | 1529281.9565
| Sub-total |  |  |  | 32114921.0861
| Total Project Costs |  |  |  | 32114921.0861

## Car Park Facility
Project Name: Stage Coach Theartre
Estimate Title: Budget Estimate
Date of issue: December 2024
Ref | Description | Quantity | Unit | Rate £ | Total £
A | Car Parking Facility | nr | 200 | 2500 | 500000
B | Services Disconnection - Allowance | Item |  |  | 50000
C | SUDS - Allowance | Item |  |  | 150000
D | White Line Markings | Item |  |  | 50000
| Sub-total |  |  |  | 750000
G | Preliminaries | 15% |  |  | 112500
| Sub-total |  |  |  | 862500
H | Contractors OHP | 8% |  |  | 69000
| Sub-total |  |  |  | 931500 | BCIS - TPI | 4Q24 | 396
407
J | Cost Plan & Design Development Contingency | 15% |  |  | 139725 |  |  | 2.778%
| Sub-total |  |  |  | 1071225
K | Inflation - mid-point of construction 3Q25 | 3% |  |  | 32136.75
| Sub-total |  |  |  | 1103361.75
L | Design Team Fees including surveys | 5% |  |  | 55168.0875
| Sub-total |  |  |  | 1158529.8375
| Total Project Costs |  |  |  | 1158529.8375

## Back
0