University of Wales Trinity Saint David

School of Engineering

Project Planning

Alexander Penny

1706431

Motorcycle Engineering

25/11/2019

Management, Innovation and Sustainability– M5X01176

Contents

Abstract	1

Group roles & Responsibilities	1

My roles	1

Overall group tasks and associated timings	2

My Tasks	3

Gateway Objectives	4

Concerns	5

Gant Charts	6

Figure 5, Group gant chart	6

Works Cited	7

Abstract	7

# Abstract

The objective of our group project is to develop a Moto 2 entry bike with the intention of maximising performance through applying engineering knowledge and research. Due to the scope of maximising a Moto 2 bike the most appropriate division of tasks was to individually take responsibility for many of the tasks required of a development team. Lap simulation and data logging are to be used to maximise suspension and engine performance.

The purpose of this plan is to ensure our group project is delivered on time and all avenues are identified early on to prevent tasks from being neglected until the final stages of this project.

.

## Group roles & Responsibilities

Zack Church – engine

Eoin Collins – electronics and wiring

Emily-Kate Flewin – suspension

Alexander Penny – exhaust

Jon LW – data analysis and lap time simulator

Lee Stewart – Data analysis and control strategies

# My roles

My responsibility lay in creating a tuned exhaust for the Triumph 765cc Moto 2 engine. Due to Moto 2 regulations the; air box, valve timings & lift and the engine internals must remain the same (Federation Internationale de Motorcylisme (FIM), 2019), subsequently the exhaust is one of the few opportunities to optimise one’s bike and gain a competitive advantage. During the course of my role I will be responsible for modelling various fluid flow scenarios to focus in on the optimal setup for our application.

My aspect of the project requires careful analysis of primary design and Moto 2 regulations. Thankfully Belbin’s model for self-analysis (Belbin, 2010) has shown me to be an Implementer taking practical ideas to actions and a Monitor Evaluator which helps in making impartial decisions, although this trait can be a hindrance to team dynamics as I am often highly critical of plans which can be polarising. Knowing this is will try and balance any flaws I see with practical solutions and discuss the positive features of a course of action. Although the bulk of my work will be completed independently it is important I ensure to maintain a strong dialog with my project group. The results suggest the traits of a Coordinator and a Team worker have not been priorities to me. When working in a team one needs to effectively motivate the team through identifying strength in the members and delegating tasks diplomatically. I believe with conscious effort and open discussion we can all be satisfied with our individual responsibilities and there should be less barriers to success.

I have been identified as type B personality suiting the traits identified by Mr Friedman and Mr Rosenman. (Mcleod, 2017) Looking introspectively, I feel a lack of urgency is an accurate weakness of mine, this may hinder the group project if not addressed. To combat the tendency to stagnate I will set small quantifiable targets in the scope of the more significant goals and gateways.

# Overall group tasks and associated timings

| Team Member | Overall Objective | Specific Goals to Achieve Final Objective | Estimated Completion Dates |
| --- | --- | --- | --- |
| Zach Church | Engine Simulation | Download Ricardo wave and Matlab software. | 10/10/19 |
|  |  | Simulate current competition engines using Ricardo wave. | 18/11/19 |
|  |  | Investigate engine performance and possible improvements. | 15/01/20 |
|  |  | Determine necessary part and flow improvements. | 01/02/20 |
| Eoin Collins | Control Systems and Engine Management | Analyse moto 2 regulations regarding electronics. | 15/11/19 |
|  |  | Contact Magneti Marelli and access the relevant software | 17/12/19 |
|  |  | Analyse a current moto 2 competition motorcycles electronic strategy. | 03/01/20 |
|  |  | Develop a control strategy with relative equipment. | 01/02/20 |
| Emily Flewin | Suspension Systems Design | Researching successful suspension systems. | 10/10/19 |
|  |  | Suspension simulation of chosen suspension system. | 12/12/19 |
|  |  | Designing a suspension system for racing applications. | 08/01/20 |
|  |  | Produce damper dyno charts for the designed suspension. | 01/02/20 |
| Jon Lloyd-Williams | Lap Time Simulator | Research lap simulators & relevant dynamics calculations. | 25/11/19 |
|  |  | Collect Data & Renew 2D licence. | 20/11/19 |
|  |  | Export the data from 2D to excel. | 26/11/19 |
|  |  | Calculate chosen track dimensions. | 04/12/19 |
|  |  | Analyse Results. | 12/12/19 |
|  |  | Create varying simulations using differing input data. | 20/12/20 |
|  |  | Compile results and draw conclusions. | 01/02/20 |
| Lee Stewart | Data analysis and control strategy design. | Gain a software license for the 2D analysis software. | 13/10/19 |
|  |  | Download the required software. | 15/10/19 |
|  |  | Source data sets from racing motorcycles. | 28/10/19 |
|  |  | Analyse the sourced data extensively. | 19/11/19 |
|  |  | Decide on a control strategy for the motorcycle. | 18/12/19 |
|  |  | Decide on sensors and equipment needed to implement the chosen strategy. | 01/02/20 |

Figure 1, Group tasks and timings

# My Tasks

| Task | Description | Estimated Time | Projected dates |
| --- | --- | --- | --- |
| Determine key performance requirements | Identify Moto 2 design and construction restrictions. Collate information on engine operating parameters. | 6h | 15/10/19-15/11/19 |
| Research potential performance gains from a cobra-head bend | Come to understand the dynamics of exhaust gases and their behaviour through a cobra-head elbow | 37h | 19/11/19-18/11/19 |
| Compare and contrast modelling software | Research software choices and availability to find which would be the most appropriate | 5h | 29/11/19 |
| Coordinate with Zack to receive key engine characteristics | The valve timing and exhaust pressure wave are required to further research | 1h | 29/11/19 |
| Simulate the current OEM design | Simulating the current design will provide an opportunity to familiarise oneself with the software and establish a base performance | 37h | 2/12/19-6/12/19 |
| Simulate the effect of such a design in the context of the project engine | I want to quantify the effects on turbulence and scavenging in comparison to a basic design | 39h | 9/12/19-13/12/19 |
| Evaluate value to the design of a full system | Analysing the information gathered to decide on the future of the design | 13h | 14/12/19-18/12/19 |
| Design and Model a primary for competition use | Enacting previous decisions to produce a full simulation | 41h | 19/12/19-03/01/20 |
| Identify potential improvements | Analyse the design to refine the product | 16h | 04/01/20-06/01/20 |
| Create a final exhaust model | Produce a model and Engineers drawings | 19h | 07/01/20-10/01/20 |
| Design jigs for constructing a prototype | Accurate manufacturing of exhausts requires intelligently designed jigs | 32h | 13/01/20-01/02/20 |

Figure 2, My personal tasks and duration

As I am aware of my tendency to lack urgency, Programme Evaluation and Review Technique (PERT) has helped me to have calculated my estimated times using skewed probable duration (Smith, 2002)with the following formula rounded to 2 significant figures:

Estimated time=  Optomistic time+3x Median time+2x Pessimistic time6

## Gateway Objectives

| Title | Classification | Description | Date |
| --- | --- | --- | --- |
| Project Viva | Gateway | Group presentation to Dr Owen Williams | 2/12/19 |
| Determine the value of a cobra-head primary to a moto 2 entry bike | Gateway | The additional complexity of manufacture needs to be justified with quantified performance gains | 22/12/19 |
| Christmas | Milestone | 3 Days off | 23/12/19-25/12/19 |
| Complete final exhaust model | Gateway | Data to be generated on predicted characteristics and fully evaluated the product | 10/01/20 |
| Exhaust and Jig technical drawings completed | Milestone | If going to production the design would be ready for prototyping at this stage. | 01/02/20 |

Figure 3, Milestones & Gateways

Figure 4, Milestone Chart

As the assessment specification advices I am going to detail one of my gateways. Gateways require quantifiable goals, when planning a project these goals make it practical to monitor progress and analyse the value of avenues of research.

It is important that development hours are being invested in the right areas particularly when working in a small team. With this in mind a key priority of mine has been to determine the value of a cobra head bend early on in the timeframe of the project. By setting SMART targets which were Specific, Measurable, Agreed, Realistic and Time Bound, myself and my team mates can monitor progress up until the gateway regularly seeing the completion of goals. A secondary benefit would be the motivational effect of a clear pathway and objectives.

A significant gateway in my aspect of the project is to determine the value of a cobra-head primary to a Moto 2 entry bike. This point will dictate all ongoing design decisions in the quest for peak performance. The precursors for this gateway is to have quantified the flow through the standard section and through an improved model. An understanding of  the principles at work will have been cultivated to base the design ethos upon. The metric determining the value of the concept will be based on the turbulent kinetic energy and the flow characteristics through the section. One would hope for a minimum 2.5% improvement in output to assure the exhaust to be a worthwhile endeavour. A 2.5% improvement to Power would be 2.26 kw increasing from 90.50kw to 92.76kw at 11,750 rpm.

To eliminate any potential bias in making this decision I am going to present my findings to the group project team and we shall vote on the future of this element of the project.

As this is a bespoke design for a bespoke application, large scale manufacture is not a priority. As a small quantity of exhausts will be built the cost to performance is comparatively high in regards to a mass-produced product. Although a bespoke exhaust is to be built certain manufacturing methods are prohibitively expensive for the application. Identifying overcomplication at an early stage will help to prevent a technically perfect but impractical design burning through research hours.

# Concerns

I have heard anecdotes of software such as Ricardo Wave producing predictions which do not align with the characteristics of the prototype when tested. This can lead to projects over promising and under delivering. This would be an enormous embarrassment and could likely have monetary implications. To mitigate this risk an awareness of the potential unreliability will help in evaluation promoting an element of scepticism, I intend to apply first principles to the problem and hopefully reach a supporting result. It is hard to predict the potential likelihood the project could be impacted by unreliable results, I believe the best defence is to carefully consider any data assessing its practicality.

When a project team has a large number of individuals requiring to learn new skills for their roles productivity can be low. The relative in inexperience and likely knowledge deficit of each of the team members could lead to delays in the implementation of the group objectives. We have tried to predict the low productivity inherent in developing proficiency with a topic. Regular meetings and a shared agenda will be used as the primary detection method for tasks lagging behind the project plan.

# Gant Charts

# Figure 5, Group gant chart

Figure 6, My personal gant chart

# Works Cited

Belbin, R. M., 2010. In: Team Roles at Work. Ruteledge: Belbin.

Mcleod, S., 2017. Simply Psychology. [Online] 
Available at: https://www.simplypsychology.org/personality-a.html
[Accessed 25 22 2019].

Smith, N. J., 2002. In: Engineering Project Management. Oxford: Blackwell Science Ltd, pp. 7-11.

# Abstract

Engineering Management:  Management, Sustainability and Innovation

Meeting:   		Meeting 1			Venue:  Room 3, First Floor, Y Fforwm      Date:  17/10/19

A/D/I (Action/Decision/Information

Attendees:

| Name | Signature |
| --- | --- |
| Lee Stewart |  |
| Alexander Penny |  |
| Zachary Church |  |
| Emily-Kate Flewin |  |
| Eoin Collins |  |
| Jon Lloyd-Williams |  |

| No | A/D/I | Objective/Description | Who | When | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | I | Discussed individual interests that group members want to research into | All | N/A | Complete |
| 2 | A | Found the course director to advise the group | All | N/A | Complete |
| No | A/D/I | Objective/Description | Who | When | Status |
| 3 | I | Discussed individual interests with the course director in order to form a group | All | N/A | Complete |
| 4 | A | Created individual plans for each person in the group | All | N/A | Complete |
| 5 | A | Accessed and downloaded the Moto2 regulations | All | N/A | Complete |
| 6 | A | Created a WhatsApp group for the group project | Emily-Kate | N/A | Complete |
| 7 | A | Created objectives to be completed by the next meeting | All | N/A | Complete |
| 8 |  |  |  |  |  |

Engineering Management:  Management, Sustainability and Innovation

Meeting:   		Meeting 2			Venue:  Room 3, First Floor, Y Fforwm      Date:  24/10/19

A/D/I (Action/Decision/Information

Attendees:

| Name | Signature |
| --- | --- |
| Lee Stewart |  |
| Alexander Penny |  |
| Zachary Church |  |
| Emily-Kate Flewin |  |
| Eoin Collins |  |
| Jon Lloyd-Williams |  |

| No | A/D/I | Objective/Description | Who | When | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | I | Discussed the groups weekly progress | All | N/A | Complete |
| 2 | D | Decided a specific time for the meetings | All | N/A | Complete |
| No | A/D/I | Objective/Description | Who | When | Status |
| 3 | A | Certain members of the group practiced opening the data software | Lee Emily-Kate Jon | N/A | Complete |
| 4 | A | Practiced opening Matlab and went through tutorials | Zack | N/A | Complete |
| 5 | I | Brainstormed certain deadlines for certain parts of the group project to be finished by | All | N/A | Complete |
| 6 | A | Created deadlines for the project | All | N/A | Complete |
| 7 | A | Created objectives to be completed by the next meeting | All | N/A | Complete |
| 8 |  |  |  |  |  |

Engineering Management:  Management, Sustainability and Innovation

Meeting:   		Meeting 3			Venue:  Room 3, First Floor, Y Fforwm      Date:  31/10/19

A/D/I (Action/Decision/Information)

Attendees:

| Name | Signature |
| --- | --- |
| Lee Stewart |  |
| Alexander Penny |  |
| Zachary Church |  |
| Emily-Kate Flewin |  |
| Eoin Collins |  |
| Jon Lloyd-Williams |  |

| No | A/D/I | Objective/Description | Who | When | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | I | Discussed the groups weekly progress | All | N/A | Complete |
| 2 | A | Created a combined word document for the report | All | N/A | Complete |
| No | A/D/I | Objective/Description | Who | When | Complete |
| 3 | I | Discussed each other’s plans and progress to see if anyone needs help or guidance that another team member can offer | All | N/A | Complete |
| 4 | I | Explained possible designs for the exhaust systems | Alex | N/A | Complete |
| 5 | I | Explained the lap time simulator and what strategies are most effective | Jon | N/A | Complete |
| 6 | A | Created objectives to be completed by the next meeting | All | N/A | Complete |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |

Engineering Management:  Management, Sustainability and Innovation

Meeting:   		Meeting 4			Venue:  Room 3, First Floor, Y Fforwm      Date:  7/11/19

A/D/I (Action/Decision/Information

Attendees:

| Name | Signature |
| --- | --- |
| Lee Stewart |  |
| Alexander Penny |  |
| Zachary Church |  |
| Emily-Kate Flewin |  |
| Eoin Collins |  |
| Jon Lloyd-Williams |  |

| No | A/D/I | Objective/Description | Who | When | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | I | Discussed the groups weekly progress | All | N/A | Complete |
| 2 | I | Discussed the price of the full project | All | N/A | Complete |
| No | A/D/I | Objective/Description | Who | When | Status |
| 3 | I | Explained the suspension trace data to the rest of the group and getting suggestions on what the best design would be | Emily-Kate | N/A | Complete |
| 4 | I | Discussed each other’s plans and progress to see if anyone needs help or guidance that another team member can offer | All | N/A | Complete |
| 5 | I | Explained the powertrain data and showed the rest of the group the Matlab file whilst receiving suggestions on the best strategy | Zack | N/A | Complete |
| 6 | A | Created objectives to be completed by the next meeting | All | N/A | Complete |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |

Engineering Management:  Management, Sustainability and Innovation

Meeting:   		Meeting 5			Venue:  Room 3, First Floor, Y Fforwm      Date:  12/11/19

A/D/I (Action/Decision/Information

Attendees:

| Name | Signature |
| --- | --- |
| Lee Stewart |  |
| Alexander Penny |  |
| Zachary Church |  |
| Emily-Kate Flewin |  |
| Eoin Collins |  |
| Jon Lloyd-Williams |  |

| No | A/D/I | Objective/Description | Who | When | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | I | Discussed the groups weekly progress | All | N/A | Complete |
| 2 | D | Changed the date of the next meeting | All | For the next meeting | Complete |
| No | A/D/I | Objective/Description | Who | When | Status |
| 3 | I | Explained the possible design and strategies for the control systems | Eoin & Lee | N/A | Complete |
| 4 | A | Improved on the current objectives and time scales | All | N/A | Complete |
| 5 | D | Changed individual plans to fit the new objective and timescales | All | N/A | Complete |
| 6 | A | Created objectives to be completed by the next meeting | All | N/A | Complete |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |

Engineering Management:  Management, Sustainability and Innovation

Meeting:   		Meeting 6			Venue:  Room 3, First Floor, Y Fforwm      Date:  14/11/19

A/D/I (Action/Decision/Information)

Attendees:

| Name | Signature |
| --- | --- |
| Lee Stewart |  |
| Alexander Penny |  |
| Zachary Church |  |
| Emily-Kate Flewin |  |
| Eoin Collins |  |
| Jon Lloyd-Williams |  |

| No | A/D/I | Objective/Description | Who | When | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | I | Discussed the groups weekly progress | All | N/A | Complete |
| 2 | A | Created a combined PowerPoint presentation for vivas | All | 2/12/19 | Complete |
| No | A/D/I | Objective/Description | Who | When | Status |
| 3 | I | Brainstormed control strategy ideas for the motorcycle | All | N/A | Complete |
| 4 | I | Considered the best control strategy for the motorcycle | All | N/A | Complete |
| 5 | A | Checked that our plans/ideas fit the regulations | All | N/A | Complete |
| 6 | I | Discussed each other’s plans and progress to see if anyone needs help or guidance that another team member can offer | All | N/A | Complete |
| 7 | A | Created objectives to be completed by the next meeting | All | N/A | Complete |
| 8 |  |  |  |  |  |