## Final
APEX CONSTRUCTION
PRELIMINARY SCHEDULE OF VALUATIONS (MONTHLY EXPENDITURE ANALYSIS)
Client | ACE Capital Project | [23 empty] | Date | 25th April 2024
Contract | Phase 1: Riverside Health Centre | [23 empty] | Revision | Rev A
[25 empty] | Programme No | DALTON BROWN
ITEM | ELEMENT | ACTUAL | PROV | TOTAL | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | Comments
[5 empty] | 2025-01-01 | 2025-01-29 | 2025-02-26 | 2025-03-26 | 2025-04-23 | 2025-05-21 | 2025-06-18 | 2025-07-16 | 2025-08-13 | 2025-09-10 | 2025-10-08 | 2025-11-05 | 2025-12-03 | 2025-12-31 | 2026-01-28 | 2026-02-25 | 2026-03-25 | 2026-04-22 | 2026-05-20 | 2026-06-17 | 2026-07-15 | 2026-08-12
0
0
3 | SUPERSTRUCTURE | 4089793.08 | 0 | 4089793.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89322 | 738800.2857 | 1028302.2857 | 1485455.3177 | 725002.6829 | 20660.508 | 0 | 0 | 0 | 0 | 0
0
3.02 | Frame | 1751548 |  | 1751548 | 2025-12-31: 500442.2857; 2026-01-28: 500442.2857; 2026-02-25: 500442.2857; 2026-03-25: 250221.1429
3.03 | Upper Floors | 426000 |  | 426000 | 2025-12-03: 42600; 2025-12-31: 85200; 2026-01-28: 127800; 2026-02-25: 127800; 2026-03-25: 42600
3.04 | Roof | 689830 |  | 689830 | 2026-01-28: 137966; 2026-02-25: 482881; 2026-03-25: 68983
3.05 | Stairs | 129920 |  | 129920 | 2025-12-03: 12992; 2025-12-31: 51968; 2026-01-28: 25984; 2026-02-25: 25984; 2026-03-25: 12992
3.06 | External Walls | 674600 |  | 674600 | 2025-12-03: 33730; 2025-12-31: 101190; 2026-01-28: 236110; 2026-02-25: 168650; 2026-03-25: 134920
3.07 | Windows & External Doors | 186640 |  | 186640 | 2026-02-25: 74656; 2026-03-25: 111984
3.08 | Internal Walls & Partitions | 206605.08 |  | 206605.08 | 2026-02-25: 82642.032; 2026-03-25: 103302.54; 2026-04-22: 20660.508
3.09 | Internal Doors | 22400 |  | 22400 | 2026-02-25: 22400
0
4 | FINISHES | 402142.41 | 0 | 402142.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20870.4 | 128654.481 | 190636.005 | 61981.524 | 0 | 0 | 0 | 0 | 0
0
4.01 | Wall Finishes | 104352 |  | 104352 | 2026-01-28: 20870.4; 2026-02-25: 41740.8; 2026-03-25: 41740.8
4.02 | Floor Finishes | 206605.08 |  | 206605.08 | 2026-02-25: 41321.016; 2026-03-25: 103302.54; 2026-04-22: 61981.524
4.03 | Ceiling Finishes | 91185.33 |  | 91185.33 | 2026-02-25: 45592.665; 2026-03-25: 45592.665
0
5 | FIXTURES & FITTINGS | 80000 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0
0
5.01 | General Fixings | 80000 |  | 80000 | 2026-03-25: 80000
0
6 | SERVICES | 545828.5 | 0 | 545828.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54836.4 | 138139.15 | 154980.45 | 130484.95 | 31454.8 | 35932.75 | 0 | 0 | 0
0
6.01 | Plumbing, Heating and Ventilation Installations | 58454 |  | 58454 | 2026-01-28: 23381.6; 2026-02-25: 23381.6; 2026-03-25: 8768.1; 2026-06-17: 2922.7
6.02 | Electrical Installations | 314548 |  | 314548 | 2026-01-28: 31454.8; 2026-02-25: 62909.6; 2026-03-25: 94364.4; 2026-04-22: 78637; 2026-05-20: 31454.8; 2026-06-17: 15727.4
6.03 | Builders Comparison | 172826.5 |  | 172826.5 | 2026-02-25: 51847.95; 2026-03-25: 51847.95; 2026-04-22: 51847.95; 2026-06-17: 17282.65
0
7 | EXTERNAL WORKS | 859340 | 0 | 859340 | 0 | 479700 | 325784 | 35904 | 17952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
7.01 | Site Clearance - Cleaning and levelling of site | 799.500.000 |  | 799500 | 2025-01-29: 479700; 2025-02-26: 319800
7.02 | New Road Layout | 59840 |  | 59840 | 2025-02-26: 5984; 2025-03-26: 35904; 2025-04-23: 17952
0
0
8 | Risk Contingency | 799108.15 | 0 | 799108.15 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 36323.0977 | 0
0
8.01 | Design Contingency | 232204.32 |  | 232204.32 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418
8.01 | Construction Risk | 232204.32 |  | 232204.32 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418
8.01 | Employers Change | 232204.32 |  | 232204.32 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418 | 10554.7418
8.01 | Other Misc. Risks | 102495.19 |  | 102495.19 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723 | 4658.8723
9 | Variations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
TOTALS - MONTHLY GROSS APPLICATION |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTALS - RETENTION (5%) |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTALS - MONTHLY NETT APPLICATION |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTALS - CUMULATIVE GROSS (Excl VAT) |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
NOTES:
Includes Contract Instructions as identified above