EMPL4009

Project Planning

Case study of Rent A Car 24 Hours Company

Student Name: Sumae Embalo

Student ID:1605442

Module Leader Name:

# Sumae Embalo e silva

Table of Contents

1.2 Is a project worth doing? Requires a Cost-Benefit Analysis with explanation	3

1.3 Project Plan PID (Delivery and Project Closure)	4

1.4 Two or more SMART milestones	13

1.5 Project Evaluation Technique - Focus Group, Interviews with Stakeholders	14

2.1 Identify financial savings from the project – 2 – 5 savings needed	15

2.2 Wider non- financial savings – increased self-esteem, team outputs improve	15

2.3 Reason for project failure:	15

References	16

# 1.2 Is a project worth doing? Requires a Cost-Benefit Analysis with explanation

Yes, the project is worth of doing as it help to demonstrate the scope and constraints of Rent A Car 24 hours company project while integrating its cab service business in Kennington.

| Year | Investment or cost (£) | Income or benefits (£) | C-B ratio |
| --- | --- | --- | --- |
| 0 | 30,000 | 10,000 | 0.333333 |
| 1 | 30,000 | 25,000 | 0.833333 |
| 2 | 30,000 | 35,000 | 1.166667 |

The cost-benefit analysis of Rent A Car 24 hour’s company project is described above in which the initial cost involved in establishment of new cab service business in Kennington is £ 30,000. The three-year C-B analysis ratio are 0.33, 0.833, 1.166 are being presented which determine that in the first two years, the firm does not make any profit on their initial investment. By analysing the C-B graph it is found that in the middle of 1st and second year the project would be able to make specific profit on their investment to gain competitive advantage.

# 1.3 Project Plan PID (Delivery and Project Closure)

| 1.3 Project Initiation Document (PID) (Blank PID to copy and paste into your assignment to fill in) | Tick when complete |
| --- | --- |
| Section 1 – What is the project all about? |  |
| Project Title Rent A Car – 24 hours a day |  |
| Background The car industry in the recent five years has drastically developed at a CAGR of 1.14% over the period of 2006-2015. Moreover, it is also found that the industry would emerge and grow through 2021 with rising per capita income of people and corporate profit. |  |
| Purpose The main purpose of the project is to reflect a project planning criteria report for Rent A Car 24 hours which is a London based company while integrating its business to Kennington to provide timely, reliable and car hire services |  |
| Objectives (and how they will be measured) - To pursue an aggressive marketing campaign and from that, penetrate at least 35% of the market share This objective would be measured by comparing and analysing the previous year market share of car rental company with its current market share figure - To be the top-rated car Hire Company in London metropolitan area by continuously monitoring, evaluating, and following up on customer call-ins. This is to be measured by taking feedback and suggestion of customers who would be liable for using rental car services in their daily life through survey session. |  |
| Project scope - Leisure car rental services - Exotic car rental - Business car rental services - Car sharing services - Car leasing services |  |
| Exclusions from scope None |  |
| Deliverables (including dates of completion) - Organising feasible study 10.01.2018 - Getting a business permit and registration 16.01.2018 - Marketing resources 16.01.2018 - Purchase of cars 23.01.2018 - Online promotion 29.01.2018 - Opening business 04.02.2018 |  |
| Constraints The project implementation date will rely on an initiated date in which the company is able to accomplish all milestones through execution of smart objectives or else project would be delayed (Chang, 2013). Registration and car vehicle acquisition are also considered as constraints that may hamper project completion and performance aspect. |  |
| Assumptions - The Car Hire services will run for 24 hours a day by operating from Monday to Saturdays only. - All the staff working in company reception and control room will work for approximately 6 hours per day on a rotational shift |  |
| Section 2: Why should this project go ahead? |  |
| Business case: Project Benefits The benefits of the project are that it would assist Rent A Car 24 to open a new business in Kennington by penetrating at least 35% of the market share. The project would also provide an opportunity for the company to use innovative technology and deliver reliable car service to customers to gain competitive advantage within Car Rental industry |  |
| Options - Attracting a large customer base - Providing real-time services to customers through GPS technology - Purchase trending, stylish and innovative cars for rental purpose |  |
| Cost and Timescale The starting up a new cab business by Rent A Car 24 hours would take approximately 1 month at a stipulated cost of £30,000 |  |
| Cost/Benefit Analysis Discussed in 1.2 section |  |
| Risk Analysis: Risk Identification Name of the risk; Occurrence rate; Probability; Impact. Unfavourable government policies; High; High; It would create an impact on business registration and permit of car within new market. Competitions within existing car rental business; Medium; High; It would reduce the market share value of Rent A Car 24 hours company. Financial issue; Medium; Moderate; Hamper in meeting project deliverables and resources within deadline time. Lack of project development allocated time; High; Moderate; Work task completion process could be delayed (Cserhati & Szabo, 2014). |  |
| Risk prevention To prevent the risk project manager of Rent A Car 24 hours should able to make an appropriate budget and time plan. Moreover, market analysis of car rental business would also reduce the risk of competition by providing high-class services to customers at an affordable price |  |
| Risk Management Not applicable |  |
| Risk Monitoring Board of members and project manager of Rent A Car 24 hours would be responsible for monitoring task activities of team members so that new business start-up project could be accomplished within deadline. |  |
| Section 3: Who will work on the project? |  |
| Roles and Responsibilities - The project manager is responsible for making blueprint of new car hire business with an appropriate budget plan - Director of Rent A Car 24 hours company roles is to make an effective decision and allocate essential resource with a budget to complete project - The administrative department is responsible for applying for permit and order from transport legislative. - The fleet manager job roles and responsibilities are to maintain and manage workshops for managers - The operational manager is liable for providing real-time services to clients associated with car rental services |  |
| Project Organisation Chart/Structure diagram |  |
| Names of: Project Sponsor Senior Management Team |  |
| Project Manager (PM) Managing Director |  |
| Section 4: How and when will the project be delivered? |  |
| Initial Project Plan |  |
| Assignments/Milestones List milestones here; List times when they should be achieved by here. Organising feasible study; 10.01.2018. Getting business permit and registration; 16.01.2018. Marketing resources; 18.01.2018. Purchase of cars; 23.01.2018. Online promotion; 29.01.2018. Opening business; 04.02.2018. Post-implementation Review; 05.02.2018. |  |
| Schedule (Gantt Chart) January 2017 Week 1; January 2017 Week 2; January 2017 Week 3; January 2017 Week 4; February 2017 Week 1. Conducting Feasibility Studies. Business Registration and Permits. Generating capital from family members. Business permits and registrations. Official Website and marketing resources set up. Car Vehicle acquisition/Purchase an acquisition. Promotion and Awareness both online and in the community. Business Opens. In the project, different steps or tasks would be done such as - Organising feasible study - Getting business permit and registration - Marketing resources - Purchase of cars - Online promotion - Opening business The project will take 1 month by starting date of 05.01.2018 and completion date is 05.02.2018 The project manager is responsible for monitoring each phase task completion success criteria before initiating another task. |  |
| Human Resource Requirements: Project Team - HR manager - Marketing personal - Technicians |  |
| Support Staff Not essential |  |
| Additional Staff Not essential |  |
| Project Control: Monitoring mechanisms The project manager has the command to monitor all task mechanism by development of Gantt chart at starting phase of Rent A Car 24 hours company project |  |
| Communication channels and schedules Communication channels like virtual meeting, conference, emails and telephonic calls are being used by project manager to contact and send project information to team members (Daw, 2016). Twice in week of implemented Rent A Car 24 hour’s company development project communication is being done which is further reported to Managing Director. |  |
| Quality Control - The business registration and permit are to be done and evaluated with prior permission from legislative - Post-implementation Review is done after achieving all project milestones |  |

# 1.4 Two or more SMART milestones

| Goal | SMART actions | Who | Deadline | Monitor |
| --- | --- | --- | --- | --- |
| To get business Registration and Permits | It would help to run the cab service business in an effective manner This goal would able to generate 35% of market share Making of Gantt chart so that all task could be distributed to individuals effectively To compete this milestone time plan and proper resource allocation is done The time duration is 1 week to complete this task | Managing director or project manager | By 14.01.2018 | Progress |
| Making of official website to star business | It would promote service car business operation Effective completion would help to enhance customer base Giving tender to IT company Would help to provide online booking and payment facility Completed in 1 week | Managing director or project manager | By 21.01.2018 | Progress |

# 1.5 Project Evaluation Technique - Focus Group, Interviews with Stakeholders

To complete the project Post Implementation Review (PIR) technique could be conducted by project managers to evaluate the delivered objectives and future actions that would assist to prosper car hire services efficiency of Rent A Car 24 Hours Company. The stakeholders associated with the project are employees and customers (Heagney, 2016). To get an idea about car service performance review will be done through a questionnaire with customers and analysing monthly sales figure of new business.

# 2.1 Identify financial savings from the project – 2 – 5 savings needed

- To use hybrid car which runs on solar energy and electrical energy

- To send cab service bills through emails and messages rather than printing papers

- To use self-driving mode cars by reducing the additional cost involved with drivers

# 2.2 Wider non- financial savings – increased self-esteem, team outputs improve

- The completion of project would assist in providing an opportunity to a local citizen of Kennington to get employment within Rent A Car 24 Hours Company.

- The customers would get a reliable and valuable cab service at a reasonable price on their doorstep

- The company would also increase their brand image and customer loyalty by enhancing business operations in a new market

- The involvement of staffs at initial level would increase their confidence and improve morale to deliver high performance within workplace

# 2.3 Reason for project failure:

The primary reason for the failure of project are as follows:

- Lack of knowledge amongst project stakeholders about project plan of Rent A Car 24 Hours Company while integrating to a new market

- Lack of guidance and leadership

- Poor planning and project development

- Inadequate support from upper management

- Unethical behaviour of driver towards customers

- Hike in pricing strategy

# References

Chang, C., 2013. Understanding the hold-up problem in the management of megaprojects: The case of the Channel Tunnel Rail Link project.. International Journal of Project Management,, 31(4), pp. .628-637.

Cserhati, G. & Szabo, L., 2014. The relationship between success criteria and success factors in organisational event projects.. International Journal of Project Management, , 32(4), pp. 613-624..

Daw, A., 2016. Systems Engineering and Project Management. London: london publiher .

Floricel, S., Bonneau, C., Aubry, M. & Sergi, V., 2014. Extending project management research: Insights from social theories.. International Journal of Project Management,, 32(7), pp. 1091-1107..

Heagney, J., 2016. Fundamentals of project management.. 1 ed. NY: AMACOM Div American Mgmt Assn..