UNIVERSITY OF WALES TRINITY SAINT DAVID

## Contemporary Themes

## Conference Learning Logs

## Student: Diana Lima

Executive Summary

In this paper a conference in the field of Hotel Industry will be planned, more precisely it will be a food waste Event in which we hope that, the goal is giving some knowledge about issues recommendations and solutions for minimize the waste in the hospitality industry. We want to achieve this result bringing real data regarding the food waste, we are working currently in Marriott Heathrow we want to address the conference to all General Manager of Marriott UK.

We will establish the team that will take care of the planning and we will draw up logs for each week until the event. In these logs, we will show what actions each team member will perform as well as the progress of our activity.

Conference Group

We are working in Marriott Heathrow (general manager: JIT, Operational manager: VERONIKA, Marketing Manager: GENNY, public relation: DIANA) and with the management team we are deciding to give a conference about food waste in Hospitality in UK. We are inviting 200 people (General Managers of Marriott in UK).  We decided to invite two guests from the government that are going to talk about food waste in hospitality in UK. We invited 200 managers but just 100 are going to attend the conference.

Structure of the conference:

- 10.00-10.10 am: welcome notes

- 10.10-10.40 am: presentation by government ministers’ hospitality

- 10.40-11.00 am: coffee break

- 11.00-12.15 am: introduction with Marriott managers

- 12.15-1.45 pm: lunch break

- 1.45-2.45 pm: recommendation and solution

- 2.45-3.15 pm: afternoon/tea break

- 3.15-4.00 pm: question time

At this stage we don’t need any more sponsorship, because we are working in the Marriott and we are organizing the conference with Marriott. Marriott is going to finance the event.

Details of our Event:

Venue:  Marriott Hotel London Heathrow

Heathrow Airport, Bath Rd, Harlington, Hayes UB3 5AN, UK.

Date: 04 /09/2020

Hour: 10:00 am -16:00pm

Sponsorship: Heathrow, Marriott Heathrow, and the University of Wales.

The capacity of Venue: 100 people

Promotion: Instagram, Facebook, Twitter.

Team distribution:

General Manager: Jit

Operations Manager: Veronica

Marketing Manager: Genny

Public Relation: Diana

Conference Learning Logs

| Student Name: | Diana Lima |
| --- | --- |

| Week 1 | Monday July 13th, 2020 |
| --- | --- |
| Planning: - Choosing topics for conference - Making teams and dividing activities to four major segments - Weekly meetings - Observing deadlines and defining tasks for each member |  |
| Organising: - We formed four major groups to divide workload for the conference - Four teams- General management, operations management, marketing, public relations - General Manager: Jit - Operations Manager: Veronica - Marketing Manager: Genny - Public Relation: Diana |  |
| Managing: - Timelines for every team to recognise the progress of tasks - Minutes for every meeting to keep track of the operations - Technical support to be provided for management and marketing activities |  |
| Marketing: - To form marketing objectives and plans - To communicate objectives and plans with other teams - Framing design plans for the conference |  |
| Technical: - Evaluation of standards - Examination of available support - Need for new supporting devices |  |
| Problems/Resolution Action Plan: - Identification of members’ personalities and distribution of team roles accordingly - Discussion regarding conference objectives and requirements - Team and group reviews for evaluation of weekly progress on tasks |  |
| Focus for the Week: - Theme selection - Team allocation - Task distribution |  |

Student Signature: ___Diana Lima______________________

Date: _____13/07/2020___________________

| Week 2 | Monday July 20th, 2020 |
| --- | --- |
| Planning: - Managing conference activities and elements - Distribution of team roles as per individual themes selected |  |
| Organising: - Selection of major theme- waste management practices as a form of sustainability in hospitality industry - Individual themes- issues of sustainability and waste management, food waste management in hospitality sector, recommended measures for reducing food waste - Deciding on conference structure and timeline - Selection of participants, volunteers and guest speakers |  |
| Managing: - Meeting minutes for division of main theme to sub-themes - Selection of different teams for discussion on separate themes - Negotiation and conflict management within groups - Developing core participants and speakers for conference |  |
| Marketing: - Decision of developing online website for marketing conference - Collaborative working between operations, marketing and public relations team for marketing activities - Evaluating progress for operations and public relations teams |  |
| Technical: - Creation of online conference portal through website - Collaboration between different teams to reduce workload and simplify complexities - Website interface design ideas and identifying probable sponsorships |  |
| Problems/Resolution Action Plan: - Communication issues between team members - Ineffective teamwork affecting progress of meetings - Decision regarding conference website layout and other variables - Teamwork building activity required |  |
| Focus for the Week: - Comprehensive layout for main topic and sub-topics for the conference to be developed - Developing strategies for better communication within teams and stakeholders - Cooperative working between operations and management team regarding technical matters and requirements |  |

Student Signature: _____Diana Lima____________________

Date: _____20/07/2020___________________

| Week 3 | Monday July 27th, 2020 |
| --- | --- |
| Planning: - Distribution of speaking time decided for volunteers, guests and participating groups - Identified charities and small organisations associated with waste management - Team interaction and involvement evaluation through progress examination - Creation of basic components within the website interface for the conference |  |
| Organising: - Evaluation of existing deadlines - Decisions regarding online streaming of conference - Technical requirements finalisations |  |
| Managing: - Group discussion based on the existing meeting minutes from previous weeks - Evaluation of progress from every team - Public relations team activities redistributed and collaborative working between marketing and public relations team |  |
| Marketing: - Marketing plan and operations realigned as per requirements - Creation of promotional content for the website - Contact list and mailing list generated for guest speakers, sponsors and participating members |  |
| Technical: - Effective communication strategy for teams and participating members - Sales and promotion matters examined by operations, marketing and public relations team - Price and availability of technical support decided |  |
| Problems/Resolution Action Plan: - Availability of technical support for large scale digital conference - Constant evaluation of marketing plan revealed lack of organisation between operations and marketing function - Collaborations increased with participating firms and charities for better fund collection and sponsorships |  |
| Focus for the Week: - Public relations and operations team to decide on the finalized version of website layout - Completed list of potential sponsors for the event - Complete list of charities to be included for the conference |  |

Student Signature: ____Diana Lima_____________________

Date: ___27/07/2020_____________________

| Week 4 | Monday August 3, 2020 |
| --- | --- |
| Planning: - Recap of previous ideas and progress evaluation for conference activities - Confirmation for guests and sponsors for the online conference - Confirmation of available technical support |  |
| Organising: - Examination of technical and audio-visual support system - Examination of website layout and user interface - Marketing and public relations team activities evaluated |  |
| Managing: - Evaluation of progress for every activity - Sponsor meetings and fund allocation for budget - Examination of audio-visual elements - Creation of draft conference schedule |  |
| Marketing: - Designated spots for sponsors on website - Development of charity plans and budgetary requirements - Formulating communication plan and strategy during conference |  |
| Technical: - Adjusting website layout and making changes as per requirements - Identifying issues with audio-visual equipment - Collaborating with public relations and operations team for better communication plan with sponsor and charities |  |
| Problems/Resolution Action Plan: - Problematic audio-visual equipment requires remedial measures - Reforming schedule as per sponsor requirements - Readjusting website layout for sponsorship advertising and accommodation of charities |  |
| Focus for the Week: - Changing layout for the website and creating larger banners for sponsors disrupts the core image display for conference - Better communication between sponsors and public relations team required for increased efficiency in message delivery |  |

Student Signature: ______Diana Lima___________________

Date: ___03/08/2020_____________________

| Week 5 | Monday August 10th, 2020 |
| --- | --- |
| Planning: - Finalise website layout and discuss fund collection process for charities - Complete listing of sponsor, guest speakers, participating brands and charities - Finalise audio-visual equipment - Evaluate network requirements and IP security measures |  |
| Organising: - Communication with public relations team and marketing team regarding finalised charities and guest speakers - Meeting between operations team and general management team regarding security issues and operations progress for fund collection and distribution - Evaluation of internet security and digital display options for conference |  |
| Managing: - Essential security items and markers for online conference - Necessary audio-visual components for group meetings - Examining fund collection process through website |  |
| Marketing: - Creation of presentations and digital posters for advertisement on different digital channels - Social media campaigns - Communication with charities for their adverts - Sponsor meeting finalised |  |
| Technical: - Website layout finalised - Payment links established - Digital adverts finalised - Equipment essentials finalised |  |
| Problems/Resolution Action Plan: - Security levels for IP addresses visiting the website need to be evaluated - Spam protection needed - Redirecting to client homepage issues and other bugs regarding website need to be resolved - Payment schemes for charities need to be developed - Internet speed and steadiness need to be maintained throughout the conference |  |
| Focus for the Week: - Creation of digital adverts, posters, presentation for social media campaigns - Identification of security issues within website and portals for conference - Focus on essential technical requirements for smooth conference process |  |

Student Signature: _________Diana Lima________________

Date: ____10/08/2020____________________

| Week 6 | Monday August 17th, 2020 |
| --- | --- |
| Planning: - Running diagnostics tests on website and payment links - Increasing communication through social platforms - Increased interaction between participating brands and charities |  |
| Organising: - Compilation of videos, posts and digital marketing items for better communication strategy - Evaluation of funds and budget audit for the conference - Fixing audio-visual elements, speakers and digital tools necessary for smooth functioning of technical items during conference |  |
| Managing: - Identifying core issues within digital tools and resolving them effectively before launch of online conference - Finalised communication and schedule for conference - Key speakers and guest line-up finalised - Evaluating security measures and possible risks during conference |  |
| Marketing: - Increasing social media interaction with participants, charities and sponsors - Direct interaction with key speakers and charities - Releasing digital adverts for social media platforms - Developing mitigation strategies for unplanned digital risks and mishaps |  |
| Technical: - Installation of firewall and security measures within website - Measuring security measures within the various components of the conference - Evaluation of technical tools and components - Creating backup of necessary technical components and power supply |  |
| Problems/Resolution Action Plan: - Issues of internet security resolved - Complex firewall system applied for lowering external threats - Additional inverters and power supply components added for better functioning of technical components |  |
| Focus for the Week: - Deliverance of materials to management team - Complete and finalised website been put up for conference streaming - Charities and payment options up and running - Smooth and streaming communication channels within the website for stakeholders of the program |  |

Student Signature: _______Diana Lima________

Date: __17/08/2020______________________

| Conference Review | Planning; Management; Organisation; Marketing of the Event and Delivery of conference |
| --- | --- |

The conference would provide a detailed knowledge regarding the issue of food wastage that is evidenced in the UK hospitality industry. Collaborating with Marriott Heathrow would increase the authenticity of the conference being essential for the hospitality sector. Since the planning strategy and work distribution strategy, for the conference was effective, there were no delays in meeting deadline for the project. It was beneficial for the organisers to collaborate with local charities invested in waste management to produce better awareness for the sustainability procedures in waste management. Gathering funds from sponsors for the launching of this conference was simple and effective as the goal for forming the conference was in alignment with the SDG12 established by the UN for improving hospitality services. The project deliverables could be communicated through a report or presentation format as progress was not delayed and there were very few high-risk issues while working as teams. The online conference strategy would enhance participation experience for all stakeholders and viewers during COVID. Since the issue of sustainability is impending problem within the UK hospitality industry, the conference would garner broad-scale viewership and attention.

# Appendices

Meeting minutes: Week 1

Attending members: All

Agenda items

1. Virtual meeting

2. Selection of theme

3. Marketing plan and website development plans

| Action items | Owners | Deadline | Status |
| --- | --- | --- | --- |
| 1. Theme selection | all | Day 1 - day 3 | Deadline met |
| 2. Formulation of teams | all | Day 3 - day 5 | Deadline met |
| 3. planning for marketing operations | Marketing team, public relations team, operations management team | Day 5 – day 7 | Deadline met |
| 4. Website plan | Public relations team, operations management team | Day 5 – day 7 | Deadline met |

Meeting minutes: Week 2

Attending teams: all

Agenda items

1. Restructuring of teams

2. Evaluation of marketing objectives

3. Selection of sub-themes

4. Funding options and selection of core participants for the conference

5. Forming a schedule related to the activities and work elements for every team for completion of the conference project

| Action items | Owners | Deadline | Status |
| --- | --- | --- | --- |
| 1. Selecting sub-themes | All teams | Day 8 – day 9 | Deadline met |
| 2. restructuring teams | All teams | Day 8 – day 10 | Deadline met |
| 3. evaluating marketing objectives | Marketing team, general management and operations management | Day 10 – day 12 | Deadline met |
| 4. selecting core participants and funding options | Public relations team, general management and marketing team | Day 12 – day 14 | Deadline met |
| 5. Forming work schedule and maintaining progress reports based on the schedule | All teams | Day 14 | Deadline met |

Meeting minutes: Week 3

Attendees: Public relations team, operations management team and marketing team

Agenda items

1. Developing schedule for conference components

2. Identification of charities and smaller brands interested in waste management

3. Website design and marketing plan fixed

4. Funding for marketing and technical components acquired

Discussion

1. Finalised primary theme and sub-themes for the conference for better communication of ideas to sponsors and stakeholders.

2. Website design finalised to promote local businesses and charities for better tactics of waste management within the industry

3. Fund allocation and budgetary plans developed for effective planning regarding material components for the conference

4. Improved communication within teams after restructuring of members and re-alignment of team roles within the planning strategy

5. Comprehensive planning for guest list and timeline for the conference in terms of order of speeches and interaction types during the course of the meeting

6. Understanding specific requirement of audio-visual equipment and other additional support requirements for better communication during conference.

Meeting minutes: Week 4

Attendees: general management team, operations management team, public relations team

Agenda items

1. Recap of previous ideas and plans

2. Evaluation and confirmation of existing technical support

3. Evaluation of progress for all teams

4. Examining user interface and website layout

| Action items | Owners | Deadline | Status |
| --- | --- | --- | --- |
| 1. Recapitulation | All teams | Day 22 | Deadline met |
| 2. Technical support related issues and evaluation | Operations management general management | Day 23 – day 24 | Deadline met |
| 3. Progress evaluation | All teams | Day 25 | Deadline met |
| 4. User interface and website layout | Public relations, general management teams | Day 26 – day 28 | Deadline met |

Meeting minutes: Week 5

Attendees: general management team, operations management, marketing and public relations team

Agenda items

1. Complete listing of guest speakers, sponsor and other stakeholders

2. Finalise audio-visual equipment, technical equipment and additional power supply requirements

3. Examination and evaluation of network security

4. Fund collection and sponsor details

5. Identifying any delays as per the pre-determined work schedule and forming remedial measures accordingly

| Action items | Owners | Deadline | Status |
| --- | --- | --- | --- |
| 1. Fund collection and sponsor details | General management, public relations and operations management teams | Day 29 – day 30 | On schedule |
| 2. Network security aspects | General management and operation management teams | Day 30 – day 31 | On schedule |
| 3. Equipment needs and requirement evaluation | General management and operation management teams | Day 32 – day 34 | On schedule |
| 4. Finalised and completed listing of participants in the conference | Public relations, marketing and operations management team | Day 35 – day 36 | On schedule |

Meeting minutes: Week 6

Attendees: All teams, sponsors and participating businesses, charities

Agenda items

1. Identification of network issues and security problems with website diagnostics

2. Resolving and finalising internet and power supply components for the conference day

3. Evaluating potential fund gathering and online footfall for the conference

4. Observing new and finalised layout as per sponsor and participants confirmations

5. Visual achievement of work schedule as per expectations

Work schedule

| Work schedule | Days allocated | Progress |
| --- | --- | --- |
| Selection of themes, team distribution, marketing plans and website layout options | Week 1 (day 1 to day 7) | On schedule, achieved |
| Selection of sub-themes, resolving team issues, identifying funding opportunities and sponsors | Week 2 (day 8 to day 14) | On schedule, achieved |
| Forming conference components, discussion on funding for marketing and equipment costs, collaboration with charities and smaller organisation, discussion regarding progress of work | Week 3 (day 15 to day 22) | On schedule, achieved |
| Recapitulation of ideas and plans, evaluation of available support, funds, progress of teams, website diagnostics and layout | Week 4 (day 23 to day 28) | On schedule, achieved |
| Sponsor agreements, evaluation of security concerns, completion of guest and participant list | Week 5 (day 29 to day 36) | On schedule |
| Resolving network and diagnostic issues, power supply issues and external threats resolved, backup plans for additional power supply and essential technical support acquired, evaluation of potential footfall and fund gathering aspects for charities | Week 6 (day 37 to day 42) | On schedule |

Discussion

1. Network problems that could hinder the progress of the conference are identified and resolved

2. Diagnostic errors for the website has been observed and resolved for smooth communication and user friendliness during conference time

3. Conference schedule has been fixed and advertised on the website as per sponsor requirements and charity organisations’ demands

4. Increasing footfall of viewers expected for the website due to potent discussion topic of waste management within hospitality sector and presence of Marriott Heathrow as a leading sponsor for the conference

5. Digital requirement of white boards and projectors have been examined and addressed by operations management team, increasing social media advertisements within university, social platforms and other digital channels increased footfall to the website

7. Collaborative working within the teams is essential in the finals week to understand the progress level and resolve essential issues that require multi-faceted involvement

8. Increasing traffic to the website requires stricter website security and firewall installation to reduce risk of data theft and piracy, operations management and general management has to consider the aspects of data security concern for the participants during the conference activities

10. Changing the final layout and updating essential information on website before the conference page goes online would ensure better communication of operational elements during the conference, it would also increase footfall of participants and viewers for enhancing the core elements of the business procedures

# Appendixes: