## Slide 1: Medical Leadership Programme 2017-2018 Dr. Richard Wheeler Consultant Cardiologist
Improving the Quality of Emergency Echocardiography and Echo Training for Specialist Registrars at the University Hospital of Wales

## Slide 2: Purpose
To achieve >80% cross checking of all emergency scans performed by cardiology registrars at the University Hospital of Wales
A phased introduction ensuring a long term system maintaining quality assurance by June 2018
Establish an enhanced registrar teaching program with supervised echo lists by April 2018

## Slide 3: Context
Large Tertiary Cardiac Centre – 1000 beds
750 cardiac surgical operations per year
12 Consultant Cardiologists, 4 Cardiac Surgeons
12 Cardiology Specialist Registrars

## Slide 4: Echocardiography
Ultrasound diagnostic technique
Portable
No ionizing radiation
Applicable to multiple patient groups and diagnoses
Expert acquisition and interpretation are essential

## Slide 6: Patient Impact
Large cohort of inpatients who need accurate and early echocardiography
Large number of requests are emergencies occurring day or night
7 day services are a government priority

## Slide 7
Finalised Report on
Xcelera Database

## Slide 8: Key issues
Most routine echocardiography done by well trained cardiac physiologists – accredited
No oncall rota for echocardiography
Majority of urgent/emergency scans delegated to the cardiology registrars
Majority have no accreditation
No active supervision
No routine cross checking of reports

## Slide 9: Key issues - continued
Major clinical governance concerns
Major potential clinical risks
Regular adverse feedback regarding the quality of ‘hands on’ echo training
‘Creating a sense of urgency’

## Slide 10: Assembling the team
RW
Lead Cardiology Registrar
Management
Consultant Colleagues
Lead Cardiac Physiologist

## Slide 11: Driver Diagram
To achieve >80%
cross checked emergency/urgent TTE scans at UHW perfomed by SpRs
Increase the number of finalised TTE scans
on Xcelera
Allocation of cardiac physiologists to review scans
Allocation of Consultants to review scans
Competent trained SpRs
Ensure timely electronic reports on Xcelera
Supervised TTE lists during the working week
Regular teaching meetings

## Slide 12: Total number of TTE performed by SpRs from August 2017 – July 2018

## Slide 13: Timing of emergency/urgent scans

## Slide 14: How to introduce a checking system
Cycle 1 – CP1 regular sessions. RW adhoc.
Cycle 2 – CP 1 + RW regular sessions

## Slide 16: Outcomes
Close to 100% of scans are now checked and are accompanied by an electronic report
Regular supervised scanning lists for registrars in place x3 per week

## Slide 17: Problems encountered
Most scans failed to generate a preliminary report
Uncertainty regarding the written report in the notes at the time of the scan
No clinical details, more time consuming
Limited opportunity for direct feedback to trainees
Regular review would allow shorter sessions – less backlog
Is a cross checked report a marker of quality and accuracy ?

## Slide 18: Actions going forwards
Always completing an electronic preliminary report straight away
Reporting stations in registrar room
Wireless download of images
Allocated time for lead physiologists and consultants to cross check scans through the week
Regular supervised scanning lists for registrars
Develop the educational/teaching role of senior physiologists
Substudy to look at variance in registrar reports vs cross checked – can we prove the concern re clinical risk

## Slide 19: Personal reflections
‘If you do what you always did you get what you always got’ – you have to be proactive
Team interactions – learning to delegate more effectively
‘Benign dictatorship’ – learning to nurture and develop autonomy within the team
Keeping the pressure up – building on the change

## Slide 20: Achievements
Cultural shift within the department in relation to the process of emergency echo
Highlighting and reinforcing the importance of exemplary registrar echo teaching
Paving the way for service development with cardiac physiology to develop educational roles

## Slide 21: Acknowledgments
Amanda Jones – Senior Cardiac Physiologist
Jason O’Neill – Specialist Registrar Cardiology
Abbas Zaidi – Consultant Cardiologist
Nav Masani – Consultant Cardiologist
Peter O’Callaghan – Clinical Director