## Production topsheet
Production: |  | Client: |  |  | Director |  | WC:
Project outline: |  | Principle Designer: |  |  | Set Design |  | DD:
Producer: |  | Principle Contractor: |  |  | Costume Design |  | Rehs:
Production Manager: |  | Scenic Contractor: |  |  | Lighting |  | Fit up:
[5 empty] | Sound |  | Tech:
Preview 1:
Stage | Task | Due by | Status | Owner | Contributors | Shared with | Shared? | Production Manager Notes
1. Early Planning
Preparation | Read the play and note any key elements | before parameters meeting | Pending | Production Manager |  | Anything major with TD | No
| Model box, drawings and previous show info to set designer | as appropriate | Pending | Production Manager | Production Administrator |  | No
| Design Deadlines agreed | either before or at Params meeting | Pending | Producer |  | PM, TD, Prod Admin (info chart), Prod Dept | No
| Show staffing numbers and headline budget figures from TD / Producer | At parameters meeting | Pending | Producer |  | PM, TD | No
| Project timeline (including costing, drafting, budget submission for sign off and creative team NAs) | after parameters meeting | Pending | Production Manager | HODs, TD, Producer | TD | No
| Get info on future life considerations, touring etc | either at or after parameters meeting | Pending | Production Manager | Technical Director, Producer |  | No
| Costume Supervisor engaged | as appropriate | Pending | Technical Director | PM, Producer, HOC | HOC | No
| SM team on board, pre-reh prep time and staggered starts agreed | after parameters meeting | Pending | Company Manager | Producer, PM, TD |  | No
| Plan for Creative team NAs (associates?, other support) | after parameters meeting | Pending | Producer | PM,TD |  | No
| Financial procedures and processess meeting | after parameters meeting | Pending | PM / Prod Admin |  |  | No
2. Design, Costing, Sign Off
White card model | Arrange White Card model showing (invites, room etc) | 2 weeks prior to deadline | Pending | Directors Office | Producer, PM, Prod Admin | Discuss with Producer | No
| Arrange WC showing for Production Dept | at PM/Producer's discretion | Pending | Directors Office | TD, Producer, Prod Admin | Prod Dept as appropriate | No
| Scenic contractor availabilty checks | ahead of WC model meeting | Pending | Production Manager |  |  | No
| Confirm drafting plan | ahead of WC model meeting | Pending | Production Manager | PM | HODs, show supervisors | No
| V1 production schedule draft with staffing input and costing | 1 week after WC model | Pending | Production Manager | Production Administrator, HODs | Prod HODs, TD, Producer | No
| Early plan for show running staff | 1 week after WC model | Pending | Production Manager | HODs, TD | TD and Producer | No
| White Card Plan and section | 1 week after WC model | Pending | Production Manager | HOS, | TD, HOS, Producer | No
| Initial seating drawing including tech gallery plan and wheelchair seats | 1 week after WC model | Pending | Production Manager | Head of Stage | TD and Producer | No
| Assessment of impact of space configuration on other activities including workshop | 1 week after WC model | Pending | Production Manager | TD, HOS | TD, HODs, WM | No
| Discuss partners workshop capacity and slot (if appropriate) | 1 week after WC model | Pending | Workshop Manager / HOS | PM, HOS, WM, TD | TD | No
| Scenic contractor WC model meeting for ballpark costing (if appropriate) | 1 week after WC model | Pending | Production Manager |  |  | No
| Sightline assessment presented to TD and producer | 2 weeks after WC model | Pending | Production Manager | Head of Stage, TD, Draftsperson | TD and Producer | No
| Assess prop/furniture buying need and discuss with TD if necessary | 2 weeks after WC model | Pending | Production Manager | Company Manager, TD | TD | No
| Assess rigging implications and discuss with HOS | 2 weeks after WC model | Pending | Production Manager | HOS, | TD (if required) | No
| Any other specialist requirements of design, timeline a plan for engaging specialists | 2 weeks after WC model | Pending | Production Manager |  |  | No
| Initial Design Risk Assessment | 2 weeks after WC model | Pending | Production Manager | As required | Prod Team, TD, Producer | No
| Collate White Card costing information and present WC production budget. | 2 weeks after WC model | Pending | Production Manager | HODs, Contractors, Other | TD and Producer | No
Final model | Arrange Final Model showing(s) (invites, room etc) | as soon as model is in | Pending | PM / Producer / Directors Office | Prod Admin, Producer, TD | Production Team (discuss with TD) | No
| Updated drawings from Final model | as soon as model is in | Pending | Production Manager |  | HODs, show supervisors | No
| Define split between build in and build out | as soon as model is in | Pending | Production Manager | Workshop Manager, HOS | Workshop Manager, HOS, TD | No
| Model meetings with Contractor(s), circulate detailed costing notes | as soon as model is in | Pending | Production Manager | Contractors | TD, Contractors, Designer, HOS | No
| Costings back from Contractors and collate | within 2 weeks of model delivery | Pending | Production Manager |  | TD, Producer | No
| Costings from YV HODs / show supervisors | within 2 weeks of model delivery | Pending | Production Manager | Hods / Show supervisors | TD, Producer | No
| Update show staffing thoughts including rehearsals | as soon as model is in | Pending | Production Manager | HODs | TD and Producer | No
| Confirm rehearsal set / other requirements | as soon as model is in | Pending | Production Manager | Creative team | TD, Producer, HODs, WM, Prod Admin | No
| Determine any specialist contractors required and book meetings | as soon as model is in | Pending | Production Manager |  |  | No
| Key production schedule information is on master schedule | within 1 week of model delivery | Pending | Prod Admin | PM |  | No
| Determine operator and DSM positions | 2 weeks after model is in | Pending | Production Manager | HODs | TD and Producer | No
| Initial thoughts on position of caption box for captioned perf | 2 weeks after model is in | Pending | Production Manager | HODs | TD and Producer | No
| Revise Design Risk Assessment and circulate | 2 weeks after model is in | Pending | Production Manager |  | TD and Producer, Prod Dept | No
| Present final costing, seating plan and sightlines to TD and Producer | 2 weeks after model is in | Pending | Production Manager | Contractors, HODs | TD and Producer | No
| Present final seating drawing including tech gallery presented and signed off | 3 weeks after model is in | Pending | Production Manager | Designer, HOS, Draftperson, TD | TD and Producer | No
| Seating meeting | Consult with producer | Pending | Production Administrator | TD, HOS | TM, DOPM, WTM, TickMan, Producer, HOS | No
| Seating on sale wth agreed holds | 3 weeks after model is in | Pending | Director of Press and Marketting | Producer, TD | Producer, Ticketing Manager, Theatre Manager, others | No
| Confirm audience and fire exit routes and FOH requirements | 3 weeks after model is in | Pending | Production Manager | Theatre Manager, HOS | HODs, show supervisors | No
Design / Budget signoff | Feedback from Exec/Producer on submitted costing. Either in the form of a signed off budget or a request to find savings | 1 week after submitting the final costing | Pending | Producer | TD, Exec | Production Manager | No
| Signed off budget and notes to director and designer | Consult with TD / Producer | Pending | Production Manager / Producer | Producer, TD | Rest of creative team as appropriate | No
| Circulate relevant sections of signed-off budget to HoDs | Consult with TD | Pending | Production Manager | TD | HODs, show supervisors | No
| Set up Rolling budget and add budget figures to Commitment Record with Production Administrator | Consult with TD / Producer | Pending | Production Manager | Production Administrator |  | No
3. Workshop Build and Production planning
Pre-workshop build | Issue PO to main scenic contractor with clear notes agreeing exactly what is included. | At PMs discretion | Pending | Production Manager |  | Prod Admin, TD | No
| Agree build timeline with contractor and local workshop including information deadlines | With purchase order | Pending | Production Manager | Contractors, HOS, WM |  | No
| Details of get in doors to Scenic contractor | With purchase order | Pending | Production Manager | HOS |  | No
| Circulate plan and section and other drawings to creative team | as soon as drawn up | Pending | Production Manager |  | Creative Team, TD, Producer | No
| Pre-build update at HoDs meeting | before construction commences | Pending | Production Manager | PM, Stage, Lighting, Sound | HODs, show supervisors | No
| Circulate production schedule for feedback / check Master schedule is up-to-date | as soon as drawn up | Pending | Production Manager | HODs / Prod Admin | HODS, TD, Producer, All at YV | No
Pre-rehearsal | Confirm Production Meeting slot and circulate | before rehearsals commence | Pending | Production Manager | Creative team |  | No
| Ground plan and info to SM for rehearsal room | before rehearsals commence | Pending | Production Manager |  |  | No
| Book Licensing Inspection | before rehearsals commence | Pending | Production Manager |  | TD | No
| Arrange petty cash float(s) for Costume Supervisor, Prop Supervisor, Stage Manager etc | as required | Pending | Production Manager | YV Finance | Prod Admin, TD | No
| Update risk assessment | before rehearsals commence | Pending | Production Manager |  | Producer, TD, Prod Dept, SM team, CT as appropriate | No
4. Rehearsal and pre production
Rehearsal room fit up | Rehearsal Room Fit Up risk assessment | before rehearsals commence | Pending | Production Manager | Stage | Stage supervisor, SM | No
| Rehearsal Room Fit Up plan inc crew booking and transport | before rehearsals commence | Pending | Production Manager | HODs | HODs, show supervisors as req | No
| Rehearsal Room Plan dwg | before rehearsals commence | Pending | Production Manager | PM, SM | PM, stage supervisor, SM | No
Rehearsals | Rehearsals risk assesment | before rehearsals commence | Pending | SM/ PM | SM | PM, company, show supervisors | No
| Smoking Plot and artistic justification (if req) | end of rehearsals | Pending | SM/ PM | SM/ Assistant Director | Lambeth Licensing copying in TD | No
| Storyboard/Scene Change Plan (if req) | before technical rehearsal | Pending | Production Manager | PM, SM, Stage | HODs, show supervisors as req | No
Alongside Rehearsals | Updated draft of Production schedule in consultation with HODs re staffing | Week 2 of rehearsals | Pending | Production Manager | Stage, Lighting, Sound | Prod Dept, Show Team, Producer, TD | No
| 6009 costing on above from Prod Admin | Week 2 of rehearsals | Pending | Production Manager | Prod Admin | Producer, TD | No
| Draft transport plan and costing. | before fit up commences | Pending | Production Manager |  |  | No
| Pre fit up Budget update (including 7001) | Final week before fit up | Pending | Production Manager | Prod Admin, HODs, Cos Super | TD & Producer | No
| Contractor visits complete with typed up and circulated notes | Through build process | Pending | Production Manager | HOS, Designer | Contractors, Designer, TD at PMs discretion | No
Production meetings | Call Production Meetings, ensure SM puts them on the call | once a week during rehs | Pending | Production Manager | CT, Producer, Prod team, show team | CT, TD Producer, Prod team, show team | No
| Production Meeting Notes | after each production meeting | Pending | Production Manager | Prod Admin | Hannah has distribution lists | No
5. Fit up, Production & Technical Rehearsals
Pre Fit up | Call Pre Production Week Meeting and ensure room is booked | 1 or 2 weeks out from fit up | Pending | Production Manager | Production Team, Prod Admin |  | No
| Final tweaks to prod schedule and staffing | 1 or 2 weeks out from fit up | Pending | Production Manager | HODs, Show Supers, Prod Admin | Everyone | No
| Wagon Loading Plan (if necessary) | before wagon arrives for unloading | Pending | Production Manager | PM, Draughtsman | PM, HODs, show supervisors | No
| Final transport schedule, cross ref with other spaces, PO transport, parking dispensation etc | 1 or 2 weeks out from fit up | Pending | Production Manager | HOS, Contractors | HODs / Show Supervisors | No
| Show Fit Up RA and circulate | before fit up commences | Pending | Production Manager | Stage, Lighting, Sound | Production Team, TD | No
| Specific element build RAMS (if req) | before fit up commences | Pending | PM / HOS | PM, Contractors, WM | PM, HODs, show supervisors | No
| Rigging/Automation RAMS (if req) | before fit up commences | Pending | PM / HOS | PM, Stage | PM, HODs, show supervisors | No
| Lifting Plan (if req) | before fit up commences | Pending | Head of Stage / Stage Supervisor | PM, Stage | PM, HODs, show supervisors | No
| Complete and circulate Construction Phase Plan | before pre production meeting | Pending | Production Manager | HOS, HODs | PM, HODs, show supervisors, Producer | No
| Book guards for any out of hours work, Sunday paint calls etc | before fit up commences | Pending | PM / HOS | Prod Admin, Theatre Manager | Theatre Manager, HODs, Prod Admin | No
Fit up | Inform building of construction phase, Signs on doors, e-mail to all. | prior to start of day 1 of fit up. | Pending | Production Manager | HODs | All staff on site | No
| Toolbox Talks/Daily Briefings | daily during fit up/tech/previews | Pending | Production Manager | HODs | All staff on site | No
| Review holds from onsale seating plan and confirm physical seats match drawing | end of fit up | Pending | Production Manager | HOS | Producer | No
| Completion of fit up and declaration that the space is now actor ready | end of fit up | Pending | Production Manager | TD, HODs | All staff on site | No
| Tech staffing assessment (and updated costing if required) | end of fit up | Pending | Production Manager | TD, HODs, Producer, Prod Admin | Producer | No
Tech / Preview | Seat numbering | during tech | Pending | Front of House |  |  | No
| Preview staffing assessment (and updated costing if required) | end of tech | Pending | Production Manager | TD, HODs, Producer, Prod Admin | Producer | No
| Confirm position for Caption box for Captioned perf | as soon as sensible | Pending | Production Manager | PM, Stage, Lighting, Sound, Ciara |  | No
| Licensing Inspection | before first preview | Pending | Production Manager | Lambeth H&S |  | No
| Show Running RA | before first preview | Pending | Production Manager | SM, HODs, other | SM team, Prod Dept, FOH if required, Producer | No
| Updated smoking plot (if required) | before first preview | Pending | SM | PM | everyone | No
| Initial maintenance schedule for show running | before press night | Pending | Production Manager | HODs | Prod Dept, Show team | No
6. Show Running
Show running | Post preview budget update | after press night | Pending | Production Manager | HODs, TD, Prod Admin | Producer, TD | No
| Show staff / plot cover plan | by press night | Pending | Production Manager | SM, HODS | Producer, TD | No
| Show stop procedures written up and signed off | by press night | Pending | Company Manager | SM, HODS | Producer, TD | No
| Overtime forecast for show running staff and SM | after press night | Pending | Production Manager | Prod Admin, CM | Producer, TD | No
| Confirm take up options weeks, show staff, hire companies | after press night | Pending | Producer | DOPM | PM, Prod Dept, show team | No
| Complete set of show records (cue sheets, focus notes, etc) | During the run | Pending | Production Manager | HODs, show supers, SM team | PM, HODs, technical staff | No
| Production archive photos | During the run | Pending | Prod Administrator | Show team , HODs |  | No
| Final seating plan with actual numbers in show file. | During the run | Pending | PM | HOS |  | No
7. Get Out, Storage and Disposal
Get out | Confirm life after final show | as soon as possible after press night | Pending | Producer / TD | ED / AD | PM, Prod Dept | No
| Items for Set Exchange or other re-use options | 3 weeks before get out | Pending | Production Manager | CM, Prod Admin, HODs | Prod Dept, YV, wider | No
| Confirm staff numbers and book em. | 4 weeks before get out | Pending | Production Manager / HODs | HODs, Show Supers |  | No
| Get Out Meeting | 2 weeks prior to get out | Pending | Production Manager | Prod Dept, show team (if appropro) | Circ notes to prod dept and show team | No
| Book Get Out transport, parking dispensation etc | 4 weeks before get out | Pending | Production Manager | HODs, show supervisors |  | No
| Show Get Out RA | before get out commences | Pending | Production Manager | HODs, show supervisors, TD | PM, HODs, technical staff | No
| Final budget figures | post get out | Pending | PM / Prod Admin | Prod Admin, HODs, Show superisors | Producer, TD, Assistant Producer | No

## References (hidden)
Pending | No
Done | Yes
N/A