UNIVERSITY OF WALES TRINITY SAINT DAVID

Managing Projects in the Organization TASK 2

STUDENT: MIHAITA GHEORGHE

STUDENT CODE: 2120440

LECTURER: ALFRED MENSAH

MODULE CODE: BMSW5104

Table of Contents

Introduction 3

Project life cycle 3

Project Methodology 3

Stakeholder analysis FEM restaurant 3

Work break structure for FEM restaurant 5

Draft of costs for FEM restaurant 7

Resources used for the restaurant project 8

Resource considerations for the project9

Gantt chart for the project 10

Risk assessment of the project11

Conclusion12

References 13

Introduction

A project is a sequential task that is completed to achieve its goals. Sometimes a project is undertaken to solve a certain problem. To ensure a healthy lifestyle for the organization, a project will be selected, and this is FEM Restaurant. To complete the project, stakeholder analysis, a Gantt chart, a work breakdown structure, the costs of the project, and the resources of the project are to be analyzed. All of these issues must be considered when completing a project properly. In the report, the project life cycle must be followed.

Project life cycle

A project has a life cycle, and the life cycle must be followed properly. A project's life cycle includes five stages.

Initiation stage: the goal and feasibility of the project will be described and explained with proper evaluation in this stage (Burke, 2015). In this stage, the project purpose and stakeholders are identified.

Planning stage: this stage is the main stage because it includes all project tasks, the timeline, and the resource allocation of the project.

Execution stage: the actions of the project are to be executed in this stage, and communication, resource allocation, and coordination are integrated in this stage (Crawford, 2018).

Monitoring: the project performance and the progress are required to be monitored. Any deviations from the project are tracked, and proper adjustments are made.

Closing: When the clients give their approval for the project, the project is closed.

Project Methodology

Without methodology, any project activity will not be possible because the project methodology includes all project-related activities that are executed to complete the project properly. The project methodology includes the work breakdown structure, Gantt chart, project test, project performance, and stakeholder analysis of the project. In the project, the project cycle will be discussed, and the resource allocation will also be included.

Stakeholder analysis of FEM Restaurant

Stakeholders are those who have an interest in the organization, so in a project, stakeholders have an interest. So, in the FEM restaurant project, the stakeholders will affect the project’s objectives and actions. In a project, all the stakeholders are not equally important. Some stakeholders have high interest, and some have less interest. The stakeholder analysis for the FEM Restaurant can be based on a power and interest basis.

| Sl | Name | Power (1-5) | Interest (1-5) |
| --- | --- | --- | --- |
|  | Owners and sponsors | 5 | 5 |
|  | Managers and staffs | 4 | 4 |
|  | Customers | 4 | 4 |
|  | Suppliers | 4 | 5 |
|  | Bank | 4 | 3 |
|  | Government | 5 | 3 |
|  | Local people | 1 | 3 |
|  | Media | 2 | 3 |
|  | Competitors | 2 | 4 |

Owners and sponsors: they can control the costs and income of the project. They create an environment to lead the project to success, and quality, costs, and time are followed in the project (Hall, 2017). They want to get information on the project, risks, and issues. The communication system with them will be meetings and reports every month.

Managers and staff: the managers keep the work to be done, and the staff are responsible for completing the work. The managers are to make policies and plans to meet the objectives. The managers will review the actions, tasks, and assignments. Every day, the communication system will be made, and the communication will be meetings and reports.

Customers: The customers will get the services of the project. The interest is to test the foods and services delivered in the restaurant for quality and satisfaction (Burke, 2015). In the restaurant, the costs and services, the price, and the food quality will be justified. These can be done every three days, and the communication system will be Facebook, the booking system, the website, and advertisements.

Supplier: the suppliers provide goods and services to the restaurant company. The interest is to ensure quality foods and timely delivery and pricing. Email, phones, and documents are the communication systems.

Bank: The bank plays a crucial role in managing the funding for the project. The interest of the bank is to ensure the stability of money for the restaurant, and the bank will disburse money on time. The cash flow will be improved efficiently. The instalment of money will be paid monthly. The communication system will be email and formal reports.

Local government: the local government is responsible for setting policy and health criteria for the restaurant. The interest of the government is to charge a tax amount on the income, and this planning system will be made before the project starts (Crawford, 2018). The communication system for this will be a formal proposal.

Competitors: near the FEM restaurant, other restaurant businesses can exist with unique services. The interest of the competitors is to ensure quality food and the best services at a reasonable price. The communication system with the competitors is a regular visit, and this will happen before starting the project and after the project.

The media plays a role in getting the word out about the restaurant. The interest of the media is to reach and reveal the news of quality food and services to the people. So, this can be made monthly using a proper communication plan. Newspapers, reports, leaflets, and other media can be used.

Work break structure for FEM Restaurant

In a project, the work breakdown structure is followed because this structure is efficient and delivers effective project performance. By following the breakdown structure, the project tasks are separated based on their importance and urgency, and then the project is accomplished (Stark, 2015). By following this structure, all the project tasks will be concise and clear. The WBS of the FEM restaurant project is described below:

| WBS name | Description |
| --- | --- |
| Project charter and scope | This will include the name of the project, the objective of the project, the budget and milestones of the project. |
| Location | An appropriate location must be selected for the project. |
| Budget | For each of the steps of the project, fund allocation is necessary. So funds are to be allocated for the activities |
| Resource management | Supervising the resources and the control of resources are important for the project. |
| License | To operate the FEM Restaurant license is necessary. Public health permission and environmental regulations are required. |
| Contract | Contracts with different service providers like interior designers, indoor and outdoor designs, and contracts suppliers for fresh food, all of these are equally important. |
| Construction | In the construction, the dining area including indoor and outdoor, kitchen, storage room, washroom, reception, doors, windows, electricity, air conditioning, parking, and flooring, all of these activities are included. |
| Installation | In the installation activity, kitchen appliances, wi-fi, and camera surveillance are completed. |
| Software development | Website development for restaurant information, mobile app for updates and bill payment will be completed. |
| Resources | Under this segment delivery van, ingredients, cutlery, dishes human resources managers, waiters, security officers, cleaners and receptionists are all to be done. Staff training and training materials are all to be included in this segment. |
| Marketing | Newspaper, magazine, social media and other techniques are to be used for the promotional activities. |
| Closing | In this segment, inspection, cleaning, inviting sponsor, and opening ceremony are to be completed. |

Draft of costs of the project for FEM Restaurant

As this project is a restaurant project named FEM Restaurant, so the costs of the project are fixed costs and variable costs. The fixed costs and variable costs of the project are described below:

Fixed costs for the FEM Restaurant

- Rent payment

- Property tax payment

- Insurance

- Salary

- Equipment cost

- Legal costs

- License costs

- Debt

Variable costs: the variable costs for the restaurant project will be like below:

- Food costs

- Beverage costs

- Labor costs

- Cleaning and maintenance costs

- Laundry costs

A probable costs chart for the FEM Restaurant is given below:

| Particular costs | Amount ($) |
| --- | --- |
| Rent cost | 10000 |
| Utilities cost | 2200 |
| Renovation cost | 10000 |
| Furniture costs | 35000 |
| Kitchen and bar equipment specialist | 100000 |
| Primary food supply | 8000 |
| Salary: general manager Assistant Manager | 45000 35000 |
| Sous Chef | 38000 |
| Sever cost | 25000 |
| Marketing and advertisement cost | 30000 |
| License costs | 7000 |
| Expert costs | 35000 |
| App installation and website development | 35000 |

Resources used for the restaurant project

The resources to be used for the restaurant project are described below:

- Oven

- Gas ranges

- Electronic orange

- Ventilation

- Batch bowl processor

- Buffalo choppers

- Combination processor

- Floor mixer

- Hand mixer

- Countertop mixer

- Slicer

- Food preparation counter

- Freezer

- Safety equipment

- Food storage container

- Cooking equipment

- Sink

- Point of sale system

- Washing equipment

- Sharpening stone

- Microwave

- Gas

Human resources for the FEM Restaurant

The human resources for the FEM Restaurant are given below:

- Kitchen staff (executive chef, sous chef, chef de partie,

- Bar staff

- Managerial staff (manager, cashier, storekeeper)

- Floor staff (captain, waiter, housekeeper, guard)

- Delivery staff (delivery boy)

Resource considerations for the project

To complete a project, different types of resources are needed, and all of these resources are important because, without them, a project will not be completed. So, the following resources are to be considered in a project:

Human resources: human resources are the most valuable resources for a project because, without humans or people, a single task of the project will not be completed (Nicholas and Steyn, 2017). In a project, the tasks are broken down, and the people complete the tasks. Some people lead and guide the project, and some do the activity. Some human resources for a project are the team leader, team members, project manager, project team, experts, and skilled workers.

Financial resources: After human resources, financial resources are another important resource. To finance the whole project and the human resources, financial resources are important. A proper budget is prepared for all of the WBS, and the funds are allocated for the WBS to complete the whole project (Hwang and Ng, 2015). Some of the financial resources for the project are the project budget, project grants, and contingency funds.

Material resources: material resources are the visible and tangible resources and equipment that are required to complete the project. In the material resources, equipment, tools, machines, raw materials, and software are included.

Time resource: a time resource is necessary for scheduling the activities of the project. Following the time resource, the deadline of the project and the milestone are followed. Following this, the performance of the employee is determined, as are the project costs. Based on the time resources, the important tasks and the emergency tasks are completed. The time resources are the project plan, project schedule, and time invested.

Gantt chart for the project

A Gantt chart is a chart that shows the visualization of the activities of the project that should be completed on time. So, the Gantt chart for the FEM Restaurant is described below:

Task A defines the project chart and the scopes, Task B describes the budget and resource management. Task c will define the license and contract of the project, and task D will describe the construction of the restaurant. Task E describes the installation and software development of the project. Task F describes the marketing of the project and Task G describes the inauguration of the restaurant.

This describes the timeline of the project. The whole project will be completed within 40 weeks. Task A will be completed by 12 weeks, task B will be completed by 8 weeks, task C will be completed by 4 weeks, task D will be completed by 12 weeks, task E will be completed by 4 weeks, task F will be completed by 4 weeks, and task G will be completed by 4 weeks.

Risk assessment of the project

Each project has risks, and these risks should be identified and analyzed. The following risks are associated with the FEM Restaurant project:

Cost risk: the cost risk happens when the costs are higher than the budgeted costs. This risk increases the total funding of the project.

Schedule risk: a proper time is scheduled and a timeline is determined. So, when the timeline and the schedule are higher than the expected time, it is a schedule risk because it increases the time for completing the project.

Performance risk: performance risk happens when the performance of the project is not consistent with the target.

Operational risk: this risk happens when there is less procurement, distribution, and production during the operation of the project.

Competition: in the restaurant industry, other restaurant companies can compete with this restaurant. The customers may deviate from this service and go to others.

As the risks are critical for a project, it is necessary to assess the risks of the project. The risks of the project can be assessed in the following ways:

The following elements are considered during the assessment of the risks of the projects:

Risk event: it is necessary to identify the risks of the project that will impact the project.

Risk time frame: the time frame should be determined for the risks related to the project.

Probability: the probability of the risks that can happen must be estimated.

Impact: It is necessary to estimate the impact of risk on the project during the project period.

Factors: the factors that could happen before the risk occurs.

The risk assessment of the project could be completed in the following ways:

Identification of potential risks: the risks that could happen during the project period could be identified.

Determination of risk probability: each of the risks has a probability, and the probability of each risk must be determined.

Determination of the impact of risk: as each of the risks has an impact on the whole project, it is necessary to determine the impact of each of the risks associated with the project.

Determination of risk score: the risk score of each of the risks must be determined at this stage.

Understanding risk tolerance: in this stage, the frequency and the risk tolerance will be determined to determine whether the risks must be tolerable or not (Nicholas and Steyn, 2017).

Prioritizing risks: each of the risks has priority, so the risks should be prioritized based on their risk score.

Development of risk response strategy: three types of risk response strategy can be followed in that case. These strategies are mitigation, avoidance, and transfer (Hwang and Ng, 2015).

Monitoring the risk plan: all of the risk plans for the project should be monitored.

Perform risk assessment: at this stage, the risk assessment should be performed continually. Because these will help assess the risk.

Identification of learned lessons: this is the last stage, and in this stage, the learned lessons in the whole risk assessment section will be identified.

Conclusion

If a project is supposed to be completed properly within the deadline, a proper plan and timeline for the project should be determined. The WBS is an important tool for the project and should be considered during the project. The cost structures, resource management, and risk assessment of the project will be determined. Various types of project resources are considered during project completion, and a Gantt chart for the project is used to visualize the activities and time required to complete the work.

References

Buckingham, M. and Coffman, C., (2016). First, break all the rules: What the world's greatest managers do differently. Simon and Schuster.

Burke, R., (2015). Project management: planning and control techniques. New Jersey, USA.

Crawford, J.K., (2018). Project management maturity model. Auerbach Publications.

Guibault, L., Westkamp, G. and Rieber-Mohn, T., (2016). Study on the implementation and effect in Member States' laws of Directive 2001/29/EC on the harmonization of certain aspects of copyright and related rights in the information society.

Hall, N.G., (2017). Project management: Recent developments and research opportunities. Journal of Systems Science and Systems Engineering, 21(2), pp.129-143.

Hwang, B.G. and Ng, W.J., (2015). Project management knowledge and skills for green construction: Overcoming challenges. International Journal of Project Management, 31(2), pp.272-284.

Kalverkamp, M., Pehlken, A. and Wuest, T., (2017). Cascade use and the management of product lifecycles. Sustainability, 9(9), p.1540.

Lovas, A., (2015). The risk of adverse selection and its management in the process of venture capital investment (The experience of Hungarian investors). Economy and Finance, 2(2), pp.186-202.

Mitra, A., (2018). Fundamentals of quality control and improvement. Wiley.

Nicholas, J.M. and Steyn, H., (2017). Project management for engineering, business, and technology. Routledge.

Osborne, R., Dunne, E. and Farrand, P., (2015). Integrating technologies into ‘‘authentic assessment design: an affordances approach. Research in Learning Technology, 21.

Stark, J., (2015). Product lifecycle management. In Product Lifecycle Management (Volume 1) (pp. 1-29). Springer, Cham

Trietsch, D. and Baker, K.R., (2018). PERT 21: Fitting PERT/CPM for use in the 21st century. International journal of project management, 30(4), pp.490-502.

Yang, J.B. and Kao, C.K., (2015). Critical path effect-based delay analysis method for construction projects. International journal of project management, 30(3), pp.385-397.