## Project Template
Problem Statement and area of Opportunity
Warranty returns on the "AWX" product line are at 2.6% of shipment volume and trending upward. The goal of this project is to identify and correct the top reasons for product returns, and reduce the warranty rate from 2.6% to 1.3% (50% improvement).
Business Need and Justification
Reducing the AWX warranty rate 50% will save £247K annually and reduce the number of negative product reviews by 50%, which will drive more sales through retail and online channels. Sales are currently trending down, in large part due to poor online reviews.
Risks and Issues |  |  |  | Assumptions and Dependencies
Data discrepancy due to large amounts of projects.
Project Ownership / Approval
Project Manager | Snow White |  | Project Champion | Queen of Hearts |  | Approval Date | 2020-01-01
Project Number |  |  | Process Owner | Cheshire Cat
Financial Benefits / Timing
Financial Benefits |  |  | Estimated Expenses / Investment |  |  | Schedule
| Goal | Actual |  | Goal | Actual |  | Goal | Actual
Incremental Sales |  |  | Expenses Incremental to Operating Budget | 50000 |  | Measure | 2020-03-01
Profitability (% OI) | [5 empty] | Analyse | 2020-04-01
Payback Period (yrs) |  |  | Capital | 0 |  | Improve | 2020-06-01
Annual Savings | 247000 |  | Other | 0 |  | Control | 2020-07-01
Project Team
Supplier Representatives |  |  | Internal Team |  |  | Customer Representatives
Name | Supplier | Title | Name | Function | Role | Name | Cust. | Title
Mickey Mouse |  |  | Peter Pan | Sales |  | Tiger Lily | OEM | Engineer
Donald Duck |  |  | John Darling | Quality
|  |  | Michael Darling | Process
|  |  | Captain Hook | Logistics