## Sheet1
Tasks | Description of Task | Responsible Person | Duration
|  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
LogBook | Filling out Longbok and keeping it up to date | JSR
Design | Design of PCB | JSR | bar: Duration Week 1
| Simulate the PCB, and ensure there are no errors | JSR | bar: Duration Week 1 to Duration Week 2
| Create Wiring Diagram for PCB | JSR | bar: Duration Week 2
| Create Model for Breadboard Circuit (Use Pebble software) | JSR | bar: Duration Week 3
Execution | Build Breadboard circuit using model created in Pebble as Reference | JSR | bar: Duration Week 4 to Duration Week 5
| Test Breadboard Circuit, Fix Errors Where found | JSR | bar: Duration Week 6 to Duration Week 7
| Order PCB Online | JSR | bar: Duration Week 5
| Build PCB | JSR | bar: Duration Week 8 to Duration Week 10
| Test PCB, Fix Errors Where found | JSR | bar: Duration Week 10 to Duration Week 11
Evaluation | Gather results from Logbook and Input them to make a final report | JSR | bar: Duration Week 12 to Duration Week 13