## Weekly Resource Plan
Week No | Week Commencing | Week Ending | Key Activities (from programme) | Milestone(s) achieved this week | Total Workforce (approx.) | Management | Operatives | Groundworks | Specialist | Steel erectors | Crane crew | Steel fixers | Concrete crew | Steel deckers | Welders | Framing | Envelope | Roofers | Glaziers | Cladders | Electricians | Plumbers | HVAC | Mechanical | Dryliners | Joiners | Plasterers | Painters | Carpenters | Floor layers | Surfacing | Commissioning | M&E | Landscapers | Main Plant/Equipment (summary) | Key Materials (summary)
1 | 2026-02-02 | 2026-02-08 | Form site boundary fencing (timber fencing) |  | 5 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hand tools, Small plant | Fixings, Timber hoarding/fencing
2 | 2026-02-09 | 2026-02-15 | Form temporary access/egress (Type 1 road); Ground investigation (boreholes); Site cabin drainage and footings |  | 15 | 3 | 0 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Breaker, Drilling rig, Mini excavator, Roller | Borehole logs, Concrete, Drainage pipe, Geotextile, Type 1 aggregate
3 | 2026-02-16 | 2026-02-22 | Ground investigation (boreholes); Site cabin drainage and footings; Site cabins/welfare delivery & install |  | 14 | 3 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Breaker, Drilling rig, Hiab truck, Mini excavator, Telehandler | Borehole logs, Concrete, Drainage pipe, Temporary services, Welfare cabins
4 | 2026-02-23 | 2026-03-01 | Reduced levels dig; Site cabins/welfare delivery & install; Traffic management routes / material storage areas | Site setup complete | 16 | 3 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20T excavator, Cones/barriers, Dumpers, Hiab truck, Telehandler | Heras/Chapter 8 barriers, Signage, Spoil disposal, Temporary services, Welfare cabins
5 | 2026-03-02 | 2026-03-08 | Piling mat for piling rig; Reduced levels dig |  | 14 | 2 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20T excavator, Dumpers, Roller | Geotextile, Hardcore, Spoil disposal
6 | 2026-03-09 | 2026-03-15 | Dig and pour piles; Piling mat for piling rig |  | 18 | 2 | 0 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20T excavator, Concrete pump, Piling rig, Roller | Concrete, Geotextile, Hardcore, Rebar cages
7 | 2026-03-16 | 2026-03-22 | Dig and pour piles |  | 11 | 1 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Concrete pump, Piling rig | Concrete, Rebar cages
8 | 2026-03-23 | 2026-03-29 | Dig and pour piles |  | 11 | 1 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Concrete pump, Piling rig | Concrete, Rebar cages
9 | 2026-03-30 | 2026-04-05 | Dig and pour piles; Form and pour pile caps |  | 21 | 2 | 0 | 10 | 6 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Concrete pump, Excavator, Piling rig | Concrete, Formwork, Rebar, Rebar cages
10 | 2026-04-06 | 2026-04-12 | Form and pour pile caps |  | 10 | 1 | 0 | 6 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Concrete pump, Excavator | Concrete, Formwork, Rebar
11 | 2026-04-13 | 2026-04-19 | Form and pour pile caps; Form and pour ringbeams |  | 19 | 2 | 0 | 11 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Concrete pump, Excavator | Concrete, Formwork, Rebar
12 | 2026-04-20 | 2026-04-26 | Drainage pop ups and drainage runs; Form and pour ringbeams; Set holding down bolts |  | 18 | 3 | 0 | 12 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Concrete pump, Hand tools, Mini excavator | Chambers, Concrete, Drainage pipe, Formwork, Holding down bolts, Rebar, Templates
13 | 2026-04-27 | 2026-05-03 | Backfill ringbeams and form slab; Blockwork substructure and DPC trays; Form and pour ringbeams |  | 23 | 3 | 2 | 11 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compactor, Concrete pump, Excavator, Telehandler | Blocks, Concrete, DPC trays, DPM, Formwork, Hardcore, Mortar, Rebar
14 | 2026-05-04 | 2026-05-10 | Blockwork substructure and DPC trays; Elevated reinforced slab for testing chamber |  | 16 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Concrete pump, Telehandler, Vibrators | Blocks, Concrete, DPC trays, Formwork, Mortar, Rebar
15 | 2026-05-11 | 2026-05-17 | Blockwork substructure and DPC trays; Crane setup & first steel delivery; Elevated reinforced slab for testing chamber; Erect columns (GF); Lay drainage to main sewer run | Groundworks complete | 35 | 5 | 2 | 4 | 0 | 8 | 4 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Concrete pump, MEWPs, Mini excavator, Mobile crane, Telehandler, Vibrators | Blocks, Bolts, Concrete, Connection fittings, DPC trays, Drainage pipe, Formwork, Mortar, Rebar, Steel columns, Steel deliveries
16 | 2026-05-18 | 2026-05-24 | Erect columns (GF); Install beams (1st floor) |  | 18 | 2 | 0 | 0 | 0 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEWPs, Mobile crane | Bolts, Steel beams, Steel columns
17 | 2026-05-25 | 2026-05-31 | Install beams (1st floor); Install metal transfer deck & stud welding (1st floor); Insulating testing chamber walls/ceiling & boarding; Steel fix & concrete (1st floor) |  | 32 | 4 | 2 | 0 | 0 | 6 | 2 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Concrete pump, MEWPs, Mobile crane, Welding gear | Boards, Bolts, Concrete, Insulation, Metal deck, Rebar, Shear studs, Steel beams
18 | 2026-06-01 | 2026-06-07 | Erect columns (1st floor); Insulating testing chamber walls/ceiling & boarding; Lightweight steel framing EXTERNAL GF; Second delivery of steel; Steel fix & concrete (1st floor) |  | 37 | 5 | 2 | 0 | 0 | 8 | 4 | 4 | 4 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Concrete pump, Hand tools, MEWPs, Mobile crane | Boards, Bolts, Concrete, Fixings, Insulation, LSF studs, Rebar, Steel columns, Steel deliveries
19 | 2026-06-08 | 2026-06-14 | Erect columns (1st floor); Install beams (2nd floor); Insulating testing chamber walls/ceiling & boarding; Lightweight steel framing EXTERNAL GF |  | 32 | 4 | 2 | 0 | 0 | 12 | 4 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Hand tools, MEWPs, Mobile crane | Boards, Bolts, Fixings, Insulation, LSF studs, Steel beams, Steel columns
20 | 2026-06-15 | 2026-06-21 | Deck & stud welding (2nd floor); Install beams (2nd floor); Insulating testing chamber walls/ceiling & boarding; Lightweight steel framing EXTERNAL GF; Steel fix & concrete (2nd floor) |  | 39 | 5 | 2 | 0 | 0 | 6 | 2 | 4 | 4 | 4 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Concrete pump, Hand tools, MEWPs, Mobile crane, Welding gear | Boards, Bolts, Concrete, Fixings, Insulation, LSF studs, Metal deck, Rebar, Shear studs, Steel beams
21 | 2026-06-22 | 2026-06-28 | Insulating testing chamber walls/ceiling & boarding; Lightweight steel framing EXTERNAL FF; Lightweight steel framing EXTERNAL GF; Screed concrete floors communal GF; Third delivery of steel |  | 31 | 5 | 2 | 0 | 0 | 2 | 2 | 0 | 4 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Hand tools, MEWPs, Mobile crane, Screed pump | Boards, Fixings, Insulation, LSF studs, Screed, Steel deliveries
22 | 2026-06-29 | 2026-07-05 | Deck & stud welding roof; Install beams roof; Insulating testing chamber walls/ceiling & boarding; Lightweight steel framing EXTERNAL FF; Screed concrete floors communal FF; Screed concrete floors communal GF |  | 40 | 6 | 2 | 0 | 0 | 6 | 2 | 0 | 8 | 4 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, MEWPs, Mobile crane, Screed pump, Welding gear | Boards, Bolts, Fixings, Insulation, LSF studs, Metal deck, Roof beams, Screed, Shear studs
23 | 2026-07-06 | 2026-07-12 | Door access systems for testing chamber; Erect parapets; Insulating testing chamber walls/ceiling & boarding; Internal plasterboarding partitions GF; Lightweight steel framing EXTERNAL FF; Screed concrete floors communal FF; Steel fix & concrete roof; Windows GF | Frame complete (structural) | 50 | 8 | 2 | 0 | 3 | 0 | 0 | 4 | 8 | 0 | 0 | 6 | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Board lifts, Concrete pump, Glazing lifters, Hand tools, MEWPs, Screed pump | Access control kits, Boards, Concrete, Fixings, Insulation, LSF studs, Parapet materials, Plasterboard, Rebar, Screed, Sealants, Studs, Window units
24 | 2026-07-13 | 2026-07-19 | Door access systems for testing chamber; Erect parapets; Internal plasterboarding partitions FF; Internal plasterboarding partitions GF; Lay insulation & waterproofing (semi watertight); Lightweight steel framing EXTERNAL FF; Lightweight steel framing EXTERNAL SF; Screed concrete floors communal FF; Windows GF |  | 55 | 9 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 12 | 7 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Board lifts, Glazing lifters, Hand tools, Hot works kit, MEWPs, Screed pump | Access control kits, Fixings, Insulation, LSF studs, Membranes, Parapet materials, Plasterboard, Screed, Sealants, Studs, Window units
25 | 2026-07-20 | 2026-07-26 | Door access systems for testing chamber; Floor finishes in testing chamber; Internal plasterboarding partitions FF; Internal plasterboarding partitions GF; Lay insulation & waterproofing (semi watertight); Lightweight steel framing EXTERNAL SF; Screed concrete floors communal SF; Windows FF; Windows GF |  | 51 | 9 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 6 | 2 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | Board lifts, Floor tools, Glazing lifters, Hand tools, Hot works kit, MEWPs, Screed pump | Access control kits, Fixings, Floor finishes, Insulation, LSF studs, Membranes, Plasterboard, Screed, Sealants, Studs, Window units
26 | 2026-07-27 | 2026-08-02 | Floor finishes in testing chamber; Gutterings; Internal plasterboarding partitions FF; Lay insulation & waterproofing (semi watertight); Lightweight steel framing EXTERNAL SF; Screed concrete floors communal SF; Windows FF |  | 39 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 6 | 2 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | Board lifts, Floor tools, Glazing lifters, Hot works kit, MEWPs, Screed pump | Downpipes, Fixings, Floor finishes, Gutters, Insulation, LSF studs, Membranes, Plasterboard, Screed, Sealants, Studs, Window units
27 | 2026-08-03 | 2026-08-09 | False floor install for M&E FF; Floor finishes in testing chamber; Green roof system; Gutterings; Internal plasterboarding partitions FF; Internal plasterboarding partitions SF; Lightweight steel framing EXTERNAL SF; Windows FF; Windows SF | Superstructure complete | 52 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | 12 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | Board lifts, Floor tools, Glazing lifters, Hand tools, MEWPs | Downpipes, Fixings, Floor finishes, Green roof build-up, Growing medium, Gutters, LSF studs, Plasterboard, Raised floor system, Sealants, Studs, Window units
28 | 2026-08-10 | 2026-08-16 | False floor install for M&E FF; Green roof system; Internal plasterboarding partitions SF; Windows SF |  | 25 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Board lifts, Glazing lifters, Hand tools, MEWPs | Green roof build-up, Growing medium, Plasterboard, Raised floor system, Sealants, Studs, Window units
29 | 2026-08-17 | 2026-08-23 | Cladding brackets & framing; False floor install for M&E FF; False floor install for M&E SF; Green roof system; Internal plasterboarding partitions SF; Windows SF |  | 38 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Board lifts, Glazing lifters, Hand tools, MEWPs | Brackets, Fixings, Green roof build-up, Growing medium, Plasterboard, Rails, Raised floor system, Sealants, Studs, Window units
30 | 2026-08-24 | 2026-08-30 | Cladding brackets & framing; False floor install for M&E SF; Green roof system |  | 20 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Hand tools, MEWPs | Brackets, Fixings, Green roof build-up, Growing medium, Rails, Raised floor system
31 | 2026-08-31 | 2026-09-06 | Cladding brackets & framing; False floor install for M&E SF; Green roof system; PV |  | 26 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Hand tools, MEWPs | Brackets, Cabling, Fixings, Green roof build-up, Growing medium, Inverters, PV panels, Rails, Raised floor system
32 | 2026-09-07 | 2026-09-13 | Cladding brackets & framing; PV |  | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEWPs | Brackets, Cabling, Fixings, Inverters, PV panels, Rails
33 | 2026-09-14 | 2026-09-20 | Cladding brackets & framing; Cladding paneling finish (watertight); PV |  | 22 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hoist, MEWPs | Brackets, Cabling, Cladding panels, Fixings, Inverters, PV panels, Rails, Sealants
34 | 2026-09-21 | 2026-09-27 | Cladding paneling finish (watertight) |  | 9 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hoist, MEWPs | Cladding panels, Sealants
35 | 2026-09-28 | 2026-10-04 | Cladding paneling finish (watertight) |  | 9 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hoist, MEWPs | Cladding panels, Sealants
36 | 2026-10-05 | 2026-10-11 | Cladding paneling finish (watertight) |  | 9 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hoist, MEWPs | Cladding panels, Sealants
37 | 2026-10-12 | 2026-10-18 | Cladding paneling finish (watertight); M&E containment & ducting communal areas GF; Roads/access/Egress/Carpark - kerbs | Weather-tight | 24 | 3 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Excavator, Hoist, MEWPs, Roller | Cable tray, Cladding panels, Concrete, Ductwork, Kerbs, Sealants
38 | 2026-10-19 | 2026-10-25 | M&E containment & ducting communal areas GF; Roads/access/Egress/Carpark - kerbs |  | 15 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Excavator, Roller | Cable tray, Concrete, Ductwork, Kerbs
39 | 2026-10-26 | 2026-11-01 | First fix M&E GF communal areas; M&E containment & ducting communal areas FF; M&E containment & ducting communal areas GF; Roads/access/Egress/Carpark - kerbs |  | 31 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Excavator, Roller | Cable tray, Cabling, Concrete, Ductwork, Kerbs, Pipework
40 | 2026-11-02 | 2026-11-08 | First fix M&E GF communal areas; M&E containment & ducting communal areas FF; Roads/access/Egress/Carpark - kerbs |  | 23 | 3 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Excavator, Roller | Cable tray, Cabling, Concrete, Ductwork, Kerbs, Pipework
41 | 2026-11-09 | 2026-11-15 | 2nd fix boarding (closing in first fix) GF; First fix M&E FF communal areas; First fix M&E GF communal areas; M&E containment & ducting communal areas FF; M&E containment & ducting communal areas SF; Roads/access/Egress/Carpark - kerbs; Roads/access/Egress/Carpark - manholes and gullies |  | 51 | 7 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 6 | 6 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Board lifts, Excavator, Roller | Cable tray, Cabling, Concrete, Ductwork, Gullies, Kerbs, Manholes, Pipework, Plasterboard
42 | 2026-11-16 | 2026-11-22 | 2nd fix boarding (closing in first fix) GF; First fix M&E FF communal areas; M&E containment & ducting communal areas SF; Roads/access/Egress/Carpark - manholes and gullies |  | 28 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Board lifts, Excavator | Cable tray, Cabling, Concrete, Ductwork, Gullies, Manholes, Pipework, Plasterboard
43 | 2026-11-23 | 2026-11-29 | 2nd fix boarding (closing in first fix) FF; 2nd fix boarding (closing in first fix) GF; First fix M&E FF communal areas; First fix M&E SF communal areas; M&E containment & ducting communal areas SF; Plastering communals GF; Roads/access/Egress/Carpark - manholes and gullies |  | 46 | 7 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 6 | 3 | 0 | 8 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Board lifts, Excavator, Mixers | Cable tray, Cabling, Concrete, Ductwork, Gullies, Manholes, Pipework, Plaster, Plasterboard
44 | 2026-11-30 | 2026-12-06 | 2nd fix boarding (closing in first fix) FF; First fix M&E SF communal areas; Plastering communals GF; Roads/access/Egress/Carpark - manholes and gullies |  | 25 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Board lifts, Excavator, Mixers | Cabling, Concrete, Gullies, Manholes, Pipework, Plaster, Plasterboard
45 | 2026-12-07 | 2026-12-13 | 2nd fix boarding (closing in first fix) FF; 2nd fix boarding (closing in first fix) SF; First fix M&E SF communal areas; Main testing chamber ducting & tray work; Plastering communals GF; Roads/access/Egress/Carpark - manholes and gullies; Roads/access/Egress/Carpark - sub base | First fix complete (communal) | 45 | 7 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 4 | 0 | 8 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Board lifts, Compactor, Excavator, Mixers, Roller | Cable tray, Cabling, Concrete, Ductwork, Geotextile, Gullies, Manholes, Pipework, Plaster, Plasterboard, Type 1
46 | 2026-12-14 | 2026-12-20 | 2nd fix boarding (closing in first fix) SF; Main testing chamber ducting & tray work; Mist coat paint GF; Plastering communals FF; Plastering communals GF; Roads/access/Egress/Carpark - sub base |  | 34 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 4 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Access towers, Board lifts, Compactor, Mixers, Roller, Rollers/spray | Cable tray, Ductwork, Geotextile, Paint, Plaster, Plasterboard, Type 1
47 | 2026-12-21 | 2026-12-27 | 2nd fix boarding (closing in first fix) SF; 2nd fix carpentry GF communal areas; Main testing chamber ducting & tray work; Mist coat paint GF; Plastering communals FF; Roads/access/Egress/Carpark - path edgings; Roads/access/Egress/Carpark - sub base |  | 40 | 7 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 4 | 0 | 4 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | Access towers, Board lifts, Compactor, Hand tools, Mini excavator, Mixers, Roller, Rollers/spray | Cable tray, Concrete, Doors/ironmongery, Ductwork, Edgings, Geotextile, Paint, Plaster, Plasterboard, Type 1
48 | 2026-12-28 | 2027-01-03 | 2nd fix carpentry GF communal areas; Main testing chamber ducting & tray work; Plastering communals FF; Roads/access/Egress/Carpark - path edgings |  | 24 | 4 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | Access towers, Hand tools, Mini excavator, Mixers | Cable tray, Concrete, Doors/ironmongery, Ductwork, Edgings, Plaster
49 | 2027-01-04 | 2027-01-10 | 2nd fix carpentry GF communal areas; Main testing chamber ducting & tray work; Mist coat paint FF; Plastering communals FF; Plastering communals SF; Roads/access/Egress/Carpark - path edgings |  | 33 | 6 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 8 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | Access towers, Hand tools, Mini excavator, Mixers, Rollers/spray | Cable tray, Concrete, Doors/ironmongery, Ductwork, Edgings, Paint, Plaster
50 | 2027-01-11 | 2027-01-17 | 2nd fix carpentry FF communal areas; 2nd fix carpentry GF communal areas; Final decoration GF; Main testing chamber ducting & tray work; Mist coat paint FF; Plastering communals SF |  | 32 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 4 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | Access towers, Hand tools, Mixers, Rollers/spray | Cable tray, Doors/ironmongery, Ductwork, Paint, Plaster
51 | 2027-01-18 | 2027-01-24 | 2nd fix carpentry FF communal areas; Climate plant & machinery delivery and install; Final decoration GF; Main testing chamber ducting & tray work; Plastering communals SF |  | 33 | 5 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 3 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Access towers, Forklift/telehandler, Hand tools, Hiab, Mixers, Rollers/spray | Cable tray, Doors/ironmongery, Ductwork, Fixings, Paint, Plant equipment, Plaster
52 | 2027-01-25 | 2027-01-31 | 2nd fix carpentry FF communal areas; Climate plant & machinery delivery and install; Final decoration GF; Mist coat paint SF; Plastering communals SF |  | 29 | 5 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | Forklift/telehandler, Hand tools, Hiab, Mixers, Rollers/spray | Doors/ironmongery, Fixings, Paint, Plant equipment, Plaster
53 | 2027-02-01 | 2027-02-07 | 2nd fix carpentry FF communal areas; 2nd fix carpentry SF communal areas; Climate plant & machinery delivery and install; Final decoration FF; Final decoration GF; Floor finishes GF; Mist coat paint SF; Paving and edgings |  | 45 | 8 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 11 | 8 | 3 | 0 | 0 | 0 | 4 | Compactor, Floor tools, Forklift/telehandler, Hand tools, Hiab, Mini excavator, Rollers/spray | Doors/ironmongery, Edgings, Fixings, Floor finishes, Paint, Paving, Plant equipment, Sub-base
54 | 2027-02-08 | 2027-02-14 | 2nd fix carpentry SF communal areas; Climate plant & machinery delivery and install; Final decoration FF; Floor finishes GF; Paving and edgings |  | 31 | 5 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 4 | 3 | 0 | 0 | 0 | 4 | Compactor, Floor tools, Forklift/telehandler, Hand tools, Hiab, Mini excavator, Rollers/spray | Doors/ironmongery, Edgings, Fixings, Floor finishes, Paint, Paving, Plant equipment, Sub-base
55 | 2027-02-15 | 2027-02-21 | 2nd fix carpentry SF communal areas; Climate plant & machinery delivery and install; Final decoration FF; Paving and edgings |  | 27 | 4 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | Compactor, Forklift/telehandler, Hand tools, Hiab, Mini excavator, Rollers/spray | Doors/ironmongery, Edgings, Fixings, Paint, Paving, Plant equipment, Sub-base
56 | 2027-02-22 | 2027-02-28 | 2nd fix carpentry SF communal areas; Climate plant & machinery delivery and install; Final decoration FF; Final decoration SF; Floor finishes FF; Main connections first and second fixing (testing chamber); Paving and edgings |  | 44 | 7 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 5 | 0 | 0 | 0 | 8 | 4 | 3 | 0 | 0 | 0 | 4 | Compactor, Floor tools, Forklift/telehandler, Hand tools, Hiab, Mini excavator, Rollers/spray, Test gear | Controls, Doors/ironmongery, Edgings, Fixings, Floor finishes, Paint, Paving, Pipework, Plant equipment, Sub-base
57 | 2027-03-01 | 2027-03-07 | Final decoration SF; Floor finishes FF; Main connections first and second fixing (testing chamber); Planters; Top coat |  | 33 | 5 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 4 | 0 | 0 | 4 | Floor tools, Hand tools, Paver, Roller, Rollers/spray, Test gear | Asphalt, Controls, Floor finishes, Paint, Pipework, Planters, Topsoil
58 | 2027-03-08 | 2027-03-14 | Final decoration SF; Line painting; Main connections first and second fixing (testing chamber); Planters | Testing chamber connected; Car park works complete | 22 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | Hand tools, Line marker, Rollers/spray, Test gear | Controls, Paint, Pipework, Planters, Road marking paint, Topsoil
59 | 2027-03-15 | 2027-03-21 | Final decoration SF; Floor finishes SF; Foliage/planting; Planters |  | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 0 | 8 | Floor tools, Hand tools, Rollers/spray | Floor finishes, Paint, Planters, Plants, Topsoil
60 | 2027-03-22 | 2027-03-28 | Floor finishes SF; Foliage/planting; Mastic and builders clean |  | 14 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | Floor tools, Hand tools | Cleaning materials, Floor finishes, Mastic, Plants, Topsoil
61 | 2027-03-29 | 2027-04-04 | Foliage/planting; Mastic and builders clean; Testing and commissioning | Landscaping complete | 17 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 4 | Hand tools, Test equipment | Cleaning materials, Mastic, O&M data, Plants, Test certificates, Topsoil
62 | 2027-04-05 | 2027-04-11 | Mastic and builders clean; Testing and commissioning |  | 12 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | Hand tools, Test equipment | Cleaning materials, Mastic, O&M data, Test certificates
63 | 2027-04-12 | 2027-04-18 | Mastic and builders clean; Snagging period; Testing and commissioning |  | 20 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | Hand tools, Test equipment | Cleaning materials, Mastic, Minor materials, O&M data, Test certificates
64 | 2027-04-19 | 2027-04-25 | Snagging period; Testing and commissioning |  | 15 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | Hand tools, Test equipment | Minor materials, O&M data, Test certificates
65 | 2027-04-26 | 2027-05-02 | Snagging period; Testing and commissioning | Practical completion; Commissioning complete | 15 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | Hand tools, Test equipment | Minor materials, O&M data, Test certificates

## Milestones
Milestone | Date (from programme)
RIBA Stage 3 Complete (deadline) | 2026-02-25
Critical subcontractor appointment deadline | 2026-02-19
RIBA Stage 4 complete (deadline) | 2026-04-20
Substructure complete (Groundworks finish) | 2026-05-15
Superstructure complete | 2026-08-04
Weather-tight (External facade finish) | 2026-10-12
First fix complete (communal areas SF) | 2026-12-07
Car park works complete (line painting finish) | 2027-03-12
Landscaping complete | 2027-04-01
Commissioning complete | 2027-04-26
Practical completion (Snagging finish) | 2027-04-28