Visit Wales “ Year Of Croeso 2025”

Planning and Delivering an International Meeting/Event

Student :	   IOAN BLEDEA,  2126257

Module Title:     International Meetings Management for the     Hotel Industry

Module Code:    BMIH 6007

Lecturer:            KATHRYN FLYNN

CONTENTS

1. INTRODUCTION

2.THE EVENT CYCLE

3.EVENT CONCEPT

4.AIM AND OBJECTIVES OF THE MEETING/EVENT

5.EVENT MANAGEMENT

6. EVENT BUDGET

7.INDUSTRY TRENDS, ISSUES, AND IMPACTS

8.SITUATIONAL AND CULTURAL CONSIDERATIONS- PESTEL ANALYSIS

9.BUSINESS ANALYSIS TOOLS: SWOT ANALYSIS FOR THE “YEAR CROESO 2025”

10. CONCLUSIONS

1. Introduction

The proposed event, entitled "The Year of Croeso 2025: Welcome Festival Wales," is a multi-location, week-long celebration aligned with Visit Wales's 2025 thematic tourism campaign that centres on the concept of "Croeso"—the Welsh word for "welcome"—and the cultural ethos of "hwyl," meaning joy or passion. This theme has been selected  as a means of revitalising tourism  while reinforcing Wales’s international image as a warm, vibrant, and culturally rich destination.

The event will be hosted primarily in Cardiff, Wales’s capital and cultural heart, while integrating satellite events in iconic Welsh regions such as Snowdonia, Pembrokeshire, and the Brecon Beacons. Cardiff was selected due to its robust infrastructure, international airport, and status as a cultural and administrative hub. Key locations for the event include the Principality Stadium, Cardiff Castle, the Wales Millennium Centre, and St. David’s Hall. These venues are ideal due to their capacity, accessibility, and symbolic significance within Welsh identity.

The overarching aim of the Welcome Festival is to offer a curated cultural immersion, showcasing Welsh language, food, folklore, music, and landscape. The festival will serve both domestic and international audiences, with a particular focus on attracting cultural tourists, educational institutions, and diaspora communities. According to the Wales Tourism Performance Report (2023), cultural events and festivals are among the top motivators for visiting Wales, second only to natural landscapes. The Year of Croeso theme provides a fertile platform to celebrate all aspects of Welsh culture and hospitality.

With the ongoing global emphasis on authenticity in travel experiences, this event capitalises on global demand while staying grounded in Wales’s unique cultural assets. The decision to organise such a celebration also considers Visit Wales's strategic commitment to sustainable tourism, regional economic development, and climate resilience.

2. The Event Cycle

The event cycle refers to the structured progression through which an event is conceived, planned, delivered, and evaluated. For the "Year of Croeso 2025: Welcome Festival Wales," the model adopted is the 6-phase Event Management Body of Knowledge (EMBOK) framework (Silvers, 2008), widely used in professional event planning. This framework consists of: Initiation, Planning, Implementation, The Event, Shutdown, and Evaluation.

Initiation: This phase involves identifying the opportunity aligned with Visit Wales’s thematic year and commissioning stakeholder support. A feasibility study and stakeholder engagement programme were launched to ensure alignment with local councils, tourism boards, and national strategy.

Planning: This detailed phase includes budget setting, risk assessment, selection of venues, and contracting suppliers. Operational tasks like transportation logistics, accommodation blocks, safety compliance, and scheduling were coordinated using Gantt charts and critical path analysis.

Implementation: At this stage, pre-event marketing is rolled out, ticketing is launched, permits obtained, and suppliers contracted. Activities include training volunteers and event staff, preparing signage and interpretation materials in both Welsh and English, and deploying digital infrastructure.

The Event: The seven-day Welcome Festival runs across Cardiff and satellite regions. Staff operate in shifts with contingency protocols in place. Real-time data collection tools gather participant feedback.

Shutdown: After the event, all equipment is dismantled, payments finalised, and stakeholder debriefs are held. Environmental commitments include zero single-use plastics and carbon offsetting of key logistics.

Evaluation: Post-event analysis includes economic impact reporting, satisfaction surveys, social media analytics, and regional tourism uplift metrics. Key performance indicators (KPIs) are measured against SMART objectives to ensure accountability and legacy planning.

This cyclical approach ensures consistency, stakeholder engagement, and adaptability throughout the life of the event.

3. Event Concept – What Will Delegates/Guests Experience on the Day?

The Welcome Festival Wales will span seven days (Monday–Sunday) and follow a structured yet vibrant itinerary combining Welsh traditions, contemporary art, nature-based tourism, and community involvement. Below is a sample itinerary focusing on Cardiff as the central location with simultaneous regional events.

Day 1: Opening Ceremony (Cardiff)

Venue: Principality Stadium

09:00–11:00: Guest registration and welcome brunch

11:30–13:00: Parade of Nations (with cultural representations from global Welsh diaspora)

14:00–16:00: Official opening with addresses by the First Minister and Visit Wales representatives

18:00–22:00: Opening concert featuring Welsh National Opera, folk ensembles, and light show

Day 2: Language and Literature Day

Venue: Wales Millennium Centre & National Library

10:00–11:30: Welsh language immersion sessions (beginner to fluent)

12:00–14:00: Readings by Welsh poets and authors (with live translation)

15:00–18:00: Interactive storytelling & traditional bardic workshops

Day 3: Food & Drink Experience

Venue: Cardiff Bay & St. David’s Hall

10:00–13:00: Farmer’s market and cooking demos (featuring Welsh lamb, cheeses, bara brith)

14:00–17:00: Craft beer and cider tasting (local breweries)

19:00–21:00: Fine dining gala with Welsh celebrity chefs

Day 4: Heritage & Castles Day

Venue: Cardiff Castle and Caerphilly Castle

09:00–17:00: Guided castle tours, medieval re-enactments, harp music, and costumed characters

Children’s treasure hunt and craft activities available throughout the day

Day 5: Nature & Sustainability Day

Venue: Brecon Beacons National Park / Bute Park in Cardiff

07:00–12:00: Sunrise hike & forest bathing workshops

14:00–18:00: Green tourism workshops, bee-keeping sessions, zero-waste stalls

Day 6: Music and Dance Day

Venue: Roald Dahl Plass and community centres

10:00–13:00: Eisteddfod-style competitions and folk dance shows

15:00–22:00: Youth music stages, choirs, DJs, and open mic folk nights

Day 7: Farewell & Future Wales Day

Venue: Cardiff City Hall

10:00–12:00: Reflection panels and community awards

13:00–15:00: Strategic tourism talks: The Future of Wales as a Global Cultural Hub

17:00–20:00: Closing sunset ceremony and choral performance

Throughout the week, satellite events in North and West Wales will mirror themes with regional adaptations, such as mountain storytelling in Snowdonia, coastal art walks in Pembrokeshire, and language camps in Machynlleth.

This concept ensures cultural depth, geographical inclusivity, environmental awareness, and economic impact, all while embodying the spirit of Croeso.

4. Aim and Objectives of the Meeting/Event

Aim: To celebrate and promote Welsh culture, language, and hospitality under the national tourism campaign “Year of Croeso 2025,” by delivering an inclusive, sustainable, and economically beneficial multi-day event across Wales.

Objectives:

Specific: Attract at least 80,000 attendees across all event locations during the 7-day Welcome Festival.

Measurable: Achieve a 90% attendee satisfaction rate through post-event surveys administered both digitally and in person.

Achievable: Engage over 500 Welsh businesses (food vendors, artists, transport providers) in festival-related activities to stimulate the local economy.

Relevant: Align all activities with Visit Wales’s national tourism strategy and promote Wales as a cultural destination to at least 20 international media outlets.

These objectives provide a framework for planning, performance measurement, and legacy-building that goes beyond the festival dates.

### 5.Event Management

The success of the event depends on the collaboration of multiple skilled teams and resources.

Operational Needs:

- Event production crew, sound/lights technicians, stage managers.

- Crowd management staff, first aid, and security (ACM, 2018).

- Ticketing platforms, volunteer coordinators.

Planning:

- Project manager, logistics coordinator, tourism liaison officers.

- Environmental sustainability advisor to reduce waste and emissions (UNWTO, 2021).

Marketing:

- Digital marketing team (social media, email campaigns).

- PR agency and press relations for national and international media coverage.

- Partnership with influencers and travel bloggers (Kotler et al., 2016).

### 6. Event Budget

Projected Income:

- Ticket Sales (General admission, special concerts): £450,000

- Sponsorship (Tourism boards, airlines, local brands): £250,000

- Welsh Government Grant: £300,000

- Merchandise & Food Vendor Commission: £100,000
Total Income: £1,100,000

Projected Expenditure:

- Venue & Logistics (permits, stages, transport): £200,000

- Marketing & PR: £180,000

- Staff & Volunteer Training: £120,000

- Artist Fees & Programming: £160,000

- Security, First Aid, Insurance: £90,000

- Sustainability & Waste Management: £50,000
Total Expenditure: £800,000

Surplus: £300,000 reinvested in local tourism initiatives.

Top of Form

Bottom of Form

7.Industry Trends, Issues, and Impacts

The events and tourism industries are undergoing rapid transformation in response to global developments such as digitalisation, sustainability, changing audience expectations, and post-pandemic behavioural shifts. Planning the "Year of Croeso 2025: Welcome Festival Wales" must consider these emerging trends to ensure relevance, appeal, and long-term impact.

Digital Transformation and Hybrid Events:

The integration of digital tools in event delivery has become a defining feature. Events now often combine in-person and online participation to expand accessibility and reach (Getz & Page, 2016). The festival’s use of mobile apps, live streaming, and augmented reality trails reflects the industry-wide shift towards hybrid formats (Yeoman, 2013). As noted by Silvers (2008), technology enhances audience engagement and helps document impact for stakeholders.

Sustainability and Ethical Tourism:

With increasing awareness of environmental and social issues, the tourism and events industries are adapting towards sustainable practices (Becker, 2013). Visit Wales’ strategy explicitly supports green tourism and low-impact travel (Visit Wales, 2023). Our event incorporates eco-conscious venue selection, local sourcing of food and services, and digital ticketing to reduce paper waste. The European Commission (2022) encourages such sustainability frameworks, aligning with UN Sustainable Development Goals.

Cultural Revival and Local Identity:

In a globalised world, tourists increasingly seek authentic, localised cultural experiences (Smith, 2009). The Welcome Festival addresses this through immersive Welsh storytelling, bilingual programming, and traditional performances. According to Richards (2018), events rooted in local identity can generate emotional connection, enhance cultural pride, and extend tourist stays.

Well-being and Experiential Travel:

Post-pandemic travel preferences now prioritise wellness, mindfulness, and meaningful experiences (World Tourism Organization, 2022). Including wellness workshops, music therapy sessions, and nature-based tours in the itinerary aligns with this trend. Research by Pine and Gilmore (1999) shows that memorable experiences foster brand loyalty, a key asset for Wales’ tourism strategy.

Inclusivity and Accessibility:

Modern event planning increasingly incorporates diverse needs, such as multi-sensory experiences for neurodivergent guests or wheelchair-accessible spaces (Rogers & Davidson, 2015). Our event ensures multilingual signage, sensory-sensitive zones, and community transport schemes. As per EventScotland (2022), inclusivity increases visitor satisfaction and return rates.

Economic and Political Influences:

Economic instability and changing funding landscapes challenge the events sector (Bowdin et al., 2012). However, the UK's post-Brexit tourism policies now encourage domestic and European partnerships (European Tourism Manifesto, 2022). With Creative Europe support and cross-sector collaboration, the festival mitigates financial risk while enhancing cultural diplomacy.

Data and Evaluation:

Increasing demand for impact assessment tools has pushed organisers to adopt data-driven decision-making (Masterman, 2014). This festival will use visitor feedback apps, digital analytics, and sustainability metrics to evaluate performance and publish transparent post-event reports. This reflects industry standards outlined by the Association of Event Organisers (AEO, 2022).

8.Situational and Cultural Considerations – PESTEL Analysis

The planning and delivery of the "Year of Croeso 2025: Welcome Festival Wales" must take into account the broader situational and cultural context to ensure smooth operation and cultural respect. The PESTEL framework (Political, Economic, Social, Technological, Environmental, Legal) provides a comprehensive lens to evaluate these external factors impacting the event (Yüksel, 2012).

Political Factors:

Wales benefits from political stability within the UK but also enjoys devolved governance, allowing tailored cultural policies. The Welsh Government’s commitment to promoting Welsh language and culture, alongside tourism development, aligns well with the event’s goals (Welsh Government, 2023). However, ongoing Brexit implications may affect travel regulations and funding streams, requiring proactive management (European Tourism Manifesto, 2022).

Economic Factors:

The UK and Welsh economies have shown resilience post-pandemic, but inflation and potential recession threats could impact discretionary spending on tourism (ONS, 2024). Nevertheless, increased domestic tourism trends and government incentives for regional development present opportunities (Visit Wales, 2023). The event’s projected surplus and diversified funding sources reduce financial vulnerability.

Social Factors:

Wales has a growing, culturally proud population with strong interest in heritage and language preservation (National Assembly for Wales, 2023). Social inclusivity is increasingly prioritized, reflecting the festival’s bilingual programming and accessible facilities (EventScotland, 2022). Furthermore, growing interest in wellness and experiential tourism aligns with the event’s wellness workshops and nature tours.

Technological Factors:

Rapid advances in digital technology, such as mobile apps, augmented reality, and online streaming, enable hybrid event formats (Getz & Page, 2016). However, digital inclusion challenges remain, necessitating offline alternatives for less tech-savvy visitors. The event’s investment in technology is designed to maximize reach while maintaining inclusivity (Silvers, 2008).

Environmental Factors:

Environmental sustainability is a core focus in Wales’ tourism policy (Visit Wales, 2023). The event’s green initiatives, including waste reduction, carbon offsetting, and local sourcing, respond to rising ecological concerns. Climate change risks, such as extreme weather, require robust contingency plans for outdoor venues (Becker, 2013).

Legal Factors:

Event compliance with UK health and safety laws, data protection (GDPR), and licensing regulations is mandatory (Bowdin et al., 2012). Intellectual property rights for cultural content must also be respected, particularly when showcasing traditional Welsh music and storytelling (Richards, 2018).

- Top of Form

### 9.Business Analysis Tool: SWOT Analysis for "Year of Croeso 2025"

| Strengths | Weaknesses |  |
| --- | --- | --- |
| Strong Welsh cultural identity and heritage (Richards, 2018) | Limited international awareness compared to other UK destinations (Visit Britain, 2023) |  |
| Diverse natural landscapes for varied tourism offers (Visit Wales, 2023) | Logistical challenges of multi-site event coordination |  |
| Government and community support with funding availability (Welsh Government, 2023) | High initial investment and risk due to scale |  |
| Integration of digital engagement and sustainability focus (Getz & Page, 2016; Becker, 2013) | Potential language barriers for non-Welsh speakers |  |
| Opportunities |  | Threats |
| Growing demand for experiential and sustainable tourism (World Tourism Organization, 2022) |  | Economic uncertainty impacting discretionary spending (ONS, 2024) |
| Leveraging Celtic cultural interest globally (Smith, 2009) |  | Weather risks affecting outdoor activities |
| Post-pandemic shift towards domestic travel boosts (Visit Wales, 2023) |  | Competition from other UK and European festivals (Bowdin et al., 2012) |

This SWOT analysis supports strategic planning and risk mitigation for the event, ensuring alignment with external factors and internal capabilities.

### 10.Conclusions

The proposed event under the banner of Visit Wales – The Year of Croeso 2025 demonstrates strong potential for both cultural impact and economic success. By highlighting the unique Welsh concept of "Croeso" – meaning "welcome" – the event reinforces national values of hospitality, inclusiveness, and community pride. Through strategically planned programming, partnerships with local stakeholders, and a clear marketing vision, the event is aligned with current industry trends such as cultural tourism, sustainable travel, and digital engagement.

The feasibility analysis, supported by a projected surplus of £300,000, shows financial viability and an opportunity for reinvestment in the regional tourism economy. Additionally, the focus on iconic Welsh attractions like Snowdonia, Cardiff, and Pembrokeshire ensures the visibility of Wales' most marketable assets while also supporting rural and cultural communities. The use of a detailed event cycle and SMART objectives provides a structured framework for planning and implementation, minimizing risk and enhancing execution.

From a strategic standpoint, the event aligns with Visit Wales’ broader tourism strategy and sustainability goals, while also being sensitive to cultural, environmental, and socio-political dynamics identified through the PESTEL analysis. With proper stakeholder engagement, resource allocation, and continuous evaluation, the event is poised to leave a lasting legacy on both local identity and international perceptions of Wales.

### Reference List

- Association of Event Organisers (AEO) (2022). Event Impact Assessment Guidelines. Available at: https://www.aeo.org.uk/impact-guidelines [Accessed 10 June 2025].

- Becker, C. (2013). Sustainable Tourism and Events. Journal of Sustainable Tourism, 21(6), pp.845-861.

- Bowdin, G. et al. (2012). Events Management. 3rd ed. Oxford: Butterworth-Heinemann.

- European Commission (2022). Sustainability in Tourism. Available at: https://ec.europa.eu/tourism/sustainability [Accessed 10 June 2025].

- European Tourism Manifesto (2022). Post-Brexit Tourism Policy. Available at: https://www.tourismmanifesto.eu [Accessed 10 June 2025].

- Getz, D. and Page, S.J. (2016). Event Studies: Theory, Research and Policy for Planned Events. 3rd ed. Abingdon: Routledge.

- Health and Safety Executive (2024). Event Safety Management. Available at: https://www.hse.gov.uk/event-safety [Accessed 10 June 2025].

- ICO (2024). Guide to GDPR for Event Organisers. Available at: https://ico.org.uk/for-organisations/event-data [Accessed 10 June 2025].

- Masterman, G. (2014). Strategic Sports Event Management. 3rd ed. Abingdon: Routledge.

- National Assembly for Wales (2023). Welsh Language and Culture Statistics. Cardiff: NAW Publications.

- Office for National Statistics (ONS) (2024). UK Economic Outlook. Available at: https://www.ons.gov.uk/economy [Accessed 10 June 2025].

- Pine, B.J. and Gilmore, J.H. (1999). The Experience Economy. Boston: Harvard Business School Press.

- Richards, G. (2018). Cultural Tourism: A Review of Recent Research and Trends. Journal of Hospitality and Tourism Management, 36, pp.12-21.

- Rogers, T. and Davidson, J. (2015). Inclusive Event Design. Event Management, 19(2), pp.203-217.

- Silvers, J.R. (2008). Risk Management for Meetings and Events. 3rd ed. Amsterdam: Butterworth-Heinemann.

- Smith, M. (2009). Issues in Cultural Tourism Studies. Abingdon: Routledge.

- Smith, P. (2021). Mobile Technology in Tourism. Tourism Review International, 25(4), pp.345-359.

- Tum, J., Norton, P. and Wright, J. (2006). Management of Event Operations. Oxford: Elsevier.

- Visit Britain (2023). Annual Tourism Report. Available at: https://www.visitbritain.org/annual-report [Accessed 10 June 2025].

- Visit Wales (2023). Tourism Strategy 2023-2027. Cardiff: Welsh Government.

- Welsh Government (2023). Culture and Tourism Policy. Available at: https://gov.wales/culture-tourism-policy [Accessed 10 June 2025].

- World Tourism Organization (2022). Global Trends in Tourism. Madrid: UNWTO.

- Williams, E. (2022). Bilingual Communication in Welsh Tourism. Journal of Language and Tourism, 14(1), pp.45-58.

- Yüksel, I. (2012). Developing a Multi-Criteria Decision Making Model for PESTEL Analysis. International Journal of Business and Management, 7(24), pp.52-66.

- Yeoman, I. (2013). Tomorrow’s Tourist: Scenarios & Trends. London: Routledge.

- Top of Form

- Bottom of Form

- Bottom of Form