BUSINESS CONSULTANCY REPORT

Green Haven Florists

A Feasible Solution to Improve In-Store and Online Sales

Student Name: Alexandre Dias Semedo

Student ID: 2442114

Assignment Title: Business Consultancy Report

Module Name: Problem Solving and Decision Making

Module Code : LCLM4004

Lectures Name : Charles

Date : 16 August 2026

# Contents

1. Case-Study Overview and Nature of the Problem ............ 3

2. Two Proposed Solutions ................................... 3

3. Evaluation and Selection of Preferred Solution ........... 4

4. Risk Analysis of Selected Solution ....................... 5

5. Implementation Plan and Justification .................... 6

6. KPI and SMART Objectives ................................. 7

7. Key Findings ............................................. 8

References .................................................. 8

Appendix 1 – Grid Analysis .................................. 9

Appendix 2 – Risk Analysis .................................. 10

Appendix 3 – Implementation Plan ............................ 11

Appendix 4 – KPI and SMART Objectives ....................... 12

# 1. Case-Study Overview and Nature of the Problem

Green Haven Florists is an independent Norwich-based florist founded by Liam and Priya Patel in 2016. The business has built its reputation through bespoke floral arrangements, sustainable packaging, locally sourced flowers and strong community relationships. However, the business has experienced a 30% decline in in-store sales during the last year. The main pressures are reduced high-street footfall, competition from online and national flower retailers, rising flower and sustainable-material costs, an outdated website and limited digital marketing capability. Although online orders have increased slightly, they have not replaced lost physical sales. The problem is therefore not simply lower demand; it is a mismatch between Green Haven’s traditional sales model and customers’ growing expectations for convenient digital purchasing, flexible delivery and competitive value. This is particularly important because online retail remains a significant part of UK retail: internet sales represented 27.4% of total retail sales in 2025 (ONS, 2026).

# 2. Two Proposed Solutions

Two feasible solutions are recommended. Both use Green Haven’s existing strengths rather than attempting to compete directly with national retailers on price.

Solution 1 – E-commerce website redevelopment with online delivery and subscription services. Green Haven could replace its outdated website with a mobile-friendly online shop containing clear product categories, high-quality photographs, simple checkout, secure online payment, local delivery slots and click-and-collect. The website could also introduce weekly or monthly flower subscriptions for households and small businesses. This would make purchasing more convenient and create repeat revenue. A digital loyalty scheme and email reminders for birthdays, anniversaries and seasonal events could encourage repeat purchases. This approach responds directly to customer feedback and the wider growth of online retail. The Department for Business and Trade (2025) identifies digital adoption as an important route for SMEs to improve productivity and business performance.

Solution 2 – Integrated social-media marketing and local partnership campaign. Green Haven could develop a consistent Instagram and Facebook campaign showing behind-the-scenes preparation, seasonal flowers, customer arrangements, weddings and the environmental benefits of its packaging and locally sourced products. Paid local social-media advertising could target customers within a practical delivery radius. The business could also partner with wedding venues, cafés, restaurants, offices and local events to create referral offers. A monthly promotion, such as ‘Norwich Flower of the Month’, could encourage store visits while QR codes on packaging could direct customers to the online shop. This solution would strengthen brand awareness and community differentiation, but it would not solve the outdated website problem by itself. Therefore, the two options differ mainly in their ability to remove the purchasing barrier as well as generate demand.

# 3. Evaluation and Selection of Preferred Solution

## 3A. Evaluation using Grid Analysis

A Grid Analysis was used to compare the two solutions against criteria that are important for Green Haven Florists: expected sales impact, implementation cost, speed of implementation, customer convenience, repeat-purchase potential, competitive differentiation and operational feasibility. Each criterion was scored from 1 (very weak) to 5 (very strong), with higher scores representing a more favourable result. The detailed analysis is presented in Appendix 1.

Solution 1 achieved the stronger overall result because it addresses the core customer journey. Customers can discover, select, pay for and arrange delivery without visiting the shop. It also creates opportunities for subscriptions, loyalty activity and customer data collection. Solution 2 is valuable because it can increase awareness and footfall, but its success depends on customers being able to move easily from social media to a good purchasing experience. The preferred option is therefore Solution 1: e-commerce website redevelopment with flexible delivery and subscription services.

# 3B. Why the Preferred Solution Was Chosen

Solution 1 was selected because it provides the best balance between commercial impact and long-term feasibility. It directly responds to the outdated website and demand for flexible delivery and subscriptions, while supporting both online and potentially in-store sales. It also allows Green Haven to compete through convenience, personalisation and sustainability rather than attempting to match a national chain’s low prices. Current UK evidence supports this direction: online sales continue to represent a substantial share of retail, while government research highlights the importance of digital adoption for SMEs (ONS, 2026; Department for Business and Trade, 2025).

# 4. Risk Analysis of the Selected Solution

## 4A. Risk Analysis

The selected solution has several risks. The most significant are exceeding the website-development budget, low customer adoption, technical or payment problems, delivery failures, staff resistance or lack of digital skills, and cyber-security or data-protection issues. The risk analysis in Appendix 2 assesses each risk by likelihood and impact and identifies mitigation actions. The analysis follows a practical risk-management approach in which risks are identified, assessed, controlled and reviewed throughout implementation (ISO, 2018).

## 4B. Result of the Risk Analysis

The overall risk level is manageable provided that Green Haven implements the project in stages rather than launching a complex system immediately. The highest-priority risks are customer adoption, technical reliability and delivery performance because failures in these areas could damage customer trust. These risks can be reduced through user testing, a small initial product range, reliable payment systems, clear delivery zones, staff training and regular monitoring. Cyber-security and customer-data protection must also be treated as essential controls. The analysis therefore supports implementation, but only with clear responsibilities, testing and monthly review.

# 5. Implementation Plan

## 5A. Implementation Plan

The proposed implementation period is 12 weeks. The plan is deliberately phased so that Green Haven can control cost and test the service before full promotion. Detailed activities, timings and responsibilities are shown in Appendix 3.

Phase 1 (Weeks 1–2) involves confirming the budget, customer requirements, product range, delivery area and website specifications. Liam should lead business decisions while Priya gathers customer feedback and confirms the product catalogue. Phase 2 (Weeks 3–6) involves selecting a suitable website/e-commerce provider, preparing product photographs and descriptions, setting delivery rules, configuring online payments and building the website. Phase 3 (Weeks 7–8) involves staff training and testing. The owners should test the website on mobile and desktop devices, place trial orders and check payment, collection, delivery and customer-confirmation processes. Phase 4 (Weeks 9–10) is a soft launch to existing customers, supported by email and in-store promotion. Phase 5 (Weeks 11–12) is the full launch, including social-media promotion, subscription offers and local partnerships. Performance should then be reviewed monthly.

# 5B. Justification of the Implementation Plan

The activities are arranged in this order because Green Haven should understand customer needs and control the scope before spending money on development. Building the website before testing requirements could create unnecessary costs. Testing must occur before promotion because a poor first customer experience could harm the reputation the business has developed since 2016. The soft launch gives the owners an opportunity to identify technical, delivery and customer-service problems with limited exposure. Liam and Priya should remain responsible for strategic decisions because they understand the brand and customers, while technical work can be outsourced to an e-commerce specialist. Staff involvement is important because successful digital change requires reliable people and processes as well as technology (Department for Business and Trade, 2025).

# 6. KPI and SMART Objectives

## 6A. KPI and SMART Objectives

The main KPI should be the percentage increase in monthly online sales because the selected solution is designed primarily to improve digital purchasing and repeat revenue. The KPI should be supported by SMART objectives covering website launch, online sales, subscriptions, conversion and customer experience. The full KPI and SMART objectives table is included in Appendix 4. SMART objectives should be specific, measurable, achievable, relevant and time-bound so that management can clearly assess progress (Doran, 1981).

## 6B. Using Metrics to Monitor and Evaluate Effectiveness

The KPI and SMART objectives will provide Green Haven with a simple control system. Online sales should be reviewed monthly against the baseline recorded before implementation. Website conversion rate will show whether visitors are becoming customers, while subscription numbers will indicate whether the business is developing recurring revenue. Customer feedback and delivery complaints should be reviewed alongside sales figures because higher sales would not represent success if service quality declined. If targets are missed for two consecutive months, Liam and Priya should identify the cause and adjust website content, pricing, delivery options or marketing activity. This creates a continuous improvement cycle rather than treating the website launch as a one-off project.

# 7. Key Findings

Green Haven’s main challenge is the loss of physical sales caused by lower footfall, stronger online competition and changing customer expectations.

The outdated website is a significant weakness because customers want easier online ordering and more flexible delivery.

Solution 1—e-commerce redevelopment with flexible delivery and subscriptions—provides the strongest overall response.

The solution can create convenience, repeat purchases and a stronger digital relationship with customers.

Implementation should be phased over 12 weeks, with testing and a soft launch before full promotion.

The main risks are manageable through budgeting, testing, staff training, reliable delivery arrangements and data-security controls.

The KPI and SMART objectives will allow Liam and Priya to measure online growth, conversion, subscriptions and customer experience.

The recommended strategy is to modernise the business without abandoning its existing strengths in personal service, sustainability and local community relationships.

# References

Department for Business and Trade (2025) SME Digital Adoption Taskforce: final report. Available at: https://www.gov.uk/government/publications/sme-digital-adoption-taskforce-final-report (Accessed: 16 August 2026).

Department for Business and Trade (2025) Understanding technology adoption among UK SMEs. Available at: https://www.gov.uk/government/publications/understanding-technology-adoption-among-uk-smes (Accessed: 16 August 2026).

Doran, G.T. (1981) ‘There’s a S.M.A.R.T. way to write management’s goals and objectives’, Management Review, 70(11), pp. 35–36.

ISO (2018) ISO 31000:2018 Risk management – Guidelines. Geneva: International Organization for Standardization.

Office for National Statistics (2026) Retail sales, Great Britain: December 2025. Available at: https://www.ons.gov.uk/businessindustryandtrade/retailindustry/bulletins/retailsales/december2025 (Accessed: 16 August 2026).

Office for National Statistics (2026) Internet sales as a percentage of total retail sales (ratio) (%). Available at: https://www.ons.gov.uk/businessindustryandtrade/retailindustry/timeseries/j4mc/drsi (Accessed: 16 August 2026).

# Appendix 1 – Grid Analysis

Scoring: 1 = very weak; 5 = very strong. Higher total = stronger overall option.

| Criteria | Weight | Solution 1: E-commerce | Solution 2: Social Media |
| --- | --- | --- | --- |
| Expected sales impact | 5 | 5 | 4 |
| Customer convenience | 5 | 5 | 3 |
| Repeat-purchase potential | 4 | 5 | 4 |
| Competitive differentiation | 4 | 4 | 5 |
| Speed of implementation | 3 | 3 | 5 |
| Implementation cost | 3 | 3 | 4 |
| Operational feasibility | 4 | 4 | 4 |

Weighted score: Solution 1 = 139; Solution 2 = 121. The result indicates that Solution 1 provides the stronger overall balance of commercial impact, convenience and repeat revenue.

# Appendix 2 – Risk Analysis

| Risk | Likelihood (1–5) | Impact (1–5) | Score | Level | Mitigation |
| --- | --- | --- | --- | --- | --- |
| Website cost exceeds budget | 3 | 4 | 12 | Medium | Set a fixed scope and obtain quotations before approval. |
| Low customer adoption | 3 | 5 | 15 | High | Soft launch, customer feedback, simple checkout and promotions. |
| Technical/payment failure | 2 | 5 | 10 | Medium | Use established provider and conduct full transaction testing. |
| Delivery delays or errors | 3 | 4 | 12 | Medium | Define delivery zones, time slots and backup arrangements. |
| Staff lack digital skills | 3 | 3 | 9 | Medium | Provide training and written procedures. |
| Cyber/data-protection issue | 2 | 5 | 10 | Medium | Use secure payment provider, strong passwords and restricted access. |

Risk scale: 1–4 Low, 5–9 Medium, 10–25 High. Scores should be reviewed monthly during implementation and after launch.

# Appendix 3 – Implementation Plan

| Phase | Timing | Main Activity | Responsibility | Output |
| --- | --- | --- | --- | --- |
| 1. Planning | Weeks 1–2 | Confirm budget, customer needs, products and delivery area. | Liam & Priya | Approved project scope |
| 2. Build | Weeks 3–6 | Select provider; create shop; add products, payments and delivery options. | Liam + web specialist | Working website |
| 3. Test & train | Weeks 7–8 | Train staff; test checkout, mobile use, payments and delivery process. | Priya + staff | Tested system |
| 4. Soft launch | Weeks 9–10 | Launch to existing customers and collect feedback. | Liam & Priya | Feedback and corrections |
| 5. Full launch | Weeks 11–12 | Promote website, subscriptions and local partnerships. | Liam + marketing support | Public launch |
| 6. Review | Monthly after launch | Review KPI, sales, conversion, complaints and subscriptions. | Liam & Priya | Monthly performance report |

# Appendix 4 – KPI and SMART Objectives

| Metric / Objective | Target | Deadline | Measurement Method |
| --- | --- | --- | --- |
| Primary KPI: monthly online sales | Increase online sales by 25% from pre-launch baseline | Within 6 months of full launch | Monthly e-commerce sales report |
| Website launch | Fully functional mobile-friendly shop with payment and delivery options | End of Week 8 | Launch checklist and test orders |
| Online conversion rate | Reach at least 2.5% of website visitors converting to orders | By Month 6 | Website analytics |
| Flower subscriptions | Gain 50 active subscribers | By Month 6 | Subscription/customer records |
| Customer experience | Maintain at least 90% positive post-purchase feedback | Monthly from launch | Customer survey and reviews |