Rhys Taylor (P150229)

Cost studies of Buildings

Assignment 1 of 1

cost studies of buildings

Rhys Taylor

Contents

Introduction	2

Aim of the report	2

Assumptions	2

Approximate estimate	3

Summary of accommodation	4

Elemental cost plans	5

Preliminaries, Fees and contingency	7

References	8

# Introduction

Cost planning is a vital part of all construction projects as the cost of a project is often the client’s main prerogative. The estimate provides the client with an approximate price for the project with a very brief breakdown of costs, whilst the cost plan itemises every aspect of a project including labour, materials and plant costs. The cost plan is ultimately a way of controlling the estimated costs. (Medak, 2018). The estimate process is completed before the cost plan there are three main estimating techniques commonly used. Estimating with unit rates, resource-based estimating and factor estimating (consultancy, 2018), in this report I will primarily use the functional unit rate approach. Similarly, there are also different ways to approach a cost plan for a project, these include;

- Functional method, this method is the cost of a functional unit is multiplied by the amount required by the client, for example the requirement for 300 desks in an office etc.  you could base your price on a recent project for 200 desks, once you’ve calculated the price of one desk you can apply it to any other scenario.

- Elemental method, this method is one of three recommended in NRM2, it is the most labour intensive of the three methods as it is based on the idea that the cost = element unit quantity x element unit rate.

- Approximate method, this tends to be completed based on the floor area of the building an approximate cost is derived using cost data and a contingency of 10-15% is applied to the final sum.

# Aim of the report

In this report I intend to complete firstly an estimate for the case study project provided and then a cost plan for the same project following NRM1. I intend to use the BCIS as my main source of information for the cost analysis as it is up to date, and a similar project can easily be selected and scaled using the indices.

The client for this job is Bam Architect LTD, there are two differing types of building on this site, Building Type one is three terraced properties and building type two is 2 semidetached houses

# Assumptions

| Reference Number | Assumption | Description | Source |
| --- | --- | --- | --- |
| 1 | It is assumed that the internal floor area for this building type is 73.25M2. assumption made based on a similar existing property in the locality | Floor area of building type 1 | https://www.zoopla.co.uk/for-sale/details/50142676?search_identifier =9bf97bad71011623c058b75140956a67 |
| 2 | It is assumed that the internal floor area for this building type is 86M2 assumption made based on a similar existing property in the locality | Floor area of building type 2 | https://www.zoopla.co.uk/for-sale/details/50199128?search_identifier=16b65c20d6de7ce1694287e1974dcf59 |
| 3 | It is assumed that each property incurs an additional cost of £6000 each for the semidetached and £4000 for each terraced property as this is the average cost of installing solar panels | Cost of solar panels per property | https://www.greenmatch.co.uk/blog/2014/08/what-is-the-installation-cost-for-solar-panels |

# Approximate estimate

Included in this section is a summarised approximate estimate which would be used prior to the tendering process, for all properties all assumptions made have been outlined in the assumptions table, all assumptions made have been educated and reasonable. The approximate estimate for each building type has been calculated accordingly using the BCIS data base then multiplied to the quantity of each dwelling type present on this site.

1 terraced row consisting of 3 1-bedroom properties @ 73.25M2 each, giving a total floor area of 219.75M2

3 semidetached 3-bedroom properties providing 6 units @ 86M2 each, giving a total floor area of 516M2

| Terrace | GIFA M2 | Cost Per M2 | Unit Cost | Total Cost |
| --- | --- | --- | --- | --- |
| Single Unit | 73.25M2 | £1941 | £142178 |  |
| Combined x3 | 219.75M2 | £1941 | £426,535 | £426,535 |
| Semi Detached | GIFA M2 | Cost Per M2 | Unit Cost | Total Cost |
| Single Unit | 86M2 | £1941 | £166,926 |  |
| Combined x6 | 516M2 | £1941 | £1,001,556 | £1,001,556 |

Total Estimated Build Cost £1,428,091.	Cost per M2 was obtained using the House prices: how much does one square metre cost in your area? Page on www.ons.gov.uk/  the price was based on the Manchester area as this is what area of Analysis from the BCIS for the cost plan (digitalcontent@ons.gov.uk, n.d.)

# Summary of accommodation

| Building Type 1 Terraced House 3 Units |  |  |
| --- | --- | --- |
| Room | 1 unit | Total |
| Kitchen | 1 | 3 |
| Lounge |  |  |
| Dining | 0 | 0 |
| W/C | 1 | 3 |
| Family Bathroom | 1 | 3 |
| En Suite | 0 | 0 |
| Double Beds | 1 | 3 |
| Single beds | 0 | 0 |
| Cot Rooms | 1 | 3 |

| Building Type 2 Terraced House 6 Units |  |  |
| --- | --- | --- |
| Room | 1 unit | Total |
| Kitchen | 1 | 6 |
| Lounge | 1 | 6 |
| Dining | 1 | 6 |
| W/C | 1 | 6 |
| Family Bathroom | 1 | 6 |
| En Suite | 2 | 12 |
| Double Beds | 3 | 18 |
| Single beds | 0 | 0 |
| Cot Rooms | 0 | 0 |
| Study | 1 | 6 |

# Elemental cost plans

# Building Type 1

| Element | Description | Cost Per M² | Total Cost |
| --- | --- | --- | --- |
| Substructure | Piled foundations | £128 | £28,515 |
| External walls | Facing brick and block external cavity walls with rendered block | £290 | £64,786 |
| Roof | Pitched timber roof with tiled finish | £81.00 | £18,161.50 |
| Stairs | Timber | £8 | £1,836.50 |
| External Windows and doors Inc. Rainwater goods | Doubled glazed windows and doors | £56 | £12,591 |
| Internal Walls and Partitions | Timber Stud | £47 | £10,407.00 |
| Internal doors | Timber doors | £32 | £7,058 |
| Wall finishes | Plasterboard Skim and emulsion | £46 | £10,216 |
| Floor finishes | Timber ply | £32 | £7,184 |
| Ceiling finishes | Plasterboard skim and emulsion | £17 | £3,825 |
| Sanitary appliances | Sanitaryware | £22 | £4,912 |
| Space heating and air conditioning Inc. Water and fuel | Hot water Radiators | £70 | £15,753 |
| Ventilation systems | Ventilation | £7.00 | £1,525 |
| Electrical installations | Electric power and light | £76 | £16,938 |
| Services builders works |  | £15 | £3,387 |
| Site works | Site preparation, landscaping paving and fencing | £255 | £57,003 |
| Drainage | Drainage | £52 | £11,575 |
| External services | Services and lighting | £57 | £12,704 |
| Fittings and furnishes |  | £36 | £8,112 |
| Solar Pannels |  |  | £12000 |
|  |  | Total | £308,489 |

(BCIS, n.d.)

# Building Type 2

| Element | Description | Cost Per M² | Total Cost |
| --- | --- | --- | --- |
| Substructure | Piled foundations | £150 | £70,274 |
| External walls | Facing brick and block external cavity walls with rendered block | £157 | £73,791 |
| Roof | Pitched timber roof with tiled finish | £76.00 | £35,740.00 |
| Stairs | Timber | £13 | £6,205.00 |
| External Windows and DOORS INC. raunwater goods | Doubled glazed windows and doors | £74 | £34,929 |
| Internal Walls and Partitions | Timber Stud | £76 | £35,905.00 |
| Internal doors | Timber doors | £29 | £13,549 |
| Wall finishes | Plasterboard Skim and emulsion | £49 | £22,887 |
| floor finishes | timber ply | £40 | £188,883 |
| ceiling finishes | Plasterboard Skim and emulsion | £18 | £8,613 |
| space heating and air conditioning Inc. water and fuel | Hot water Radiators | £141 | £66,458 |
| electrical installations | Electric power and light | £37 | £17,161 |
| services builders works |  | £6 | £2,804 |
| site works | Site preparation, Landscaping Paving and fencing | £251 | £118,152 |
| drainage | Drainage | £160 | £75,000 |
| external services | Services and lighting | £53 | £24,909 |
| fittings and furnishes |  | £56 | £26,281 |
| Solar Pannels |  |  | £36000 |
|  |  | Total | £857,541 |

(BCIS, n.d.)

# Preliminaries, Fees and contingency

The following costs are an addition to the elemental GIFA cost build up, it is important to apply an enough of a contingency for unforeseen elements of the project which could see the principle contractor at a loss.

| Post Additional costs |  | £1,166,030 |
| --- | --- | --- |
| Preliminaries +20% | Site set up and additional costs to the contractor (WIKI, 2019) | £233206 |
| Professional and design fees +7% | Architects, project management cost | £81622.1 |
| Contingency +6% |  | £69961.8 |
|  | Total Construction Cost | £1,550,819.90 |

There are many elements of a project that often don’t go to plan or schedule, most of the time it is not fault of the project team but sometimes factors such as delayed manufacturing processes or adverse weather conditions meaning a temporary structure may have to be erected to protect employees as they work.  As well as the preliminaries which cover the site set up and additional costs to the contractor, preliminaries may include things such as method statements, quality management procedures, the method of sub-contracting, dates for partial possession, site waste management plan, and a description of the commissioning strategy, separating setting to work and balancing tasks. (WIKI, 2019)

Some further elements that may contribute to any additional costs could be;

- Hold up with planning permission or building regulation consent

- Utilities and site infrastructure changes

- Last minute changes to the design

- Hold up in finances with the client or funders

- Contaminated land especially if it is a brownfield site

- Tree preservation orders

- Asbestos

- Demolition of existing buildings on site

- Subsoil variation

- Water courses, rivers drains, flood prevention ditches

Once the estimate and cost plan have been completed the tender is usually given to the client who should have more than one price to consider, often the cheapest isn’t always the best, there needs to be an element of quality and company reliability. For example, the client may have worked with a particular contractor before, they know they are reliable and have produced quality work before then they may use them although they have not provided the lowest tender.

# References

BCIS. (n.d.). Retrieved from https://www.rics.org/uk/products/data-products/

consultancy, C. e. (2018, Febuary 20). 3 types of construction cost estimating. Retrieved from www.costengineering.eu: https://www.costengineering.eu/blog-article/3-types-of-construction-cost-estimating

digitalcontent@ons.gov.uk. (n.d.). https://www.ons.gov.uk/peoplepopulationandcommunity/housing/articles/housepriceshowmuchdoesonesquaremetrecostinyourarea/2017-10-11. Retrieved from https://www.ons.gov.uk/peoplepopulationandcommunity/housing/articles/housepriceshowmuchdoesonesquaremetrecostinyourarea/2017-10-11

Medak, K. (2018, December 19). A project manager’s guide to cost estimating and cost planning. Retrieved from www.framegroup.com.au: https://www.framegroup.com.au/cost-estimating-and-planning/

WIKI, D. B. (2019, January 6). preliminaries in construction . Retrieved from www.designingbuildings.co.uk/: https://www.designingbuildings.co.uk/wiki/Preliminaries_in_construction