## Cashflow task
You have been asked to complete the casflow for a new project starting soon.
Complete the casflow and identify where an overdraft and or loan would be required.
The usual payment one after valuation is expected. The profit and retention are provided below.
Profit 10%
Retention 7% |  | Retention - 50% returned on completion of the project and 50% after 6 months
Month | Amount
1 | 12000
2 | 10120
3 | 9300
4 | 13045
5 | 12450
6 | 10650
7 | 8345
8 | 9450
9 | 12500
10 | 5450
11 | 6340
12 | 4350
114000

## Gantt Chart task
Management task
Each project is the same
Project A starts day 1
Project B starts day 7
Project C starts day 20
The company owns 30 box shutters you need to advise on if this is sufficient or if another approach should be taken
Activity | Task Name | Duration | Predecessors | Shuttering requirement
1 | Site Set Up | 1 Day
2 | Groundworks | 13 Days | 1
3 | Clearance | 2 Days | 1
4 | Drill for Piles | 5 Days | 3
5 | Casting of Piles | 6 Days | 4
6 | Substructure Construction | 9 Days | 5
7 | Shuttering for Pile Caps | 4 Days | 5 | 10
8 | Cast Pile Caps | 5 Days | 7 | 10
9 | Shuttering for Abutments | 2 Days | 5 | 12
10 | Cast Abutments | 5 Days | 9 | 12
11 | Shuttering for Piers | 2 Days | 5 | 20
12 | Cast Piers | 5 Days | 11 | 20
13 | Bridge Deck Construction | 13 Days | 12
14 | Delivery of Pre-Constructed Bridge Deck | 1 Day | 12
15 | Bridge Deck Installation | 7 Days | 14
16 | Shuttering for Parapets | 2 Days | 15 | 18
17 | Casting for Parapets | 3 Days | 16 | 18
18 | Road and Footway | 10 Days | 17
19 | Installation of Drainage | 3 Days | 17
20 | Installation of Other Utilities | 3 Days | 17
21 | Install Kerbs | 2 Days | 17
22 | Sub Base for Carriageway and Footway | 4 Days | 19,20,21
23 | Surfacing for Carriageway and Footway | 3 Days | 22
24 | Finishing | 4 Days | 23
25 | Landscaping | 4 Days | 23,20
26 | Handover | 6 Days | 25
27 | Snagging | 2 Days | 25
28 | Rectifications (if any) | 3 Days | 27
29 | Sign off | 1 Day | 28