Lecturer: Kareem Sani

LCLM 5003 – Project Portfolio

Mohammed Razzaque - 2126598

Part A – Project Proposal Poster	2

Part B – Critical Reflection on Feedback	3

Part C – Project Management Plan	4

# Part A – Project Proposal Poster

Part B – Critical Reflection on Feedback

The feedback I received on my project proposal poster has helped me critically evaluate the quality of my initial work and identify clear improvements for my final project management plan. Although the poster addressed the main requirements, the feedback showed that the final plan needs to be more structured, measurable, academically supported, and professionally presented.

One key strength of my poster was that it presented a relevant and practical project idea. The proposal clearly focused on the digital modernisation of passenger flow and logistics coordination after the closure of a major UK transport hub. It included real-time travel information, passenger-flow monitoring, freight scheduling, cybersecurity controls, stakeholder communication, and risk management actions. The stakeholder section was also detailed, as it considered local authorities, transport operators, commuters, businesses, residents, digital infrastructure providers, accessibility groups, funding bodies, and regulators. This showed that I understood the wide impact of the project and the importance of stakeholder engagement in successful delivery.

However, the most important improvement is the need to make the aims and objectives clearer and more measurable. In my poster, some objectives were repeated and were written in a general way, which made it harder to understand how success would be measured. In the final project management plan, I will improve this by using SMART objectives so that each objective is specific, measurable, achievable, relevant, and time-bound. For example, instead of saying that the project will “reduce overcrowding,” I could state that the project will reduce passenger congestion at temporary transport points by a defined percentage within a set period. Modi (2024) explains that clear project goals should be specific and measurable so that progress can be tracked and outcomes can be assessed. This will help make my final plan more focused and easier to evaluate.

Another improvement is the need to apply more project management tools and academic literature. The poster described the project well, but it did not use enough formal project management concepts. In the final plan, I will include a stakeholder matrix to show levels of interest and influence, a risk register to assess probability and impact, a Gantt chart to present the project timeline, and a RACI matrix to clarify roles and responsibilities. These tools will make the plan more professional and show how the project will be planned, monitored, and controlled.

The feedback also showed that I need to improve the visual and written presentation of my work. The poster contained too much text and some repeated content, which affected clarity. In the final project plan, I will reduce repetition, use clearer headings, and present key information through tables, diagrams, and charts where appropriate. This will make the plan easier to follow and more suitable for a project management audience.

Overall, the feedback has helped me understand that a strong project proposal must go beyond identifying a relevant problem. The final project management plan must show measurable objectives, stronger academic support, clearer use of project management tools, and a more concise professional structure.

# Part C – Project Management Plan

# Executive Summary

This Project Management Plan proposes the digital modernisation of passenger flow and logistics coordination following the closure of a major UK metropolitan transport hub. The closure has disrupted rail, bus, commuter and freight operations, creating pressure on local authorities to restore service coordination, reduce public dissatisfaction, support local businesses and contribute to wider regeneration objectives.

The selected project focuses on the delivery of a digital transport coordination system rather than physical redevelopment. This approach is justified because it offers a faster and more practical operational response while supporting longer-term transport recovery. The project will deliver real-time passenger information, passenger-flow monitoring, freight scheduling, an integrated operational dashboard, cybersecurity controls, secure data-sharing arrangements, staff training and stakeholder communication.

The plan applies key project management tools to support successful delivery. The scope defines the required digital outputs, while the Work Breakdown Structure divides the project into manageable work packages. The Quad Chart summarises the project purpose, stakeholders, desired results and success measures. The Gantt Chart sets out a nine-month schedule, and the stakeholder analysis and RACI matrix clarify involvement, responsibility and accountability. The resource plan identifies the human, technical, financial and specialist resources required, while the risk register highlights key risks including system integration failure, poor data quality, cybersecurity threats, supplier delays, low adoption and digital exclusion.

Successful delivery depends on strong governance, stakeholder cooperation, secure data management, accessible communication and continuous monitoring. If implemented effectively, the project will reduce disruption, improve passenger and freight coordination, support economic recovery and strengthen public confidence in the wider regeneration programme.

# Table of Contents

Executive Summary	1

Table of Contents	2

Introduction	3

Project Description	3

Scope	4

Work Breakdown Structure	5

Quad Chart	6

Gantt Chartz	7

Stakeholders' Involvement	7

Allocation of Resources	9

Risk Analysis	9

Conclusion	10

References	12

# Introduction

The closure of a major UK metropolitan transport hub has disrupted commuters, freight operators, local businesses, residents, transport providers and public authorities. Because the hub supports rail, bus, passenger movement and freight logistics, the closure creates immediate concerns around safety, accessibility, service continuity and economic impact.

This Project Management Plan focuses on digital modernisation of passenger flow and logistics coordination. The option is justified because it can be delivered faster than full physical redevelopment while supporting the wider regeneration programme. The project includes real-time passenger information, passenger-flow monitoring, freight scheduling, operational dashboards, cybersecurity controls, staff training and stakeholder communication. These functions are prioritised because they respond directly to the disruption experienced by passengers, businesses and operators while the wider regeneration programme is developed.

Effective project management is required because delivery involves technical complexity, public accountability, operational risks and multiple stakeholders. Structured planning coordinates scope, time, cost, resources, quality, risk and stakeholder engagement across the project lifecycle (Kerzner, 2022). This plan applies a WBS, Quad Chart, Gantt Chart, stakeholder analysis, RACI matrix, resource allocation and risk register to demonstrate controlled delivery. The plan is written for relevant stakeholders who need assurance that the digital response is practical, measurable and aligned with service recovery priorities.

# Project Description

The selected project is the digital modernisation of passenger flow and logistics coordination following the closure of the transport hub. It addresses disruption to rail, bus, commuter and freight activity by improving how transport information, passenger-flow data and freight scheduling information are collected, shared and acted upon.

The project is selected because the closure creates an immediate coordination problem and a longer-term regeneration challenge. Full redevelopment requires planning approval, design, procurement, construction and major capital investment. In contrast, digital modernisation can be implemented more quickly while remaining useful during future redevelopment. Digital transformation can reshape organisational processes, services and value creation (Vial, 2019), while digital business strategy supports coordinated use of technology across organisational boundaries (Bharadwaj et al., 2013).

The project introduces an integrated digital approach. Commuters need reliable route information, operators need coordinated service updates, freight companies need predictable delivery arrangements, businesses require supply continuity and local authorities need oversight of network performance. Expected outcomes are improved passenger confidence, reduced uncertainty, stronger freight and transport coordination, better visibility of operational risks and wider public value through accessibility, resilience, sustainability and economic recovery. The project also provides data that can inform later physical redevelopment, such as passenger demand patterns, congestion points and freight movement pressures. This makes the digital system valuable beyond the emergency closure period.

The expected outcomes are improved passenger confidence, reduced uncertainty, better freight and transport coordination, and stronger visibility of operational risks. The project also supports wider public value by contributing to accessibility, resilience, sustainability, and economic recovery. Success depends not only on installing a digital system, but on whether it improves decision-making, supports affected stakeholders, protects data, and helps manage disruption effectively.

# Scope

The scope covers the planning, procurement, development, testing, implementation and handover of a digital transport coordination system. Scope management clarifies the work required to deliver agreed outcomes and provides a baseline for controlling time, cost, quality, resources and stakeholder expectations (Project Management Institute, 2021). The table below will provide further information regarding scope and deliverables.

Table 1: Project scope and deliverables

| Scope area | Included deliverables | Purpose |
| --- | --- | --- |
| Passenger information | Live updates via displays, web and mobile channels | Reduces uncertainty and supports journey planning |
| Passenger-flow monitoring | Monitoring tools and crowding dashboards at temporary points | Supports safer movement and congestion response |
| Freight coordination | Booking and scheduling platform for logistics users | Improves delivery planning and business continuity |
| Operational dashboard | Shared dashboard for approved operational stakeholders | Enables joined-up disruption management |
| Data governance | Data-sharing protocols, access controls and reporting rules | Supports lawful and consistent information use |
| Cybersecurity | Security testing, authentication and incident response procedures | Protects connected systems and operational resilience |
| Training and communication | Staff training, briefings and accessible public guidance | Supports adoption and effective use |

The scope also includes requirements gathering, supplier selection, stakeholder engagement, schedule control, risk monitoring, quality checks and reporting. Cybersecurity and data governance are included from the start because the system depends on connected infrastructure, live operational data and public-private information sharing. Secure design helps protect services and maintain trust in connected transport systems (National Cyber Security Centre, 2021). The scope assumes that the local authority provides sponsorship, funding and access to transport data; operators and freight partners support testing and data sharing; suppliers provide technical capacity; and accessibility groups review public communication. Scope success will be measured through accepted digital deliverables, successful pilot testing, reliable live updates, active dashboard use, secure data sharing, completed training and improved passenger and freight coordination.

# Work Breakdown Structure

The Work Breakdown Structure (WBS) divides the project into smaller work packages and deliverables. This supports planning because the project manager can identify what must be delivered, how work is sequenced, who contributes and how progress will be monitored. Turner (2014) argues that structured work packages connect project objectives with delivery activities, improving planning and control. The table below will outline the WBS.

Table 2: Work Breakdown Structure

| Code | Work package | Key activities | Deliverable |
| --- | --- | --- | --- |
| 1.0 | Initiation and governance | Confirm business case, appoint project manager, establish reporting | Approved project brief |
| 2.0 | Requirements and stakeholder analysis | Gather user, operator, freight, authority and accessibility requirements | Requirements specification |
| 3.0 | System design and procurement | Define specification, assess suppliers, agree contract | Supplier contract and system design |
| 4.0 | Digital platform development | Configure information, monitoring, freight and dashboard functions | Working platform |
| 5.0 | Data governance and cybersecurity | Develop controls, access rules, security testing and incident response | Secure data framework |
| 6.0 | Testing and pilot | Test functionality, user acceptance, accessibility and pilot use | Tested pilot system |
| 7.0 | Training and communication | Train staff, brief stakeholders, produce public guidance | Trained users and materials |
| 8.0 | Implementation and handover | Roll out, monitor performance, resolve issues and close project | Operational system and closure report |

The WBS treats the project as more than a technology installation by including governance, stakeholder engagement, cybersecurity, testing, training and handover. This allows responsibilities to be allocated and progress to be tracked against clear deliverables. It also supports later schedule and resource planning because each work package can be linked to activities, owners, dependencies and acceptance criteria.

# Quad Chart

The Quad Chart summarises project logic by linking purpose, stakeholders, desired results and success measures. This supports early clarity because project success depends on stakeholder value as well as output completion (Larson and Gray, 2021; Shenhar and Dvir, 2007).

Table 3: Quad Chart

| Quad element | Summary |
| --- | --- |
| Purpose, aims and objectives | Digitally modernise passenger-flow and freight coordination after hub closure. Objectives: live passenger information, flow monitoring, freight scheduling, dashboard reporting and secure data sharing. |
| Key stakeholders | Local authority, transport authority, rail/bus operators, freight companies, passengers, businesses, residents, emergency services, suppliers, cybersecurity specialists, accessibility groups, regulators and funders. |
| Desired results | A functioning digital coordination system that improves disruption management, service visibility, freight planning, passenger confidence, accessibility and public accountability. |
| Measures of success | Delivery within schedule and budget; successful pilot; reliable live updates; dashboard use; completed training; secure data-sharing; positive feedback; fewer information complaints. |

| Work package | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Initiation | X |  |  |  |  |  |  |  |  |
| 2. Requirements | X | X |  |  |  |  |  |  |  |
| 3. Design/procure |  | X | X |  |  |  |  |  |  |
| 4. Build |  |  | X | X | X |  |  |  |  |
| 5. Data/cyber |  | X | X | X | X | X |  |  |  |
| 6. Test/pilot |  |  |  |  | X | X |  |  |  |
| 7. Training |  |  |  |  |  | X | X |  |  |
| 8. Rollout |  |  |  |  |  |  | X | X | X |
| 9. Close |  |  |  |  |  |  |  | X | X |

# Gantt Chartz

The Gantt Chart converts the WBS into a nine-month schedule by showing activity duration, sequencing and overlaps. Gantt charts support progress control because they present task timing and dependencies in a simple visual form (Maylor, 2010).

Table 4: Gantt Chart

The schedule starts with initiation, governance and reporting, followed by requirements analysis and procurement. Early requirements work is essential because inaccurate assumptions about passenger behaviour, freight demand or operator data could weaken the technical design. Development occurs in Months 3-5, while data governance and cybersecurity run alongside design, build and testing. Pilot testing occurs in Months 5-6, training in Months 6-7 and full rollout from Month 7. The staged approach reduces delivery risk by testing the system before wider implementation. The overlap between cybersecurity, development and testing also prevents security from becoming a late correction, which is important where public confidence depends on reliable and protected digital services.

# Stakeholders' Involvement

Stakeholder involvement is essential because the project affects public services, business continuity, accessibility, passenger experience and local recovery. Stakeholders can influence success through resources, cooperation, expectations or resistance. Freeman (1984) defines stakeholders as groups that affect or are affected by organisational objectives, while Bourne (2016) emphasises active engagement to build support and reduce opposition.

Table 5: Stakeholder involvement plan

| Stakeholder | Interest | Influence | Required involvement |
| --- | --- | --- | --- |
| Local authority/city council | Service recovery, funding, accountability | High | Sponsor, approve budget, govern and report |
| Transport authority | Network coordination and safety | High | Lead operations and share data |
| Rail, bus and coach operators | Service continuity and route planning | High | Provide live service data and test systems |
| Freight operators/local businesses | Reliable delivery and supply continuity | Med/High | Use scheduling platform and provide feedback |
| Commuters/passengers | Accurate information and reduced delay | Medium | Provide feedback and use information channels |
| Residents/community groups | Reduced disruption and accessible communication | Medium | Consultation and feedback |
| Accessibility groups | Inclusive design and communication | Medium | Review formats and advise on needs |
| Digital suppliers | Technical delivery and system performance | High | Design, build, test and support |
| Regulators/safety bodies | Compliance, safety and data protection | High | Review compliance requirements |

High-power stakeholders require close management because they control funding, compliance, data or delivery capability. Passengers, residents, accessibility groups and businesses require consultation because the system must meet practical user needs. Engagement will combine governance meetings, operational workshops, supplier reviews, public updates and feedback channels. This approach helps build ownership, reduce resistance and improve design quality before full rollout.

Table 6 uses a RACI matrix to clarify participation in key activities. R means responsible, A accountable, C consulted and I informed.

Table 6: RACI matrix

| Activity | PM | Sponsor | Transport Authority | Supplier | Cyber/Data | Comms |
| --- | --- | --- | --- | --- | --- | --- |
| Approve brief and budget | R | A | C | I | I | I |
| Gather requirements | A | C | R | C | C | C |
| Select supplier | R | A | C | C | C | I |
| Design system | A | C | C | R | C | I |
| Establish data/cyber controls | A | C | C | R | R | I |
| Pilot and testing | A | I | R | R | C | C |
| Training and public communication | A | I | C | C | I | R |
| Handover and closure | R | A | C | C | C | I |

# Allocation of Resources

Resource allocation ensures that the project has the people, technology, finance and specialist expertise required to deliver agreed outputs. Poor allocation of skills, budget or responsibilities can cause delay, cost growth and quality issues (Lock, 2020). Competence is also important because project performance depends on technical, contextual and behavioural capability (Crawford, 2005).

Table 7: Resource allocation plan

| Category | Resources | Purpose |
| --- | --- | --- |
| Project management | Project manager, support officer, board | Controls scope, schedule, budget, reports and risks |
| Technical delivery | Developer, data analyst, integration specialist, dashboard designer | Builds information, monitoring, freight and dashboard functions |
| Cybersecurity/data | Cybersecurity specialist, DPO, governance lead | Ensures secure design, access control and compliance |
| Transport operations | Authority, rail/bus leads, freight lead | Provides service data, routes and scheduling input |
| Stakeholder engagement | Communications officer, accessibility adviser, business liaison | Supports consultation, accessible communication and adoption |
| Training/support | Training lead, helpdesk, supplier support | Trains staff and resolves early issues |
| Financial resources | Budget, contingency fund, procurement allowance | Funds supplier contracts, software, testing and risk response |

Technical resources peak during design, development, testing and rollout, while communication and stakeholder resources remain active throughout. A contingency allowance is required for supplier delay, integration issues, extra testing or accessibility improvements. Resource use will be reviewed against the Gantt Chart so that specialist support is available at the right stage and inactive capacity is avoided. This is important in a public-sector project where budget control and value for money must be visible to sponsors and stakeholders.

# Risk Analysis

Risk analysis is required because the project is delivered under public pressure, relies on connected digital systems and depends on cooperation between organisations. Risk management should identify, assess, respond to and monitor uncertainty throughout the lifecycle (Hillson and Simon, 2020). Broader risk thinking also supports decisions where uncertainty affects cost, time, quality and stakeholder outcomes (Chapman and Ward, 2011).

Table 8: Risk register

| Risk | Likelihood | Impact | Mitigation/response |
| --- | --- | --- | --- |
| System integration failure | Med | High | Early technical mapping, phased integration and interface testing |
| Inaccurate or delayed live data | Med | High | Set data standards, owners and quality monitoring |
| Cybersecurity breach | Med | High | Access controls, supplier checks, penetration testing and response plan |
| Low user adoption | Med | Med | Training, guidance, stakeholder briefings and feedback channels |
| Digital exclusion | Med | Med | Screens, printed guidance, helpline and accessible formats |
| Supplier delay or weak performance | Med | High | Milestones, service levels, reviews and contingency |
| Stakeholder disagreement | Med | Med | Governance meetings, escalation routes and data protocols |
| Public dissatisfaction during rollout | Med | High | Pilot first, communicate clearly and resolve issues quickly |

The highest-priority risks are integration failure, poor data quality, cybersecurity threats and supplier delay because they affect system reliability and public confidence. Risk control will use regular reviews, supplier performance meetings, pilot testing, issue logs and stakeholder reporting. The register remains live throughout procurement, development, testing and rollout. Each high-priority risk requires a named owner, review date and escalation route so that warning signs are acted on early rather than after disruption becomes visible to passengers or freight users.

# Conclusion

In conclusion, this Project Management Plan proposes a controlled and structured approach for delivering the digital modernisation of passenger flow and logistics coordination following the closure of a major UK metropolitan transport hub. The project is justified because the closure has created urgent disruption for passengers, freight operators, local businesses, transport providers and public authorities. While full physical redevelopment is likely to require significant time, funding, planning approval and construction activity, digital modernisation offers a faster and more practical operational response. It can improve coordination during the closure period while also supporting the wider regeneration programme.

The proposed project will deliver real-time passenger information, passenger-flow monitoring, freight scheduling, an integrated operational dashboard, secure data-sharing arrangements, staff training and stakeholder communication. These outputs are designed to reduce uncertainty, improve operational visibility and support more effective decision-making across the transport network. The project also contributes to wider strategic objectives by supporting accessibility, resilience, economic recovery, sustainability and public confidence.

The plan applies a range of project management tools to demonstrate how the project will be delivered successfully. The Work Breakdown Structure defines the main work packages and deliverables, while the Quad Chart summarises the project’s purpose, stakeholders, desired results and success measures. The Gantt Chart provides a nine-month implementation schedule, and the stakeholder analysis and RACI matrix clarify involvement, accountability and communication requirements. The resource plan identifies the people, technology, financial resources and specialist expertise needed, while the risk register supports proactive management of technical, operational, cybersecurity, supplier and adoption risks.

Successful implementation depends on strong governance, clear responsibilities, secure data sharing, stakeholder cooperation, accessible communication and continuous monitoring throughout the project lifecycle. If delivered effectively, the digital coordination system will reduce disruption, improve passenger and freight coordination, support affected users and provide local authorities with better evidence for managing the wider regeneration programme. Overall, the proposal provides a realistic and value-focused project response to the transport hub closure.

# References

Bharadwaj, A., El Sawy, O.A., Pavlou, P.A. and Venkatraman, N. (2013) ‘Digital business strategy: toward a next generation of insights’, MIS Quarterly, 37(2), pp. 471–482.

Bourne, L. (2016) Stakeholder Relationship Management: A Maturity Model for Organisational Implementation. 2nd edn. London: Routledge.

Chapman, C. and Ward, S. (2011) How to Manage Project Opportunity and Risk: Why Uncertainty Management Can Be a Much Better Approach than Risk Management. 3rd edn. Chichester: Wiley.

Crawford, L. (2005) ‘Senior management perceptions of project management competence’, International Journal of Project Management, 23(1), pp. 7–16.

Freeman, R.E. (1984) Strategic Management: A Stakeholder Approach. Boston: Pitman.

Hillson, D. and Simon, P. (2020) Practical Project Risk Management: The ATOM Methodology. 3rd edn. Oakland: Berrett-Koehler.

Kerzner, H. (2022) Project Management: A Systems Approach to Planning, Scheduling, and Controlling. 13th edn. Hoboken: Wiley.

Larson, E.W. and Gray, C.F. (2021) Project Management: The Managerial Process. 8th edn. New York: McGraw-Hill Education.

Lock, D. (2020) Project Management. 11th edn. London: Routledge.

Modi, S. (2024) ‘Achieve your research goals: a project management toolkit for graduate studies’, Trends in Genetics, 40(10), pp. 811–814.

Maylor, H. (2010) Project Management. 4th edn. Harlow: Pearson Education.

National Cyber Security Centre (2021) Connected Places Cyber Security Principles. London: NCSC. Available at: https://www.ncsc.gov.uk/collection/connected-places-security-principles

Project Management Institute (2021) A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th edn. Newtown Square: Project Management Institute.

Shenhar, A.J. and Dvir, D. (2007) Reinventing Project Management: The Diamond Approach to Successful Growth and Innovation. Boston: Harvard Business School Press.

Turner, J.R. (2014) Handbook of Project-Based Management: Leading Strategic Change in Organizations. 4th edn. New York: McGraw-Hill.

Vial, G. (2019) ‘Understanding digital transformation: a review and a research agenda’, The Journal of Strategic Information Systems, 28(2), pp. 118–144