## Sheet1
Motorsport Gantry Re-Creation | Week 1 |  |  | Week 2 |  |  | Week 3 |  | Week 4 | Week 5 | Week 6 |  |  |  | Week 7 |  | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Record of results | Alongside Tasks for logbook creation
Research of system | 3 Days
Block diagram/component choice |  | 3 Days
Simulated Circuit Design |  |  | 1 Day
Breadboard Development |  |  |  | 2 Days
User Manual Creation |  |  |  |  | Alongside development
Software Design |  |  |  |  | Once breadboard has a working circuit to test on. | [11 empty] | May need changes on PCB Iteration
Casing Design | [5 empty] | 5 Days |  |  | Before end of Week 3
PCB Design | [6 empty] | 4 Days |  | Before end of Week 3
PCB Creation/delivery | [7 empty] | 2 Weeks |  |  | Post Delay
Casing creation | [7 empty] | 1 Week
PCB Soldering/Testing/Fixing | [10 empty] | 3 Days
Circuit updates. | [11 empty] | 2 Days
PCB Iteration Design | [12 empty] | 2 Days |  |  | Before end of Week 6/7 with Delay
Project Casing Iteration. | [12 empty] | 2 Days |  |  | Before end of Week 6/7 with Delay
PCB Iteration creation/delivery | [13 empty] | 2 Weeks |  |  |  | Post Delay
PCB Iteration Soldering/testing | [17 empty] | 1 Day
Logbook Creation | [15 empty] | Once enough data collected
Presentation Creation | [13 empty] | Once logbook mostly completed |  |  |  |  | Changes during practice
Presentation Practice | [17 empty] | Practice alongside final changes
Spare Time | [18 empty] | Post Delays
Expected Development Time.
Reasonable over-run Time.
Possible but unexpected Delays
Target Date
| Presentation Day |  |  |  |  | Presentation Day
Not our control Development time.