Individual Report

Title: Understanding the Importance of Stakeholder Engagement in the Successful Commencement and Completion of a Project

Name: Valdice Cristina Albuquerque Sousa

ID: 2435221

Module: Understanding and Engaging Stakeholders

Module Code: LCLM5001

Lecturer: Muhammad Tariq

Submission Date: 18 August 2026

# Abstract

This report examines stakeholder engagement in the ConnectPlus project at ASDA. The report identifies key internal and external stakeholders and analyses their power, interest, influence and responsibilities. Different stakeholder management tools are applied, including stakeholder mapping, the Power–Interest Matrix, the Salience Model, the Stakeholder Engagement Plan, the Communication Plan, the RACI Matrix and the 4Cs framework. The report also considers the benefits, challenges, sustainability and risks of stakeholder engagement. The findings show that clear communication, appropriate stakeholder involvement and regular monitoring can support successful project implementation. The report concludes with recommendations to improve stakeholder relationships, manage risks and support the successful delivery of ConnectPlus.

# Acknowledgements

I would like to thank my lecturer for the guidance, feedback and support provided throughout this project. I also appreciate the learning and resources provided during the module, which helped me develop my understanding of stakeholder engagement and project management.

# Executive Summary

This report examines stakeholder engagement in the ConnectPlus project at ASDA. The project aims to introduce a digital platform using Artificial Intelligence (AI) to provide personalised recommendations, improve customer experience and increase customer loyalty within a six-month project period.

The report identifies the main internal and external stakeholders and analyses their roles, interests, power and influence. Key internal stakeholders include Senior Management, the Project Manager, the IT Team, Marketing, Sales, Customer Service and Store Managers and Employees. External stakeholders include customers, suppliers, investors, government and regulators, trade unions, local communities and Technology Partners. The analysis shows that different stakeholders require different levels of communication and engagement depending on their power, interest and influence.

The report also identifies key risks that may affect stakeholder engagement and project delivery. These include different stakeholder expectations, resistance to change, communication problems, limited resources, data privacy, AI fairness and regulatory requirements. Technology Partners are particularly important because their technical knowledge and support can affect the development, security and performance of the ConnectPlus platform. Managing these risks can help protect customer trust, employee support and project performance.

Several stakeholder management tools were applied, including stakeholder mapping, the Power–Interest Matrix, the Salience Model, the Stakeholder Engagement Plan, Communication Plan, RACI Matrix, 4Cs framework and conflict management. The analysis shows that stakeholders need different levels of engagement and communication. These tools also help ASDA identify responsibilities, communication needs, risks and the level of attention required for each stakeholder.

The report recommends that ASDA regularly review stakeholder priorities, strengthen communication and consultation, work closely with Technology Partners and monitor privacy, AI and regulatory risks. Clear responsibilities, regular feedback and suitable engagement methods should also be used throughout the project. Overall, effective and continuous stakeholder engagement can support the successful delivery of ConnectPlus, improve customer satisfaction and help ASDA achieve its project objectives.

Table of Contents

Abstract	2

Acknowledgements	3

Executive Summary	4

1-Introduction	6

2- SMART Objectives	6

3-Stakeholder Identification and Analysis	7

3.1 Internal Stakeholders	7

3.2 External Stakeholders	7

3.3 Stakeholder Mapping	8

3.4 Power-Interest Matrix	9

3.5 Salience Model	9

4.1 Roles and Responsibilities	11

4.2 Benefits of Stakeholder Engagement	12

4.3 Challenges of Stakeholder Engagement	13

5- Stakeholder Engagement Strategy	13

5.1 Stakeholders Engagement Plan	13

5.2 Communication Plan	14

5.3 RACI MATRIX	15

5.4 4Cs Stakeholder Engagement Framework	16

6: Sustainable Stakeholder Engagement	17

6.1 Importance of Stakeholder Engagement	17

6.2 Financial Performance	17

6.3 Operational Efficiency	18

6.4 Brand Reputation	18

6.5 Employee Engagement	18

6.6 Summary	18

7. Conclusion	18

8. Recommendations	19

References	19

# 1-Introduction

ASDA is one of the largest food retailers in the United Kingdom and continues to invest in digital technology and customer experience. To support these goals, ASDA plans to implement the ConnectPlus platform, a digital platform designed to improve customer engagement and loyalty through AI-powered product recommendations, personalised offers, a mobile rewards programme and customer data analysis. The project is planned to be implemented over a six-month period to improve customer experience and support business performance (Bellis Finco PLC, 2025; ASDA, 2025).

The main purpose of the ConnectPlus project is to improve customer satisfaction, increase customer retention and support better business decisions. The platform will help ASDA understand customer needs and provide more personalised services. Effective stakeholder engagement is important because communication and collaboration can reduce project risks, build trust and improve project performance (Freeman, 1984; Oliveira and Rabechini Jr, 2019).

This report identifies and analyses the main internal and external stakeholders involved in the ConnectPlus project. It examines their roles, interests, power and influence and applies stakeholder management tools, including stakeholder mapping, the Power–Interest Matrix, the Salience Model, the Stakeholder Engagement Plan, Communication Plan, RACI Matrix and 4Cs framework. The report also considers sustainable stakeholder engagement, conflict management and the risks associated with the project. Finally, it provides recommendations to support effective stakeholder engagement and the successful implementation of ConnectPlus.

# 2- SMART Objectives

Objectives:

- To increase 5% sales in the next six months by using the ConnectPlus platform.

- To increase 3% customer retention in the next six months using the ConnectPlus platform.

The SMART framework is used to create clear, measurable and achievable project objectives. SMART stands for Specific, Measurable, Achievable, Relevant and Time-bound. The framework helps the project team define clear targets, measure progress against a baseline and assess whether the objectives can be achieved within the six-month project period (Bjerke and Renger, 2017).

| SMART Element | Objective 1 | Objective 2 |
| --- | --- | --- |
| Specific | Launch the ConnectPlus platform in ASDA stores and online. | Improve customer loyalty through personalised rewards and offers. |
| Measurable | Measure a 5% increase in sales against the pre-launch baseline. | Measure a 3% increase in customer retention against the pre-launch baseline. |
| Achievable | Use the project team, IT systems, Technology Partners and company resources. | Use AI technology and customer data to improve services. |
| Relevant | Support ASDA’s digital transformation and customer experience. | Improve customer satisfaction and business performance. |
| Time-bound | Achieve the 5% sales increase within the six-month project period. | Achieve the 3% retention increase within the six-month project period. |

# 3-Stakeholder Identification and Analysis

Stakeholders are individuals or groups who can affect or are affected by a project (Freeman, 1984).They are important because they can influence project decisions and outcomes. Good stakeholder identification helps the project team understand who should be involved and how to communicate with them. In the ConnectPlus project, both internal and external stakeholders play an important role in the successful planning and implementation of the new digital loyalty platform.

## 3.1 Internal Stakeholders

Internal stakeholders work inside ASDA and help to plan, manage, and deliver the ConnectPlus project.

- Senior Management provides leadership, approves decisions, and supports the project.

- Project Manager plans the project, manages the team, controls the budget, and ensures the project is completed on time.

- IT Team develops the ConnectPlus platform, tests the system, and solves technical problems.

- Marketing Team promotes the new platform and creates campaigns to encourage customers to use ConnectPlus.

- Sales Team helps explain the benefits of ConnectPlus to customers and supports the launch of the platform.

- Customer Service Team answers customer questions, solves problems, and collects customer feedback.

- Store Managers and Employees introduce the platform in stores and help customers use the new digital services.

## 3.2 External Stakeholders

- External stakeholders are people or organisations outside ASDA. They do not work for the company, but they can affect or be affected by the ConnectPlus project.

- Customers are the main users of ConnectPlus. Their feedback and satisfaction are important for the success of the platform.

- Trade Unions represent employees’ interests and may be involved if the ConnectPlus project changes working practices, employee responsibilities or working conditions.

- Suppliers provide products and services to ASDA. They help the company keep products available for customers.

- Technology Partners support the development and maintenance of the ConnectPlus platform. They help with software, security, and system performance.

- Investors want the project to improve business performance and increase company value. They expect good financial results.

- Government and Regulators make sure ASDA follows laws about data protection, consumer rights, and business practices during the project.

- Local Communities are affected by ASDA’s business activities. They expect the company to act responsibly and support local development.

Good communication with external stakeholders helps ASDA build trust, reduce risks, and improve the success of the ConnectPlus project.

## 3.3 Stakeholder Mapping

Stakeholder Mapping identifies individuals and groups who influence or are affected by the ConnectPlus project. It helps the Project Manager understand stakeholder interests, expectations and influence. However, Stakeholder Mapping alone cannot prioritise stakeholders, so it should be used together with the Power–Interest Matrix and the Salience Model (Bourne, 2015).

| Stakeholder | Internal/External | Main Interest | Influence |
| --- | --- | --- | --- |
| Senior Management | Internal | Business success and project performance | High |
| Project Manager | Internal | Successful project delivery | High |
| IT team | Internal | Platform development and security | High |
| Marketing Team | Internal | Customer adoption | Medium |
| Sales Team | Internal | Sales and customer engagement | Medium |
| Customer Service Team | Internal | Customer support and feedback | Medium |
| Store Managers and Employees | Internal | Successful implementation in story | Medium |
| Customers | External | Better service and personalised offers | High |
| Suppliers | External | Product availability | Low |
| Technology Partners | External | Software, security and system perfomance | High |
| Technology Partners | External | Financial and business performance | High |
| Investors | External | Financial and business performance | High |
| Government and Regulators | External | Legal and data protection compliance | High |
| Trade Unios | External | Employee interests | Medium |
| Local Communities | External | Local impact and reputation | Low |

## 3.4 Power-Interest Matrix

The Power–Interest Matrix helps classify stakeholders according to their level of power and interest. It allows the Project Manager to choose the most appropriate communication and engagement strategy for each stakeholder group (Mendelow, 1991).

| Stakeholder Category | ConnectPlus Example | Engagement Approach |
| --- | --- | --- |
| High power – High interest (Manage closely) | Senior Management, Project Manager, IT Team, Technology Partners. | Frequent progress meetings, milestone reviews, risk discussions, technical consultation and regular feedback. |
| High power – Low interest (Keep satisfied) | Investors, Government and Regulators | Strategic updates, performance reports, compliance information and exception reporting. |
| Low power – High interest (Keep informed) | Customers, Marketing Team, Sales Team, Customer Service Team, Store Managers and Employees, Trade Unions | Regular updates, consultation, feedback, customer surveys and staff communication. |
| Low power – Low interest (Monitor) | Suppliers, Local Communities | General updates and monitoring of stakeholder interest. |

The Power–Interest Matrix helps ASDA choose the most appropriate engagement strategy for each stakeholder group. High-power stakeholders require closer management because they can influence important project decisions. Technology Partners are included in the high-power, high-interest group because their technical knowledge and support can affect the development, security and performance of the ConnectPlus platform. Lower-power stakeholders still need appropriate communication to maintain trust and support throughout the project (Mendelow, 1991).

## 3.5 Salience Model

The Salience Model identifies stakeholders based on power, legitimacy and urgency. Stakeholders with all three attributes require the highest level of management attention. The model should be reviewed regularly because stakeholder priorities may change during the project lifecycle (Mitchell, Agle and Wood, 1997).

| Stakeholder | Power | Legitimacy | Urgency | Salience Category |
| --- | --- | --- | --- | --- |
| Senior Management | High | High | High | Definitive |
| Project Manager | High | High | High | Definitive |
| IT Team | High | High | Medium | Dominant |
| Marketing Team | Medium | High | Medium | Discretionary |
| Sales Team | Medium | High | Medium | Discretionary |
| Customers Service Team | Medium | High | Medium | Dependent |
| Store Managers and Employees | Medium | High | Medium | Discretionary |
| Customers | Medium | High | High | Dependent |
| Suppliers | Medium | Medium | Medium | Demanding |
| Technology Partners | High | High | Medium | Dominant |
| Investors | High | High | Medium | Dominant |
| Government and Regulators | High | High | High | Definitive |
| Trade Unios | Medium | High | Medium | Discretionary |
| Local Communities | Low | Medium | Low | Discretionary |

The Salience Model shows that Senior Management, the Project Manager and Government and Regulators require the highest level of management attention because they have high power, legitimacy and urgency. Customers have high urgency and legitimacy but lower power, so they are classified as dependent stakeholders and require consultation and feedback. Stakeholder priorities may change during the ConnectPlus project, so the model should be reviewed regularly (Mitchell, Agle and Wood, 1997).

3.6 Summary of Stakeholder Analysis

The stakeholder analysis shows that different stakeholders have different levels of power, interest and influence in the ConnectPlus project. Senior Management and the Project Manager are key stakeholders because they have high power and high interest. The IT Team is also important because it supports the development, security and performance of the platform.

Customers, Store Managers and Employees, the Marketing Team, the Sales Team and the Customer Service Team have high interest because they are directly involved in or affected by the project. Customers are particularly important because their feedback can help ASDA improve the service and customer experience.

Investors and Government and Regulators have high influence and require regular communication. Trade Unions have an interest in employee matters, while Suppliers, Technology Partners and Local Communities have different levels of influence and require appropriate communication. Effective stakeholder engagement should be organised according to stakeholder needs and project conditions (Lehtinen and Aaltonen, 2020).

Overall, stakeholder analysis helps ASDA understand stakeholder needs, improve communication and select suitable engagement approaches. Stakeholder priorities should also be reviewed regularly because they may change during the project lifecycle.

## 4.1 Roles and Responsibilities

Table Roles and Responsibilities of Key Stakeholders

| Stakeholder | Roles and Responsibilities |
| --- | --- |
| Senior Management | Approve the project, provide funding, make important decisions and monitor project progress. |
| Project Manager | Plan organise and manage the project. Coordinate stakeholders and ensure project objectives are achieved. |
| IT Team | Develop, test and maintain the ConnectPlus digital platform. Provide technical support during implementation. |
| Marketing Team | Promote ConnectPlus, prepare marketing campaigns and encourage customers to join the platform. |
| Sales Team | Explain the benefits of ConnectPlus to customers and encourage membership during purchases. |
| Customer Service Team | Answer customer questions, solve problems and collect customer feedback. |
| Store Managers and Employees | Support the project in stores, train employees and ensure daily operations run smoothly. |
| Customers | Use the platform, provide feedback and help improve the service. |
| Suppliers | Support product availability and cooperate with ASDA when required. |
| Technology Partners | Provide software, system, integration and technical expertise. Support the security, maintenance and performance of the ConnectPlus platform. |
| Investors | Monitor project performance and expect positive business results |
| Government and Regulators | Ensure the project follows legal and data protection requirements. |
| Trade Unions | Represent employee interests, provide feedback and support communication between employees and ASDA. |
| Local Communities | Benefit from improved services and support ASDA’s reputation within the community. |

Each stakeholder has different roles and responsibilities during the ConnectPlus project. Internal and external stakeholders have different roles and responsibilities during the project. Effective stakeholder management helps improve communication, support decision-making and increase the likelihood of project success (Freeman, 1984). Senior Management provides leadership and approves major decisions, while the Project Manager coordinates the project and ensures that activities are completed on time. The IT Team develops the digital platform, while the Marketing, Sales and Customer Service Teams support its implementation and customer engagement. External stakeholders, including customers, suppliers, technology partners, investors, government and regulators, trade unions and local communities, also contribute to the project’s success through cooperation, feedback and compliance with relevant requirements.

## 4.2 Benefits of Stakeholder Engagement

Stakeholder engagement is an important part of the ConnectPlus project because it helps ASDA build strong relationships with the people involved in or affected by the project. Effective engagement can improve communication, increase trust and support collaboration between stakeholders. It can also help the project team understand different stakeholder needs and reduce potential problems during implementation (Bourne, 2015).

One important benefit is better communication. Regular meetings, emails and feedback allow stakeholders to understand project objectives and raise concerns early. This can reduce misunderstandings and help the Project Manager respond to problems before they affect the project. For example, regular communication with the IT Team and Technology Partners can help identify technical issues early, while communication with employees and customers can provide useful feedback about the platform.

Another benefit is improved decision-making. Senior Management and the Project Manager can make better decisions when they receive information from employees, customers and other stakeholders. Different stakeholders provide different perspectives, so involving them can help the project team identify issues that may not be visible from a management perspective. This can support better project decisions and reduce the risk of overlooking important stakeholder needs (Olander, 2007).

Stakeholder engagement can also improve customer satisfaction. Customers can provide feedback about the ConnectPlus platform, allowing ASDA to improve its services and personalised recommendations. Employees and the Customer Service Team can also identify common customer problems and communicate them to the project team. This feedback can help ASDA improve the customer experience and encourage continued use of the platform.

Finally, effective stakeholder engagement can reduce project risks and support successful implementation. Regular communication with suppliers, Technology Partners and employees can help identify potential problems early and reduce delays. However, engagement needs to be appropriate for each stakeholder because different groups have different levels of interest and influence. Overall, effective stakeholder engagement can improve communication, decision-making and customer satisfaction while supporting the successful implementation of ConnectPlus.

## 4.3 Challenges of Stakeholder Engagement

Although stakeholder engagement provides benefits, ASDA may face several challenges during the ConnectPlus project. Different stakeholders may have different priorities and expectations, which can create disagreements and make decision-making more difficult (Aaltonen and Kujala, 2016).

Resistance to change is another challenge. Employees may feel uncomfortable using new technology or changing their daily working practices. Training and clear communication can help reduce this resistance.

Communication can also be difficult because the project involves many internal and external stakeholders. For example, delays in communication between the IT Team, Technology Partners and management could affect the development and implementation of the platform.

ASDA must also manage limited time, budget and staff resources. In addition, ConnectPlus uses customer data for personalised recommendations, creating privacy, security and ethical risks. ASDA must comply with GDPR and ensure that AI recommendations are fair, transparent and do not discriminate against customers.

These challenges show why ASDA should identify risks early, communicate clearly and review stakeholder needs throughout the project.

# 5- Stakeholder Engagement Strategy

Effective stakeholder engagement is important for the success of the ConnectPlus project at ASDA. A clear engagement strategy supports communication, trust and cooperation between stakeholders. The strategy includes a Stakeholder Engagement Plan, Communication Plan, RACI Matrix and conflict management process.

## 5.1 Stakeholders Engagement Plan

| Stakeholder | Current/ Desired Engagemnet | Owner/ Frequency | KPI/Feedback Route | Risk/Review |
| --- | --- | --- | --- | --- |
| Senior Management | Consult-Collaborate | Project Manager/ monthly | Project progress/Management meetings | Delayed decisions/ Monthly |
| Project Manager | Collaborate/ Empower | Senior Management/ Weekly | Milestones achieved/ Project meetings | Poor coordination/ weekly |
| IT Team | Consult/ Collaborate | Project Manager/ Weekly | Technical issues resolved/ Technical meetings | Technical problems/ weekly |
| Marketing Team | Inform/ Collaborate | Marketing Manager/ Weekly | Campaign engagement/ Team Feedback | Low customer adoption/ Monthly |
| Sales Team | Inform/ Involve | Sales Manager/ Monthly | Customer sign-ups/ Staff feedbacks | Low staff engagement/ monthly |
| Customer Service Team | Consult/Involve | Customers Service Team/Monthly | Customer feedback/ Customer reports | Unresolved complaints/ weekly |
| Store Managers | Inform/Involve | Store Managers/ Monthly | Training completion/ Staff feedback | Resistance to change/ Monthly |
| Customers | Consult/Involve | Customers Service Team/Monthly | Customers satisfaction/ Surveys | Low engagement/ Monthly |
| Suppliers | Inform/Consult | Project Manager/ monthly | Product availability/ Supplier meetings | Supply delays/ Monthly |
| Technology Partners | Consult-Collaborate | IT team/ weekly | Platform performance / technical reviews | Security or system issues/ weekly |
| Investors | Inform/Consult | Senior Management/ Quarterly | Financial performance/ investor updates | Loss of confidence/ quarterly |
| Government and Regulators | Inform/Consult | Compliance Manager/ As required | Compliance checks/ Formas report | Regulatory issues/ quarterly |
| Trade Unions | Inform/Consult | HR manager/ Monthly | Employee feedback/ Consultation meetings | Employee concerns/ monthly |
| Local Communities | Inform/Consult | Asda Management/ Quarterly | Community feedback/ community meetings | Reputation issues/ quarterly |

ASDA should adjust engagement according to stakeholder needs. High-priority stakeholders require regular involvement and decision-making, while lower-priority stakeholders mainly need relevant updates and opportunities to provide feedback. The plan should be reviewed regularly to respond to changes in stakeholder needs and project risks.

## 5.2 Communication Plan

| Stakeholder | Weekly Meeting | Monthly Meeting | Weekley Project Status | Monthly Highlight Report | Monthly Newsletter | Exception Report |
| --- | --- | --- | --- | --- | --- | --- |
| Senior Management | X F2F | X F2F | INTERNAL TO PROJECT X E | X E |  | X TC |
| Project Manager | X F2F | X F2F | X E | X E |  | X TC |
| IT Team | X F2F |  | X E | X E |  | X TC |
| Marketing Team | X VC |  | X E | X E | X E |  |
| Sales Team | X VC |  | X E |  | X E |  |
| Customer Service Team | X VC |  | X E |  | X E |  |
| Store Managers | X VC | X F2F | X E | X E |  | X TC |
| Customers |  |  | EXTERNAL TO ORGANISATION |  | X E |  |
| Suppliers |  | X VC | X E |  |  | X TC |
| Technology Partners | X VC | X VC | X E | X E |  | X TC |
| Investors |  | X F2F |  | X E |  |  |
| Government and Regulators |  |  |  |  |  | X E |
| Trade Unions |  | X F2F |  |  | X E |  |
| Local Communities |  |  |  |  | X E |  |

Key

- F2F – Face-to-Face Meeting

- VC – Video Conference

- TC – Telephone Conference

- E – Email

The communication plan ensures that all stakeholders involved in the ConnectPlus project receive the right information at the appropriate time. Different communication methods are used depending on each stakeholder’s role, level of interest and level of influence. Regular communication helps ASDA improve collaboration, monitor project progress and support successful stakeholder engagement.

## 5.3 RACI MATRIX

| Activity | Senior Management | Project Manager | IT Team | Marketing | Sales | Customers Service | Store Managers | Legal/ Data Protection | Procurement | Technology Partners | Government & Regulators |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approve Project | A | R | I | I | I | I | I | C | C | I | I |
| Project Planning | C | A/R | C | C | I | I | I | C | C | C | I |
| Platform Development | I | C | A/R | I | I | I | I | C | I | C | I |
| Marketing Campaign | I | C | I | A/R | C | I | I | I | I | I | I |
| Staff Training | I | C | C | I | I | C | A/R | I | I | C | I |
| Customer Support | I | I | C | I | I | A/R | C | C | I | C | I |
| Project Monitoring | A | R | C | C | C | C | C | C | C | C | I |
| Data Protection Approval | I | C | R | I | I | C | I | A | I | C | C |
| Supplier Integration | I | A | C | I | I | I | I | I | R | C | I |
| Customer Testing | I | A | R | C | C | C | C | C | C | I | C |
| Security Review | I | A | R | I | I | I | I | C | I | C | C |
| Go-Live | A | R | R | C | C | C | C | C | C | C | I |
| Post-Launch Review | A | R | C | C | C | C | C | C | C | C | C |

Key

- R = Responsible

- A = Accountable

- C = Consulted

- I = Informed

The RACI matrix clearly defines the responsibilities of each stakeholder during the ConnectPlus project. It helps avoid confusion, improves accountability and ensures that every team member understands their role.

## 5.4 4Cs Stakeholder Engagement Framework

| 4C Element | Application to ConnectPlus | Key Stakeholders | Owner/ Chanel | Measurable Outcome |
| --- | --- | --- | --- | --- |
| Communication | Provide regular project updates, training, emails and meetings to keep stakeholders informed during the six-month project. | Senior Management, Customers, Employees, Government and Regulatory Bodies | Project Manager / Meetings, email and reports | Stakeholders receive updates on time and understand project progress |
| Collaboration | Encourage IT, Marketing, Customer Service and Store Managers to work together to support the successful implementation of ConnectPlus. | IT Team, Marketing Team, Customer Service Team, Store Managers | Project Manager / Weekly meetings and workshops | Issues are resolved and project milestones are achieved. |
| Consultation | Collect feedback through customer surveys, employee meetings and supplier discussions before important project decisions. | Customers, Employees, Suppliers, Government and Regulators | Project Manager / Surveys, meetings and feedback sessions | Feedback is collected and actions are recorded. |
| Commitment | Maintain stakeholder support, encourage participation and ensure commitment to the project objectives throughout the project lifecycle. | Senior Management, Project Manager, Employees, Customers | Project Manager / Meetings and progress reviews | Stakeholder participation is maintained and project objectives remain on track. |

The 4C Framework supports effective stakeholder engagement by improving communication, collaboration, consultation and commitment. These four elements help ASDA maintain strong stakeholder relationships and support the successful delivery of the ConnectPlus project over the six-month implementation period (Bourne, 2015).

# 6: Sustainable Stakeholder Engagement

Sustainable stakeholder engagement is essential for the long-term success of the ConnectPlus project at ASDA. Building and maintaining positive relationships with stakeholders helps the organisation improve communication, increase customer satisfaction and support sustainable business growth. Continuous engagement also allows ASDA to respond to stakeholder needs and improve project outcomes.

## 6.1 Importance of Stakeholder Engagement

Stakeholder engagement is a continuous process that should continue throughout the project and after its completion. Regular communication helps ASDA build trust, reduce misunderstandings and strengthen relationships with internal and external stakeholders. According to Bourne (2015), continuous stakeholder engagement helps organisations build stronger relationships and improve long-term project success. ( Shaukat et al., 2022).

For the ConnectPlus project, continuous stakeholder engagement helps ASDA understand customer expectations, improve employee collaboration and ensure that technology partners and suppliers continue to support the platform after implementation.

## 6.2 Financial Performance

Effective stakeholder engagement can improve ASDA’s financial performance. Customers who receive personalised offers through ConnectPlus are more likely to make repeat purchases and remain loyal to the company. Employees also contribute by delivering better customer service, while suppliers and technology partners help maintain efficient business operations. Performance measures can help ASDA monitor whether these stakeholder activities are contributing to business results (Neely, Adams and Kennerley, 2002).

Table Financial Performance

| KPI | Baseline | Target | Data Source | Owner | Review Date |
| --- | --- | --- | --- | --- | --- |
| Customer Retention | Pre-launch retention rate | 3% increase within six months | Customer loyalty data | Customer Service Manager | Monthly |
| Revenue Growth | Pre-launch sales | 5% increase within six months | Sales reports | Sales Manager | Monthly |
| Return on Investment (ROI) | Pre-launch project cost and return | Positive ROI after implementation | Finance reports | Finance Manager | Monthly |

These KPIs help ASDA evaluate whether stakeholder engagement is contributing to the financial success of the ConnectPlus project.

## 6.3 Operational Efficiency

Sustainable stakeholder engagement improves operational efficiency by encouraging teamwork and effective communication. Employees, suppliers and technology partners work together to reduce delays, solve problems quickly and improve service quality. Regular communication also supports better decision-making and smoother project implementation improves teamwork and project performance (Too and Weaver, 2014)

## 6.4 Brand Reputation

Maintaining strong relationships with stakeholders helps improve ASDA’s brand reputation. Customers are more likely to trust a company that communicates openly, protects personal information and responds to customer feedback. Compliance with GDPR and responsible business practices also strengthen customer confidence in the ConnectPlus platform.(Walsh et al.,2009).

## 6.5 Employee Engagement

Employees play a key role in the success of the ConnectPlus project. Regular training, communication and teamwork help staff understand the new platform and provide better customer service. Engaged employees are more motivated, contribute new ideas and support continuous improvement across the organisation helps improve motivation and organisational performance (Saks, 2006)

## 6.6 Summary

Sustainable stakeholder engagement supports the long-term success of the ConnectPlus project at ASDA. Continuous communication and collaboration with stakeholders improve financial performance, operational efficiency, brand reputation and employee engagement. By maintaining strong stakeholder relationships, ASDA can achieve sustainable business growth and deliver greater value to customers.

# 7. Conclusion

This report examined the importance of stakeholder engagement in the successful commencement and completion of the ConnectPlus project at ASDA. It identified the main internal and external stakeholders and explained their roles, responsibilities, benefits and challenges throughout the six-month project.

The report applied different stakeholder management tools, including Stakeholder Mapping, the Power–Interest Matrix, the Salience Model, the Communication Plan, the Stakeholder Engagement Plan, the RACI Matrix and the 4C Framework. These tools were used to identify stakeholder priorities, improve communication, support collaboration and define responsibilities during project implementation.

The report also discussed the importance of sustainable stakeholder engagement and explained how effective stakeholder management can support financial performance, operational efficiency, brand reputation and employee engagement. Overall, this report demonstrated that effective stakeholder engagement is essential for successful project delivery. Using appropriate stakeholder management tools can help ASDA improve communication, reduce project risks and support the successful implementation of the ConnectPlus project.

# 8. Recommendations

Based on this report, ASDA should continue developing the ConnectPlus platform to improve customer engagement and business performance. ASDA should provide regular training for employees so they can use the platform confidently and provide better customer service.

ASDA should communicate regularly with all stakeholders during the project. Good communication will help reduce misunderstandings and improve teamwork. ASDA should collect customer feedback and monitor Key Performance Indicators (KPIs) to measure the success of the ConnectPlus project.

Finally, ASDA should continue protecting customer data and follow GDPR requirements to maintain customer trust and support long-term business success.

# References

Aaltonen, K. and Kujala, J. (2016) ‘Towards an improved understanding of project stakeholder landscapes’, International Journal of Project Management, 34(8), pp. 1537–1552.

ASDA (2025) About ASDA. Available at: https://corporate.asda.com/(Accessed: 25 July 2026).

Bellis Finco PLC (2025) Annual Report and Financial Statements 2025. Leeds: Bellis Finco PLC. Available at: ASDA Investor Relations (Accessed: 7 August 2026).

Bjerke, M.B. and Renger, R. (2017) ‘Being smart about writing SMART objectives’, Evaluation and Program Planning, 61, pp. 125–127.

Bourne, L. (2015) Making Projects Work: Effective Stakeholder and Communication Management. Newtown Square, PA: Project Management Institute.

Freeman, R.E. (1984) Strategic Management: A Stakeholder Approach. Boston: Pitman.

Lehtinen, J. and Aaltonen, K. (2020) ‘Organizing external stakeholder engagement in inter-organizational projects: Opening the black box’, International Journal of Project Management, 38(2), pp. 85–98.

Mendelow, A.L. (1991) ‘Stakeholder Mapping’, Proceedings of the 2nd International Conference on Information Systems, Cambridge, MA.

Mitchell, R.K., Agle, B.R. and Wood, D.J. (1997) ‘Toward a Theory of Stakeholder Identification and Salience: Defining the Principle of Who and What Really Counts’, Academy of Management Review, 22(4), pp. 853–886.

Neely, A., Adams, C. and Kennerley, M. (2002) The Performance Prism: The Scorecard for Measuring and Managing Business Success. London: Financial Times Prentice Hall

Olander, S. (2007) ‘Stakeholder impact analysis in construction project management’, Construction Management and Economics, 25(3), pp. 277–287.

Oliveira, G.F. de and Rabechini Jr, R. (2019) ‘Stakeholder management influence on trust in a project: A quantitative study’, International Journal of Project Management, 37(1), pp. 131–144.

Saks, A.M. (2006) ‘Antecedents and consequences of employee engagement’, Journal of Managerial Psychology, 21(7), pp. 600–619.

Shaukat, M.B., Latif, K.F., Sajjad, A. and Eweje, G. (2022) Revisiting the relationship between sustainable project management and project success: The moderating role of stakeholder engagement and team building. Sustainable Development, 30(1), pp. 58–75.

Too, E.G. and Weaver, P. (2014) ‘The management of project management: A conceptual framework for project governance’, International Journal of Project Management, 32(8), pp. 1382–1394.

Walsh, G., Mitchell, V.-W., Jackson, P.R. and Beatty, S.E. (2009) ‘Examining the antecedents and consequences of corporate reputation: A customer perspective’, British Journal of Management, 20(2), pp. 187–203.