Programme: BA (Hons) Business Management

Module: Project Management

Lecturer: David Oyebisi

Module code: LCBB5005

Student Name: Deni Apostolov

Student ID: 2244458

Table of Contents

Introduction	3

Project Aim, Objectives and Scope	3

Project Deliverables and Results	4

Project Activities	6

Project Breakdown Structure	8

Deliverables and Milestones of Project Tasks	10

Resource Allocation	12

Conclusion	13

References	14

# Introduction

The purpose of this document is to create a brief project development report about the selected project that will be undertaken and carried out. The project is about constructing or building a Smart Greenhouse which will be used for urban farming. In recent years, urban farming is increasingly being considered and implemented to produce crops. It is also considered to be a significant solution for sustainable agriculture while also being used for meeting food requirements in high-population areas (Likitswat, 2021). In this project, the key purpose is to build the Smart Greenhouse because this will be an advanced and technology-driven approach to creating an environment that is suitable for urban farming and can be controlled accordingly as per requirements.

Among the technologies to be integrated, there will be IoT (Internet of Things) sensors, which can sense the climate and control the movements to modify it. This can also be connected to lighting, humidity, temperature, and irrigation, and thus, it can control the environment to create the optimal climate for the plants or crops to grow. Thus, finishing this project can create a scope for people to engage in urban farming without making it a time-consuming or labour-intensive task (Hosny et al., 2024). So, it can be created as an ideal solution that can be suitable for urban farming to be done effectively and seamlessly.

In this project management report, the aim, objectives, and scope of this project will be laid down. The project deliverables and activities will be explained in combination with a project breakdown structure to create a visual representation of the activities and sub-activities. The milestones will also be given as per the intended results and activities. Finally, there will be a plan for resource allocation needed to finish this project successfully.

# Project Aim, Objectives, and Scope

The key aim of this project is to create a smart greenhouse using IoT sensor technologies for the purpose of urban farming. The project will design, build and create a smart greenhouse that can automatically control the environment and create an optimal climate for plants and crops to grow fully (Maraveas and Bartzanas, 2021). Thus, with this project, the target is to construct an automated and technology-driven environment that can minimise the use of manual labour.

Based on this, the project objectives include:

- To finish the construction of a smart greenhouse that can be used for urban farming.

- To develop the greenhouse by integrating IoT sensors for lighting, temperature and humidity and make an automated control system, where it can be adjusted automatically.

- To create automated systems for irrigation by integrating smart sensors for soil moisture and water distribution and thus minimise water consumption level.

- To incorporate a mobile monitoring system and control application attached to the automated systems of the greenhouse by developing an app and enabling remote management.

- To use smart lighting with energy-saving options for reducing electricity consumption despite maintaining an optimal environment for farming.

- To consider the accessibility of the greenhouse for urban farming so that it can be scaled as per different settings and locations.

- To extensively assess the systems to ensure their functionality and validate the system.

Therefore, the scope of this project includes necessary steps that are important for successfully finishing the construction of the smart greenhouse and making it optimal for urban farming (Maraveas and Bartzanas, 2021). So, the project scope consists of the entire project lifecycle, starting from creating the initial designs, to developing and implementing the systems and optimisation.

The key elements of this project involve:

- Building the structure of the greenhouse.

- Installing IoT sensors and integrating automated systems.

- Developing an intuitive and user-friendly software and mobile monitoring and control app.

- Integrating the greenhouse with the software components for creating the automated systems.

- Testing and optimising the system.

- Final deployment and monitoring.

# Project Deliverables and Results

The project for the construction of a smart greenhouse for urban farming is meant to create a greenhouse with an automated system which can be controlled remotely. In terms of using IoT sensors for temperature, humidity, lighting and irrigation, the optimal environment can be created effectively and remotely for the crops and plants to grow (Li et al., 2021). Moreover, a mobile monitoring and control app or software will be needed to control this remotely. So, it also needs to be tested along with the system to ensure that it can function accurately and automatically. Then, it can be deployed finally and farming can be started (Don Chua et al., 2024). These make up the expected results for this project and it also determines the project deliverables accordingly as per the entire process or the project lifecycle. Thus, the greenhouse can be used for sustainable and effective farming in any urban setting. Based on this, the deliverables include:

The key deliverable of the project is to successfully build the structure of the smart and automated greenhouse, which can be used for optimally growing and producing plants and crops. In constructing the structure, the necessary materials will be determined based on the design, including water resistance, ventilation, internal structure, materials, insulation, etc. This is to ensure the accessibility, adaptability and durability of the setting (Wacas, 2024).

The second deliverable is to create and install IoT sensors to sense different things in the internal climate or environment, including temperature, light, soil moisture, and humidity. The sensors are meant to capture the parameters and collect data in real time, enabling the systems to automatically set the environment to be optimal for farming (Don Chua et al., 2024).

The third deliverable is to integrate the automated irrigation system with the sensors. This system needs to be intelligent and determine the necessity of irrigation and dispersing water on the crops based on the soil moisture and humidity level detected by the sensors in real-time. This is targeted towards ensuring that the crops receive sufficient hydration but also reduce water waste.

Fourthly, the project will deliver a smart system or mechanism for controlling the temperature and internal environment to maintain ideal conditions for farming. So, apart from the previously mentioned technologies, this also requires materials or elements for shading, heating and especially ventilation to regulate the temperature seamlessly (Don Chua et al., 2024).

The project will develop a suitable mobile monitoring and control app so that it can be used by farmers to detect, understand, and adjust the internal environment of the greenhouse remotely. The app will be user-friendly and equipped with features to see real-time data about the parameters and receive automated alerts (Lean et al., 2024). It is also necessary for the app to have complete control by including a manual override feature.

The sixth deliverable is to minimise energy or electricity consumption through energy-efficient lighting. So, it will use LED lights that can be regulated as per lighting availability and internal temperature. The energy efficiency factor will also be considered during the structure design to ensure that it can use daylight as well.

Lastly, the project will develop a system that can take advantage of the real-time data being collected through the sensors and keep records. Thus, the data can be analysed and interpreted to understand crop growth trends and performance based on internal environmental settings (Lean et al., 2024). This can be applied in the long run to gradually increase the scale of farming and crop yields.

At the end of the project and final deployment, the project will provide a comprehensive manual, which can be used for resolving generic technical issues and training farmers to use the systems to their full potential.

# Project Activities

To finish this project successfully and create the smart greenhouse as per the requirements of urban farming, there is a set of activities that need to be followed and completed. The activities also reflect the project deliverables as well as the intended or expected results (Don Chua et al., 2024). Thus, it can be recognised that following the activities can ensure that the project can progress smoothly and seamlessly.

Project Planning and Design

- Performing market research, project feasibility analysis, and considering previous designs for identifying the suitable design and technological systems

- Establishing project aim, objectives, scopes, deliverables, and constraints

- Creating blueprints for the design and construction of the structure of the greenhouse

- Determining a suitable design for the IoT sensor network and its integration with the automated systems

Material and Item Procurement

- Determining the materials and items needed for constructing the structure

- Procuring the goods from suppliers

- Acquiring technological equipment from reliable technology providers or suppliers needed for automation

- Purchasing licenses and other components needed to create the mobile monitoring app

Construction of Greenhouse

- Preparing the construction site as per blueprints

- Installing frames for the structure

- Installing materials and systems for creating ventilation, heating and shading

- Setting up infrastructure for irrigation, supply and drainage

Implementation of IoT Sensors

- Integrating and deploying the sensors with the existing structure and system for monitoring and collecting data from the plants/ crops and their infrastructure

- Configuring the sensors and equipping them for internal irrigation and environmental control

- Integrating a cloud-based server and system with the sensors for real-time data collection and processing

Mobile App Development

- Designing the application, its interface, and features for remote controlling

- Developing the app for remote monitoring, controlling and usability

- Implementing features for visualising data, manually controlling and receiving automated alerts

- Performing app testing routinely for its usability, functionality, and performance

System Integration and Pilot Testing

- Integrating the systems with the existing structure and system, including both hardware and software elements

- Checking for communication and data collection

- Performing pilot testing on the system for stress tests, simulations, and system failure

- Refining the app based on final testing results and stakeholder feedback

Documentation

- Creating comprehensive manuals for operating the greenhouse’s system and following guidelines

- Inserting details for training farmers and operators

Project Closure, Handover and Final Deployment

- Finalising the greenhouse structure and its smart systems

- Performing final inspections

- Project closure and handover to original clients

- Monitoring the system functionality after final deployment during farming

# Project Breakdown Structure

Based on the project activities identified previously, a breakdown structure can be created. For this, the WBS or Work Breakdown Structure will be applied. WBS refers to a specific tool in project management, which is generally used for visualising the project tasks and activities. The main purpose of using the WBS is to break down the project’s main steps or tasks into much smaller sub-activities and tasks. Thus, this makes the tasks more manageable and attainable. This helps in defining the tasks based on the project scope and outcomes and enables the members of the project team to understand the tasks’ status and interdependency (Piras et al., 2024). As per the WBS for a project, the activities are assigned to the members or certain groups distinctly. They can also access and audit the project concerning the formulated WBS with the aim of ascertaining the progress of the project.

The WBS for this project is being developed below:

Figure 1: Work Breakdown Structure

# Deliverables and Milestones of Project Tasks

The deliverables and the milestones in this section are determined for every project task once the project has been segmented into short and focused activities. This aligns with the project's identified sub-tasks, which can be used to foster assessment of project progress. Thus, it can be used for tracking and reporting on the progress of the project with respect to the complete project lifecycle and timeline (Hussain et al., 2024). The project will also follow the Waterfall project methodology. Therefore, it will progress in a linear fashion. This refers to the process where the phases come one after another in a linear manner, and one task needs to be completed before moving on to the next one. Thus, this also determines the order or sequences of the tasks (Yu, 2024). Since this project will use the Waterfall methodology, the WBS has been developed accordingly, and the milestones are also being created as per the WBS task sequences. The milestones and deliverables are being given in a table format below:

| Project Task | Sub-Activities | Project Deliverables | Milestones |
| --- | --- | --- | --- |
| Initiation |  | Project feasibility report Documents of project scope and objectives | Receiving approval from stakeholders |
| Planning | Planning and Design | Completed architectural and engineering blueprints System design documents Procurement list | Design approval Procurement completed |
| Execution | Construction of Smart Greenhouse | Structure construction completed Systems installed | Completed and functional structure |
|  | Implementation of IoT Sensors | Installed sensors Automated irrigation system installation completed Finish control set-up | System integration was successfully completed, and functional |
|  | Mobile Application Development | App developed Pilot testing was done for functionalities, features, monitoring and remote controlling. | App development is completed and fully functional. |
| Control | Monitoring and Control | System evaluation and performance checking completed and reports Systems optimised | Positive results from the system's pilot testing and optimisation |
| Closure |  | User manual, guidelines and training documentation developed Final inspection Final deployment | The project was successfully handed over Post-deployment monitoring initiated |

Alongside the project deliverables, it is also essential to have a clear and detailed understanding of the project timeline based on the milestones for more accurate tracking. The timeline is given below:

| Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Initiation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Greenhouse Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IoT Implementation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mobile App Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| System Testing & Optimisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training and Documentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Deployment & Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Resource Allocation

To ensure that the project can be successfully completed within time and satisfies the given project scope and deliverables, it is of utmost importance to allocate resources carefully. This includes financial, materials and human resources (Hussain et al., 2024). Moreover, this also ensures that resources are not being wasted. This can be showcased using the table below:

| Phase | Personnel | Materials |
| --- | --- | --- |
| Initiation | Project Manager Market Researcher Financial Analyst | Feasibility study reports Data analysis tools Documentation Software |
| Planning | Project Manager Architect and Project Engineer IoT Specialists Procurement Officer and Team | Computer-aided design (CAD) software Procurement lists and databases IoT system design tools |
| Greenhouse Construction | Civil Engineers Construction Workers Electricians and Plumbers | Steel or aluminium frames, polycarbonate sheets, insulation materials Ventilation fans, water pipes, solar panels |
| IoT System Implementation | IoT Engineers Software Developers Electricians | Temperature, humidity, and soil moisture IoT sensors Automated irrigation systems Climate control actuators |
| Mobile Application Development | UI/UX Designers Software Developers Testers | App development software Cloud storage and IoT integration tools |
| Monitoring and Control | Quality Assurance Engineers IoT Specialists Agronomists | Testing equipment Data analytics software |
| Closure | Documentation team Maintenance Engineers | Training manuals Guidelines and operational manuals Maintenance toolkits |

# Conclusion

In conclusion, this project management report has been comprehensively created on the smart greenhouse system project that will be used for urban farming. Since it is meant to have a technology-driven approach, the greenhouse will be equipped with IoT sensors, automated systems, mobile monitoring and controlling apps and cloud-based servers. This report has specified the project scopes and objectives. Based on this, its expected results and activities have been explained as well. This has led to the creation of a work breakdown structure showcasing all sub-activities. Milestones and deliverables have also been given for each project task and sub-activity, along with a project timeline. Resource allocation was discussed to ensure that resources are being used optimally and not being wasted.

# References

Don Chua, W.F., Lim, C.L., Koh, Y.Y. and Kok, C.L., 2024. A Novel IoT Photovoltaic-Powered Water Irrigation Control and Monitoring System for Sustainable City Farming. Electronics, 13(4), p.676.

Hosny, K.M., El-Hady, W.M. and Samy, F.M., 2024. Technologies, Protocols, and applications of Internet of Things in greenhouse Farming: A survey of recent advances. Information Processing in Agriculture.

Hussain, A., Khalid, Q.S., Alkahtani, M. and Khan, A.M., 2024. A Mathematical Model for Optimizing NPV and Greenhouse Gases for Construction Projects Under Carbon Emissions Constraints. IEEE Access, 12, pp.31875-31891.

Lean, C.P., Krishnan, G., Li, C., Yuan, K.F., Kiat, N.P. and Khan, M.R.B., 2024. A Raspberry Pi-powered IoT smart farming system for efficient water irrigation and crop monitoring. Malaysian Journal of Science and Advanced Technology, pp.149-158.

Li, H., Guo, Y., Zhao, H., Wang, Y. and Chow, D., 2021. Towards automated greenhouse: A state of the art review on greenhouse monitoring methods and technologies based on internet of things. Computers and Electronics in Agriculture, 191, p.106558.

Likitswat, F., 2021. Urban farming: Opportunities and challenges of developing greenhouse business in Bangkok metropolitan region.

Maraveas, C. and Bartzanas, T., 2021. Application of Internet of Things (IoT) for optimised greenhouse environments. AgriEngineering, 3(4), pp.954-970.

Piras, G., Muzi, F. and Tiburcio, V.A., 2024. Digital management methodology for building production optimisation through digital twin and artificial intelligence integration. Buildings, 14(7), p.2110.

Wacas, R., 2024. SMART GREENHOUSE: AN IOT-BASED MONITORING AND CONTROL SYSTEM WITH PREDICTIVE ANALYTICS RONALD WACAS.

Yu, A., 2024. Environmental Projects Management (on the Example of the “Green Oasis” Urban Garden Project).