## Purple
Project: Purple
Contoso, Ltd.
Hayden Cook
Project start date: | 2026-06-15 | [10 empty] | Scrolling increment: | [5 empty] | 48
Milestone marker: | 1 | 1 |  |  | August | [34 empty] | September
 | time axis 2026-08-02 to 2026-09-26
Milestone description | Assigned to | Progress | Start | Days | time axis 2026-08-02 to 2026-09-26
Weeks 1, 2 and 3
Discussion |  | 25% | 2026-06-15 | 6
Allocation |  |  | 2026-06-19 | 1
Research |  | 50% | 2026-06-21 | 14
Research |  |  | 2026-06-21 | 14
Case Design |  | 10% | 2026-07-05 | 6
Weeks 4, 5 and 6
PCB Design |  | 60% | 2026-07-10 | 13
Ordering |  | 50% | 2026-07-14 | 9
Board Assembly |  | 33% | 2026-07-20 | 11
Prototype Build |  |  | 2026-07-28 | 6
Prototype Testing |  |  | 2026-07-29 | 24
Weeks 7, 8 and 9
Prototype Testing |  |  | 2026-07-29 | 24
Prototype Testing |  |  | 2026-08-11 | 14
Prototype Testing |  |  | 2026-08-18 | 14
Prototype Testing |  |  | 2026-08-18 | 14
Prototype Testing |  |  | 2026-08-18 | 19
Weeks 10 and 11
Evaluation |  |  | 2026-09-06 | 14
Evaluation |  |  | 2026-09-06 | 14
Improvements |  |  | 2026-09-18 | 7
To add more data, Insert new rows ABOVE this one