## Sheet1
Risk | To Whom | A = Worst Case outcome | B= Likelyhood | Level of risk (A x B) | Existing Precautions
Participant Dying due to ill health | Participants | 5 | 3 | 15 | St Johns Ambulance on site
Participants Dehydrated | Participants | 5 | 2 | 10 | Refreshment Stops Located at different points thoughout the race course
Food Allergies | Participants | 5 | 2 | 10 | Make sure any food is clearly labled before given to participants/ make sure St John's ambulance have epipens
Weather Issues | All | 5 | 2 | 10 | Grit on hand for slippery services/ Sheltered areas for staff. Sandbags for in case of flooding
People being run over by cars | All | 5 | 2 | 10 | Road Closures to prevent cars driving in race/spectator areas
Members of Public getting in the way of runners | Participants | 3 | 2 | 6 | Safety Barriers dividing the race course from the participants
Entertainment Getting in the way of race | Participants | 3 | 2 | 6 | Designated performance areas
Terrorism | Staff, Participants, Attendees | 5 | 2 | 10 | Police presence and stewards patrolling looking out for suspicious activity
Fire | All | 5 | 2 | 5 | Make sure electrical equipment is inspected beforehand
Trips/falls | All | 3 | 5 | 15 | Clear course of obstacles
Runners overcrowding/coliding | Participants | 5 | 1 | 5 | Staggered start times
Emergency Services not being able to get on site | All | 5 | 1 | 5 | Entry points /traffic management for emergency services to enter the race course if needed
Event cancelled due to suppliers not being able to deliver on time | All | 5 | 1 | 5 | Terms of contracts stating time and dates of delivery
Stray dogs attacking participants /staff/ public | All | 4 | 1 | 4 | Alert dog warden of any stray dogs close to race course
Parked cars in way of course | Participants | 3 | 2 | 6 | Inform residents of road closures prior to event
Police horse spooked by loud noise | All | 5 | 1 | 5 | Locate police horses away from PA speakers/entertainment
Falling trees | All | 5 | 1 | 5 | Visual check of trees on route day before event/safety advisory group
Uneven Surfaces | All | 3 | 2 | 6 | Design course to avoid any uneven surfaces/fence off any potential risks
Marquees blowing over | All | 4 | 1 | 4 | Make sure all marquees are weighted and stable
Violence/disorder | All | 5 | 1 | 5 | Police presence and stewards patrolling looking out for violent behavior
Race timers not recording times | Participants, Event Organiser | 3 | 2 | 6 | Test all equipment before race
Cyclists coliding with runners | Participants | 4 | 2 | 8 | Signs stating no vehicles permitted
Lost property | Participants/ Public | 1 | 3 | 3 | Lost property point near end of course
Lost Children | Participants/Public | 3 | 2 | 6 | Lost children point in city centre
Not enough toilet facilities | All | 3 | 2 | 6 | Hire in portaloos
Key Scales
A= 5 being the worst case outcome, 1 being very unlikely to cause harm
B= 5 being the most likely to happen, 1 being very unlikely to happen