## Sheet1
TASK | DURATION | START DATE | FINISH DATE
Site Set Up | 11 days | Wed 06/05/20 | Wed 20/05/20
Build Site Area | 3 days | Wed 06/05/20 | Fri 08/05/20
Install Temporary Services | 2 days | Wed 06/05/20 | Thu 07/05/20
Build Temporay Roads | 6 days | Mon 11/05/20 | Mon 18/05/20
Substucture | 48 days | Mon 04/05/20 | Wed 08/07/20
Excavation & Pilling | 14 days | Mon 04/05/20 | Thu 21/05/20
Excavation Formworkss | 12 days | Fri 22/05/20 | Mon 08/06/20
Reinforcment | 8 days | Tue 09/06/20 | Thu 18/06/20
Concrete Pouring | 2 days | Fri 19/06/20 | Mon 22/06/20
Concrete Curing & Strike Formwork | 12 days | Tue 23/06/20 | Wed 08/07/20
Superstructure | 110 days | Thu 09/07/20 | Wed 09/12/20
Building Frame (Concrete Columns and Beams | 50 days | Thu 09/07/20 | Wed 16/09/20
Concrete Curing & Strike Formwork | 15 days | Thu 17/09/20 | Wed 07/10/20
External Brickwork | 45 days | Thu 08/10/20 | Wed 09/12/20
Steel Framed Roof | 52 days | Mon 12/10/20 | Tue 22/12/20
Constrct Steel Frame | 12 days | Mon 12/10/20 | Tue 27/10/20
Finishes to the Roof | 40 days | Wed 28/10/20 | Tue 22/12/20
Scaffolding | 4 days | Thu 08/10/20 | Tue 13/10/20
Construct Scaffolding | 2 days | Thu 08/10/20 | Fri 09/10/20
Strike Scaffolding | 2 days | Mon 12/10/20 | Tue 13/10/20
Internal Works | 97 days | Wed 23/12/20 | Thu 06/05/21
Internal Stucture | 30 days | Wed 23/12/20 | Tue 02/02/21
Doors | 3 days | Wed 03/02/21 | Fri 05/02/21
Skirting Boards | 3 days | Mon 08/02/21 | Wed 10/02/21
Floor | 24 days | Thu 11/02/21 | Tue 16/03/21
Screeding | 4 days | Wed 17/03/21 | Mon 22/03/21
Plastering | 33 days | Tue 23/03/21 | Thu 06/05/21
Servicing | 22 days | Wed 03/02/21 | Thu 04/03/21
Eletrical | 20 days | Wed 03/02/21 | Tue 02/03/21
Mechanical | 22 days | Wed 03/02/21 | Thu 04/03/21
Internal Finishes | 55 days | Fri 07/05/21 | Thu 22/07/21
Carpentry | 20 days | Fri 07/05/21 | Thu 03/06/21
Painting | 20 days | Fri 04/06/21 | Thu 01/07/21
Floor Finishes | 15 days | Fri 02/07/21 | Thu 22/07/21
Ceiling Finishes | 15 days | Fri 04/06/21 | Thu 24/06/21
Clean Up | 5 days | Fri 25/06/21 | Thu 01/07/21
External Works | 153 days | Fri 22/05/20 | Tue 22/12/20
Drainage | 64 days | Fri 22/05/20 | Wed 19/08/20
Landscaping | 50 days | Wed 14/10/20 | Tue 22/12/20