## Slide 1: Feasibility Plan for an International Meeting
Theme: Equality, Diversity, and Inclusion within Industry
Event: Inclusion Summit 2025
Student name: Julian Gjoka {2230507}
Lecturer's name: Christopher Wilkin
Module: International meetings management for the hotel industry BMIH6007
Notes: This presentation is a feasibility plan designed for an international meeting. The theme of the plan is based on equality, diversity, and inclusion within the hospitality industry. The event under consideration is named as Inclusion Summit of 2025, and the plan will be devised accordingly for this meeting.

## Slide 2: Introduction
Objective:
Evaluate the feasibility of hosting an international EDI-focused three-day meeting for the hospitality sector at QEII center.
Key Features:
Tailored Event: MICE industry-specific, addressing EDI in hospitality (Lee and Park, 2023).
EDI Awareness: Promote inclusive policies, equitable workplaces, and diverse customer experiences (Kiradoo, 2022).
Purpose:
Market: Assess demand, audience, competition, and marketing.
Operations: Evaluate the venue, resources, staffing, logistics.
Notes: This presentation aims to study whether the possibilities of hosting a three-day international meeting for Equality Diversity and Inclusion (EDI) within the area of Hospitality are possible at QEII center. It is conceived as a bespoke vent for the Meetings, Incentives, Conferences, and Exhibitions (MICE) industry. This focus provides a way to ensure the event addresses the EDI-related challenges of hospitality and has the opportunity to promote a more inclusive industry. The event is targeted toward industry professionals to push for the adoption of inclusive policies, and diversity in the workplace and create diverse practices meant to engage customer experiences (Lee and Park, 2023; Kiradoo, 2022). The intention is to look at three critical areas to determine feasibility. Next, we'll examine market factors; that is, we look at the demand for such an event, estimate the audience we want to attract, and consider competition and the best way to market as much of the event as possible. First, venue availability, resource allocation, staffing requirements and logistical considerations will be evaluated as operational factors. The elements, however, make the event practical, as well as scalable. Then, in the last part, financials will cover all specific budget breakdowns, potential sources of funding (for example, sponsorship), as well as looking for ways to earn revenue. By the end of this analysis, we will find out if the economic and social aspects of hosting such an event are possible in the hospitality sector.

## Slide 3: Event content
TYPE AND NATURE OF EVENT
Keynote speeches by hospitality leaders of Marriott and Hilton.
Panel discussions with HR executives and policymakers.
Workshops on inclusive hiring, cultural competency, and accessibility.
Networking opportunities: breakout sessions and gala dinners.
PROPOSED THEME
Challenges and opportunities in EDI within hospitality
Addressing leadership underrepresentation (Bryan et al., 2023).
Promoting cultural competency for diverse guest needs (Wolbring and Nguyen, 2023).
Creating inclusive, accessible environments (Calver et al., 2023).
EVENT GOALS
Raise awareness of EDI’s impact on workplace culture and guest satisfaction.
Share best practices and actionable tools for inclusivity.
Inspire actionable change to drive innovation and success.
Notes: This event is intended to be a bold, live international conference created to tackle the substantial issue of EDI (Equality, Diversity, and Inclusion) within the hospitality scene. Notably, it has keynote speeches from industry leaders at companies like Marriott and Hilton, which have pioneered work in cultivating inclusive workspaces. Featuring real-world success stories of EDI promotion, these speeches will lay the tone for what you can do too. Keynotes will be complemented by panel discussions bringing together HR executives, educators and policymakers to provide a forum for strategic conversations on implementable EDI practices. In addition to learning, hands-on workshops will teach how to create an inclusive hiring strategy, increase cultural competency in guest service, and design an accessible hotel environment. Breakout sessions and gala dinners allow attendees to network establish future partnerships and collaborate on future big ideas. The central theme, called "Challenges and Opportunities in Promoting EDI Within Hospitality", focuses on critical topics such as missing leadership diversity (Bryan et al., 2023), the need for cultural sensitivity to accommodate different needs of the guests (Wolbring and Nguyen, 2023), and creating an inclusive and accessible environment for all (Calver et al., 2023). The goals are to showcase EDI's transformative power, share lessons learned and inspire attendees to drive genuine change within their organizations.

## Slide 4: Market factors
Target Market:
  Primary Audience: Hospitality executives, HR managers, venue operators, event organizers.
  Secondary Audience: Hospitality students, educators, policymakers, and NGOs.
Demand:
  Increased focus on EDI due to global movements (e.g., Black Lives Matter, #MeToo) (Wall, Brough and Cooper, 2021).
  Hospitality under pressure to diversify workforces and cater to multicultural guests (Zaghmout et al., 2024).
  Growing interest in EDI training among industry professionals.
Competition:
  Limited Direct Competitors: Few EDI-focused hospitality events.
  Potential Indirect Competitors: Generic HR/diversity conferences and GBTA events.
Marketing Activities:
  Social media ads (LinkedIn, Instagram, Twitter) (Domenico et al., 2021).
  Partnerships with WTTC and UNWTO.
  Email campaigns to industry leaders.
  Press releases to hospitality publications.
Notes: The target market for this event has been determined by narrowing it down to the stakeholders in the hospitality industry who will find it most relevant. Key audiences include hospitality executives and executive HR, venue operators and event organizers, responsible for driving EDI intervention across their organization. This secondary audience includes hospitality students and educators, policymakers, and NGOs interested in workplace inclusion and cultural competency. These are the groups that are going to constitute the future of the industry and can quite well trigger substantial systemic changes. Increasing global attention to EDI means this event has the demand stemming from movements such as Black Lives Matter and #MeToo (Wall, Brough & Cooper, 2021). Increasingly, hospitality organizations are subjected to a demand to diversify their workforces and to provide culturally competent services to a growing multicultural clientele (Zaghmout et al., 2024). Additionally, surveys show EDI professionals are just eager to receive training and knowledge-sharing opportunities specific to that EDI process. By and large, few direct competitors do hospitality-specific EDI events, but indirect competition includes other generic HR or diversity conferences that GBTA hosts, for example. Marketing activities like social media campaigns on LinkedIn, Instagram, and Twitter (Domenico et al., 2021), strategic partnership with WTTC and UNWTO, direct mail to industry leaders, and press releases to specific hotel press shops will be used to reach the market.

## Slide 5: Operational factors
Proposed Location
QEII center.
Reason for selection: Central location, excellent transport links, and venue facilities (Niu and Silva, 2021).
Venue Availability
Checked for the proposed dates; capacity for 500 attendees.
Required Resources
Catering: Breakfast, lunch, and refreshments.
AV setup: Projectors, microphones, and lighting.
Parking facilities and accessibility features.
Staffing Requirements
Event planners, technical staff, volunteers, catering team, and security.
Notes: QEII center in Westminister is chosen as the proposed location for the event, due to its central location, and combination of excellent transport links with world-class venue facilities (Niu and Silva, 2021). As a globally recognized hub for business and tourism, it is an ideal location both for local and international attendance at this event. With the infrastructure in place to support a large-scale event, the center makes the amenities to create the best experience for the attendees. Availability on proposed dates was checked in the venue that can host at least 500 attendees comfortably. This way, the event will have a place to accommodate keynote speeches, panel discussions, workshops and networking sessions without offending the comfort of the attendees. For the logistical needs of the event, the specific kind of services they require, and you are catering services will be to provide breakfast, lunch and refreshments to attendees. You have projectors, microphones, and professional lighting for the AV setup to produce seamless delivery of presentations and speeches. The event will be accessible to everyone, with parking and wheelchair-friendly entrances taking precedence. Preparation needs a skilled team of event planners, technical staff, volunteers, catering staff and guards to help with a smooth piece. Together, these things make sure that the event conforms to professional and operational standards.

## Slide 6: Financial factors
Item | Estimated Cost | Justification | Source (In-Text Citation)
Venue Hire (QEII Centre – Westminster, London) | £9,000 (1 day, full hire) | Central, prestigious location with conference facilities for up to 300 delegates | QEII Centre, 2024
Catering (Lunch + Refreshments for 300 people) | £6,750 (£22.50 per person) | Includes tea/coffee, pastries, buffet lunch, and dietary accommodations | Eden Caterers, 2024
A/V Equipment & Technical Support | £3,000 | Essential for hybrid delivery (microphones, projectors, live stream support) | AV Alliance, 2024
Marketing & Promotion (digital ads, social media, flyers) | £2,500 | Outreach to environmental professionals and students | Eventbrite, 2024
Notes: The financial planning for the sustainability conference has been carefully structured to ensure both feasibility and impact. Venue hire at the QEII Centre in Westminster is estimated at £9,000 for a full day, offering a centrally located, professional setting with the capacity to host 300 delegates (QEII Centre, 2024). Catering is budgeted at £6,750, based on £22.50 per person, and includes refreshments and a sustainable buffet lunch with dietary accommodations, provided by Eden Caterers (Eden Caterers, 2024). To support a hybrid event format, £3,000 is allocated for A/V equipment and technical support, ensuring seamless presentations and live streaming (AV Alliance, 2024). Marketing and promotion are projected at £2,500, covering targeted digital advertising, social media outreach, and printed materials to attract a professional audience interested in sustainability topics (Eventbrite, 2024). Each cost is justified based on functionality, audience expectations, and alignment with the event’s environmental focus, ensuring value and operational efficiency.

## Slide 7: Financial factors (Contd.)
Speaker Fees (3 experts @ £1,000 each) | £3,000 | Attract well-known sustainability experts to boost credibility and attendance | Speakers Corner, 2024
Staffing & Security (4 stewards, 2 security personnel) | £1,800 | Ensure smooth registration, guest experience, and safety | G4S, 2024
Printed Materials (programs, name badges, signage) | £700 | Branding, delegate experience, and navigation | Instantprint, 2024
Contingency (10%) | £2,175 | Covers unforeseen costs | Common event planning best practice
Total Estimated Budget: £28,925
Notes: To further support the success of the sustainability conference, several additional financial considerations have been integrated into the budget. Speaker fees are estimated at £3,000, covering three expert speakers at £1,000 each. Securing knowledgeable and reputable speakers in sustainability not only adds credibility to the event but also helps attract a professional audience (Speakers Corner, 2024). Staffing and security are allocated £1,800 to ensure smooth registration, delegate support, and safety, with a team of four stewards and two professional security personnel from a trusted provider (G4S, 2024). For branding and professional presentation, £700 is budgeted for printed materials, including event programs, name badges, and directional signage to guide attendees effectively (Instantprint, 2024). Lastly, a contingency of £2,175—equivalent to 10% of the total budget—is included to account for unexpected expenses, aligning with best practices in event planning. Altogether, the total estimated budget is £28,925, reflecting a well-rounded and realistic financial plan.

## Slide 8: Breakeven analysis
Revenue Source | Amount
300 attendees x £100 ticket | £30,000
Total Revenue | £30,000
Total Cost | £28,925
Estimated Profit / Breakeven Margin | £1,075 surplus
Notes: The breakeven analysis highlights the financial viability of the event. With an expected attendance of 300 delegates, each paying a £100 ticket fee, the projected total revenue amounts to £30,000. When compared to the total estimated cost of £28,925, this results in a modest surplus of £1,075. This small profit margin indicates that the event is not only financially sustainable but also provides a buffer for minor, unforeseen expenses. The ticket price is set at a competitive rate, balancing affordability with the value offered through expert speakers, catering, and a central London venue. This breakeven calculation demonstrates sound financial planning and ensures that the event remains cost-effective while delivering a high-quality experience for all participants.

## Slide 9: Strategic Pre-planning
Research Conducted
  Identified gaps in hospitality-specific EDI events.
  Highlighted Marriott’s focus on leadership diversity and Hilton’s initiatives on cultural competency (Selin, 2022; Russo, Figueira and Mataruna-dos Santos, 2023).
  Conducted stakeholder interviews to assess demand for actionable EDI solutions (Lehto et al., 2024).
  Analyzed competitors to emphasize this event’s unique focus on EDI in hospitality operations (Hung et al., 2024).
Risk Assessment
  Developed COVID-19 contingency plans for virtual or hybrid event formats (Hahang, Bayraktar and Jiménez, 2022).
  Reviewed venue cancellation and refund policies to protect financial investments.
Sustainability Measures
  Implementing digital ticketing to reduce environmental impact.
  Offering eco-friendly catering options with reusable or compostable materials (Xess, Bhargave and Kumar, 2021).
Notes: The EDI audit has been conducted as a strategic preplanning phase to specific gaps and opportunities in EDI within the hospitality industry. Studies indicate the shortage of hospitality EDI events delivering actionable solutions for operational diversity improvement at the workplace and in guest service. The industry shows a growing focus on the need for more collaboration, as Marriott's leadership diversity initiatives (Selin, 2022), and Hilton's cultural competency efforts (Russo, Figueira & Mataruna-dos Santos, 2023), illustrate. To confirm the strong demand for practical EDI strategies, stakeholder interviews with HR professionals, diversity officers, and educators were carried through. Further competitor analysis found that one of the conferences that address EDI does not have a specific target towards EDI using hospitality operations (Hung et al., 2024). The planning process has been risk-assessed. COVID-19 contingency plans, including virtual or hybrid formats, were developed to ensure resilience (Hahang, Bayraktar Jiménez, 2022). Also reviewed were venue cancellation and refund policies to minimize lost financial investment. Support of measures to promote sustainability is the order of the day, while paperless digital ticketing has been implemented to cut on paper waste. We will offer eco-friendly options regarding catering using reusable or compostable materials (Xess, Bhargave & Kumar, 2021). The event's goal is to minimize single-use plastics to be more sustainable.

## Slide 10: Value proposition
Supports Global Goals: Aligns with UN’s Sustainable Development Goals (SDG 5: Gender Equality, SDG 8: Decent Work and Economic Growth) (Kreinin and Aigner, 2022, p. 8; Birdthistle and Hales, 2023).
Fills Industry Gaps: Addresses the lack of EDI-focused events specific to the hospitality sector.
Facilitates Collaboration: Provides a platform for industry leaders to share actionable insights and best practices (Brun, Karaosman and Barresi, 2020).
Drives Innovation: Encourages the adoption of innovative EDI strategies in workplace diversity, cultural competency, and accessibility (Akter et al., 2022).
Enhances Branding: Positions participating organizations as leaders in sustainability and inclusivity within the hospitality industry (Kondapatti Chandiran, 2021).
Notes: For the hospitality industry, this event is important as it fills remaining gaps and aligns with significant global initiatives such as the United Nations Sustainable Development Goals (UN SDG). By aligning with SDG 5: As gender Equality and SDG 8, the topic underlines the need to generate inclusive offices and offices, and also unbiased applies in the field (Kreinin and Aigner, 2022, p. 8; Birdthistle and Hales, 2023). The work on EDI is directly addressing a notable gap in events, as there are few events tailored, for the specific challenges facing hospitality work in this area. In addition, it is an occasion to brainstorm with a wealth of industry figures and forge new partnerships and alliances based on partnerships and alliances formed in other areas (Brun, Karaosman & Barresi, 2020). This will encourage innovation by prompting attendees to embrace new strategies that will help institutionalize workplace diversity and cultural competency throughout operations and customer service (Akter et al., 2022). Furthermore, organizations participating in this event gain branding opportunities, being able to showcase themselves as leaders in sustainability and inclusivity in the hospitality sector. Not only does it strengthen the public's perception, but it also entices socially aware customers and employees (Kondapatti Chandiran, 2021). Hence, these aspects make this event valuable as its impact could lead to systemic change across the entire industry.

## Slide 11: Recommendations
Key Steps to Ensure Success
  Launch early marketing campaigns to drive ticket sales.
  Build partnerships with EDI-focused organizations and media outlets.
  Implement feedback mechanisms for continuous improvement.
Future Prospects
  Establish the event as an annual platform to champion EDI in hospitality.
Notes: Several strategic steps are identified to ensure that the event becomes successful. First, the launching of early marketing campaigns is paramount to maximizing ticket sales, gaining an audience, and procuring the prospective clientele. The social media platforms, including LinkedIn, Instagram, and Twitter, will get early promotion and will spread awareness and excitement about it amongst potential attendees. Further, hospitality executives, HR managers and educators will be directly emailed to guarantee that the right message reaches important industry decision-makers. Secondly, running the event, and building partnerships with EDI-focused organizations and media outlets can make the event what it should be reaching and great. Not only will this expand the reach, but organizations such as the World Travel and Tourism Council (WTTC), the United Nations World Tourism Organization (UNWTO) and diversity advocacy groups will also deliver sponsorship opportunities. Industry partnerships will be formed with media partners like Hotel Management & Hospitality Net, which will further boost visibility and attract participation from a greater dimension. Third, for continuous improvement, ongoing feedback mechanisms have to be implemented. Through attendee surveys, post-event evaluations and direct feedback from stakeholders, we will learn what worked well and what needs fine-tuning. This will facilitate the evolution of the event, keeping it current, making sure it is relevant and addressing the evolving trends in Equality and Diversity and Inclusion (EDI) within the Hospitality industry. The event looks to turn the page toward the future as an annual platform to champion EDI within the industry. It will position itself as a go-to solution, and by establishing a legacy, it will embed itself as the go-to event in the workplace diversity, cultural competency, and accessibility space. Long-term collaborations will also be encouraged by an annual format, allowing participants to follow up with progress, and share EDI update information. These recommendations not only ensure the immediate success of the event but also for its long-term impact on the hospitality industry.

## Slide 12: Gannt Chart
-
Task | Responsible Party | Week 1–2 | Week 3–4 | Week 5–6 | Week 7–8 | Week 9–10 | Week 11 | Week 12 (Event Week)
Define event objectives and theme | Event Manager | ✅ |  |  |  |  |  | 
Secure venue (QEII Centre) | Logistics Coordinator | ✅ | ✅ |  |  |  |  | 
Contact and confirm speakers | Program Coordinator | ✅ | ✅ | ✅ |  |  |  | 
Develop budget and secure funding | Finance Lead | ✅ | ✅ |  |  |  |  | 
Design marketing materials | Marketing Team |  | ✅ | ✅ | ✅ |  |  | 
Launch marketing campaign | Marketing Team |  |  | ✅ | ✅ | ✅ | ✅ | 
Notes: The first phase of the event planning timeline focuses on laying a strong foundation for the sustainability conference. During Weeks 1–2, the Event Manager finalizes the event’s objectives and overarching theme, ensuring alignment with the target audience’s interests. Simultaneously, the Logistics Coordinator begins the process of securing the QEII Centre, which continues into Week 4. The Program Coordinator contacts potential speakers from Week 1 to Week 6 to confirm availability and secure high-profile contributors. In parallel, the Finance Lead develops the event budget and explores funding sources to ensure financial viability. From Week 3 onward, the Marketing Team begins designing promotional materials, followed by the campaign launch during Week 5. This promotional effort continues through Week 11, targeting environmental professionals and students via digital platforms. This structured timeline ensures key logistical and promotional elements are addressed early, setting the stage for a successful event.

## Slide 13: Gannt Chart
-
Open registration portal | Admin Team |  |  | ✅ | ✅ | ✅ | ✅ | ✅
Confirm catering order | Logistics Coordinator |  |  | ✅ | ✅ |  |  | 
Arrange A/V equipment and tech support | Technical Lead |  | ✅ | ✅ | ✅ |  |  | 
Recruit and schedule staff/security | HR Coordinator |  |  |  | ✅ | ✅ |  | 
Prepare printed materials (badges, signage) | Admin/Design Team |  |  |  |  | ✅ | ✅ | 
Final site inspection and logistics check | Event Manager |  |  |  |  |  | ✅ | 
Event day management & execution | All Teams |  |  |  |  |  |  | ✅
Post-event evaluation and follow-up | Event Manager |  |  |  |  |  |  | ✅
Notes: The second half of the conference planning timeline focuses on operational readiness and execution. Beginning in Week 5, the Admin Team opens the registration portal, keeping it active until the event week to maximize delegate participation. The Logistics Coordinator confirms catering arrangements by Week 6 to ensure food accommodations are met. Simultaneously, the Technical Lead coordinates A/V and streaming services to support both in-person and virtual attendees. The HR Coordinator handles staffing logistics, recruiting stewards and security in Weeks 7 and 8. By Weeks 9 and 10, the Admin and Design Team finalizes printed materials like name badges and signage. The Admin Team also confirms final attendance figures for accurate planning. In Week 11, the Event Manager conducts a final site inspection and logistics review to preempt any issues. The event is executed in Week 12, followed by a post-event evaluation to gather feedback and document lessons learned for future improvements.

## Slide 14: Conclusion
✅ Successful event planning requires clear structure and timeline
📍 Prestigious venue (QEII Centre) enhances credibility and attendance
💷 Budget of £28,925 justified with real-world costs and sources
📈 Breakeven analysis shows financial viability (£1,075 surplus)
🗣️ Expert speakers and strategic marketing ensure engagement
🛠️ Operational tasks aligned with timeline for smooth execution
🔄 Post-event evaluation enables continuous improvement
Notes: In conclusion, this event plan demonstrates a comprehensive and structured approach to delivering a successful, professional-level sustainability conference. We began by establishing clear objectives and aligning them with a precise timeline, ensuring every task was strategically scheduled. The selection of the QEII Centre in Westminster not only offers logistical convenience but also adds prestige, elevating the overall impact of the event. Financially, we ensured transparency and feasibility with a detailed, real-world cost breakdown totaling £28,925, all supported by reputable industry sources. A breakeven analysis revealed a projected surplus of £1,075, confirming the plan’s financial viability. The inclusion of expert speakers and targeted marketing enhances both reach and engagement. Operational elements such as A/V, staffing, and materials were carefully planned in sequence to support seamless delivery. Finally, a post-event evaluation is built into the timeline, providing valuable insights for future improvements and reinforcing the event’s long-term value.

## Slide 15: references
Akter, S., Michael, K., Uddin, M.R., McCarthy, G. and Rahman, M. (2022) ‘Transforming business using digital innovations: the application of AI, blockchain, cloud and data analytics’, Annals of Operations Research, 308(1), pp. 7–39. Available at: https://doi.org/10.1007/s10479-020-03620-w.
Birdthistle, N. and Hales, R. (eds) (2023) Attaining the 2030 Sustainable Development Goal of Gender Equality. Emerald Publishing Limited. Available at: https://doi.org/10.1108/9781804558324.
Brun, A., Karaosman, H. and Barresi, T. (2020) ‘Supply Chain Collaboration for Transparency’, Sustainability, 12(11), p. 4429. Available at: https://doi.org/10.3390/su12114429.
Bryan, J., Johnson, K., Ali, H., McIlveen-Brown, E., Kernick, A., Primavesi, R., Kitty, D. and LeBlanc, C. (2023) ‘Leadership for change: working toward equity, diversity, and inclusion’, Canadian Journal of Emergency Medicine, 25(4), pp. 278–281. Available at: https://doi.org/10.1007/s43678-023-00453-x.
Calver, J., Dashper, K., Finkel, R., Fletcher, T., Lamond, I.R., May, E., Ormerod, N., Platt, L. and Sharp, B. (2023) ‘The (in)visibility of equality, diversity, and inclusion research in events management journals’, Journal of Policy Research in Tourism, Leisure and Events, 0(0), pp. 1–25. Available at: https://doi.org/10.1080/19407963.2023.2228820.
Domenico, G.D., Sit, J., Ishizaka, A. and Nunan, D. (2021) ‘Fake news, social media and marketing: A systematic review’, Journal of Business Research, 124, pp. 329–341. Available at: https://doi.org/10.1016/j.jbusres.2020.11.037.
Hahang, E., Bayraktar, S. and Jiménez, A. (2022) ‘Early evidence of leadership skills and strategies in managing the impact of COVID-19 pandemic in the hospitality industry’, Cross Cultural &amp; Strategic Management, 29(3), pp. 493–515. Available at: https://doi.org/10.1108/CCSM-03-2021-0041.
Hung, L., Wong, K.L.Y., Rasekaba, T., Ren, L.H., Douglass, D., Slatter, S., Berndt, A. and Blackberry, I. (2024) ‘How can equity, diversity, and inclusion (EDI) principles be incorporated into research excellence with industry and community partners? Lessons learned from Canada and Australia on projects with a dementia focus’, Research Involvement and Engagement, 10(1), p. 106. Available at: https://doi.org/10.1186/s40900-024-00644-5.
Kiradoo, G. (2022) ‘Diversity, Equity, and Inclusion in the Workplace: Strategies for Achieving and Sustaining a Diverse Workforce’. Rochester, NY: Social Science Research Network. Available at: https://papers.ssrn.com/abstract=4392136 (Accessed: 27 January 2025).
Kondapatti Chandiran, G. (2021) ‘LUXURY BRANDING: WHAT IT TAKES TO BE RECOGNISED AS A LUXURY BRAND?’
Kreinin, H. and Aigner, E. (2022) ‘From “Decent work and economic growth” to “Sustainable work and economic degrowth”: a new framework for SDG 8’, Empirica, 49(2), pp. 281–311. Available at: https://doi.org/10.1007/s10663-021-09526-5.
Lee, J.-S. and Park, S. (2023) ‘Scale development for the practices involved in creating value propositions in the exhibition industry: Service-dominant logic with a mixed-methods approach’, Tourism Management, 99, p. 104780. Available at: https://doi.org/10.1016/j.tourman.2023.104780.
Lehto, X.Y., Kirillova, K., Wang, D. and Fu, X. (2024) ‘Convergence of Boundaries in Tourism, Hospitality, Events, and Leisure: Defining the Core and Knowledge Structure’, Journal of Hospitality & Tourism Research, 48(3), pp. 407–419. Available at: https://doi.org/10.1177/10963480221108667.
Niu, H. and Silva, E.A. (2021) ‘Delineating urban functional use from points of interest data with neural network embedding: A case study in Greater London’, Computers, Environment and Urban Systems, 88, p. 101651. Available at: https://doi.org/10.1016/j.compenvurbsys.2021.101651.
Russo, E., Figueira, A.R. and Mataruna-dos Santos, L.J. (2023) ‘The Hilton hotels in the midst of the UAE 2071 centennial plan: Redesigning the UAE on the path of innovation and international tourism’, Tourism and hospitality management, 29(4), pp. 627–638. Available at: https://doi.org/10.20867/thm.29.4.17.
Selin, J. (2022) ‘More than Just a Workplace: A Case Study of Diversity, Equity, and Inclusion in Marriott International Inc. Hotels’, Experience Industry Management [Preprint]. Available at: https://digitalcommons.calpoly.edu/expindsp/23.
Wall, T., Brough, P. and Cooper, C.L. (2021) ‘The SAGE Handbook of Organizational Wellbeing’, pp. 1–100.
Wolbring, G. and Nguyen, A. (2023) ‘Equity/Equality, Diversity and Inclusion, and Other EDI Phrases and EDI Policy Frameworks: A Scoping Review’, Trends in Higher Education, 2(1), pp. 168–237. Available at: https://doi.org/10.3390/higheredu2010011.
Xess, A., Bhargave, H. and Kumar, P. (2021) ‘A study on influence of eco-friendly technologies in hospitality industry’, Journal of Physics: Conference Series, 1950(1), p. 012024. Available at: https://doi.org/10.1088/1742-6596/1950/1/012024.
Zaghmout, B., Achi, F., Padmini Ema, U. and Adeshipo, A. (2024) ‘Ethical Leadership in Dubai Hospitality Industry: Navigating Cultural Sensitivity and Inclusivity in a Globalized Market’, Open Journal of Leadership, 13(3), pp. 385–411. Available at: https://doi.org/10.4236/ojl.2024.133022.
Notes: These are the references that I have used.