Tendering documents – Best Practice

MC to SC

Procuring a package – say Drylining

I’m your commercial manager and I want you to tell me the best way to procure that package – from ground zero to placing the order

Then we are going to discuss each section in detail….

- Look into spec first for ‘equal or approved’ opportunity to make money form estimating stage by value engineering the spec. if its ‘client spec’ed’ then forget it e.g. kitchen.

- Drawings are key, think about all drawings that could have an impact on the package

- Scope of works (what can I pass down to the SC)

- Best is a fully detailed BoQ (seldom are they done, why?) time and resources

- Next best is ‘spec and drawings’ and leave the SC to take off quantities

- Any provisional sums for possible misc. items e.g. access hatches

- Or schedule of rates! (‘contract sum analysis!’)

- BoQ helps the tender analysis, when they come back from the SCs.

- Call them all before we send the tender out, saying what it is for, important return date and any queries etc. to me

- Meet them on site in 1 weeks’ time. Check attendance list what are we going to supply and what are they going to supply!

- Email the tender out!!!! Invitation to Tender:

- What happens if just before return date arch gives you REV2? – tender addendum

- What about mid tender meeting? – needed for complex, high value packages following all SC site visit. Take minutes and include in the order.

- How many you going out to tender too?

- Tender return periods! Got to give SC time (4 weeks is go to, 6 for M&E) quicker if have BoQ

- What about digital procurement (not word or excel). Using a central hub, good for communicating changes

- Where do you get your scopes from? Give them an AI example.

- I think the way you have done this is a really good job, of procuring your package!

1.

2.

3.

Example SoW

4.

5.