Module Title: Problem Solving and Decision Making

Module Code: LCLM 4004

Assessment: Component 2 Report

Student Name: Siddika Sultana

Student Number: 2331479

Lecturer’s Name: Deji Olagboye

Table of Contents

Contents                              			    Page Number

Task 1: 	Overview of Case-study							3

# Task 2:	Two proposed solutions 							3

# Task 3b): 	Evaluation Results and Justifications					4

# Task 4b): 	Risk Analysis Results and Justifications 					4

# Task 5b): 	Justifications for the Implementation Plan				4

# Task 6b): 	Justifications for the KPI and SMART objectives			5

# Task 7: 	Key Findings 								5

Reference List                                                                                                          6

# Appendices

# Appendix 1: Task 3a) PMI Analysis Table……………………………………8

# Appendix 2: Task 4a) Risk Analysis Table…………………………………………….9

# Appendix 3: Task 5a) Implementation Plan……………………………………………10

# Appendix 4: Task 6a) KPI and SMART Table…………………………………………11

Task 1: Overview of Case-study

Green Haven Florists is an independent flower shop in Norwich recognised for its bespoke arrangements and sustainable practices. Despite its powerful reputation, the business has experienced a 30% decline in in-store sales. The root problem is its failure to adapt to changing consumer behaviour, particularly the shift towards online purchasing. Contributing factors include reduced high street footfall, increased competition from online retailers, rising costs and an outdated website. Additionally, limited digital marketing has reduced customer engagement and visibility. These issues highlight a lack of digital transformation, which is significantly impacting business performance and long-term competitiveness (Chaffey, 2022). Furthermore, the emergence of digitally advanced competitors offering convenient delivery options and competitive pricing has intensified pressure on the business. Customer expectations have also evolved with many prioritising convenience, accessibility and speed of service, which Green Haven currently struggles to meet. As a result, the business is losing both new and existing customers, further weakening its market position and financial stability.

# Task 2: Two Proposed Solutions

### Solution A: Website Redesign and E-commerce Optimisation

### This solution involves redesigning Green Haven’s website to create a modern and user-friendly e-commerce platform. Features would include mobile optimisation, improved navigation, secure payment systems, same-day delivery options and subscription services. This directly addresses customer concerns about convenience and accessibility. A well-designed website improves user experience and significantly increases conversion rates (Chaffey, 2022). Additionally, subscription services provide consistent revenue. By enhancing its digital presence, Green Haven can compete effectively with online retailers while keeping its unique brand identity, improving both online and overall sales performance.

### Solution B: Social Media Marketing Strategy

### This solution focuses on strengthening Green Haven’s social media presence through platforms such as Instagram and TikTok. By sharing high-quality visuals, customer testimonials and engaging content, the business can increase brand awareness and customer interaction. Influencer partnerships and targeted advertising could further expand reach. According to Kotler et al. (2021), digital marketing enhances customer engagement and loyalty. However, while this approach improves visibility, its impact on direct sales is less immediate compared to e-commerce improvements, making it a supporting rather than primary solution.

# Task 3b) Evaluation Results and Justifications

Based on the PMI analysis, solution A is the most appropriate option. The evaluation criteria included cost, revenue impact, implementation time, and long-term sustainability, with greater weighting assigned to revenue and sustainability due to the decline in sales. Solution A achieved a higher overall score as it directly influences customer purchasing behaviour and generates measurable financial outcomes. In contrast, Solution B primarily improves brand awareness with less immediate impact on revenue. The use of the PMI framework supports structured decision-making (De Bono, 1992), justifying the choice of Solution A (Chaffey, 2022). Furthermore, Solution A provides a more direct response to the core issue of declining sales by enhancing the purchasing process and improving customer accessibility. It also offers greater long-term value through scalability and the potential for continuous revenue growth, strengthening the overall strategic position of the business.

# Task 4b) Risk Analysis Results and Justifications

The risk analysis shows key risks including high implementation costs, technical challenges, and low initial website traffic. These risks were evaluated using likelihood and impact criteria, with financial risks given greater importance. Although the initial investment is significant, it can be managed through phased implementation. Technical risks can be reduced through professional development and thorough testing. Risk analysis frameworks support effective decision-making by finding and mitigating potential issues (Hopkin, 2018). Therefore, the selected solution is considered reliable, as the risks are manageable and outweighed by long-term benefits (Laudon and Laudon, 2020).

# Task 5b) Justifications for the Implementation Plan

The implementation plan follows a structured sequence of planning, development, testing, and launch. This order ensures that objectives are clearly defined before execution, reducing inefficiencies. The 12-week schedule allows enough time for development and quality assurance. Responsibilities are divided between the business owners and external developers to ensure both strategic and technical expertise. Structured planning improves project success by enhancing control and reducing risk (Kerzner, 2019). Therefore, the proposed plan is logical, efficient and coordinated with best practice project management principles.

# Task 6b) Justifications for the KPI and SMART Objectives

The selected KPI is monthly online sales revenue, as it directly measures the effectiveness of the e-commerce solution. This indicator is relevant, measurable, and aligned with the business objective of increasing sales. The SMART objectives provide clear targets, such as achieving a 25% increase in online sales within six months. These objectives are specific, measurable, attainable, relevant, and time-bound, ensuring effective performance tracking (Doran, 1981). Using structured performance metrics enables continuous monitoring and supports informed decision-making, ensuring the success of the implemented solution. Furthermore, the use of this KPI allows the business to track progress over time and find trends in customer purchasing behaviour. Regular evaluation of performance data will enable adjustments to be made where necessary, improving overall effectiveness. This approach ensures that the business stays responsive to market conditions while keeping focus on achieving its strategic aims.

# Task 7) Key Findings

- Green Haven Florists is experiencing declining sales due to limited digital adaptation.

- The main issue is failure to respond to the growth of online shopping.

- Website redesign is the most effective solution as it directly increases revenue.

- Social media marketing supports awareness but has less immediate financial impact.

- Risks are present but can be mitigated through structured planning.

- A phased implementation plan ensures efficient execution.

- KPIs and SMART objectives allow effective monitoring of performance.

- Digital transformation is essential for long-term competitiveness and sustainability.

- Customer expectations have shifted towards convenience, speed, and accessibility.

- An improved online presence can enhance customer experience and engagement.

- Investment in digital capabilities can create new revenue streams such as subscriptions.

- Strengthening competitive positioning is necessary to compete with online and local rivals.

Reference List

Chaffey, D. (2022) Digital Business and E-Commerce Management. Pearson.

Kotler, P., Keller, K.L. and Chernev, A. (2021) Marketing Management. Pearson.

Laudon, K.C. and Laudon, J.P. (2020) Management Information Systems. Pearson.

Kerzner, H. (2019) Project Management: A Systems Approach. Wiley.

Doran, G.T. (1981) ‘There’s a S.M.A.R.T. way to write management’s goals and objectives’, Management Review, 70(11), pp. 35–36.

De Bono, E. (1992) Serious Creativity. HarperCollins.

Hopkin, P. (2018) Fundamentals of Risk Management. Kogan Page.

Appendices

Appendix 1 – Task 3a

PMI Analysis Table

The PMI framework evaluates decision-making by analysing positive, negative and interesting factors (De Bono, 1992).

| Solution A |  |  |
| --- | --- | --- |
| Plus | Minus | Interesting |
| Increases online sales | Inflated costs | Scalable |
| Improves UX | Technical skills needed | Subscription model |
| Better delivery options | Time to build | Professional image |
| Competitive advantage | Maintenance needed | Analytics integration |
| TOTAL: 16 | TOTAL: 10 | TOTAL: 12 |

Therefore: Overall Total for Solution A = 18

| Solution B |  |  |
| --- | --- | --- |
| Plus | Minus | Interesting |
| Low cost | Time-consuming | Brand building |
| More awareness | Slow sales impact | Younger audience |
| Engagement | Needs consistency | Loyalty |
| New customers | Delayed results | Promotions |
| TOTAL: 14 | TOTAL: 11 | TOTAL: 11 |

Therefore: Overall Total for Solution B = 14

Appendix 2 – Task 4a

Risk Analysis Table

Risk analysis evaluates potential threats based on likelihood and impact (Hopkin, 2018).

|  | What could cause a risk? | What is the likelihood of the risk occurring? (1 – 5) | What is the impact of this risk? (1 – 5) | Risk Factor = Likelihood X Impact | What can you do to reduce this risk from happening? | If it happens – what can you do to minimise the impact? |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | High cost | 3 | 5 | 15 (3x5) | Budget planning | Adjust pricing |
| 2 | Technical issues | 2 | 4 | 8 (2x4) | Professional support | Fix quickly |
| 3 | Low traffic | 3 | 4 | 12 (3x4) | SEO marketing | Discounts |

Appendix 3 – Task 5a

Implementation Plan

Implementation planning ensures structured execution and task management (Kerzner, 2019).

Problem: Declining sales.

Solution: Website redesign.

|  | Task | WHAT | WHEN | WHO | Done |
| --- | --- | --- | --- | --- | --- |
| 1 | 1 | Planning | Weeks 1-2 | Owners | ☐ |
| 2 | 2 | Development | Weeks 3-6 | Developer | ☐ |
| 3 | 3 | Testing | Weeks 7-9 | All | ☐ |
| 4 | 4 | Launch | Weeks 10-12 | Owners | ☐ |

Appendix 4 – Task 6a

SMART objectives provide structured goal setting (Doran, 1981).

The Key Performance Indicator is: Monthly online sales revenue.

| Specific | Measurable | Attainable | Relevant | Time-Bound |
| --- | --- | --- | --- | --- |
| Increase online sales | Plus 25% revenue | Based on improvements | Addresses problem | Within 6 months |