## Front
NRM1 Cost Plan Template
James Lloyd
1900878
06th February 2023

## Status
NRM1 Elemental Cost Plan Template
06th February 2023
Document Status
Revision | Date | Status | Prepared by | Checked by | Authorised by
Rev A | 2022-11-11 |  | James Lloyd
Rev B | 2022-11-25 |  | James Lloyd
Rev C | 2022-12-09 |  | James Lloyd
Rev D | 2022-12-23 |  | James Lloyd
Rev E | 2023-01-06 |  | James Lloyd
Rev F | 2023-01-20 |  | James Lloyd
Rev G | 2023-02-03 |  | James Lloyd
DISCLAIMER
This document and its contents have been prepared and are intended solely for Ceri Jones information and use in relation to 'Innovation Matrix'
Faithful+Gould assumes no responsibility to any other party in respect of or arising out of or in connection with this document and/or its contents.
COPYRIGHT
The copyright of this document is vested in Faithful+Gould. This document may not be reproduced in whole or in part without their express written permission.
Formulas:
Date = [Date, row below]-14

## Information Used
Information Used & Assumptions
1 | Information Used
Design Drawings;
152481-STL-XX-XX-DR-A-PL_0003-Existing Site Plan
152481-STL-XX-00-DR-A-PL_011-Proposed Landscape Plan
152481-STL-XX-00-DR-A-PL_0103-Ground Floor Shell & Core
152481-STL-XX-01-DR-A-PL_0104-First Floor Shell & Core
152481-STL-XX-XX-DR-A-PL_0105-Roof Plan - Full Building
152481-STL-XX-XX-DR-A-PL_0201-Elevations GA
152481-STL-XX-XX-DR-A-PL_0202-Elevation Detail 01
152481-STL-XX-XX-DR-A-PL_0203-Elevation Detail 02
152481-STL-XX-XX-DR-A-PL_0301-Section
152481-STL-XX-XX-DR-A-PL_0501-Ground Floor Layout - Full Building
152481-STL-XX-XX-DR-A-PL_0502-First Floor Layout - Full Building
2 | General Assumptions;
External Works is excluded unless specifically identified within the cost plan.
Cavity Wall with no insulation is assumed.
Costs are based upon the information as provided.
We have assumed a project bank account will not be required for this scheme.
We have assumed that the area of works will be decanted for the project. No allowance is made for throughways or dealing with building occupants.
The exact nature of specification for internal doors, screens, folding partitions and finishes is assumed.
All costs are provisional awaiting design development.
All base costs are based on Q42022
3 | General Notes and Exclusions;
All included costs are subject to variation following design development.
Land Costs
A risk allowance of 10% is included for this estimate.
VAT is excluded from the estimate.
Works will be undertaken in a single phase.
Local Authority Fees
Building Regulation fees
Party Wall Awards
Acquisition & associated legals

## Summary Original
Project details: Innovation Matrix
Building Works Estimate
Based on GIA of: 1,950m2 |  |  |  |  | 1950
| Group Element | Element Type | Total | £/m2
| Group element 0 | FACILITATING WORKS | 205000 | 105.1282
| Group element 1 | SUBSTRUCTURE | 404250 | 207.3077
| Group element 2 | SUPERSTRUCTURE | 3032437.5 | 1555.0962
| Group element 3 | INTERNAL FINISHES | 184845 | 94.7923
| Group element 4 | FITTINGS AND FURNISHINGS | 0 | 0
| Group element 5 | SERVICES | 979307.5 | 502.209
| Group element 8 | EXTERNAL WORKS - Not Included within Scope of Works | 0 | 0
| Group element 9 | MAIN CONTRACTOR'S PRELIMINARIES | 828151.2 | 424.6929
Works cost estimate (sub total A) |  |  | 5633991.2 | 29809.4772
Location Factor Calculator
| Current TPI | 1.24
| Forecasted 2022 Q4 TPI | 1.284
5833907.0168
| Wales Location Factor | 0.85
4958820.9643
Prov Sums (sub total B)
| Internal Screens to Classrooms |  | 11600
| University Fittings, Furniture & Equipment Fit-Out |  | 150000
| External Works (Hard & Soft Landscaping) |  | 35000
196600
Base cost estimate A + B (sub total C) |  |  | 5155420.9643 | 29809.4772
Group element 13
| Design Contingency | Risk allowance @ 2.5% | 128885.5241 | 66.0951
| Construction Risk | Risk allowance @ 2.5% | 128885.5241 | 66.0951
| Employers Change Risk | Risk allowance @ 2.5% | 128885.5241 | 66.0951
| Other Mis. Risk | Risk allowance @ 2.5% | 128885.5241 | 66.0951
Total Risk allowances (sub total D) |  |  | 515542.0964 | 264.3806
Total Construction Cost (C + D) |  |  | 5670963.0607 | 2908.1862

## NRM1 CP template
Cost Plan for Innovation Matrix
NRM 1 phaseologies
Elemental Cost Plan
Elements in red are NRM1 Phraseologies
Ref. | Element | Timesing | Quantity |  | Unit | Rate | Sub-Total | Group-Total | Notes
[6 empty] | £ | £ | £
0 | Facilitating Works | [6 empty] | 205000
0.1 | Facilitating Works
0.1.2 | Demolition Works |  |  | 1 | nr | 150000 | 150000 |  | As per Query Sheet Nr 01
0.1.2 | Drainage Adaptions |  |  | 1 | nr | 55000 | 55000 |  | As per Query Sheet Nr 01
1 | SUBSTRUCTURE | [6 empty] | 404250
1.1 | Foundations |  | 28
|  |  | 77 | 2156
2156
1.1.1 | Raft foundations; simple reinforced concrete raft on poorer ground for development |  |  | 2156 | m2 | 187.5 | 404250 |  | Take-off attached under '01-Foundations' Spons Pg. 182
2 | SUPERSTRUCTURE | [6 empty] | 3032437.5
2.1 | Frame |  | 26
|  |  | 75 | 1950
1950
2.1.1 | Steel frame; suspended slab; permanent steel shuttering with 130mm thick concrete; no coverings or finishes |  |  | 1950 | m2 | 300 | 585000 |  | As per Query Sheet Nr 02
2.2 | Upper Floors |  | 562.86
178.91
|  |  | 510.64 | 1252.41
1252.41
2.2.1 | Precast concrete suspended floors; steel decking |  |  | 1252 | m2 | Incl. | Incl. |  | Included within Steel Frame Price
2.3 | Roof | 2 | 13.57
|  |  | 76 | 2062.64
2062.64
2.3.1 | Kingspan Box Profiled insulated Wall Panel KS1000 FCColour TBC. Shown RAL 8019 |  |  | 2063 | m2 | 450 | 928350 |  | Take-off attached under '04-Roofing' As per Query Sheet Nr 03
|  |  | 64 | 64
64
2.3.5 | Day-Lite Trapezodial Rooflight Plus KS1000 DLTR Plus Rooflights |  |  | 64 | nr | 3000 | 192000 |  | As per Query Sheet Nr 03
2.4 | Stairs & Ramps |  | 5 | [5 empty] | Number of flights
2.4.1 | Staircase; terrazzo finish; mild steel balustrades and handrails; plastered and decorated soffit |  |  | 5 | no | 10850 | 54250 |  | Spons Pg. 194
2.5 | External Walls
|  |  | 647.58 | [5 empty] | Perimeter Calculation
|  |  | 647.38 | [5 empty] | 8.3
|  |  | 68.17 | [5 empty] | 8.3
|  |  | 70.39 | 1433.52 |  |  |  |  | 11.65
|  |  |  | 1433.52 |  |  |  |  | 11.65
39.9
|  | 48 | 6.99
|  |  | 1.4 | 469.728
|  |  |  | 469.728 | DDT Window Openings
963.792
2.5.1 | 'Kingspan Box Profiled insulated Wall Panel KS1000 FCColour TBC. Shown RAL 8019 |  |  | 964 | m2 | 450 | 433800 |  | Take-off attached under '06-External Walls'
139.15
|  |  | 166.55 | 305.7
305.7
2.5.1 | Integrated Window Systems; Aluminium framed integrated window system |  |  | 306 | m2 | 550 | 168300 |  | Take-off attached under '07-Windows & External Doors' As per Query Sheet Nr 03
2.6 | Windows and external doors
|  | 48 | 6.99
|  |  | 1.4 | 469.728
469.728
2.6.1 | Integrated Window System; Aluminium framed intergrated window system; including - fixed glazing, top hung opening light, louver panel (colour matching to cladding) and solid insulated panel (colour match to cladding) |  |  | 470 | m2 | 550 | 258500 |  | Take-off attached under '07-Windows & External Doors' As per Query Sheet Nr 03
|  |  | 2 | 2
2
2.6.2 | Steel External Doors; Wheelchair Pass-Through access |  |  | 2 | nr | 2800 | 5600 |  | As per Query Sheet Nr 03
|  |  | 2 | 2
2
2.6.2 | Mechanical Revolving Door |  |  | 2 | nr | 15000 | 30000 |  | As per Query Sheet Nr 03
2.7 | Internal walls
|  | 12 | 8.24 | GF
|  |  | 3.8 | 375.744
|  | 1 | 63.09
|  |  | 3.8 | 239.742
|  | 1 | 8.45
|  |  | 7.6 | 64.22
|  | 1 | 8.45
|  |  | 7.6 | 64.22
|  | 13 | 8.25
|  |  | 3.8 | 407.55
|  | 1 | 45.22
|  |  | 3.8 | 171.836
|  | 2 | 33.76
|  |  | 3.8 | 256.576
|  | 2 | 2.89
|  |  | 3.8 | 21.964
|  | 1 | 6.23
|  |  | 3.8 | 23.674
|  | 1 | 8.84
|  |  | 3.8 | 33.592
|  | 1 | 8.95 | FF
|  |  | 3.8 | 34.01
|  | 6 | 9.6
|  |  | 3.8 | 218.88
|  | 1 | 18.1
|  |  | 3.8 | 68.78
|  | 1 | 8.85
|  |  | 3.8 | 33.63
|  | 1 | 18.2
|  |  | 3.8 | 69.16
|  | 1 | 8.95
|  |  | 3.8 | 34.01
|  | 1 | 9.19
|  |  | 3.8 | 34.922
|  | 11 | 8.22
|  |  | 3.8 | 343.596
|  | 1 | 33.21
|  |  | 3.8 | 126.198
|  | 2 | 2.91
|  |  | 3.8 | 22.116
|  | 2 | 33.76
|  |  | 3.8 | 256.576
|  | 1 | 15.07
|  |  | 3.8 | 57.266
2958.262
2.7.1 | 130mm thick partition; 70mm steel studs at 600mm centres generally; 2 layers 15mm Soundbloc board each side; joints filled with joint filler and joint tape; emulsion paint finish; softwood skirtings with gloss finish |  |  | 2958 | m2 | 85 | 251430 |  | Take-off attached under '08-Internal Walls & Partitions' 'Spons Pg. 203
|  |  | 185 | 185
185
2.7.2 | Balustrade and handrial with glass infill panels |  |  | 185 | m | 475 | 87875 |  | 'Spons Pg. 204
2.8 | Internal doors & screens
109
2.8.1 | Standard doors; cellular core; softwood architrave; aluminium ironmongery (latch only) Dingle leaf; moulded panel; gloss paint finish |  |  | 109 | nr | 342.5 | 37332.5 |  | Spons Pg. 206
58
2.8.5 | Internal Glazed Screens |  |  | 58 | nr | Prov Sum | Prov Sum
3 | INTERNAL FINISHES | [6 empty] | 184845
3.1 | Wall finishes
|  | 12 | 8.24 | GF
|  |  | 3.8 | 375.744
|  | 1 | 63.09
|  |  | 3.8 | 239.742
|  | 1 | 8.45
|  |  | 7.6 | 64.22
|  | 1 | 8.45
|  |  | 7.6 | 64.22
|  | 13 | 8.25
|  |  | 3.8 | 407.55
|  | 1 | 45.22
|  |  | 3.8 | 171.836
|  | 2 | 33.76
|  |  | 3.8 | 256.576
|  | 2 | 2.89
|  |  | 3.8 | 21.964
|  | 1 | 6.23
|  |  | 3.8 | 23.674
|  | 1 | 8.84
|  |  | 3.8 | 33.592
|  | 1 | 8.95 | FF
|  |  | 3.8 | 34.01
|  | 6 | 9.6
|  |  | 3.8 | 218.88
|  | 1 | 18.1
|  |  | 3.8 | 68.78
|  | 1 | 8.85
|  |  | 3.8 | 33.63
|  | 1 | 18.2
|  |  | 3.8 | 69.16
|  | 1 | 8.95
|  |  | 3.8 | 34.01
|  | 1 | 9.19
|  |  | 3.8 | 34.922
|  | 11 | 8.22
|  |  | 3.8 | 343.596
|  | 1 | 33.21
|  |  | 3.8 | 126.198
|  | 2 | 2.91
|  |  | 3.8 | 22.116
|  | 2 | 33.76
|  |  | 3.8 | 256.576
|  | 1 | 15.07
|  |  | 3.8 | 57.266
2958.262
3.1.1 | One mist and two coats emulsion paint |  |  | 2958 | m2 | Incl. | Incl. |  | Take-off attached under '08-Internal Walls & Partitions' 'Included within Internal Walls & Partitions Price
3.2 | Floor finishes | 1 | 1014.98
|  |  |  | 1014.98 | Open Space
|  | 4 | 11.83
|  |  |  | 47.32 | Plant Rooms
|  | 8 | 19.77
|  |  |  | 158.16 | Toilets
1220.46
3.2.1 | Flexible tiling; welded sheet or butt joint tiles; adhesive fixing; vinyl floor tiling; 2.00mm thick |  |  | 1220 | m2 | 17.15 | 20923 |  | Take-off attached under '11-Floor Finishes' 'Spons Pg. 209
|  | 1 | 830.96
|  |  |  | 830.96 | Ground Floor Lecture Rooms
|  | 1 | 4.3
|  |  |  | 4.3 | First Floor Lecture Rooms
835.26
3.2.2 | Carpet tiles; including underlay, edge gripper |  |  | 835 | m2 | 68.5 | 20923 |  | Take-off attached under '11-Floor Finishes' 'Spons Pg. 209
3.3 | Ceiling finishes | 1 | 830.74
|  |  |  | 830.74 | Ground Floor Lecture Rooms
|  | 8 | 19.77
|  |  |  | 158.16 | Toilets
|  | 1 | 923.08
|  |  |  | 923.08 | First Floor Lecture Rooms
|  | 1 | 744.34
|  |  |  | 744.34 | Open Area
2656.32
|  |  |  | 2656 | m2
3.3.1 | Armstrong suspended ceiling; mineral fibre; medium quality; Corline; concealed grid |  |  | 2656 | m2 | 53.5 | 142096 |  | Take-off attached under '12-Ceiling Finishes' 'Spons Pg. 210
|  | 4 | 19.12
|  |  |  | 76.48 | Plant Rooms
|  | 1 | 133.07
|  |  |  | 133.07 | Under First Floor Gantry/Suspended Walkway
209.55
|  |  |  | 210 | m2
3.3.2 | Emulsion paint to plaster; one mist and two coats. |  |  | 210 | m2 | 4.3 | 903 |  | Take-off attached under '12-Ceiling Finishes' 'Spons Pg. 210
| FITTINGS AND FURNISHINGS | [6 empty] | 0
4 | General fittings, furnishings and equipment
4.1 | Fittings, Furniture & Equipment Fit-Out |  |  | 1 | Nr | Prov Sum | Prov Sum
5 | SERVICES | [6 empty] | 979307.5
5.1 | Sanitary installations |  | 26
|  |  | 75 | 1950
1950
5.1.1 | Generally |  |  | 1950 | GIFA | 14.1 | 27495 |  | Spons Pg. 212
5.4 | Water installations |  | 26
|  |  | 75 | 1950
1950
5.4.1 | Mains Water Supply |  |  | 1950 | GIFA | 53 | 103350 |  | Spons Pg. 213
5.6 | Space Heating and Air Conditioning |  | 26
|  |  | 75 | 1950
1950
5.6.1 | Space Heating and Air Conditioning |  |  | 1950 | GIFA | 150 | 292500 |  | Spons Pg. 214
5.7 | Ventilation systems |  | 26
|  |  | 75 | 1950
1950
5.7.1 | Ventilation Systems |  |  | 1950 | GIFA | 23.25 | 45337.5 |  | Spons Pg. 214
5.8 | Electrical Installations |  | 26
|  |  | 75 | 1950
1950
5.8.1 | Electrical Mains and Sub-Mains Distribution |  |  | 1950 | GIFA | 167.5 | 326625 |  | Spons Pg. 214
5.1 | Lifts and Enclosed Hoists
5.10.1 | Passenger lifts (standard brushed stainless steel finish; 2 panel centre opening doors) |  |  | 2 | nr | 92000 | 184000 |  | Spons Pg. 215
9 | MAIN CONTRACTOR'S PRELIMINARIES | [6 empty] | 828151.2
| Main contractors preliminaries |  |  | 10 | % | 552100.8
| OHP |  |  | 10 | % | 276050.4
| SECTION SUB-TOTAL | [5 empty] | 828151.2
5633991.2
Note on I70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Due to External Walls being the same material as the roof, I've assumed the same rate as told in Query Sheet Nr 03.
Note on I216: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Included within Internal Walls & Partitions