## Data Entry
FAILURE MODE AND EFFECTS ANALYSIS
Item: | Weibel Tracking Radar |  |  |  | Responsibility: |  | All Operators & Inst Managers |  |  |  | FMEA number: | 1
Model: | MSL-60034 |  |  |  | Prepared by: |  | C.Budden |  |  |  | Page : | 1 of 2
Core Team: | Dynamic Instrumentation (QinetiQ) | [9 empty] | FMEA Date (Orig): | 2017-12-05 | Rev: |  | 1
Process Function | Potential Failure Mode | Potential Effect(s) of Failure | Sev | Class | Potential Cause(s)/ Mechanism(s) of Failure | Occur | Current Process Controls | Detec | RPN | Recommended Action(s) | Responsibility and Target Completion Date | Action Results
[12 empty] | Actions Taken | Sev | Occ | Det | RPN
Deployment of Radar | Incorrect position | Failure to track full trajectory | 8 |  | Incorrect judgement/ methodology | 6 | Current site set-up/ Operator judgement | 2 | 96 | Extensive training needed | Instrumentation Line Manager | Extended training course | 8 | 3 | 1 | 24
Set-up of Radar | Incorrect settings | Failure to track/ capture | 8 |  | Overlooked setting options | 4 | Standard operating porocedure/ competency | 8 | 256 | Re-assess/ Refresh on competency/ training |  | Re-assesment | 8 | 2 | 4 | 64
Converting/ Input Co-Ords | Mis-read figures | Projectile position error | 5 |  | Concentration | 2 |  | 4 | 40 | Confirmation sheet, 1 to 2 to double check |  | Check sheet & additional person | 5 | 1 | 2 | 10
|  | Incorrect results | 5 |  | Mis-written figures | 4 | Double checking, compare to previous | 2 | 40 | Compare 'look in angles' to guns L.O.F & Az |  | Extra check | 5 | 2 | 1 | 10
|  | Incorrect Radar look-in angle | 8 |  |  | 5 | Physically look at Radar look-in angle | 2 | 80 | Radar shouldn't exceed ± 2.5° in El & Az on first 'look in'. |  | Guideline added to S.O.P | 8 | 2 | 1 | 16
Calibration/ Align Radar | Overlooked/ forgetting | Inaccurate trajectory results | 5 |  | Pressure/ rushing | 6 | Training/ Standard operating procedure | 8 | 240 | Re-assessment/ Tick sheet |  | Re-assesment/ Checksheet | 5 | 2 | 4 | 40
Input of projectile data | Incorrect/ wrong data inputted | Wrong projectile trajectory data | 5 |  | Lack of communication | 4 | Communication/ confirmation | 4 | 80 | Radars projectile data to be formally written in work instruction |  | Data written into Instrumentation trial instruction | 5 | 2 | 2 | 20
Triggering of Radar | No trigger | No cature of trajectory | 10 |  | Lack/ overlooked trigger test | 1 | Collabetation in team/ S.O.P | 2 | 20 | Trigger test must be carried out in accordance to pre-firing checks |  | Mandatory check added to S.O.P | 10 | 0 | 1 | 0
| False trigger/ early trigger | Incorrect timings | 8 |  | Sun glare/ electrical interference | 2 | Training | 9 | 144 | Operator to determine current site set up & adjust accordingly |  | Extended training | 8 | 1 | 4 | 32
Measure projectile in flight | Loose track mid-flight | Partial data captured | 9 |  | Incorrect set-up | 5 | Training/ Standard operating procedure | 8 | 360 | Yearly re-assessment/ competancy check |  | Yearly refresher | 9 | 2 | 4 | 72
|  |  | 10 |  | Loose/ damaged connectors | 2 | Visual checks | 1 | 20 | Operator to report any damaged cables to electronic workshop |  | Visual check & reporting procedure | 10 | 1 | 0 | 0
| Noisy signal | Un-readable/ corrupt data | 8 |  | Multipathing | 5 | None | 6 | 240 | Unavoidable at long distances. Operator judgement |  | Notify T.M. & customer at low altitude detection | 8 | 2 | 3 | 48
|  |  | 9 |  | Obscurity/ Obstacles | 5 | None | 8 | 360 | Unavoidable at long distances. Operator judgement |  | Far obsticles to be reported, wildlife unavoidable | 9 | 2 | 4 | 72
Systems Engineering M6X00947_Q Christopher Budden P148323

## About This Template
This template was written for the American Society for Quality by
Stat Aids
Your feedback is welcome and encouraged. Please e-mail to:
Stat_Aids@yahoo.com