BA HONS in Leadership and Management Skills Level 5

Report – Assignment

Student Name: Ashfak Miah

Student ID: 2114741

Module Name: Managing Projects in the Organisation

Module Code: (BMSW5104_LON)

Lecturer Name: Olusegun Awolaran

Word Count: 2500

Submission date:

Contents

Executive Summary…………………………………………………………………………………………………………………………..1

Introduction………………………………………………………………………………………………………………………………………2

Project Scope…………………………………………………………………………………………………………………………………….3

Quad Chart………………………………………………………………………………………………………………………………………..4

Project Work Break Down Structure (WBS)……………………………………………………………………………………….5

Gantt Chart……………………………………………………………………………………………………………………………………….6

Stakeholders’ Analysis and Communication Plan………………………………………………………………………………7

Stakeholder Communication Plan…………………………………………………………………………………………………….8

Cost Analysis…………………………………………………………………………………………………………………………………….9

Evaluation………………………………………………………………………………………………………………………………………..10

Risk Management…………………………………………………………………………………………………………………………….11

Project Life Cycle……………………………………………………………………………………………………………………………..12

Conclusion……………………………………………………………………………………………………………………………………….13

Reference........…………………………………………………………………………………………………………………………………14

Appendices........………………………………………………………………………………………………………………………………15

- Executive summary:

Insights into the management plan titled "Onsite Catering Implementation to Decrease Congestion and Foster Healthy Living" are provided in the executive summary. According to Amponsah-Tawiah (2018), the purpose of this project is to cut down on the number of workers who go off-site for lunch. This will help alleviate pressure on the local transport system and encourage employees to make dietary choices that are more beneficial to their health. The plan calls for designated eating rooms, updated cooking facilities, and a selection of nutritious food alternatives all of which are included in the blueprint.

Through exhaustive research, the project's stakeholders have been uncovered, and rigorous engagement tactics will guarantee that they continue to support and participate in the initiative. Initial estimates of a project take into account resource distribution and budgetary considerations. A recent risk assessment identified many dangers and unpredictability’s in the situation. Gantt charts depict the project timetables, emphasizing milestones and critical path analyses. The work breakdown structure (WBS) of the project provides information about the tasks, subtasks, and projected deliverables of the project.

- Introduction:

Because it serves several objectives, such as providing a chance for staff employees and those working in the same department or organisation to engage in social and mental conversation, lunch break is considered by many organizations and organizations to be an essential component of a healthy work-life balance.

Because of the necessity of having a satisfying lunch, many employees often leave the premises of the business in order to have lunch, which results in a great deal of complications. In addition, members of the staff are returning to their respective departments after lunch breaks quite late, which contributes not only to poor job performance but also to extreme exhaustion and a general lack of interest in the workplace. This results in numerous members of staff being absent from work, which has a negative impact on the reputation of the organisation.

This project is a straightforward answer to the problem of how to prevent staff employees from leaving the office for lunch and cut down on absences. This idea displays an easy and free access to a canteen space for all of the workers inside the department, along with the ability to purchase nutritious food and drinks there.

- Project Scope:

This is the establishment of an on-site canteen at the work premises is to envision a comprehensive solution to address multiple aspects of employee welfare and operational efficiency. This initiative seeks to go beyond just by providing a dining space; it's about curating an environment that seamlessly blends nutrition, convenience, and community bonding.

The objective is by overarching a setup of an in-house canteen that serves timely, delicious, and nutritious meals. The goal isn't just to satiate hunger, but to provide energy and invigoration for the rest of the workday. Having this facility on-site will drastically reduce the time employees spend searching for food externally, thereby optimizing break durations and potentially improving overall productivity.

- Quad Chart:

A Gantt chart is a popular project management tool used to represent the timeline of a project. It displays project tasks against time, showcasing the start and finish dates of the terminal elements and summary elements of a project. It can be visually likened to a horizontal bar chart.

| Project Name: AJKAL Canteen for the workplace |  |
| --- | --- |
| Main Goals: - Improve staff productivity - Promote team bonding - Offer healthier food options | Potential Risks: - Overestimation of daily food requirements leading to wastage. - Unsatisfactory food quality or service - Potential initial resistance from employees used to eat out |
| Graphical Representation: - Pie chart showing anticipated division of initial costs (e.g., infrastructure 40%, kitchen equipment 30%, initial stock 20%, miscellaneous 10%). | Progress Summary: (This section will be updated regularly, e.g., "Successfully secured canteen space and finalized vendor contracts.") |

In essence, a Gantt chart serves as both a planning tool and a progress tracker, bridging the gap between the initiation and execution stages of a project. Its visual nature simplifies complex projects, making it an indispensable tool in modern project management.

- Project Work Break Down Structure (WBS):

A Work Breakdown Structure (WBS) is a hierarchical decomposition of a project into smaller, more manageable parts or tasks. Each level of a WBS represents an increased level of detailed definition of the project work.

|  | Work Break Down Structure | Start Date: |
| --- | --- | --- |
| Deliverables 1 |  | 01/10/2023 |
| Deliverables 2 |  | 10/10/2023 |
| Deliverables 3 |  | 11/10/2023 – 08/11/2023 |
| Deliverables 4 |  | 11/10/2023 – 24/10/2023 |

In essence, a WBS is foundational in project management. It transforms abstract project objectives into tangible tasks, serving as a roadmap that guides teams from initiation to completion, ensuring that nothing is overlooked and that every task aligns with the project's goals.

- Gantt Chart:

A Gantt chart is a popular project management tool used to represent the timeline of a project. It displays project tasks against time, showcasing the start and finish dates of the terminal elements and summary elements of a project. It can be visually likened to a horizontal bar chart.

In essence, a Gantt chart serves as both a planning tool and a progress tracker, bridging the gap between the initiation and execution stages of a project. Its visual nature simplifies complex projects, making it an indispensable tool in modern project management.

- Stakeholders’ Analysis and communicate Plan:

- Management:

- Role and Interest: Decision-makers responsible for providing the necessary approvals, oversight, and budget allocations. Their interest lies in the canteen's profitability, employee satisfaction, and its alignment with organizational goals.

- Communication Strategy: Formal channels such as monthly progress reports, quarterly performance reviews, and ad-hoc meetings for crucial decisions. Brief them on major milestones, potential roadblocks, and budgetary adjustments.

- Employees:

- Role and Interest: Primary patrons of the canteen, their experience directly affects their satisfaction and indirectly, their workplace productivity. They are keen on food quality, variety, and affordability.

- Communication Strategy: Engage them right from the onset. Use digital platforms or suggestion boxes for continuous feedback. Conduct initial surveys to understand their preferences and organize periodic feedback sessions to fine-tune the canteen offerings.

- Vendors:

- Role and Interest: Key partners in delivering food and other essential services. Their consistent performance and reliability are crucial. They seek timely payments, clear communication, and long-term partnerships.

- Communication Strategy: Establish clear terms of engagement. Regular operational meetings to ensure aligned goals, and bi-annual or annual performance reviews to assess quality, reliability, and areas of improvement.

- Facility Management:

- Role and Interest: They're in charge of the canteen’s physical space, infrastructure, and amenities. Their interest revolves around the efficient utilization of space, safety standards, and maintenance.

- Communication Strategy: Maintain open lines of communication. Weekly check-ins during the setup phase transitioning to monthly coordination meetings. Immediate escalation channels for urgent issues related to infrastructure or safety.

Successful stakeholder involvement and communication are key for Ajkal Canteen. The canteen may promote cooperation, foresee issues, and adapt to changing demands by knowing and resolving stakeholder interests and concerns.

- Stakeholder Communication Plan:

In the field of management, a strategy to maintain openness will be implemented by means of monthly progress reports and quarterly performance assessments. Furthermore, we will convene impromptu gatherings to deliberate on crucial determinations, aiming to guarantee that participants possess comprehensive knowledge about project milestones, fiscal stability, and forthcoming obstacles.

The employees, being the key beneficiaries, would be provided with outlets via which they may express their thoughts and provide feedback. By using digital platforms, suggestion boxes, and periodical surveys, our objective is to get insight into the eating preferences of our customers and make necessary adaptations to our services.

Effective communication is crucial when dealing with vendors. Regular operational meetings will be scheduled to ensure alignment in aims and service expectations. In addition, the implementation of bi-annual or yearly performance evaluations may serve as a valuable tool for evaluating the quality of service and identifying opportunities for mutual development.

Finally, in the context of Facility Management, the commencement phase requires regular weekly evaluations to ensure that all aspects are progressing as intended. Following the initial setup, regular monthly coordination meetings will be crucial in order to engage in discussions pertaining to space utilisation, safety requirements, and any necessary maintenance tasks.

- Cost analysis:

Gaining a comprehensive understanding of expenses is crucial for Ajkal Canteen to operate with optimal efficiency and achieve profitability. This analysis provides a fundamental examination of the methodology used to deconstruct and comprehend the financial outlays associated with the canteen.

- Costs of Ingredients:

- Food and supplies cost money.

- Plan: Buy in bulk and use things that are in season.

- Costs of doing business:

- Costs for rent and electricity.

- Tip: Check your tools often so you don't have to pay a lot to fix it.

- Costs of labor:

- How much we pay our workers.

- Tip: Set up your schedule well, especially during slow times.

- Costs of marketing:

- Set aside money for ads and marketing.

- Use online ads to get a better deal.

- Unplanned Costs:

- Set aside money for things that might go wrong, like tools.

The Significance of This Matter:

By gaining knowledge on the allocation of financial resources, Ajkal Canteen can enhance its decision-making process, identify potential cost-saving measures, and strategically allocate funds towards chances for expansion and development. The use of cost analysis is crucial in maintaining the financial stability of the canteen, therefore enabling it to efficiently provide to its clientele.

- Evaluation:

It is vital to conduct an effective assessment of the canteen programme in order to guarantee alignment with the company's objectives and the happiness of the workforce. As you can see in the bullet points below, there is some virtual information that we must follow in order to keep the canteen running well.

- Quantitative Metrics:

- Utilization Rate: Measure daily employee usage to gauge acceptance and potential areas for promotion.

- Cost-effectiveness: Monthly reviews will analyze expenses against the allocated budget, with specific metrics such as cost-per-meal to guide decision-making.

- Food Wastage: Aim to maintain wastage rates below a predetermined threshold (e.g., 5%).

- Qualitative Metrics:

- Employee Satisfaction Surveys: Quarterly surveys will assess feelings towards food quality, ambiance, and service.

- Feedback Mechanism: An accessible portal or kiosk for real-time feedback allows immediate identification of areas needing improvement.

- Reviews: Engage stakeholders periodically to discuss challenges and bottlenecks from a functional perspective.

- KPI Monitoring: Regularly track Key Performance Indicators, such as Employee Satisfaction Rate, budget adherence, and food wastage, to guide decision-making.

- Benchmarking: Position the canteen's performance against industry standards to identify areas of strength and those requiring enhancement.

The continuation of the review, using a mix of qualitative and quantitative metrics, will play a critical role in ensuring that the canteen is effectively operated and that it aligns with Akjal's commitment to the well-being and operational excellence of its employees. These five criteria will be used in the evaluation.

- Risk Management:

Ajkal Canteen must pay close attention to risk management if it wants to ensure that its operations run smoothly, protect its reputation, satisfy its clients, and maintain its profitability. The canteen operates in an environment that is always changing and is shaped by factors such as the reliability of its suppliers, the preferences of its customers, and the effectiveness of its operations. As you can see down below, I have summarized in bullet points some of the most significant reasons why effective risk management is essential.

- Risk Identification:

- Potential risks: Spoiled ingredients, late supplier delivery, equipment breakdown, health and safety concerns, and unpredictable client footfall are all issues.

- Methods: Inspections on a regular basis, consumer feedback, and supplier assessments.

- Risk Assessment:

- Goals: Understand the possible impact and likelihood of identified hazards on canteen operations.

- Outcome: A prioritized list of hazards, from the most critical to the least significant.

- Risk Response Planning:

- Strategies:

- For spoiled ingredients: Maintain stringent quality checks, use first-in-first-out methods.

- For equipment malfunctions: Regular maintenance schedules, keeping backup equipment.

- For health and safety: Training staff on hygiene practices, ensuring cleanliness.

- For fluctuating customer footfall: Diversify menu, offer promotions.

- Risk Monitoring & Control:

- Goals: Track and appraise the identified risks as well as the effectiveness of mitigation actions on an ongoing basis.

- Outcome: Risk assessments, allows to revised tactics, and the lessons gained will make massive effect on a regular basis.

- Risk Closure:

- Goals: Document the outcomes and tactics utilised when a risk has been handled or is no longer relevant.

- Outcome: A collection of risk experiences that may be used to direct future risk management initiatives.

In the context of Ajkal Canteen, the proactive management of risks encompasses not only the prevention of losses but also the strategic utilization of possibilities. By proficiently detecting and mitigating possible challenges, the canteen can guarantee client contentment, minimize operational disruptions, and preserve a favorable reputation within the community. In a highly competitive food-service industry, effective risk management practices can serve as a distinguishing factor, leading to increased customer loyalty and improved financial performance.

- Project Life Cycle:

The Project Life Cycle is a systematic method for taking an idea from conception to completion with maximum efficiency, effectiveness, and positive results.

- Initiation:

- Goal: Define the project's purpose and feasibility.

- Outcome: Project Charter or basic initiation document.

- Planning:

- Goal: Set the project's roadmap.

- Outcome: Detailed Project Management Plan.

- Execution:

- Goal: Implement the plan to achieve project outcomes.

- Outcome: Project deliverables.

- Monitoring & Controlling:

- Goal: Track project's progress and make adjustments.

- Outcome: Regular status updates and revised plans if needed.

- Closure:

- Goal: Finish the project and evaluate performance.

- Outcome: Project closure report with insights.

- Conclusion:

The establishment of the Akjal canteen is not only a choice made for logistical reasons; rather, it is a demonstration of the company's dedication to its staff members. There is an old proverb that states, "The way to a person's heart is through their stomach." This canteen, which will become more than simply a place to eat, will become a cornerstone of Akjal's cafeteria, bringing employees together and highlighting the significance of well-being and shared experiences in the workplace. Not only will Ajkal be providing meals, but they will also be fostering a culture within the organisation that is healthier, more cohesive, and more productive. This will be accomplished via careful planning and execution.

This is not only an assessment; rather, it is a one-time action that is part of an ongoing process. It guarantees that the canteen continues to be a cherished asset for Akjal and aligns with the company's dedication to the well-being of its employees, the development of community, and the improvement of operational efficiency. The canteen's continued performance may be ensured via the utilisation of periodic reviews in conjunction with both reactive and proactive initiatives.

- References:

- Amponsah-Tawiah, K. (2018) ‘Socio-cultural practices and health and safety behaviors among Ghanaian employees’, Occupational Health and Safety - A Multi-Regional Perspective, pp. 104–114. doi:10.5772/intechopen.75821.

- Reilly, K.L. et al. (2018) Economic Analysis of three interventions of different intensity in improving school implementation of a government healthy canteen policy in Australia: Costs, incremental and relative cost effectiveness - BMC public health, BioMed Central. Available at: https://bmcpublichealth.biomedcentral.com/articles/10.1186/s12889-018-5315-y (Accessed: 20 August 2023).

- Work breakdown structure (no date) workbreakdownstructure.com. Available at: https://www.workbreakdownstructure.com/ (Accessed: 24 August 2023).

- Asana (no date) Asana timeline: Create and View Project Timelines • Asana, Asana. Available at: https://asana.com/go/timeline?&utm_campaign=NB--EMEA--UK--EN--Gantt_Chart-Timeline&utm_source=google&utm_medium=pd_cpc_nb&gad=1&gclid=EAIaIQobChMIh6ec5572gAMVwIlQBh2EEgbpEAAYASAAEgK97_D_BwE&gclsrc=aw.ds (Accessed: 21 August 2023).

- Patanakul, P., Iewwongcharoen, B. and Milosevic, D. (2010) ‘An empirical study on the use of project management tools and techniques across project life-cycle and their impact on Project Success’, Journal of General Management, 35(3), pp. 41–66. doi:10.1177/030630701003500304.

- Wang, S.Q., Aguria, M.Y. and Dulaimi, M.F. (2010) Risk management framework for construction projects in developing, Taylor & Francis Online. Available at: https://www.tandfonline.com/doi/abs/10.1080/0144619032000124689 (Accessed: 19 August 2023).

- Appendices: