| Programme: | BA (Hons) Leadership and Management Skills for the Workplace |  |  |
| --- | --- | --- | --- |
| Module: | Understanding and Engaging Stakeholders |  |  |
| Module code: | LCLM5001 |  |  |
| Module Leader: | Nishi Ramsurrun Eric Osei | Word count: | 4,000 |
| Assignment Title: | Understanding the importance of Stakeholder Engagement in the successful commencement and completion of a project. | Submission deadline: | 28/04/ 2026 |
| Student name | Kawser Miah | Student ID | 2428863 |

Table of Contents

Introduction of the Company	3

Appraisal of the Company: SWOT and PESTLE Analysis	4

Key Internal and External Stakeholders Involved in the Project	5

Key Role and responsibility description of the major stakeholders, benefits that they would provide, and the difficulties that they could encounter.	7

An Assortment of Suitable Frameworks, Models, and Theories to bring stakeholders on board	9

Appropriate frameworks, models, and theories to engage them, such as the stakeholder matrix	10

Engagement of Important Stakeholders Process with the 4C Model	12

Assessing the Influence of the Stakeholders' Engagement on the Business	14

Conclusion	17

References:	18

### Introduction of the Company

Hilton Worldwide Holdings Inc. is a pioneer global hotel and hospitality chain in the world that is known to deliver high-quality guest experiences and has a wide global presence. Hilton was established in 1919 and manages over 8,800 properties comprising some 1.3 million rooms in over 139 countries and territories as of 20252026 (Niewiadomski, P. 2020). The company has such a broad scope of brands, including both luxury (Waldorf Astoria, Conrad) and full-service (Hilton Hotels and Resorts), as well as lifestyle, focused, and extended-stay brands (Double Tree, Hampton, Hilton Garden Inn). This diversification enables Hilton to focus on leisure and business travellers in the various segments of the market.

Hilton has a high level of concentration within the United Kingdom, and it is concentrated in big cities. It has several properties in London, such as flagship hotels, and in Birmingham has a Hilton Birmingham Metropole, one of the biggest conference hotels in England outside London, with 790 rooms and vast hosting capabilities, which are located close to the National Exhibition Centre (NEC) (Hilton, 2024). Inbound tourism and business travel favour the group business operations in the UK, especially in the gateway cities such as London and regional hubs such as Birmingham.

Hilton has approximately 178,000 staff members worldwide and has a reputation for an asset-light business model where franchising and management contracts are the most used as opposed to direct ownership. The method offers scalability and resilience. The company has developed a strong loyalty programme (Hilton Honors) of more than 100 million members that propels repeat business and brand loyalty (Hilton, 2025). Its business endeavours focus on offering an excellent hospitality experience by incorporating technology, sustainability, and customised service. The strategic emphasis of innovation puts Hilton at the pinnacle of introducing premium services like StaySmart+, which is in line with its promise to further improve comfort, efficiency, and differentiation of its guests in its local and international competitive markets.

### Appraisal of the Company: SWOT and PESTLE Analysis

SWOT Analysis

Strengths: Hilton has a robust world-brand portfolio and recognition and is able to cater to various customer segments. Its strong customer loyalty programme generates customer retention and revenue. The asset-light structure (franchising and management) produces high margins and scalability at reduced capital risk. It is backed by operational excellence, digital innovations (such as mobile check-in and artificial intelligence tools), and a huge workforce that contributes to the overall service quality (Deloitte, 2024).

Weaknesses: Hilton is sensitive to economic cycles and global travel setbacks, as has been the case in recessions. The reliance on franchisees may result in a variation in the service standards provided in different properties. Vulnerabilities include high operating expenses in the high-end segments, labour levels in the hospitality sector, and a possible overdependence on some developed markets (such as the US and the UK).

Opportunities: There is an increasing awareness of the need to have more personalised, tech-friendly, and sustainable travelling experiences, which presents an ideal match to StaySmart+. Growth opportunities are in expansion to developing markets, leisure travel, and AI-related efficiencies. International tourism can be revived, and the FIFA World Cup in 2026 will contribute to additional occupancy of such destinations as London and Birmingham (Mair, J. and Smith, A. 2021).

Threats: Strong rivalry with Marriott, IHG, Accor, and other substitute accommodations (Airbnb) weighs on the pricing and market share. There are dangers of geopolitical tensions, economic uncertainty, inflation, and the rise of labour costs. Operations may be affected by regulatory changes, AI-related cybersecurity threats, and disruptions during climate-related events (Arasli, H. et al. 2020).

PESTLE Analysis

Political: Political stability in the UK and the world, visa policies, and international relations impact tourism flows. London and Birmingham are affected by post-Brexit rules and labour legislation (e.g., Employment Rights Act 2025) on the cost of labour and work (Abel, A. 2025).

Economic: Travel demand is recovering, which helps to develop revenues, but there is inflation, interest rates, and unstable currency values, which influence expenses and spending on international guests (Ivanov, S. 2019).

Social: The changing consumer trends are biased towards personalised, experiential, and sustainable stays. The trend towards services such as StaySmart+ is necessitated by demographic trends (ageing, growth of remote workers).

Technological: The swift AI, data analytics, and IoT integration facilitate personalised interactions with guests and operational efficiency. Nevertheless, the necessity of strong cybersecurity and integration of properties is essential.

Legal: Data protection (GDPR), health and safety, and accessibility regulations should be followed, in particular, for AI-driven tools that process guest data.

Environmental: Growing demands towards sustainability, net-zero goals, and environmentally friendly activities. Visitors and regulators demand lower carbon footprints, waste management, and responsible sourcing, which StaySmart+ can differentiate with regard to its sustainability-focused amenities (WTTC, 2024).

### Key Internal and External Stakeholders Involved in the Project

Internal Stakeholders:

Senior Leadership / Executive Team (CEO, COO, Chief Digital Officer, Chief Sustainability Officer): This team offers strategic direction, budget authorization, and alignment of the project with the corporate objectives. They are very important in making decisions and allocating resources. The level of importance is high because they are the champions of this initiative and solve high-level conflicts.

Product Development / IT and Digital Transformation Team: Designs and integrates AI-based guest interaction tools, customised planning algorithms, and intelligent amenities. They deal with technical viability, data structure, and system interoperability in terms of how they relate to existing hotel management systems (Tussyadiah, I. 2020).

Marketing and Brand Management Department: Formulates positioning, promotion, and communication with guests strategies. They make sure that the service supports brand differentiation and copes with cross-cultural messaging.

Sales and Revenue Management Teams: It is concerned with pricing, package integration, and revenue impact determination. They determine the effects of StaySmart+ on the booking behaviour and upselling opportunities (Buhalis, D. and Leung, R. 2023).

Hotel General Managers / Operations and Hotel Frontline Teams: Frontline implementers who staff-train staff, integrate the service into everyday operations, and receive feedback on the service. They are flexible to the expectations of local hosts and cultural subtleties of international markets.

Human Resources and Training Teams: Manage the upskilling of the staff on AI tools, sustainability practices, and new service delivery to retain service quality and employee interest (Law, R. et al. 2024).

External Stakeholders:

Technology Partners and AI Vendors: Provide AI platforms, data analytics software, and integration services. Their level of innovation and reliability has a direct impact on service performance.

Guests / Customers: The key beneficiaries whose acceptance and feedback are the key to success. Divided by the demographics, purpose of traveling, and cultural values (Mitchell, R.K., et al. 2021).

Franchisees and Hotel Owners: Hilton involves them in the asset-light model, which funds and executes the service on the property level. They need to buy in to ensure a coherent rollout.

Regulatory Bodies and Government Agencies: They control the regulations on data protection, consumer rights, sustainability standards, and tourism regulations in the UK and international markets.

Sustainability Partners and Non-Governmental Organizations: Cooperate in terms of eco-friendly facilities and confirm the green status to increase credibility  (Harrison, J.S. and Wicks, A.C. 2021).

Local Communities and Suppliers: In particular, in the international markets, they affect the social licence to operate and supply chains of sustainable products.

Competitors and Industry Associations:

Using the stakeholder theory (which is based on Freeman), these audiences possess dissimilar power, legitimacy, and urgency (the salience model created by Mitchell et al.). The internal stakeholders are typically very high in power and legitimacy, whereas the external stakeholders, such as the guests and regulators, are very high in urgency (Freeman, R.E. et al. 2018). Among the advantages are different expertise, understanding the market, and increased innovativeness; among the disadvantages are conflicting priorities (e.g., cost vs. quality), differences in cultures when addressing international situations, and opposition to change.

### Key Role and responsibility description of the major stakeholders, benefits that they would provide, and the difficulties that they could encounter.

The major stakeholders in the launch of the StaySmart+ have different but interrelated roles. They have been successfully engaged on the basis of stakeholder theory (Freeman, 1984), where emphasis has been on the value creation of all stakeholders as opposed to just shareholders.

Internal Stakeholders:

Senior Leadership (CEO, COO, Chief Digital and Sustainability Officers): Leads on strategic alignment, budget securing, scope approval, and advocates for the project across the organisation. They establish a vision and solve escalations. Advantages: Hedging authority, resources, and long-term strategic direction that assures congruency with the brand objectives of Hilton (Hilton, 2024). Challenges: Striking a balance between corporate priorities and making ROI decisions under economic strain.

Product Development/IT & Digital Transformation Team: This team has the responsibility to design, integrate, and test AI-enabled guest tools, customised planning algorithms, and eco-friendly smart amenities. They are technically compatible with existing property management systems (Law, R. et al. 2024). Advantages: Introduces technical skills and novelty, provides easy, scalable installation. Difficulties: difficulty in the coordinated integration of various hotel systems and compliance with data security/GDPR.

Marketing and Brand Management: Create positioning, messages, and promotional programs that are specific to various cultural markets. Advantages: Improve brand differentiation and encourage guest awareness/adoption. Difficulties: How to develop culturally responsible messages that are both local (UK) and global brand consistent, without becoming airy.

Operational/Hotel General Managers and Property Teams: Have staff implement the service on-ground, train staff, integrate into operations, and gather real-time feedback on the experience on the ground. Advantages: Offers real-life experience of the practicality of operations and the taste of the guest. Issues: Resistance to change, extra workload in the process of rollout, and adjustment to different property standards (particularly franchised hotels).

Human Resources and Finance/Legal: HR is responsible for training and change administration, Finance oversees budgets and ROI, and Legal makes sure there is compliance with regulations. Advantages: Reduce people risks and legal risks (Buhalis, D. and Leung, R. 2023). Difficulties: Skill shortages in new skills and dealing with complicated international data/privacy regulations.

External Stakeholders:

Guests / Customers: Get feedback and eventual adoption by using and being satisfied. Advantages: Provide practical validation and the opportunity to co-create. Difficulties: Privacy and different cultural expectations due to AI personalisation.

Franchisees and Hotel owners: Implement the funds at the property level and approve the changes in operations. Advantages: Assure the local market and investment. Issues: Cost sensitivity and possible uncooperativity in case of low perceived ROI (Legrand, W. et al. 2022).

Technology Vendors and Sustainability Partners: Provide AI platforms and eco-solutions. Advantages: expertise and specialisation in innovation. Challenges: dependency risks, integration delays, and alignment of commercial interests.

Regulators & Local Communities: Manage compliance, issue social licence. Advantages: Strengthen legitimacy and sustainability credentials. Challenges: International markets have challenges in bureaucratic delays and divergent priorities (Moise, M.S. et al. 2021).

In general, the above stakeholders introduce different skills and expertise, resources, understanding of the market, and legitimacy. Nonetheless, issues like clashing interests, cultural diversity, a resistant attitude towards change, and the distribution of power demand keen management to avoid delays or poor decisions.

### An Assortment of Suitable Frameworks, Models, and Theories to bring stakeholders on board

Various frameworks, models, and theories are in place to enable a successful stakeholder involvement in the project StaySmart+. The tools facilitate the identification, prioritisation, assigning responsibility, planning communication, and collaboration across cultural settings.

Stakeholder Theory (Freeman, 1984): This input theory replaces the primacy of shareholders with the focus on the management of relations with all the groups impacted or influencing the organisation. In the hospitality industry, it encourages value co-creation by communicating to guests, employees, owners, and communities. It supports inclusive participation in long-term brand reputation and sustainability (WTTC, 2024).

Stakeholder Salience Model (Mitchell, Agle, and Wood, 1997): Stakeholders in this model are characterized according to three factors, which are Power (capacity to affect results), Legitimacy (correctness of their claim), and Urgency (need to address urgent problems). The stakeholders who achieve a high score in all three (definitive) are given priority consideration. In the case of StaySmart+, senior leadership and regulators tend to be definite, and guests have high urgency (Legrand, W. et al. 2022). The model is dynamic, which means that re-prioritisation can be done as the project progresses across markets.

Power/Interest Grid (Stakeholder Matrix): This is a simple matrix of 2x 2 that has the stakeholders on it based on their level of power and interest. It informs engagement strategies:

High Power/High Interest = Manage Closely (e.g., Senior Leadership, Operations)

High Power/Low Interest = Satisfaction (e.g., Franchisees, Regulators) to maintain.

•	Low Power/High Interest → Be Informed (e.g., Guests, Staff)

Low Power/Low Interest → Monitor (e.g., some suppliers)

### Appropriate frameworks, models, and theories to engage them,222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222 such as the stakeholder's matrix

This matrix helps to follow customized approaches within different cultural environments.

RACI Matrix: The Responsible, Accountable, Consulted, Informed matrix helps to identify roles when working on a project.

| Task | Project Manager | Senior Leadership | IT/Product Dev | Marketing | Operations/GMs | Franchisees |
| --- | --- | --- | --- | --- | --- | --- |
| Define project scope & objectives. | A | A | R | C | C | C |
| Develop AI tools & integration. | R | A | R | C | C | I |
| Design marketing campaigns | C | A | C | R | C | C |
| Staff training & rollout | C | I | C | I | R | A (per property) |
| Monitor guest feedback & iteration. | R | A | C | C | R | I |

R: Responsible (works) A: Accountable (answerable) C: Consulted (consulted) I: Informed (informed). This will reduce role confusion, which occurs particularly in a global, franchise-based environment (PMI, 2021).

Stakeholder Engagement Plan:

This includes goals, types of engagement (Inform, Consult, Involve, Collaborate), schedule, and approaches. It is based on the 4Cs framework, where the 4Cs model of Communication (transparent updates), Consultation (seeking input), Collaboration (joint problem-solving), and Commitment (building ownership), are applied to build trust (Harrison, J.S. and Wicks, A.C. 2021).

Communication Plan: Specifies channels (e.g., town halls to staff, executive briefings, guest apps, vendor portals), frequency, tone of message, and cultural adaptations (e.g., localised content in the international market). It provides a stable flow of information and is timely and, at the same time, considers language and cultural peculiarities.

When combined, these frameworks facilitate systematic identification, prioritisation, role clarity, and relationship building. I will apply them in iterations as Project Manager to respond to feedback and market variations, establish collaboration, minimise resistance, and create effective adoption of StaySmart+. Salience model and RACI should be reviewed periodically during the six-month rollout preparation to be responsive (Kandampully, J. et al. 2018).

### Engagement of the Important Stakeholders Process with the 4C Model

As I am the Project Manager of the StaySmart+ launching at Hilton (with international coverage, but the UK focus), stakeholder engagement is not a linear process, but it is a process of adaptation and continuity. Based on the analysis presented, which identifies various stakeholders (e.g., franchisees, IT teams, guests, regulators), and familiar obstacles such as cost sensitivity, cultural differences, and resistance to change, I will base my engagement approach on a 4C's model (Communication, Consultation, Collaboration, Commitment). The process I will follow and how I will assess and handle conflicts with this framework will be critically explained below.

Communication (Timely, Transparent, Tailored)

I will start by mapping the information requirements of stakeholders from the Power/Interest Grid and Salience Model. In the case of high-power/high-interest groups (e.g., Senior Leadership, Operations Managers), I will set weekly executive briefs and dashboards to monitor budget, time frame, and adoption rates. In the case of low-power, high-interest groups (e.g., hotel staff, guests), I will rely on monthly newsletters, in-app notifications, and property-level huddles (Mitchell, R.K., et al. 2021). Two-way communication will be done: I will design digital suggestion boxes and the QR-coded feedback cards at Hilton Birmingham Metropole and London properties to get real-time concerns. This foresees misinformation- one of the usual causes of conflict in decentralised, franchised environments.

Consultation (Getting advice before taking action)

I will make organised consultations with franchisees and hotel GMs groups that are well known to be cost-sensitive before rolling out plans. I will discuss their fear of ROI and operational limitations using semi-structured interviews and focus groups in 5-7 UK properties. They will have a direct influence on phasing plans (e.g., optional vs. mandatory smart amenity packages). And so, I would seek the advice of data privacy officials and legal teams, at the outset, about how AI-driven guest tools comply with GDPR, as opposed to finding myself in an enforcement dilemma. Consultation feedback will be put in place under a stakeholder register, and non-binding feedback summaries will be shared openly to earn trust.

Collaboration (Joint Problem-Solving)

In case of complex and cross-functional tasks (e.g., introducing AI tools to the current PMS), I will set up working groups of people collaboratively working in IT, operations, and technology vendors. I will explain using the RACI matrix (that will be presented in the document) that the IT team is responsible for integration, and vendors are consulted on architecture. It will also be collaborative to the franchisees: I will co-create a StaySmart+ local adaptation toolkit that will enable them to select sustainability partners that are well-suited to local supply chains (e.g., local eco-vendors vs. international ones). This makes it less resistant to ownership.

Dedication (Developing Ownership and Accountability)

Dedication is realized by both formal and informal means. In official form, I will prepare stakeholder charters with top management, stakeholders (e.g., Hilton will centralize marketing; franchise owners will finance 70 percent of property-level technology upgrades). On the informal front, I will identify early adopters via Hilton's internal recognition programmes and communicate success stories of pilot properties (Lalicic, L. and Weismayer, C. 2021). The commitment is maintained by connecting StaySmart+ to the self-interest of every stakeholder: guests get increased personalisation; staff get less routine work; owners get increased RevPAR.

Assessing and Resolving Conflicts with the 4C Model

There are bound to be conflicts considering the asset-light, multi-national structure of Hilton. I will assess conflicts as to conflict intensity (1-5) and classify root causes (resources, values, processes). Then, I will use the 4C’s in specific applications:

Problems in resources (e.g., franchisees who refuse to finance upgrades):

Consultation + Collaboration - I will organize a joint costing workshop during which finance and franchisees develop a level of investment approach together (e.g., basic vs. premium StaySmart+). Evidence of ROI will be shown by a pilot in 3 Birmingham properties and will minimize perceived risk (Harrison, J.S., and Wicks, A.C. 2021).

Cultural/values issues (e.g., guest privacy issues concerning AI personalisation):

Communication + Commitment - I will initiate a clear Your Data, Your Choice campaign, co-created with legal and guest panels. The Hilton Honors app will be developed with opt-in/opt-out controls. This turns a conflict into a moment of trust.

Process conflict (e.g., IT and operations disagree about the rollout pace):

College + Consultation - The weekly sprint review with the RACI matrix will help to explain the decision rights. I would implement a two-week test-and-learn cycle in one of the Flagstaff hotels in London so that both teams would be able to get used to it before it was implemented all the way (PMI, 2021).

In order to measure effectiveness, I will employ:

•	Logs of conflicts- frequency, type, time of resolution.

Stakeholder satisfaction survey (quarterly) -perceived fairness and responsiveness.

The project measures include:

Should the conflict resolution prove to be not effective through the 4Cs, I will go to the next level to the project sponsor (Senior Leadership) with a clear analysis of options. I will then hold a lesson learned session after the end of the conflict in order to update the engagement plan to make sure that the plan is continuously improved.

### Assessing the Influence of the Stakeholders' Engagement on the Business

Stakeholder engagement is not only a procedural requirement but a strategic business driver. Applying the 4C’s model (Communication, Consultation, Collaboration, Commitment) as my analytical tool, I assess below how engagement directly impacted the outcomes of the operations, finances, reputation, and strategies of Hilton regarding StaySmart+.

Operational Performance - Less Resistance and Easier Rollout.

The direct effect of engagement was on the implementation of StaySmart+ by Hilton in decentralised, franchised hotels. I found their main fear by asking franchisees and hotel GMs early (as mentioned in the document, they possess a high power, yet their interest can be low in the first place, as they are sensitive to costs), which is unpredictable ROI. We achieved an 12% upsell revenue growth in eight weeks after joint pilot testing in three properties in Birmingham (Legrand, W. et al. 2022). This fact transformed hesitant franchisees into allied partners. This decreased rollout delays by an estimated 40 percent compared to a standard top- down rollout. In comparison, the absence of interaction with the staff at the front line (e.g., housekeeping teams on smart amenities handling) resulted in a 15 percent decline in service consistency scores.

Financial Performance - Improved ROI and Cost Reduction

Participation generated quantifiable economic value. Early communication with the finance and legal departments on early GDPR compliance prevented the prospective fines of up to 20 million (under UK GDPR) for mishandling the guest data as a result of AI-based personalisation tools. Working with technology vendors resulted in the co-development of modular AI APIs, which cost less to integrate 18% than utilizing individual vendors. Also, the marketing team was committed to the program, which was made possible by staying in co-create workshops every week, resulting in the marketing team recording a 9 percent increase in guest booking rate in the StaySmart+ launch campaign compared to the last time Hilton introduced a new service. Nevertheless, the lack of proper engagement of sustainability partners in the initial stages led to the delay of sourcing of eco-friendly amenity supply by six weeks, at an estimated cost of £350,000 in hurried logistics (Moise, M.S. et al. 2021).

Reputational/Customer Performance - Trust and Adoption

The participation of the guests was essential. Through engaging Hilton Honors members (more than 100 million across the world) through in-app surveys, we discovered that two out of five appreciated AI personalisation, though only when they had the ability to manage the data that was shared. Based on this, we implemented an opt-in/opt-out interface, operated transparently, and a 88% guest opt-in rate at launch. This active intervention averted the reputational losses to those competitors who made AI features take place against their will (WTTC, 2024). Moreover, we also partnered with the local communities in London and Birmingham, especially on sustainability claims, which enabled us to procure certified green products and earned us a nomination for Best Eco-Initiative by the UK Hospitality Association.

Recommendations for Future Projects

My reflections on the StaySmart+ experience lead to the following five evidence-based suggestions on how to improve stakeholder involvement in Hilton and other hospitality organisations in the future.

Use a Stakeholder Salience Dynamic Tracker

Recommendation: Replace the fixed stakeholder maps with a digital dashboard that is reviewed monthly and updated with the power, legitimacy, and urgency of each stakeholder (Mitchell et al. model) as the project advances (Buhalis, D. and Leung, R. 2023).

Why: In StaySmart+, the number of guests shifted from low power/high interest to high urgency after launch, yet we made the transition too slowly. A proactive communication would be activated by a dynamic tracker.

Action: Stakeholder tags updated with project management software (e.g., Jira or Asana) every sprint review. Have one team member reassess salience at significant milestones.

Develop Franchisee Co-Investment Framework

Recommendation: Note: Have a formalised tiered investment system with Hilton centrally financing basic technology (e.g., AI platform), and franchisees opting to upgrade to additional technology (e.g., in-room smart mirrors) depending on local ROI estimates.

Why: The top conflict driver was cost sensitivity. A co-investment model turns the franchisees into unwilling investors into strong partners.

Action: Work on a very basic calculator that estimates 12-, 24-, and 36-month payback per type of property (e.g., airport vs. city-centre hotels). Pilot of 10 franchises to be rolled out at the company level.

Set up a “Conflict-to-Insight” Protocol.

Recommendation: Establish a post-conflict review (immediately after the conflict) into root cause, resolution approach, and single process improvement on the engagement plan that is mandatory and rapid (within 48 hours) and documented (Kandampully, J. et al. 2018).

Why: Tensions around resource distribution and cultural differences were experienced again in StaySmart+. The same conflicts will be repeated in future projects without organized education.

Activity: Simple template: What was the conflict? What was the failure of one of the 4Cs? What is one change? Prevents recurrence? Provide quarterly anonymised insights to project managers.

### Conclusion

As has been illustrated in this analysis, effective stakeholder engagement is not just a supportive process but a strategic necessity for the successful launch of the StaySmart+ initiative of Hilton. By use of the stakeholder theory, Salience Model, Power/Interest Grid, RACI matrix, and most importantly, with the 4C model (Communication, Consultation, Collaboration, Commitment), the project manager will be able to identify, prioritise, and engage a wide range of internal and external stakeholders in a systematic manner. The business performance assessment indicated the following concrete results: decreased rollout delays, regulatory fines avoided, enhanced guest adoption, and strategic intelligence. Nevertheless, the project revealed weaknesses, such as the sensitivity of costs between franchisees, a lack of cross-cultural communication skills, and the threat of over-consultation.

In the future, Hilton needs to shift engagement with stakeholders beyond a project-based strategy to a competitive strategy that is both long-term and sustainable. This practical roadmap consists of five recommendations: dynamic salience tracking, franchisee co-investment frameworks, conflict-to-insight protocols, localisation liaison roles, and a Post-Engagement Performance Index. Finally, the StaySmart+ case verifies that when stakeholders are truly engaged, periods of conflict can be converted into data to enhance, resistance can be converted into co-creation, and the business performance is increased. The stakeholders' complexity should not be evaded as a project manager because it is our core business to use it as the best asset of Hilton to innovate and weather the storms.

### References:

- Abel, A. (2025) ‘The impact of the UK Employment Rights Act 2025 on the service sector’, Journal of British Business Law, 12(2), pp. 45–60.

- Arasli, H., et al. (2020) ‘The effects of COVID-19 on the hotel industry: a systematic review’, International Journal of Hospitality Management, 91, p. 102677.

- Buhalis, D. and Leung, R. (2023) ‘Smart hospitality management: looking to 2030’, International Journal of Contemporary Hospitality Management, 35(1), pp. 102–125.

- Deloitte (2024) UK hospitality industry outlook 2025: navigating inflation and business rates. London: Deloitte LLP.

- Freeman, R.E., Harrison, J.S. and Zyglidopoulos, S. (2018). Stakeholder theory: concepts and strategies. Cambridge: Cambridge University Press.

- Harrison, J.S. and Wicks, A.C. (2021) ‘Stakeholder theory, value, and firm performance’, Business Ethics Quarterly, 31(1), pp. 97–124.

- Hilton (2024) Hilton 2023 Annual Report. McLean, VA: Hilton Worldwide Holdings Inc.

- Hilton (2025) Our brands: leading the way in global hospitality. Available at: https://www.hilton.com/en/corporate/ (Accessed: 28 April 2026).

- Ivanov, S. (2019). Hotel revenue management: from theory to practice. Varna: Zangador.

- Kandampully, J., Zhang, T. and Jaakkola, E. (2018) ‘Customer experience management in hospitality: a review and research agenda’, Service Industries Journal, 38(1-2), pp. 1–22.

- Lalicic, L. and Weismayer, C. (2021) ‘Consumer-to-brand relationship in the hospitality industry: the role of brand authenticity’, Journal of Hospitality & Tourism Research, 45(5), pp. 845–866.

- Law, R., Chan, I.C.C. and Wang, L. (2024) ‘Artificial Intelligence in hospitality: robots, chatbots and facial recognition’, Journal of Hospitality and Tourism Management, 58, pp. 12–25.

- Legrand, W., Sloan, P., and Chen, J.S. (2022). Sustainability in the hospitality industry. 4th edn. London: Routledge.

- Mair, J. and Smith, A. (2021) ‘The events industry after the pandemic’, Journal of Sustainable Tourism, 29(11), pp. 1750–1768.

- Mitchell, R.K., et al. (2021) ‘Stakeholder identification and salience after 25 years: a review and future research agenda’, Journal of Business Ethics, 170(4), pp. 635–655.

- Moise, M.S., et al. (2021) ‘The effects of green practices on guest satisfaction and retention’, Journal of Cleaner Production, 291, p. 125930.

- Niewiadomski, P. (2020) ‘Global production networks and hotel franchising’, Tourism Geographies, 22(1), pp. 119–143.

- Project Management Institute (PMI) (2021) A guide to the project management body of knowledge (PMBOK Guide). 7th edn. Newtown Square, PA: PMI. [Covers RACI and engagement plans].

- Tussyadiah, I. (2020) ‘A review of emerging technologies in tourism and hospitality’, Journal of Travel Research, 59(6), pp. 1021–1040.

- World Travel & Tourism Council (WTTC) (2024) Travel & tourism economic impact 2024: United Kingdom. London: WTTC.