## Slide 1
CONSTRUCTION MANAGEMENT
DELAY ANALYSIS
Juan Antonio Ferriz-Papi

## Slide 2
DELAY ANALYSIS
Planning
Construction
Monitoring and control
Assessment

## Slide 3
DELAY ANALYSIS
There will be difficulties to cope with during the construction stage
To guide this process we have the:
CONTRACT MASTER PROGRAMME
Signed by both the client and the contractor
The contractor has a contractual duty to complete the works on or before the date of completion
If he fails he may suffer the deduction of liquidated and ascertained damages from his contract payment

## Slide 4
DELAY ANALYSIS
HOW TO CONTROL TIME
The contractor’s programme
Milestones
Early warning systems
Progress recording

## Slide 5
DELAY ANALYSIS
DELAY AND DISRUPTION
Definitions for delay and disruption:
Delay
Act or state of being late
Caused by events or circumstances that lead to failure to start or complete on time
Delays to progress: the programmed activity do not start or finish on time, but it does not necessarily affect the overall completion date of the project
Delays to contract completion: the project is not finished when agreed
  The cause of the delay must be determined to consider an extension of time, or
  It is liquidated and ascertained damages may be charged

## Slide 6
DELAY ANALYSIS
DELAY AND DISRUPTION
Definitions for delay and disruption:
Disruption
Concerned with loss of efficiency due to lower productivity then expected or some interference with normal progress.
The contractor is involved in
duplication of effort
out of sequence working or
Bringing subcontractors or other resources to site to do more work
It does not necessarily lead to a delay but will result in a claim for loss and expense under the contract due to the extra effort required to do the work.

## Slide 7
DELAY ANALYSIS
TYPES OF DELAYS
Delay event
Something that happens that lead to a delay
Culpable delay
The delay is the fault of the contractor (non-excusable delay or contractor delay)
Non-culpable delay
The contractor is delayed through no fault of his own (excusable delay or employer delay)

## Slide 8
DELAY ANALYSIS
DELAY AND DISRUPTION
Reasons for delay and disruption:
Where the client is at fault:
  Incomplete design at commencement on site
  Delays in the flow of design information
  Variations and changes in the scope of works
  Discrepancies in contract documents
Where the contractor is at fault:
  Poor quality of workmanship
  Inadequate planning
  Under resourcing of site operations
  Accidents and incidents on site
Where no one is at fault:
  Unforeseen physical conditions
  Strikes affecting site labour or the supply of materials
  Fire, explosion or any other accident
  Bad weather

## Slide 9
DELAY ANALYSIS
EXTENSIONS OF TIME
It is expressly dealt within standard construction contracts through specific clauses:
Extensions of time for specific events beyond the contractor´s control
Procedures for the contractor to follow when making an application for an extension of time
Procedures for the contract administrator to follow when giving consideration to the contractor´s application

## Slide 10
DELAY ANALYSIS
TYPES OF DELAYS
Neutral delay
Caused by factors beyond the control or either of the contracting parties
  At contractor´s risk:
    Bad weather
    Late delivery of material
    Delay of subcontractors
  At employer´s risk:
    -exceptionally bad weather
    -discovery of ancient artefacts on the site
    -strikes affecting site work, off-site manufacture or transport
Concurrent delay
Two or more delay events arise at the same time and at least one has been caused by the client and another by the contractor

## Slide 11
DELAY ANALYSIS
DELAY AND DISRUPTION REGULATIONS
Joint Contracts Tribunal (JCT) or New Engineering Contracts (NEC)
Use of appropriate contract and description
Society of Construction Law (SCL)
Delay and Disruption Protocol (updated in 2016)
  It is guidance to deal with main delay and disruption issues

## Slide 12
DELAY ANALYSIS
DELAY ANALYSIS TECHNIQUES
As-planned vs As-built
Non-excusable delays are taken away from the total delay sum.
Example:
Total delay of works: 10 days
Non-excusable delays: 8 days
The client is only responsible for 2 days delay

## Slide 13
DELAY ANALYSIS
DELAY ANALYSIS TECHNIQUES
Impacted As-planned
Each delay is added to the as-planned programme and shown how the project is being delayed (step by step).
Each delay has an impact on the total project.
Only impacts for excusable delays are considered.
Example:
Chronology | Activity | Delay type | Duration | Impact
1 | 2-4 | Non-excus | 4 days | 2 days
2 | 6-7 | Excusable | 3 days | 1 day
3 | 7-8 | Excusable | 4 days | 0 days
4 | 9-11 | Non-excus | 3 days | 1 day
The client will be responsible only for 1 day delay

## Slide 14
DELAY ANALYSIS
DELAY ANALYSIS TECHNIQUES
As-planned But for
Only delays due to one party are included in the programme. The difference with the total delay at the end shows the responsibility of the other party.
Contractor’s point of view: only consider non-excusable delays
Client’s point of view: only consider excusable delays

## Slide 15
DELAY ANALYSIS
DELAY ANALYSIS TECHNIQUES
Collapsed As-Built
Similar to the previous one, but instead of as-planned, we use the As-built network. The corresponding delays for one party are taken away. The resulting end of works is taken away from the actual.
Contractor’s point of view: only consider excusable delays
Client’s point of view: only consider non-excusable delays

## Slide 16
DELAY ANALYSIS
DELAY ANALYSIS TECHNIQUES
“Window” analysis
The total project duration is divided into a number of time periods (windows or snapshots). Every period is analysed separately.
Delays in this period are introduced and actual end of works compared to scheduled.

## Slide 17
DELAY ANALYSIS
DELAY ANALYSIS TECHNIQUES
Time Impact analysis
Similar to the previous one, but now it concentrates on a specific delay or delaying event
The schedule is updated at this delay period and the effect is analysed to establish a new completion date.
Effective technique as delays are analysed using real time