## Table 1
Risk Register - StageCoach Theartre | [10 empty] | Date: |  | 2025-05-07 |  | 2025-05-01
[11 empty] | Rev: |  | 1
ID. | Element | Perceived Risk | Consequence | Risk Owner | Pre-control |  |  |  | Potential Commercial Impact | Mitigating Actions / Controls | Post Control |  |  |  | Potential Commercial Impact | Risk open/closed | RIBA Stage Close Out
[5 empty] | Likelihood | Impact | Programme Impact | Rating |  |  | Likelihood | Impact | Programme Impact | Rating
1.0 Contractual
1.01 | Budget | Works cost exceeds budget | Increased time and cost | Client | 3 | 5 | Y | 15 | 0 | Origional cost plan was based upon high level infromation, to which more information has now become avaliable. The new figure has been based upon further developed designs provided by the client, to which a elemental cost plan has been produced to better inform ACE Capital Projects. | 2 | 5 |  | 10 | 0 | open | 4
1.02 | Inflation | Inflation costs exceed current allowance | increased cost | Contractor | 3 | 5 | N | 15 | 0 | M.E.S.S Construction Services Ltd elemental cost plan includes market assessment for inflation for project duration. M.E.S.S Construction Services Ltd to monitor market costs throughout the contract period. Current data indicates construction inflation is stabilising however Inflation allowances to be includes as an item in the cost plan. | 2 | 5 |  | 10 | 0 | open | 4
1.03 | Sign off | Delays in Gateway sign-offs in accordance with M.E.S.S Construction Services Ltd construction programme | Increased time and cost | Client | 3 | 5 | Y | 15 |  | Clear definition of engagement process included in suubmitted programme. Sufficient allowances made for client sign offs required. Full technical drawings to be provided at RIBA Stages as defined in by client (design team sitting with ACE Capital Projects Ltd) | 2 | 5 |  | 10 | 0 | open | 4
1.05 | Programme | PCSA programme period too short to complete engagement/design works | Increased time and cost | Contractor | 2 | 3 | Y | 6 | 0 | MS PCSA programme includes design periods with additional time for enhanced engagement. (in-line with our SEN Whitepaper). MS PCSA programme includes 1 week betterment compared to client tender programme. | 2 | 3 |  | 6 | 0 | Closed | 3
1.06 | Programme | Construction programme does not allow adequate time to complete works and meet key dates | Increased time and cost | Contractor | 1 | 1 | Y | 1 | 50000 | M.E.S.S Construction Services Ltd construction programme has tried to allow all works completed within client’s tender periods and all key milestones however, this has been identified as unachievable. The programme has been generated with acceptable float included, but any item that is effected on the critical path due to design related changes (design team with client), then this will result in the programme being in delay. | 1 | 1 |  | 1 | 50000 |  | 5
1.07 | Programme | Clients governance process for Construction Contract Award takes longer than programmed | Increased time and cost | Client | 2 | 3 | Y | 6 | 15000 | M.E.S.S Construction Services Ltd will draft the contract during the pre-contract period for the client to review prior to entering into - this will allow sufficient ammendments to be made if necessary, and prevent delay into entering into contract. Not entering into contract on the required date would result in M.E.S.S Construction Services Ltd being at risk of prices not being fixed with sub-contractors due to inflation etc. | 1 | 3 |  | 3 | 15000 | open | 4
1.08 | Programme | Welsh Government Funding requirements have not been fully developed in terms of when expentiture profiles and forecasting needs to be submitted. | increased time and cost | Client | 2 | 3 | Y | 6 | 25000 | M.E.S.S Construction Services Ltd programme demonstrates adequate time to adjust for alternate dates or ammend cashflow in accordance with spend requirements. | 2 | 3 |  | 6 | 25000 | open | 2
1.09 | Sub-contractors | Subcontractor insolvency | increased time and cost | Contractor | 2 | 4 | Y | 8 | 500000 | M.E.S.S Construction Services Ltd to select from approved supply chain based on capacity, performance and financial health.Commercial Manager Max James monitors all suppliers for resilience. | 1 | 3 |  | 3 | 500000 |  | 5
1.1 | Budget | Potential scope reduction required to remain within ACE Capital Projects budgetry requirements | increased time and cost | Client | 4 | 5 | Y | 20 | 100000 | ACE Capital Limited to confirm any scope changes / value engineering required. | 4 | 5 |  | 20 | 100000 | open | 4
1.11 | Budget | Welsh Government match funding may have maximum allowance | increased time and cost | Client | 4 | 5 | Y | 20 | 50000 | M.E.S.S Construction Services Ltd to provide support on cost data including abnormal costs which may be rationale as to why the project is at the current cost. | 4 | 5 |  | 20 | 100000 | open | 4
1.12 | Value Engineering | Potential Value Engineering required to achieve budget - impact on Planning and redesign | increased time and cost | client | 2 | 5 | Y | 10 | 100000 | Assessment of scope by ACE Capital Projects | 1 | 5 |  | 5 | 100000 | open | 4
1.13 | FBC submission | Potential Full Business Case (FBC) to be submitted to Welsh Govermeent to inform funding | increased time and cost | client | 4 | 5 | Y | 20 | 10000 | No allwance made within programme for funding applications to be submitted, projected start date is as per programme and any deviation to this will result in a later completion. | 1 | 5 |  | 5 | 10000 | open | 4
1.14 | Land Ownership | Potential Land ownership / party wall issues challneged with adjacent properties. | increased time and cost | client | 4 | 5 | Y | 20 | 50000 | Design avoids interaciton with land owned by the party wall and all relevant party walls to be consulted by ACE Capital Projects Design team prior to commencement. M.E.S.S Construction Services to liase with clients appointed party wall surveyor and also the properties surrounding the site. | 1 | 5 |  | 5 | 50000 | open | 4
1.15 | Land Ownership | Space allowance required to create public realam element to facilitate car parking and public realam deviates from origional master plan which Planning Consent are believed to be based upon - potential delay to completion | increased time and cost | client | 5 | 4 | N | 20 | 10000 | Redesign cost to be confirmed. Drawings to be amended to ensure the latest master plan is presented and this is what is being constructed as reported to client. | 1 | 4 |  | 4 | 10000 | open | 5
[8 empty] | 0 |  |  |  | 0 |  | 0 | 0
2.0 Planning and SAB
2.01 | Programme | Ecology surveys may delay planning application | increased time and cost | Client | 2 | 4 | Y | 8 | 25000 | Limited ecology on site Surveys to be undertaken prior to any start on site Additional bat surveys required | 1 | 4 |  | 4 | 25000 | open | 4
2.02 | Programme | Delays to Planning Approval | increased time and cost | Client | 2 | 4 | Y | 8 | 15000 | Develop a tender Planning Tracker to highlight key risks and manage Planning process, engaging early with Planning Authority to ensure requirements for pre-app consultation, PAC to be undertaken once design adequately mature. | 1 | 4 |  | 4 | 15000 | open | 4
2.03 | Programme | Delay to planning submission | increased time and cost | Contractor | 2 | 4 | Y |  | 100000 | Programme to reflect key planning dates. Clientt design deliverables aligned to complete deign work in line with required dates for Planning | 1 | 4 |  | 4 | 100000 | open | 4
2.04 | Programme | Pre-commencement Planning Conditions delay start on site | increased time and cost | Client | 2 | 4 | Y | 8 | 100000 | M.E.S.S Construction Services to engage early with planning Authority to ensure any conditions are addressed in the Planning Submission. Planning Application programmed to allow time to discharge any outstanding pre-commencement conditions prior to contract award. Undertake early engagement wiht Planning Authority. Review opportunity to undertake early preapp review with Plannign Authority prior to main pre-app 8/11/24 - Risk reduced in meeting. amount retained forwhilst planning application for Respite centre is in processd 31/01/25 - Risk closed following planning approval for the respite care | 2 | 4 |  | 8 | 100000 | open | 5
2.06 | Planning | Ecology requirements - Bat/Bird boxes etc | increased time and cost | Contractor | 3 | 2 | Y | 6 | 15000 | Allowance included in cost plan | 1 | 2 |  | 2 | 15000 | open | 4
2.08 | Planning | Planning consultations take longer than anticipated | increased time and cost | Client | 3 | 4 | Y | 12 | 10000 | Float to be included in programme, pre-app and ongoing engagement with Planning Officer | 2 | 4 |  | 8 | 10000 | open | 4
2.09 | Planning | Off site highways improvements may be required as part of Planning Consent | increased time and cost | Client | 3 | 3 | Y | 9 | 100000 | Pre-app consultation with highways team | 2 | 3 |  | 6 | 100000 |  | 5
3.0 Site
3.01 | Sub-contractors | Subsistence requirements for subcontractors depending on selected suppliers | Increased cost | Contractor | 3 | 3 | N | 9 |  | Included in priced works | 1 | 3 |  | 3 | 0 | open | 5
3.02 | Ecology | Delays to programme associated with removal of existing habitats within correct seasons | increased time and cost | Client | 2 | 2 | Y | 4 | 50000 | Intrusive ecology surveys to be undertaken to determine exact scope of works required. Programed works to reflect these dates and coincide with any key ecology dates for consideration i.e. bird nesting season etc | 1 | 2 |  | 2 | 50000 |  | 5
3.03 | Ecology | Nesting Birds and Bats delay works | increased time and cost | Client | 2 | 4 | Y | 8 | 25000 | As mitigation methods above | 1 | 4 |  | 4 | 25000 |  | 5
3.04 | Ground water | Watercourse near site | increased cost | Contractor | 5 | 3 | N | 15 | 50000 | Ground investigation to be undertaken to confirm soakaway capacity. Drainage surveys to confirm network capacity. Enageg with SAB officer to explore design options. | 1 | 3 |  | 3 | 50000 | open
3.06 | Sewer | Insufficient capacity in sewer network - limited existing service drawings | increased cost | Client | 2 | 2 | N | 4 | 25000 | Early engagement with statutory services to allow sufficient time / lead time on upgrading any networks or services that may be required. | 1 | 2 |  | 2 | 25000 | open | 4
3.08 | Electrical Connection | Inadequate capacity in grid for export | increase time | Client | 2 | 4 |  | 8 | 25000 | With the option of PV installation, confirmation required with National Grid that there is capacity to export any energy if required, as surrounding buildings within area have lots of PV installed | 2 | 4 |  | 8 | 25000 | open | 4
3.09 | Electrical connection | Available electrical capacity | increased cost | Client | 4 | 3 | N | 12 | 25000 | As sewer mitigation | 1 | 3 |  | 3 | 25000 | open | 4
3.1 | Water connection | Availability/pressure of Water supply. Water Authority unable to guarantee minimum pressure. | increased cost | Client | 5 | 4 | N | 20 | 25000 | As sewer mitigation | 2 | 4 |  | 8 | 25000 | open | 4
3.12 | Telecoms | Telecoms Service Capacity | increased cost | Client | 2 | 2 | N | 4 | 15000 | As sewer mitigation | 1 | 2 |  | 2 | 15000 | open | 4
3.14 | Soft Spots | Presence of Soft Spots | increased time and cost | client | 3 | 3 | Y | 9 | 75000 | Large cut and fill operation, proof rolling required. More intrusive Ground investigation will provide thorough assessment of site conditions and geotechnical conditions - in current informaiton, appears to be soft spots | 1 | 3 |  | 3 | 75000 | open | 5
3.16 | Invasive species | Invasive Species | increased time and cost | Client | 2 | 3 | N | 6 | 25000 | Invasive species removal to be included in ecology assessments, landscaping design and cost plans. | 1 | 3 |  | 3 | 25000 | open | 5
3.18 | Contamination | Presence of contamination in existing ground | increased time and cost | Client | 3 | 3 | Y | 9 | 250000 | Further intrusive ground investigation to be undertaken, as demolition of former bus stop may of caused contamination due to inadequate removal of certain materials | 1 | 3 |  | 3 | 250000 | open | 5
3.19 | Asbestos | Asbestos in ground | increased time and cost | Client | 5 | 4 | Y | 20 | 100000 | As above | 2 | 4 |  | 8 | 100000 | open | 5
3.22 | UXO | Presence of UXO | increased time and cost | Client | 3 | 5 | Y | 15 | 20000 | Historical records indicate risk. Ground Penetrating Radar Survey will identify any abnormalities in the ground. | 1 | 5 |  | 5 | 20000 | open | 5
3.32 | Specification | Works completed by other contractor in regards to decomission and demoliton of bus shelter non compliant / re-leveling of site (most recent works) | increased time and cost | Client | 2 | 3 | Y | 6 | 50000 | Client to obtain details of these works, details provided to M.E.S.S. to align remaining design work to this spec / what was complete | 2 | 3 |  | 6 | 50000 | open | 5
3.36 | Ground Conditions | Cut material unsuitable for reuse | increased time and cost | Contractor | 4 | 4 | Y | 16 | 500000 | Intrusive Ground Investigation required to indicate condition / any contaminates in material, programme to include earthworks in summer months when wet weather less likely to impact the soil conditions | 1 | 4 |  | 4 | 500000 | open | 5
3.41 | Road Safety Audit | Client may require RSA to be completed. | increased cost | Client | 5 | 5 |  | 25 | 100000 | RSA likely to be required for these works | 3 | 5 |  | 15 | 100000 | open
4.0 Design
4.01 | Highways | Additional Highways works required to enhance site entrance and exit. | increased time and cost | Client | 4 | 4 |  | 16 | 25000 | Highways to be engaged through preapp. Section 278 agreement may be required if improvements are required through Planning | 2 | 4 |  | 8 | 25000 | open | 4
4.02 | Externals | Space constraints limit opportunity for SUDS features | increased cost | Client | 4 | 3 |  | 12 | 50000 | Engage with SAB Officer to explore scheme design - site footprint is sufficient however, the overall masterplan indicates other buildings within the facinity. Any additional SUDS features could be incorporated within the other buildings, view of the scheme as a whole i.e. full masterplan | 1 | 3 |  | 3 | 50000 | open | 4
4.04 | Project Brief | Late design changes (post RIBA Stage 3) as a result of stakeholder input | increased cost | Client | 4 | 5 |  | 20 | 20000 | Gateway process included in CEMs and programme to ensure development of design is managed with stakeholders understanding the process and the impact of change at each stage. | 2 | 5 |  | 10 | 20000 | open | 4
4.1 | Surveys | Inadequate survey information available to complete design | increased time and cost | Client |  |  |  | 0 | 0 | Full suite of surveys to support the design process, undertaken by M.E.S.S Construction Services |  | 0 |  | 0 | 0 | open | 3
4.11 | Specialist Support | Specialist subcontractors not appointed in time to support design | increased time and cost | Client |  |  |  | 0 | 0 | Key specialists engaged with in tender period. Engage with stage specialists etc at a early stage to allow for potential lead tines |  | 0 |  | 0 | 0 | open | 4
4.14 | Net Zero Carbon | NZC challenging due to increased energy demand from stage equipment / application of building | increased cost | Client | 3 | 5 |  | 15 | 50000 | Commence assessments / engagement with specialist and sufficient modelling and BREAAM calculations, with fully intergrated design. Sufficient energy calculations and PV array size | 1 | 5 |  | 5 | 50000 | open | 4
4.16 | Utilities | National Grid may reject or limit export of excess energy back to the grid | increased costs | Client | 3 | 5 |  | 15 | 25000 | Fabric first approach to limit energy demand for heating load allowing reduction in PV. Promote campus wide solution that allows connection of other buildings to PV to allow excess energy to be used on site by services that run all year round - allowance for connection to buildings within the masterplan if required | 3 | 5 |  | 15 | 25000 | open | 5
4.17 | Project Brief | Increase in planned pupil numbers over brief | increased time and cost | Client | 4 | 4 |  | 16 | 15000 | Brief fixed and confirmed in RIBA Stage 2 | 1 | 4 |  | 4 | 15000 | open | 2
4.19 | Earthworks | Cut and fill model volumes inaccurate / unachievable due to ground conditions | increased costs | Contractor | 4 | 3 |  | 12 | 50000 | Ongoing review and will be further informed by ground condition surveys | 1 | 3 |  | 3 | 50000 | open | 5
4.2 | Fire protection requirements | Fire protections to structural steel - additional requirements | increased costs | client | 4 | 4 |  | 16 | 50000 | Design to include fire protection Further protection requriements may be requested by Building Control | 4 | 4 |  | 16 | 50000 | open | 4
4.23 | Fire Engineering | Complex Fire engineering solutions may lead to Building Control needing to seek outside advice | Increased time | Contractor | 4 | 4 |  | 16 | 15000 | Ongoing fire engineering design targetting simple solutions with Building Control's agreement | 2 | 4 |  | 8 | 15000 | open | 4
4.25 | User Change | Late design changes (post contract) from users | Increased time and costs | client | 4 | 4 |  | 16 | 100000 | Regular engagement with the client through constract Complete final engagement process (colour selection etc) | 2 | 4 |  | 8 | 100000 | open | 5
4.26 | User Change | Change in fencing requirements for pupils or securing of site features (SUDS etc) | Increased time and costs | client | 3 | 4 |  | 12 | 50000 | Regular engagement with the client through constract Complete final engagement process (colour selection etc) | 3 | 4 |  | 12 | 50000 | open | 5
4.28 | Unidentified services | Services not identified may impact works | Increased time and costs | client | 4 | 4 |  | 16 | 50000 | Utility Searches to be completecomplete GPRS to be complete | 3 | 4 |  | 12 | 50000 | open | 5
4.29 | Coal tar | Undiscovered coal tar may incure additonal disposal costs | Increase time | client | 4 | 4 |  | 16 | 100000 | Ground investigation to inform | 4 | 4 |  | 16 | 100000 | open | 5
[11 empty] | Allocated to Contractor |  |  |  |  | 1280000
[11 empty] | Allocated to Client |  |  |  |  | 2005000

## Sheet1
open
closed
Client
Contractor
4
5
6