## Sheet1
NRM Ref | Description | Quantity | Unit | Cost per Unit | Total Cost before indicies | Unit Cost After indicies | Total cost after indicies | Comments
Bill no1. For excavation pile caps ,lift pits and other pits with construction of pit slabs and walls | [7 empty] | As stated in NRM2 5.6.1 Bulk excavtion rules are applicable to basement like strucutres such as lift shafts and other pits.
5.6.1 Bulk Excavation ( For lift pits)
5.6.1.2 | Bulk excavation for lift pits total 2.4m depth including excavation for lift pit slab and shear walls. | 33.2 | m3 | 12.3 | 408.26 |  | 1010.25 | Calculation shown in part 3.1 of resport.
5.6.1.1.1 | No Known obstructions in ground.
11.2.2 Slab for lift pit
11.2.2 | Slab for lift pit 1200mm thick binding to all pile caps. | 18.048 | m3 | 127.96 | 2309 | 316.56 | 5712.26 | Calculation shown in part 3.2 of report.
11.5.1 200mm thick rc walls for pits
11.5.1.3 | 3 no. 200mm thick rc walls for lift pits | 1.69 | m3 | 161.01 | 272.1 | 398.32 | 673.15 | 25N RC assumed as no RC specifications provided on drawings. 25N rc chosen as it is most economical options. Calculations shown in part 3.3 of report.
5.6.1 Bulk excavation for pit 1 (900x900x900)
5.6.1.1 | Bulk excavation by machine for pit 1. 0.9m deep | 0.729 | M3 | 9.1 | 6.63 | 22.513 | 16.4 | Calculation shown in part 3.4 of report.
5.6.1.1.1 | No known obstructions.
11.2.1 Slab for pit 1
11.2.1 | Slab for pit1 200mm thick | 0.162 | m3 | 129.61 | 21 | 320.64 | 51.95 | 25N RC assumed as no RC specifications provided on drawings. 25N rc chosen as it is most economical options. Calculations shown in part 3.5 of report.
11.5.1 200mm thick rc walls for pits
11.5.1.3 | 200mm thick rc walls for pit 1 | 0.648 | m3 | 161.01 | 104.33 | 398.32 | 258.1 | 25N RC assumed as no RC specifications provided on drawings. 25N rc chosen as it is most economical options. Calculations shown in part 3.6 of report.
5.6.1 Bulk excavation for pit 2 (1500x900x900)
5.6.1.1 | Bulk excavation by machine for pit 2. 0.9m deep | 1.215 | M3 | 10.52 | 12.78 | 26.03 | 31.62 | Calculation shown in part 3.7 of report.
5.6.1.1.1 | No Known obstructions in ground.
11.2.1 Slab for pit 2
11.2.1 | Slab for pit 2 200mm thick | 0.27 | m3 | 129.61 | 35 | 321 | 86.6 | 25N RC assumed as no RC specifications provided on drawings. 25N rc chosen as it is most economical options. Calculations shown in part 3.8 of report.
11.5.1 200mm thick rc walls for pits
11.5.1.3 | 200mm thick rc walls for pit 2 | 0.79 | m3 | 161.01 | 127.12 | 398.32 | 314.48 | 25N RC assumed as no RC specifications provided on drawings. 25N rc chosen as it is most economical options. Calculations shown in part 3.9 of report
5.6.2 Foundation excavation (For Pile caps)
5.6.2.1 | Foundation excavation for pile caps | 42.7 | m3 | 11.46 | 489.34 | 28.35 | 1210.6 | Calculation shown in part 3.10 of report.
5.6.2.1.1 | No Known obstructions in ground.
Bill no2. for Driven piles
| Provision of plant (1 rig), including transport to and from site aswell as erection and dismantling at each pile position for up to 100 piles. | 1 | Item | 16275 | 16275 | 40262.92 | 40262.92 | Calculations shown in part 3.11 of report.
7.2.1 Bored Piles
7.2.1 Single Pile sections
7.2.1 | Bored Piles
7.2.2 | 450mm diameter
7.2.3 | Bored length of piles to be up to 20m | [6 empty] | Pile length not available on drawings but size advised by client to be 18-20m
7.2.4 | Total concreted Length to be up to 5.925m in length after cut off
7.2.5 | total number of piles | 24 | NR | 910.4 | 21849.6 | 2252.25 | 54054.05 | Calculations show in 3.12 of report
7.2.1.2 | Pile cap to be 750 x750mm - 3 no. H Bars 1400 lng minimum 650mm into cap. Minimum 1.5m concrete infill at top of steel tube pile | 24 | NR | 750 | 18000 | 1855.43 | 44530.4 | Calculations shown in part 3.13 of report.
5.20 Cutting off tops of piles. | [7 empty] | As per NRM2 - 5.20.1.1 The cutting off tops of piles is deemed to include the preparation and integration of reinforcement into the pile caps. Pricing is included in cap description price.
5.20.1 | Number of piles cut | 24 | Nr |  |  |  |  | Cost for cutting piles inluded in 7.2.1.2
internal sections with 2 piles (Standard) | [7 empty] | Prices for piles are priced to 300mm piles. The project uses 250/244 diameter piles as per drawings but costing are not available for the specific piles
7.2.1 | Bored Piles
7.2.2 | 450mm diameter
7.2.3 | Bored length of piles to be up to 20m | [6 empty] | Pile length not available on drawings but size advised by client to be 18-20m
7.2.4 | Total concreted Length to be up to 5.925m in length after cut off
7.2.5 | total number of piles | 22 | NR | 910.4 | 20028.8 | 2252.25 | 49503.6 | Calculation shown in part 3.14 of report.
7.2.1.2 | Pile cap to be 750x 1300mm with 3 no. H Bars 1400 lng minimum 650mm into cap. Minimum 1.5m concrete infill at top of pile | 22 | NR | 750 | 16500 | 1855 | 40819.55 | Calculation shown in part 3.15 of report.
5.20 Cutting off tops of piles. | [7 empty] | As per NRM2 - 5.20.1.1 The cutting off tops of piles is deemed to include the preparation and integration of reinforcement into the pile caps. Pricing is included in cap description price.
5.20.1 | Number of piles cut | 22 | Nr |  |  |  |  | Cost for cutting piles inluded in 7.2.1.2
sections with 2 piles (Type A) | [7 empty] | Prices for piles are priced to 300mm piles. The project uses 250/244 diameter piles as per drawings but costing are not available for the specific piles
7.2.1 | Bored Piles
7.2.2 | 450mm diameter
7.2.3 | Bored length of piles to be up to 20m | [6 empty] | Pile length not available on drawings but size advised by client to be 18-20m
7.2.4 | Total concreted Length to be up to 5.925m in length after cut off
7.2.5 | total number of piles | 20 | NR | 910.4 | 18208 | 2252.25 | 45045 | Calculation shown in part 3.16 of report.
7.2.1.2 | Pile cap to be 1100x 1300mm with 3 no. H Bars 1400 lng minimum 650mm into cap. Minimum 1.5m concrete infill at top of pile | 20 | NR | 1675 | 33500 | 4143.8 | 82876.03 | Calculation shown in part 3.17 of report.
5.20 Cutting off tops of piles.
5.20.1 | Number of piles cut | 20 | Nr |  |  |  |  | Cost for cutting piles inluded in 7.2.1.2
Internals sections with 3 piles | [7 empty] | Prices for piles are priced to 300mm piles. The project uses 250/244 diameter piles as per drawings but costing are not available for the specific piles
7.2.1 | Bored Piles
7.2.2 | 450mm Diameter Piles
7.2.3 | Bored length of piles to be up to 20m | [6 empty] | Pile length not available on drawings but size advised by client to be 18-20m
7.2.4 | Total concreted Length to be up to 5.925m in length after cut off
7.2.5 | total number of piles | 30 | NR | 910.4 | 27312 | 2252.25 | 67576.47 | Calculations shown in part 3.18 of report
7.2.1.2 | Pile cap to be 1250x 1300mm with 3 no. H Bars 1400 lng minimum 650mm into cap. Minimum 1.5m concrete infill at top of pile | 30 | NR | 1675 | 50250 | 4143.8 | 124314.04 | Calculations shown in part 3.19 of report
5.20 Cutting off tops of piles. | [7 empty] | As per NRM2 - 5.20.1.1 The cutting off tops of piles is deemed to include the preparation and integration of reinforcement into the pile caps. Pricing is included in cap description price.
5.20.1 | Number of piles cut | 30 | Nr |  |  |  |  | Cost for cutting piles inluded in 7.2.1.2
Edge Section Piles | [7 empty] | Prices for piles are priced to 300mm piles. The project uses 250/244 diameter piles as per drawings but costing are not available for the specific piles
7.2.1 | Bored Piles
7.2.2 | 250/244 Dia Piles
7.2.3 | Bored length of piles to be up to 20m | [6 empty] | Pile length not available on drawings but size advised by client to be 18-20m
7.2.4 | Total concreted Length to be up to 5.925m in length after cut off
7.2.5 | total number of piles | 4 | NR | 910.4 | 3641.6 | 2252.25 | 9009.15 | Calculation shown in part 3.20 of report.
7.2.1.2 | Pile cap to be 750 x750mm - 3 no. H Bars 1400 lng minimum 650mm into cap. Minimum 1.5m concrete infill at top of pile | 4 | NR | 750 | 3000 | 1855 | 7421 | SPONS estimated pricing used for piles caps as no measured costs for pile caps available in spons 2020 arichitects price book. Calculations shown in part 3.21 of report.
5.20 Cutting off tops of piles. | [7 empty] | As per NRM2 - 5.20.1.1 The cutting off tops of piles is deemed to include the preparation and integration of reinforcement into the pile caps. Pricing is included in cap description price.
5.20.1 | Number of piles cut | 4 | Nr |  |  |  |  | Cost for cutting piles inluded in 7.2.1.2
7.8 Reinforcement to piling
7.8.1 | Reinforcement to piles (description of reinforcement) |  | T |  |  |  |  | included in piling cost
5.9 Disposal of excavated material.
5.9.1 | Disposal of excavated material to destination if not at the contractors disctrection- active non-hazardous waste off site; to tip notexceeding 13 km (using lorries); including LandfillTax | 340.5 | m3 | 32.47 | 11056.04 | 80.33 | 27351.7 | Inluding 305 m3 of excacated material from piling based on a depth of 20m and diameter of 450mm. Calculations shown in part 3.22 of report.
7.12 Tests
7.12.1 | Pile Testing- Using tension piles as reaction; Using typical loading test 600kn | 96 | Item | 6400 | 614400 | 15833 | 1519971.1 | Calculation shown in part 3.23 of report.
7.12.1.1 | Integrity Tesing | 96 | Nr | 16 | 1536 | 39.6 | 3799.93 | Calculation shown in part 3.24 of report.