## Light
Fantasia Reimagined
| Jennifer Jade Bevan |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
| Project Start Date: | 2022-07-21 |  |  |  | September | [20 empty] | October
| Scrolling Increment: | 51 | time axis 2022-09-10 to 2022-11-04
| Milestone description | Category | Progress | Start | Days | time axis 2022-09-10 to 2022-11-04
Fantasia Reimagined
| Research composers | On Track | 100% | 2022-07-21 | 2
Source | Source Video Material | On Track | 100% | 2022-08-13 | 1
| Familiarise with Fantasia Imagery | On Track | 100% | 2022-07-28 | 86
| Write Proposal 2500 words & Submit | On Track | 100% | 2022-07-21 | 23
| Define Instruments Needed | On Track | 100% | 2022-07-28 | 86
| Note Reflections | On Track | 100% | 2022-07-27 | 87
| Research For Proposal | On Track | 100% | 2022-07-12 | 32
| Scene select and cut ready for DAW | On Track | 100% | 2022-08-14 | 3
| Remove any controversial scenes | On Track | 100% | 2022-08-18 | 3
| Count time of each scene to fulfill time requirement of 30 minutes. | On Track | 100% | 2022-08-14 | 1
| Insert each clip into a different Daw Session | On Track | 100% | 2022-08-15 | 1
| Install & Learn how to use Splice | On Track | 100% | 2022-08-16 | 1
| Refer back to guidance material | On Track | 100% | 2022-07-21 | 93
| Ensure everything has a backup / Dropbox | On Track | 100% | 2022-07-21 | 93
100 | Compose a complete track for each scene (mix as best I can as I go along) | On Track | 100% | 2022-08-21 | 56
| Install & Learn how to use Ozone10 | On Track | 80% | 2022-08-28 | 40
| Add all movement and Viual sound affects | On Track | 100% | 2022-08-21 | 56
| Go through each clip and look for missing Sound FX | On Track | 100% | 2022-10-01 | 10
| Mixing | On Track | 100% | 2022-08-21 | 56
| IMovie Video stitch / Create iMOVIE with all scenes together | On Track | 100% | 2022-10-01 | 5
| Level each scene so that they are about the same volume | On Track | 100% | 2022-10-01 | 5
E | Export & Compress ready for submission | On Track | 100% | 2022-10-16 | 1
Check | Check on lower quality speakers | On Track | 100% | 2022-10-16 | 1
Tripp | Triple check Video ensure all is present and correct | On Track | 100% | 2022-10-16 | 1
| Files Ready for Submission & Submit | On Track | 100% | 2022-10-16 | 1
S | Essay Deadline | On Track | 100% | 2022-09-26 | 25
| Begin Essay 5000 words | On Track | 100% | 2022-09-26 | 25
| Essay research | On Track | 100% | 2022-09-26 | 25
| Further research into copywright law and the Disney franchise personal copywright standards | On Track | 100% | 2022-09-21 | 1
| Research the art of music sync | On Track | 100% | 2022-08-23 | 2
| Further research into the TV and Film Sync industry | On Track | 100% | 2022-10-13 | 6
| Initial research into TV and Film Sync industry | On Track | 100% | 2022-10-11 | 1
To add more data, Insert new rows ABOVE this one