## Summary Project Costings
Summary Project Costings:
Item Number: | Item Description: | Unit of Measurement: | Material Cost | Total Material Cost: | Total Material Amount: | Contractors Overheads and Profits @12% of total cost: | Prelims @5% of total cost: | Total Costs (inclusive of prelims and O+P):
1 | Common Brick | m² | 120 | 484680 | 4039 | 58161.6 | 24234 | 567075.6
2 | Gypsum Wall Board | m² | 6.72 | 167811.84 | 24972 | 20137.4208 | 8390.592 | 196339.8528
3 | Fibreglass Batt Insulation | m² | 6.65 | 26746.3 | 4022 | 3209.556 | 1337.315 | 31293.171
4 | Plaster | m² | 12.28 | 200851.68 | 16356 | 24102.2016 | 10042.584 | 234996.4656
5 | Insulation/Frame Support | m² | 5.76 | 23103.36 | 4011 | 2772.4032 | 1155.168 | 27030.9312
6 | Board Formed Concrete | m² | 27 | 108378 | 4014 | 13005.36 | 5418.9 | 126802.26
7 | Nitrile Rubber | m² | 22.4 | 90473.6 | 4039 | 10856.832 | 4523.68 | 105854.112
8 | Concrete Cast In-Situ | m³ | 107.16 | 147880.8 | 1380 | 17745.696 | 7394.04 | 173020.536
9 | Light Gauge Steel Framing | m² | 74.94 | 394484.16 | 5264 | 47338.0992 | 19724.208 | 461546.4672
10 | Rigid Foam Insulation Board | m² | 12.5 | 73375 | 5870 | 8805 | 3668.75 | 85848.75
11 | Polythene Film Membrane | m² | 4.37 | 12825.95 | 2935 | 1539.114 | 641.2975 | 15006.3615
12 | Damp Proofing | m² | 5.13 | 15056.55 | 2935 | 1806.786 | 752.8275 | 17616.1635
13 | Concrete Slab Topping | m² | 165 | 1924725 | 11665 | 230967 | 96236.25 | 2251928.25
14 | EPDM Roof Membrane | m² | 45.63 | 133924.05 | 2935 | 16070.886 | 6696.2025 | 156691.1385
15 | Crushed Stone/Gravel | m³ | 51.07 | 29978.09 | 587 | 3597.3708 | 1498.9045 | 35074.3653
16 | Triple-glazed sealed units | m² | 297.6 | 242841.6 | 816 | 29140.992 | 12142.08 | 284124.672
17 | Aluminium Doors | nr | 1678.99 | 184688.9 | 110 | 22162.668 | 9234.445 | 216086.013
18 | Aluminium Curtain Walling | m² | 1225 | 632100 | 516 | 75852 | 31605 | 739557
19 | Engineering Brick | m² | 132.5 | 76320 | 576 | 9158.4 | 3816 | 89294.4
20 | Birch Wood | m² | 14.27 | 34904.42 | 2446 | 4188.5304 | 1745.221 | 40838.1714
21 | Textile/Fabric | m² | 8.63 | 20116.53 | 2331 | 2413.9836 | 1005.8265 | 23536.3401
22 | Porcelain | m² | 5.43 | 3887.88 | 716 | 466.5456 | 194.394 | 4548.8196
23 | Air Infiltration Barrier | m² | 4.57 | 15515.15 | 3395 | 1861.818 | 775.7575 | 18152.7255
24 | Internal moulded panel door; half hour fire resisting (FD30) | nr | 114.25 | 88086.75 | 771 | 10570.41 | 4404.3375 | 103061.4975
25 | Door Frame/ Mullion | nr | 30.58 | 6849.92 | 224 | 821.9904 | 342.496 | 8014.4064
26 | Door Architrave | nr | 26.8 | 6003.2 | 224 | 720.384 | 300.16 | 7023.744
27 | Metal-Steel (Furniture) | m² | 37.61 | 15232.05 | 405 | 1827.846 | 761.6025 | 17821.4985
28 | Air | m² | 0 | 0 | 4028 | 0 | 0 | 0
29 | Cabinets | nr | 137.91 | 88538.22 | 642 | 10624.5864 | 4426.911 | 103589.7174
30 | Laminate- Ivory | m² | 12.84 | 14149.68 | 1102 | 1697.9616 | 707.484 | 16555.1256
31 | Laminate- Marble | m² | 31.49 | 27049.91 | 859 | 3245.9892 | 1352.4955 | 31648.3947
32 | Cast In-Place Concrete | m² | 83.78 | 131283.26 | 1567 | 15753.9912 | 6564.163 | 153601.4142
33 | Televisions | nr | 229 | 3206 | 14 | 384.72 | 160.3 | 3751.02
34 | Window Frame | m² | 218 | 17004 | 78 | 2040.48 | 850.2 | 19894.68
35 | Concept Doors | nr | 6695 | 80340 | 12 | 9640.8 | 4017 | 93997.8
36 | Concrete Masonry Unit | nr | 7.63 | 220507 | 28900 | 26460.84 | 11025.35 | 257993.19
[6 empty] | Total Project Costings: |  | 6719215.0545
[6 empty] | Total project cost, encorportating the Tender Price Index (TPI) which is: (126.7-124)÷ 124(x100%)) |  | 6865693.9427
[6 empty] | Total project cost encorporating the Location Factor for Wales (which is 0.85): |  | 5711332.7963
[6 empty] | Total project cost, encorporating both the TPI and Location Factor for Wales: |  | 5835839.85

## Interim Valuation 1
Interim Valuation 1:
Item Number: | Item Description: | Unit of Measurement: | Material Cost | Total Material Cost: | Total Material Amount: | Contractors Overheads and Profits @12% of total cost: | Prelims @5% of total cost: | Total Costs (inclusive of prelims and O+P): | % of the element completed; | Cost of works to date:
1 | Common Brick | m² | 120 | 484680 | 4039 | 58161.6 | 24234 | 567075.6 | 100% | 567075.6
2 | Gypsum Wall Board | m² | 6.72 | 167811.84 | 24972 | 20137.4208 | 8390.592 | 196339.8528 | 50% | 98169.93
3 | Fibreglass Batt Insulation | m² | 6.65 | 26746.3 | 4022 | 3209.556 | 1337.315 | 31293.171 | 50% | 15646.59
4 | Plaster | m² | 12.28 | 200851.68 | 16356 | 24102.2016 | 10042.584 | 234996.4656 | 30% | 70498.94
5 | Insulation/Frame Support | m² | 5.76 | 23103.36 | 4011 | 2772.4032 | 1155.168 | 27030.9312 | 40% | 10812.37
6 | Board Formed Concrete | m² | 27 | 108378 | 4014 | 13005.36 | 5418.9 | 126802.26 | 40% | 50720.9
7 | Nitrile Rubber | m² | 22.4 | 90473.6 | 4039 | 10856.832 | 4523.68 | 105854.112 | 40% | 42341.64
8 | Concrete Cast In-Situ | m³ | 107.16 | 147880.8 | 1380 | 17745.696 | 7394.04 | 173020.536 | 70% | 121114.38
9 | Light Gauge Steel Framing | m² | 74.94 | 394484.16 | 5264 | 47338.0992 | 19724.208 | 461546.4672 | 100% | 461546.47
10 | Rigid Foam Insulation Board | m² | 12.5 | 73375 | 5870 | 8805 | 3668.75 | 85848.75 | 80% | 68679
11 | Polythene Film Membrane | m² | 4.37 | 12825.95 | 2935 | 1539.114 | 641.2975 | 15006.3615 | 60% | 9003.82
12 | Damp Proofing | m² | 5.13 | 15056.55 | 2935 | 1806.786 | 752.8275 | 17616.1635 | 80% | 14092.93
13 | Concrete Slab Topping | m² | 165 | 1924725 | 11665 | 230967 | 96236.25 | 2251928.25 | 100% | 2251928.25
14 | EPDM Roof Membrane | m² | 45.63 | 133924.05 | 2935 | 16070.886 | 6696.2025 | 156691.1385 | 80% | 125352.91
15 | Crushed Stone/Gravel | m³ | 51.07 | 29978.09 | 587 | 3597.3708 | 1498.9045 | 35074.3653 | 100% | 35074.37
16 | Triple-glazed sealed units | m² | 297.6 | 242841.6 | 816 | 29140.992 | 12142.08 | 284124.672 | 50% | 142062.34
17 | Aluminium Doors | nr | 1678.99 | 184688.9 | 110 | 22162.668 | 9234.445 | 216086.013 | 40% | 86434.4
18 | Aluminium Curtain Walling | m² | 1225 | 632100 | 516 | 75852 | 31605 | 739557 | 80% | 591645.6
19 | Engineering Brick | m² | 132.5 | 76320 | 576 | 9158.4 | 3816 | 89294.4 | 100% | 89294.4
20 | Birch Wood | m² | 14.27 | 34904.42 | 2446 | 4188.5304 | 1745.221 | 40838.1714 | 20% | 8167.63
21 | Textile/Fabric | m² | 8.63 | 20116.53 | 2331 | 2413.9836 | 1005.8265 | 23536.3401 | 20% | 4707.27
22 | Porcelain | m² | 5.43 | 3887.88 | 716 | 466.5456 | 194.394 | 4548.8196 | 20% | 909.76
23 | Air Infiltration Barrier | m² | 4.57 | 15515.15 | 3395 | 1861.818 | 775.7575 | 18152.7255 | 60% | 10891.64
24 | Internal moulded panel door; half hour fire resisting (FD30) | nr | 114.25 | 88086.75 | 771 | 10570.41 | 4404.3375 | 103061.4975 | 40% | 41224.6
25 | Door Frame/ Mullion | nr | 30.58 | 6849.92 | 224 | 821.9904 | 342.496 | 8014.4064 | 40% | 3205.76
26 | Door Architrave | nr | 26.8 | 6003.2 | 224 | 720.384 | 300.16 | 7023.744 | 40% | 2809.5
27 | Metal-Steel (Furniture) | m² | 37.61 | 15232.05 | 405 | 1827.846 | 761.6025 | 17821.4985 | 20% | 3564.3
28 | Air | m² | 0 | 0 | 4028 | 0 | 0 | 0 | 0% | 0
29 | Cabinets | nr | 137.91 | 88538.22 | 642 | 10624.5864 | 4426.911 | 103589.7174 | 20% | 20171.94
30 | Laminate- Ivory | m² | 12.84 | 14149.68 | 1102 | 1697.9616 | 707.484 | 16555.1256 | 20% | 3311.03
31 | Laminate- Marble | m² | 31.49 | 27049.91 | 859 | 3245.9892 | 1352.4955 | 31648.3947 | 20% | 6329.68
32 | Cast In-Place Concrete | m² | 83.78 | 131283.26 | 1567 | 15753.9912 | 6564.163 | 153601.4142 | 90% | 138241.27
33 | Televisions | nr | 229 | 3206 | 14 | 384.72 | 160.3 | 3751.02 | 0% | 0
34 | Window Frame | m² | 218 | 17004 | 78 | 2040.48 | 850.2 | 19894.68 | 80% | 15916
35 | Concept Doors | nr | 6695 | 80340 | 12 | 9640.8 | 4017 | 93997.8 | 100% | 93997.8
36 | Concrete Masonry Unit | nr | 7.63 | 220507 | 28900 | 26460.84 | 11025.35 | 257993.19 | 80% | 206394.55
[6 empty] | Total Project Costings: |  | 6719215.0545 |  | Interim Valuation 1 Total:
5411337.57
[6 empty] | Total project cost, encorportating the Tender Price Index (TPI) which is: (126.7-124)÷ 124(x100%)) |  | 6865693.9427
[6 empty] | Total project cost encorporating the Location Factor for Wales (which is 0.85): |  | 5711332.7963
[6 empty] | Total project cost, encorporating both the TPI and Location Factor for Wales: |  | 5835839.85