1 Title

Construction project schedule management system based on particle swarm optimization

# 2 Introduce

Modern project management is a new field of management discipline developed in recent years, which is very different from general operation enterprise management in terms of principles and methods, and has gradually formed a more complete discipline system, and established several international modern project management associations, including the International Project Management Association (IPMA), mainly in Europe, and the Project Management Institute (PMI), led by the United States, as representatives.

With the development of information technology and the prevalence of outsourcing, the interconnectedness of businesses is becoming more and more evident and the traditional vertically integrated mode of operation is increasingly being replaced by a horizontal, hypertextual one. This means that the traditional boundaries of the enterprise are becoming increasingly blurred and are gradually disappearing. In this context, business activities will increasingly be run as projects. It is in this sense that project-centered activities, rather than organizational structures, are becoming more and more common, and it is in this sense that project management is becoming more and more popular.

1984, PMI developed "The Guide to the Project Management Body of Knowledge" (PMBOK) in an attempt to establish a global project management standard. In 1987 and 1996, the PMBOK was revised twice. The document has been recognized as a global standard by the world project management community. The International Organization for Standardization (ISO) also used the document as a framework to develop the ISO10006 standard.

PMI divides the process of project management into the following three major processes: I. The project planning process, II. Project execution process, and III. Project monitoring process.

The main tasks of the project planning process include: establishing the WBS plan, confirming the project process, confirming a detailed project plan, plan review, approving the project plan, determining the project plan baseline, etc.; the tasks of project execution and monitoring process include: executing the project plan, managing project, monitoring project plan, and completion, project change control, project process review, etc.

At the present stage, construction schedule management is mainly based on the traditional task decomposition after the process constraints to develop the schedule plan to guide the on-site construction management. However, the execution of each construction task will take up the corresponding resources, and if the resources required for a task are occupied by other tasks, the task can only wait for the release of its required resources, which will certainly affect the actual construction progress and make a large deviation between the planned and actual progress, weakening the utility of construction schedule management. Therefore, the schedule plan that satisfies both process constraints and resource constraints is more suitable for guiding on-site construction management. Moreover, in the actual construction management, due to the influence of various uncertainties and changes in the focus of management objectives, it is necessary to adjust the construction schedule plan for resource and schedule optimization in time. The resource-constrained project scheduling problem (RCPSP) is a typical operations research problem, which is one of the hot research topics in recent years. According to the different settings and focus of the research problem, researchers have proposed various scheduling schemes and solution algorithms.

A typical resource-constrained project scheduling problem (RCPSP) can be described as follows: In a project, there are J jobs included. Due to technical requirements, there is a tight precedence relationship between some jobs, for example, job j cannot be started until any of its tight precedence jobs h, h ∈ Pj (Pj is the set of tight precedence jobs of the job) is completed. The structure of the whole project is represented by a directed network diagram, in which the nodes represent the jobs and the arcs represent the immediately preceding relations among the jobs. The sequential numbering of the jobs in the diagram should ensure that the job number in P is less than j. Job 1 is the only earliest job to start and job J is the only latest job to complete, both are virtual jobs (no resource consumption and execution time of 0), and represent the beginning and end of the entire project, respectively. A feasible plan requires that the start time of each job has been determined, and meet both inter-job tight ahead constraints and resource constraints.

Let job j (j=1, 2, ..., J) requires a kth resource amount of rjk to complete and an execution time of d. The total kth resource amount is a constant Rk (k = 1, 2, ..., k), the start time of the work is Sj, and At is the set of ongoing work in the period (t-1, t], then a typical resource-constrained engineering scheduling problem can be mathematically modeled as follows [9,10].

（1）

（2）

（3）

Eq. (1) is the objective function expression, which indicates that the objective is to minimize the duration; Eq. (2) is the immediate preceding constraint expression, which represents that all operations can start only after their immediate preceding operations are completed; Eq. (3) is the resource constraint expression, which indicates that the total resource consumption of all executed operations cannot exceed the agreed total resources per day during the project start.

Mathematically, RCPSP belongs to the NP-hard problem, i.e., under the assumption that P ≠ NP, no algorithm can be found that guarantees an optimal solution in polynomial time. There are two directions of solution schemes for this class of problems: the full algorithm is guaranteed to get the optimal solution, but the running time is of exponential complexity and thus difficult to adapt to large-scale instances; the approximation algorithm, on the other hand, only requires finding an approximate solution that can end in polynomial time, and the RCPSP problem mainly uses heuristic algorithms to seek an approximate solution that meets the objective. At present, a considerable number of heuristic algorithms such as genetic algorithms (GA), ant colony algorithms (ACO), and particle swarm algorithms (PSO) have been applied to the solution of RCPSP problems.

# 3 Literature Review

Algorithms for solving RCPSP problems can be roughly divided into two main categories: the accurate algorithm and the metaheuristic algorithm which can also be called an intelligent optimization algorithm.

## 3.1 Resource-constrained project scheduling problem based on accurate algorithm

In 1967, Johnson [1] first used a branch-and-bound method to solve the RCPSP problem in his Ph.D. thesis. Most branch-and-bound methods use depth-first search of enumeration trees, and the branching process contains various methods for expansion part scheduling. The number of possible choices for expanding partial scheduling is reduced by using lower bound and dominance laws as well as direct selection.

Branch delimitation methods for solving problems can be classified into four categories: (i) branch delimitation algorithms based on timing trees [2,3], (ii) branch delimitation algorithms based on extended substitution sets [4], (iii) branch delimitation algorithms based on delayed substitution sets [5], and (iv) branch delimitation algorithms based on scheduling schemes [6].

Patterson [2] used a temporal tree as the basis of the algorithm, with a virtual start activity as the root node and a search tree with layers, where each node of the search tree corresponds to an activity and each layer of the search tree is gradually expanded according to the temporal relationship constraints between activities.

Sprercher[3] extended on Patterson's basis by proposing a more powerful pruning technique making the algorithm more efficient.

Stinson[4] proposed a branch delimitation algorithm based on extended substitution sets, which uses decision time points as nodes of the search tree as opposed to activity-based temporal tree algorithms.

Christofides[5] proposed the concept of delayed substitution sets. While the decisions in the previous two algorithms cannot be changed once they are determined in the previous phase, the scheduling determined in the previous phase in the delayed substitution set-based algorithm may be delayed in the later phase.

Brucker[6] proposed a branch delimitation method for representing the nodes of a search tree in terms of a scheduling scheme by introducing relationships between individual activities.

## 3.2 Resource-constrained project scheduling problem based on genetic algorithm

The genetic algorithm (GA) is a method to search for the optimal individual (solution of the problem) in a given environment (problem domain) based on biological genetic and evolutionary theories. The inherent parallel search properties, strong robustness, and simplicity of implementation of genetic algorithms have shown superior performance in solving a large number of complex combinatorial optimization problems. Since 1985, when Davis first used a genetic algorithm to solve scheduling problems, the algorithm has been used more and more widely in the field of scheduling. The genetic algorithm is applied to RCPSP, focusing on the chromosome (individual) representation, genetic operations, and scheduling generation schemes.

Hartmann[7], Alcaraz[8] and Valls[9] et al. have studied RCPSP using genetic algorithms based on task list encoding, where the adaptive genetic algorithm proposed by Hartmann and the peak cross genetic algorithm proposed by Valls have better performance.

Hartmann[7] proposed a genetic algorithm with an activity set as genetic encoding and compared it with seven other heuristic algorithms by thinking of a case for solving and proving the superiority of this genetic algorithm.

Alcaraz[8] proposed a robust genetic algorithm to solve a single-mode resource-constrained project scheduling problem and used a new crossover method in this approach.

Valls[9] proposed a hybrid genetic algorithm (HGA) which is divided into two phases, the first phase follows the conventional genetic algorithm and the second phase starts the operation based on the neighboring populations of the results of the first phase as the initial populations. In addition to this, the authors have solved the problem in PSPLIB instance sets j60 and j120 by using this scheme and compared it with other good algorithms.

The RCPSP using priority number encoding based genetic algorithm has been studied by Leo[10], Hindi[11], Mendes[12], and Debel[13], among which the genetic algorithm proposed by Mendes and the genetic algorithm proposed by Debel have better performance.

Leo[10] studied a genetic algorithm based on priority coding and combined this genetic algorithm with problem space neighborhoods and proved that the method can effectively solve the resource-constrained scheduling problem using cases.

Hindi [11] proposed a genetic algorithm based on priority coding and proved the usefulness of the algorithm by solving a scheduling case consisting of 330 activities and a case consisting of 2370 activities, respectively.

Mendes[12] combined a genetic algorithm with a schedule generator program that generates parameterized activity schedules and new merit metrics to propose an algorithm called Genetic Algorithm for Project Scheduling (GAPS) and compared GAPS with 25 other algorithms through 1560 standard test problem examples were compared.

Debel[13] extended a so-called decomposition-based genetic algorithm (DBGA) and proposed a new genetic algorithm (GA) capable of providing near-optimal heuristic solutions.

## 3.3 Resource-constrained project scheduling problem based on genetic algorithm

Swarming insects use collective power to forage, defend against enemies, and build nests, and individual individuals can only perform simple tasks, while a group of individual individuals can perform complex tasks. For example, bees collect nectar, build nests, and ants forage and build nests. The algorithms designed by studying the principles of swarm intelligence are called swarm intelligence algorithms, which are inspired by the cooperation of swarming insects in their work. Particle Swarm Optimization (PSO) is an evolutionary algorithm based on the swarm intelligence approach, which was proposed by Kenndy, an American social psychologist, and Eberhart, an electrical engineer [14-17], and inspired by the results of the Artificial life study. The basic concept originated from the study of the predatory behavior of bird flocks. The particle swarm algorithm is similar to other evolutionary algorithms in that it moves the individuals in the population to a good area according to their adaptation to the environment; the difference is that it does not use evolutionary operators for individuals like other evolutionary algorithms, but treats each individual as a particle with no mass and no volume in the search space, and flies at a certain speed in the search space. By learning and adapting to the environment, the flight speed is dynamically adjusted according to the combined analysis of individual and group flight experiences.

The first one is the priority-based particle swarm algorithm, which adopts the encoding of priority and searches the continuous space, and can be solved directly by the original PSO algorithm; the other one is the alignment-based particle swarm algorithm, which adopts the encoding of activity list and searches the discrete space, and needs to use the DPSO algorithm.

The fundamental difference between these two approaches is that the priority coding needs to give priority to the inter-activity immediate precedence and posteriority constraints in the decoding process, and then scheduling according to the coding priority; while the immediate precedence and posteriority constraints of the activity list are manifested in the initialization process of coding and the "migration" process of particles.

Zhang [18] investigated PSO based on priority number and task list-based representations of PSO.

Linyi Deng [19] used an activity alignment-based particle swarm algorithm to solve the RCPSP problem by updating the particle encoding through the intersection of particle point locations.

Wang Wei [20] also introduced the priority-based particle swarm algorithm based on activity alignment and used the activity alignment-based particle swarm algorithm and genetic algorithm to solve an RCPSP algorithm simultaneously, concluding that the computation time of the PSO algorithm and the probability of obtaining the optimal solution is much higher than that of the GA algorithm.

# 4 Methods

With the construction plan as the main body, according to the plan to the construction process implementation and construction process monitoring, for the entire project department organizational structure, in accordance with the principle of mutual collaboration of their respective responsibilities. The front-end of the system is built using Vue framework, the back-end uses Spring boot, the database uses MySQL, and JDBC uses mybatis framework.

Step 1 WBS decomposition and the process of resource allocation. The project is divided to the bottom level by top-down configuration and all the jobs are imposed with due tight front and back constraints, and after that the resources are configured for each bottom level job.

Step 2 Design of scheduling algorithm. Based on the resource and cost information derived from the job decomposition in the previous step, and the backward and forward relationships among the jobs, an improved particle swarm algorithm is used to obtain a plan with relatively optimal duration and resource load balance. After that, the plan is coded by back-to-forth planning method to identify the key chains corresponding to the plan and build buffers for them.

Step 3 Construction process management. During the construction process, according to the two roles of project manager and builder in the construction of different jobs, each job is managed through the workflow to achieve real-time construction progress update, which is convenient for the project manager to control the progress and resource usage during the whole construction process.

Step 4 is the reporting and monitoring function of the system. The reports are mainly provided to the project manager to summarize the project every week, and show the progress and resource usage of the smart construction site in the form of charts and graphs to improve the project manager's refinement management of the smart construction site. Monitoring function is the system to monitor the progress and cost of construction execution, through early warning to avoid delays or resource shortages, and when the actual progress and cost deviate from the plan by a certain amount, the system will analyze which operation or operations have problems and how to eliminate such deviations through the multi-level earned value method, which improves the system's intelligent management of the smart construction construction site. Management degree.

The most critical and difficult step in the whole system is the scheduling algorithm, which I plan to use particle swarm algorithm to solve.

When PSO solves an optimization problem, the solution of the problem corresponds to the position of a bird in the search space, calling these birds "particles" (particles) or "subjects" (agents) Each particle has its position and velocity (which determines direction and distance of flight), and an adaptation value determined by the function being optimized. Each particle remembers, follows the current optimal particle, and searches in the solution space. The process of each iteration is not completely random, and if a better solution is found, it will be used as a basis to find the next solution. The particle updates its velocity and position according to the following equations (3) and (4). The information of particle i can be represented by a D-dimensional vector, and the position is denoted as, and the velocity is, and the other vectors are similar. Then the velocity and position update equations are

（3）

（4）

is the velocity of particle i in dimension d in the kth iteration;  is the current position of particle i in dimension d in the kth iteration;  is a random number between [0, 1];  is the position (i.e., coordinates) of the individual extremum of particle i in dimension d;  is the position of the global extremum of the whole swarm in dimension d. c1, c2 are acceleration factors (or learning factors) that regulate the direction toward the global best particle and the individual best particle, respectively The maximum step of the flight, if too small, the particles may move away from the target region, if too large, it will lead to sudden flight toward or over the target region. A suitable c1, c2 can speed up the convergence and is less likely to fall into the local optimum, usually so that c1=c2=2. The specific RCPSP solution process will not be introduced due to space limitation.

# 5 Result

The results of the scheduling algorithm will be used as a case study with the help of the PSPLIB standard problem set, and a time scheduling table will be used as a scheduling result to measure the excellence of the algorithm based on the average minimum duration of the scheduling result and the computing time.

The system will show the architecture, process and key interfaces as a result.

# 6 Evaluation

In order to promote the standardization and informatization of construction schedule management, ensure the construction period and construction quality, reasonably allocate construction resources, and propose the optimization method of construction schedule plan for project team under resource constraints, which helps to improve the utilization rate of construction resources and make the project team work period reach the shortest. However, due to the unsoundness of personal knowledge system and time reasons, the factors considered in the construction schedule plan are not comprehensive enough. In order to obtain better schedule management, based on the research in this paper, the subject members can conduct in-depth research in the following aspects, mainly including:

1) The model mainly considers the resource constraints and the immediately preceding constraint relationship between sub-projects, but in the actual renovation, there are also space constraints, i.e. some sub-projects cannot be carried out at the same time due to the limited space in the residence although there is no immediately preceding constraint relationship.

(2) In order to facilitate the solution, the model only considers one execution mode of subprojects, i.e., a subproject has only one resource demand, and once the resource demand is not reached, the execution cannot be started. However, in the actual renovation construction process, the number of subprojects into groups is not unique, i.e., residential subprojects have multiple execution modes.

(3) Construction schedule management can be affected by many contingent factors, and the degree of influence can be great, such as the painting project is affected by the weather. Considering adding these chance factors to the model with certain probability will make the construction schedule more flexible and operable, and more in line with the actual process of renovation.

# Reference

- Johnson, Thomas Joel Russell. An algorithm for the resource constrained project scheduling problem. Diss. Massachusetts Institute of Technology, 1967.

- Patterson, James H. "A comparison of exact approaches for solving the multiple constrained resource, project scheduling problem." Management science 30.7 (1984): 854-867.

- Sprecher A. Scheduling resource-constrained projects competitively at modest memory requirements[J]. Management science, 2000, 46(5): 710-723.

- Stinson, Joel P., Edward W. Davis, and Basheer M. Khumawala. "Multiple resource–constrained scheduling using branch and bound." AIIE Transactions 10.3 (1978): 252-259.

- Christofides, Nicos, Ramon Alvarez-Valdés, and José M. Tamarit. "Project scheduling with resource constraints: A branch and bound approach." European Journal of Operational Research 29.3 (1987): 262-273.

- Brucker, Peter, et al. "A branch and bound algorithm for the resource-constrained project scheduling problem." European journal of operational research 107.2 (1998): 272-288.

- Hartmann, Sönke. "A competitive genetic algorithm for resource‐constrained project scheduling." Naval Research Logistics (NRL) 45.7 (1998): 733-750.

- Alcaraz, Javier, and Concepción Maroto. "A robust genetic algorithm for resource allocation in project scheduling." Annals of operations Research 102.1 (2001): 83-109.

- Valls, Vicente, Francisco Ballestin, and Sacramento Quintanilla. "A hybrid genetic algorithm for the resource-constrained project scheduling problem." European journal of operational research 185.2 (2008): 495-508.

- Leon, V. Jorge, and Ramamoorthy Balakrishnan. "Strength and adaptability of problem-space based neighborhoods for resource-constrained scheduling." Operations-Research-Spektrum 17.2 (1995): 173-182.

- Hindi, Khalil S., Hongbo Yang, and Krzysztof Fleszar. "An evolutionary algorithm for resource-constrained project scheduling." IEEE Transactions on evolutionary computation 6.5 (2002): 512-518.

- Mendes, Jorge JM, José Fernando Gonçalves, and Mauricio GC Resende. "A random key based genetic algorithm for the resource constrained project scheduling problem." Computers & operations research 36.1 (2009): 92-109.

- Debels, Dieter, and Mario Vanhoucke. "A decomposition-based genetic algorithm for the resource-constrained project-scheduling problem." Operations Research 55.3 (2007): 457-469.

- Eberhart, Russell, and James Kennedy. "A new optimizer using particle swarm theory." MHS'95. Proceedings of the sixth international symposium on micro machine and human science. Ieee, 1995.

- Kennedy, James, and Russell Eberhart. "Particle swarm optimization." Proceedings of ICNN'95-international conference on neural networks. Vol. 4. IEEE, 1995.

- Shi, Yuhui, and Russell C. Eberhart. "Parameter selection in particle swarm optimization." International conference on evolutionary programming. Springer, Berlin, Heidelberg, 1998.

- Kennedy, James, and Russell C. Eberhart. "A discrete binary version of the particle swarm algorithm." 1997 IEEE International conference on systems, man, and cybernetics. Computational cybernetics and simulation. Vol. 5. IEEE, 1997.

- Zhang, Hong, Heng Li, and C. M. Tam. "Particle swarm optimization for resource-constrained project scheduling." International Journal of Project Management 24.1 (2006): 83-92.

- 邓林义,and 林焰."粒子群算法求解任务可拆分项目调度问题." 控制与决策 .06(2008):681-684+688. doi:10.13195/j.cd.2008.06.83.dengly.006.

- 王巍,and 赵国杰."粒子群优化在资源受限工程调度问题中的应用." 哈尔滨工业大学学报 .04(2007):669-672.

itle

Construction project schedule management system based on particle swarm optimization

2 Introduce

Modern project management is a new field of management discipline developed in recent years, which is very different from general operation enterprise management in terms of principles and methods, and has gradually formed a more complete discipline system, and established several international modern project management associations, including the International Project Management Association (IPMA), mainly in Europe, and the Project Management Institute (PMI), led by the United States, as representatives.

With the development of information technology and the prevalence of outsourcing, the interconnectedness of businesses is becoming more and more evident and the traditional vertically integrated mode of operation is increasingly being replaced by a horizontal, hypertextual one. This means that the traditional boundaries of the enterprise are becoming increasingly blurred and are gradually disappearing. In this context, business activities will increasingly be run as projects. It is in this sense that project-centered activities, rather than organizational structures, are becoming more and more common, and it is in this sense that project management is becoming more and more popular.

1984, PMI developed "The Guide to the Project Management Body of Knowledge" (PMBOK) in an attempt to establish a global project management standard. In 1987 and 1996, the PMBOK was revised twice. The document has been recognized as a global standard by the world project management community. The International Organization for Standardization (ISO) also used the document as a framework to develop the ISO10006 standard.

PMI divides the process of project management into the following three major processes: I. The project planning process, II. Project execution process, and III. Project monitoring process.

The main tasks of the project planning process include: establishing the WBS plan, confirming the project process, confirming a detailed project plan, plan review, approving the project plan, determining the project plan baseline, etc.; the tasks of project execution and monitoring process include: executing the project plan, managing project, monitoring project plan, and completion, project change control, project process review, etc.

At the present stage, construction schedule management is mainly based on the traditional task decomposition after the process constraints to develop the schedule plan to guide the on-site construction management. However, the execution of each construction task will take up the corresponding resources, and if the resources required for a task are occupied by other tasks, the task can only wait for the release of its required resources, which will certainly affect the actual construction progress and make a large deviation between the planned and actual progress, weakening the utility of construction schedule management. Therefore, the schedule plan that satisfies both process constraints and resource constraints is more suitable for guiding on-site construction management. Moreover, in the actual construction management, due to the influence of various uncertainties and changes in the focus of management objectives, it is necessary to adjust the construction schedule plan for resource and schedule optimization in time. The resource-constrained project scheduling problem (RCPSP) is a typical operations research problem, which is one of the hot research topics in recent years. According to the different settings and focus of the research problem, researchers have proposed various scheduling schemes and solution algorithms.

A typical resource-constrained project scheduling problem (RCPSP) can be described as follows: In a project, there are J jobs included. Due to technical requirements, there is a tight precedence relationship between some jobs, for example, job j cannot be started until any of its tight precedence jobs h, h ∈ Pj (Pj is the set of tight precedence jobs of the job) is completed. The structure of the whole project is represented by a directed network diagram, in which the nodes represent the jobs and the arcs represent the immediately preceding relations among the jobs. The sequential numbering of the jobs in the diagram should ensure that the job number in P is less than j. Job 1 is the only earliest job to start and job J is the only latest job to complete, both are virtual jobs (no resource consumption and execution time of 0), and represent the beginning and end of the entire project, respectively. A feasible plan requires that the start time of each job has been determined, and meet both inter-job tight ahead constraints and resource constraints.

Let job j (j=1, 2, ..., J) requires a kth resource amount of rjk to complete and an execution time of d. The total kth resource amount is a constant Rk (k = 1, 2, ..., k), the start time of the work is Sj, and At is the set of ongoing work in the period (t-1, t], then a typical resource-constrained engineering scheduling problem can be mathematically modeled as follows [9,10].

（1）

（2）

（3）

Eq. (1) is the objective function expression, which indicates that the objective is to minimize the duration; Eq. (2) is the immediate preceding constraint expression, which represents that all operations can start only after their immediate preceding operations are completed; Eq. (3) is the resource constraint expression, which indicates that the total resource consumption of all executed operations cannot exceed the agreed total resources per day during the project start.

Mathematically, RCPSP belongs to the NP-hard problem, i.e., under the assumption that P ≠ NP, no algorithm can be found that guarantees an optimal solution in polynomial time. There are two directions of solution schemes for this class of problems: the full algorithm is guaranteed to get the optimal solution, but the running time is of exponential complexity and thus difficult to adapt to large-scale instances; the approximation algorithm, on the other hand, only requires finding an approximate solution that can end in polynomial time, and the RCPSP problem mainly uses heuristic algorithms to seek an approximate solution that meets the objective. At present, a considerable number of heuristic algorithms such as genetic algorithms (GA), ant colony algorithms (ACO), and particle swarm algorithms (PSO) have been applied to the solution of RCPSP problems.

3 Literature Review

Algorithms for solving RCPSP problems can be roughly divided into two main categories: the accurate algorithm and the metaheuristic algorithm which can also be called an intelligent optimization algorithm.

3.1 Resource-constrained project scheduling problem based on accurate algorithm

In 1967, Johnson [1] first used a branch-and-bound method to solve the RCPSP problem in his Ph.D. thesis. Most branch-and-bound methods use depth-first search of enumeration trees, and the branching process contains various methods for expansion part scheduling. The number of possible choices for expanding partial scheduling is reduced by using lower bound and dominance laws as well as direct selection.

Branch delimitation methods for solving problems can be classified into four categories: (i) branch delimitation algorithms based on timing trees [2,3], (ii) branch delimitation algorithms based on extended substitution sets [4], (iii) branch delimitation algorithms based on delayed substitution sets [5], and (iv) branch delimitation algorithms based on scheduling schemes [6].

Patterson [2] used a temporal tree as the basis of the algorithm, with a virtual start activity as the root node and a search tree with layers, where each node of the search tree corresponds to an activity and each layer of the search tree is gradually expanded according to the temporal relationship constraints between activities.

Sprercher[3] extended on Patterson's basis by proposing a more powerful pruning technique making the algorithm more efficient.

Stinson[4] proposed a branch delimitation algorithm based on extended substitution sets, which uses decision time points as nodes of the search tree as opposed to activity-based temporal tree algorithms.

Christofides[5] proposed the concept of delayed substitution sets. While the decisions in the previous two algorithms cannot be changed once they are determined in the previous phase, the scheduling determined in the previous phase in the delayed substitution set-based algorithm may be delayed in the later phase.

Brucker[6] proposed a branch delimitation method for representing the nodes of a search tree in terms of a scheduling scheme by introducing relationships between individual activities.

3.2 Resource-constrained project scheduling problem based on genetic algorithm

The genetic algorithm (GA) is a method to search for the optimal individual (solution of the problem) in a given environment (problem domain) based on biological genetic and evolutionary theories. The inherent parallel search properties, strong robustness, and simplicity of implementation of genetic algorithms have shown superior performance in solving a large number of complex combinatorial optimization problems. Since 1985, when Davis first used a genetic algorithm to solve scheduling problems, the algorithm has been used more and more widely in the field of scheduling. The genetic algorithm is applied to RCPSP, focusing on the chromosome (individual) representation, genetic operations, and scheduling generation schemes.

Hartmann[7], Alcaraz[8] and Valls[9] et al. have studied RCPSP using genetic algorithms based on task list encoding, where the adaptive genetic algorithm proposed by Hartmann and the peak cross genetic algorithm proposed by Valls have better performance.

Hartmann[7] proposed a genetic algorithm with an activity set as genetic encoding and compared it with seven other heuristic algorithms by thinking of a case for solving and proving the superiority of this genetic algorithm.

Alcaraz[8] proposed a robust genetic algorithm to solve a single-mode resource-constrained project scheduling problem and used a new crossover method in this approach.

Valls[9] proposed a hybrid genetic algorithm (HGA) which is divided into two phases, the first phase follows the conventional genetic algorithm and the second phase starts the operation based on the neighboring populations of the results of the first phase as the initial populations. In addition to this, the authors have solved the problem in PSPLIB instance sets j60 and j120 by using this scheme and compared it with other good algorithms.

The RCPSP using priority number encoding based genetic algorithm has been studied by Leo[10], Hindi[11], Mendes[12], and Debel[13], among which the genetic algorithm proposed by Mendes and the genetic algorithm proposed by Debel have better performance.

Leo[10] studied a genetic algorithm based on priority coding and combined this genetic algorithm with problem space neighborhoods and proved that the method can effectively solve the resource-constrained scheduling problem using cases.

Hindi [11] proposed a genetic algorithm based on priority coding and proved the usefulness of the algorithm by solving a scheduling case consisting of 330 activities and a case consisting of 2370 activities, respectively.

Mendes[12] combined a genetic algorithm with a schedule generator program that generates parameterized activity schedules and new merit metrics to propose an algorithm called Genetic Algorithm for Project Scheduling (GAPS) and compared GAPS with 25 other algorithms through 1560 standard test problem examples were compared.

Debel[13] extended a so-called decomposition-based genetic algorithm (DBGA) and proposed a new genetic algorithm (GA) capable of providing near-optimal heuristic solutions.

3.3 Resource-constrained project scheduling problem based on genetic algorithm

Swarming insects use collective power to forage, defend against enemies, and build nests, and individual individuals can only perform simple tasks, while a group of individual individuals can perform complex tasks. For example, bees collect nectar, build nests, and ants forage and build nests. The algorithms designed by studying the principles of swarm intelligence are called swarm intelligence algorithms, which are inspired by the cooperation of swarming insects in their work. Particle Swarm Optimization (PSO) is an evolutionary algorithm based on the swarm intelligence approach, which was proposed by Kenndy, an American social psychologist, and Eberhart, an electrical engineer [14-17], and inspired by the results of the Artificial life study. The basic concept originated from the study of the predatory behavior of bird flocks. The particle swarm algorithm is similar to other evolutionary algorithms in that it moves the individuals in the population to a good area according to their adaptation to the environment; the difference is that it does not use evolutionary operators for individuals like other evolutionary algorithms, but treats each individual as a particle with no mass and no volume in the search space, and flies at a certain speed in the search space. By learning and adapting to the environment, the flight speed is dynamically adjusted according to the combined analysis of individual and group flight experiences.

The first one is the priority-based particle swarm algorithm, which adopts the encoding of priority and searches the continuous space, and can be solved directly by the original PSO algorithm; the other one is the alignment-based particle swarm algorithm, which adopts the encoding of activity list and searches the discrete space, and needs to use the DPSO algorithm.

The fundamental difference between these two approaches is that the priority coding needs to give priority to the inter-activity immediate precedence and posteriority constraints in the decoding process, and then scheduling according to the coding priority; while the immediate precedence and posteriority constraints of the activity list are manifested in the initialization process of coding and the "migration" process of particles.

Zhang [18] investigated PSO based on priority number and task list-based representations of PSO.

Linyi Deng [19] used an activity alignment-based particle swarm algorithm to solve the RCPSP problem by updating the particle encoding through the intersection of particle point locations.

Wang Wei [20] also introduced the priority-based particle swarm algorithm based on activity alignment and used the activity alignment-based particle swarm algorithm and genetic algorithm to solve an RCPSP algorithm simultaneously, concluding that the computation time of the PSO algorithm and the probability of obtaining the optimal solution is much higher than that of the GA algorithm.

4 Methods

With the construction plan as the main body, according to the plan to the construction process implementation and construction process monitoring, for the entire project department organizational structure, in accordance with the principle of mutual collaboration of their respective responsibilities. The front-end of the system is built using Vue framework, the back-end uses Spring boot, the database uses MySQL, and JDBC uses mybatis framework.

Step 1 WBS decomposition and the process of resource allocation. The project is divided to the bottom level by top-down configuration and all the jobs are imposed with due tight front and back constraints, and after that the resources are configured for each bottom level job.

Step 2 Design of scheduling algorithm. Based on the resource and cost information derived from the job decomposition in the previous step, and the backward and forward relationships among the jobs, an improved particle swarm algorithm is used to obtain a plan with relatively optimal duration and resource load balance. After that, the plan is coded by back-to-forth planning method to identify the key chains corresponding to the plan and build buffers for them.

Step 3 Construction process management. During the construction process, according to the two roles of project manager and builder in the construction of different jobs, each job is managed through the workflow to achieve real-time construction progress update, which is convenient for the project manager to control the progress and resource usage during the whole construction process.

Step 4 is the reporting and monitoring function of the system. The reports are mainly provided to the project manager to summarize the project every week, and show the progress and resource usage of the smart construction site in the form of charts and graphs to improve the project manager's refinement management of the smart construction site. Monitoring function is the system to monitor the progress and cost of construction execution, through early warning to avoid delays or resource shortages, and when the actual progress and cost deviate from the plan by a certain amount, the system will analyze which operation or operations have problems and how to eliminate such deviations through the multi-level earned value method, which improves the system's intelligent management of the smart construction construction site. Management degree.

The most critical and difficult step in the whole system is the scheduling algorithm, which I plan to use particle swarm algorithm to solve.

When PSO solves an optimization problem, the solution of the problem corresponds to the position of a bird in the search space, calling these birds "particles" (particles) or "subjects" (agents) Each particle has its position and velocity (which determines direction and distance of flight), and an adaptation value determined by the function being optimized. Each particle remembers, follows the current optimal particle, and searches in the solution space. The process of each iteration is not completely random, and if a better solution is found, it will be used as a basis to find the next solution. The particle updates its velocity and position according to the following equations (3) and (4). The information of particle i can be represented by a D-dimensional vector, and the position is denoted as, and the velocity is, and the other vectors are similar. Then the velocity and position update equations are

（3）

（4）

is the velocity of particle i in dimension d in the kth iteration;  is the current position of particle i in dimension d in the kth iteration;  is a random number between [0, 1];  is the position (i.e., coordinates) of the individual extremum of particle i in dimension d;  is the position of the global extremum of the whole swarm in dimension d. c1, c2 are acceleration factors (or learning factors) that regulate the direction toward the global best particle and the individual best particle, respectively The maximum step of the flight, if too small, the particles may move away from the target region, if too large, it will lead to sudden flight toward or over the target region. A suitable c1, c2 can speed up the convergence and is less likely to fall into the local optimum, usually so that c1=c2=2. The specific RCPSP solution process will not be introduced due to space limitation.

5 Result

The results of the scheduling algorithm will be used as a case study with the help of the PSPLIB standard problem set, and a time scheduling table will be used as a scheduling result to measure the excellence of the algorithm based on the average minimum duration of the scheduling result and the computing time.

The system will show the architecture, process and key interfaces as a result.

6 Evaluation

In order to promote the standardization and informatization of construction schedule management, ensure the construction period and construction quality, reasonably allocate construction resources, and propose the optimization method of construction schedule plan for project team under resource constraints, which helps to improve the utilization rate of construction resources and make the project team work period reach the shortest. However, due to the unsoundness of personal knowledge system and time reasons, the factors considered in the construction schedule plan are not comprehensive enough. In order to obtain better schedule management, based on the research in this paper, the subject members can conduct in-depth research in the following aspects, mainly including:

1) The model mainly considers the resource constraints and the immediately preceding constraint relationship between sub-projects, but in the actual renovation, there are also space constraints, i.e. some sub-projects cannot be carried out at the same time due to the limited space in the residence although there is no immediately preceding constraint relationship.

(2) In order to facilitate the solution, the model only considers one execution mode of subprojects, i.e., a subproject has only one resource demand, and once the resource demand is not reached, the execution cannot be started. However, in the actual renovation construction process, the number of subprojects into groups is not unique, i.e., residential subprojects have multiple execution modes.

(3) Construction schedule management can be affected by many contingent factors, and the degree of influence can be great, such as the painting project is affected by the weather. Considering adding these chance factors to the model with certain probability will make the construction schedule more flexible and operable, and more in line with the actual process of renovation.

Reference

- Johnson, Thomas Joel Russell. An algorithm for the resource constrained project scheduling problem. Diss. Massachusetts Institute of Technology, 1967.

- Patterson, James H. "A comparison of exact approaches for solving the multiple constrained resource, project scheduling problem." Management science 30.7 (1984): 854-867.

- Sprecher A. Scheduling resource-constrained projects competitively at modest memory requirements[J]. Management science, 2000, 46(5): 710-723.

- Stinson, Joel P., Edward W. Davis, and Basheer M. Khumawala. "Multiple resource–constrained scheduling using branch and bound." AIIE Transactions 10.3 (1978): 252-259.

- Christofides, Nicos, Ramon Alvarez-Valdés, and José M. Tamarit. "Project scheduling with resource constraints: A branch and bound approach." European Journal of Operational Research 29.3 (1987): 262-273.

- Brucker, Peter, et al. "A branch and bound algorithm for the resource-constrained project scheduling problem." European journal of operational research 107.2 (1998): 272-288.

- Hartmann, Sönke. "A competitive genetic algorithm for resource‐constrained project scheduling." Naval Research Logistics (NRL) 45.7 (1998): 733-750.

- Alcaraz, Javier, and Concepción Maroto. "A robust genetic algorithm for resource allocation in project scheduling." Annals of operations Research 102.1 (2001): 83-109.

- Valls, Vicente, Francisco Ballestin, and Sacramento Quintanilla. "A hybrid genetic algorithm for the resource-constrained project scheduling problem." European journal of operational research 185.2 (2008): 495-508.

- Leon, V. Jorge, and Ramamoorthy Balakrishnan. "Strength and adaptability of problem-space based neighborhoods for resource-constrained scheduling." Operations-Research-Spektrum 17.2 (1995): 173-182.

- Hindi, Khalil S., Hongbo Yang, and Krzysztof Fleszar. "An evolutionary algorithm for resource-constrained project scheduling." IEEE Transactions on evolutionary computation 6.5 (2002): 512-518.

- Mendes, Jorge JM, José Fernando Gonçalves, and Mauricio GC Resende. "A random key based genetic algorithm for the resource constrained project scheduling problem." Computers & operations research 36.1 (2009): 92-109.

- Debels, Dieter, and Mario Vanhoucke. "A decomposition-based genetic algorithm for the resource-constrained project-scheduling problem." Operations Research 55.3 (2007): 457-469.

- Eberhart, Russell, and James Kennedy. "A new optimizer using particle swarm theory." MHS'95. Proceedings of the sixth international symposium on micro machine and human science. Ieee, 1995.

- Kennedy, James, and Russell Eberhart. "Particle swarm optimization." Proceedings of ICNN'95-international conference on neural networks. Vol. 4. IEEE, 1995.

- Shi, Yuhui, and Russell C. Eberhart. "Parameter selection in particle swarm optimization." International conference on evolutionary programming. Springer, Berlin, Heidelberg, 1998.

- Kennedy, James, and Russell C. Eberhart. "A discrete binary version of the particle swarm algorithm." 1997 IEEE International conference on systems, man, and cybernetics. Computational cybernetics and simulation. Vol. 5. IEEE, 1997.

- Zhang, Hong, Heng Li, and C. M. Tam. "Particle swarm optimization for resource-constrained project scheduling." International Journal of Project Management 24.1 (2006): 83-92.

- 邓林义,and 林焰."粒子群算法求解任务可拆分项目调度问题." 控制与决策 .06(2008):681-684+688. doi:10.13195/j.cd.2008.06.83.dengly.006.

- 王巍,and 赵国杰."粒子群优化在资源受限工程调度问题中的应用." 哈尔滨工业大学学报 .04(2007):669-672.

APPLICATION FOR ETHICAL APPROVAL

In order for research to result in benefit and minimise risk of harm, it must be conducted ethically. A researcher may not be covered by the University’s insurance if ethical approval has not been obtained prior to commencement.

The University follows the OECD Frascati manual definition of research activity: “creative work undertaken on a systematic basis in order to increase the stock of knowledge, including knowledge of man, culture and society, and the use of this stock of knowledge to devise new applications”. As such this covers activities undertaken by members of staff, postgraduate research students, and both taught postgraduate and undergraduate students working on dissertations/projects.

The individual undertaking the research activity is known as the “principal researcher”.

Ethical approval is not required for routine audits, performance reviews, quality assurance studies, testing within normal educational requirements, and literary or artistic criticism.

Please read the notes for guidance before completing ALL sections of the form.

This form must be completed and approved prior to undertaking any research activity. Please see Checklist for details of process for different categories of application.

Delete the Guidance Notes at the end of the form BEFORE submitting your application

SECTION A: About You (Principal Researcher)

| 1 | Full Name: |  | Ben Wang |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 2 | Tick all boxes which apply: |  | Member of staff: | ☐ | Honorary research fellow: | ☐ |
| 3 | Undergraduate Student | ☐ | Taught Postgraduate Student | ☐ | Postgraduate Research Student | ☒ |

| 4 | Institute/Academic Discipline/Centre: | University of Wales Trinity Saint David |
| --- | --- | --- |
| 5 | Campus: | SA1 8PH |
| 6 | E-mail address: | 2106352@student.uwtsd.ac.uk |
| 7 | Contact Telephone Number: | +86-13637825478 |
|  | For students: |  |
| 8 | Student Number: | 2106352 |
| 9 | Programme of Study: | MSc Software Engineering |
| 10 | Director of Studies/Supervisor: | Tim Bashford |

SECTION B: Approval for Research Activity

| 1 | Has the research activity received approval in principle? (please check the Guidance Notes as to the appropriate approval process for different levels of research by different categories of individual) |  | YES | ☒ | NO | ☐ |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Date |  |
| 2 | If Yes, please indicate source of approval (and date where known): Approval in principle must be obtained from the relevant source prior to seeking ethical approval | Research Degrees Committee |  | ☒ | 31/03/2022 |  |
| 3 |  | Institute Research Committee |  | ☐ |  |  |
| 4 |  | Other (write in) |  | ☐ |  |  |

SECTION C:  Internal and External Ethical Guidance Materials

|  | Please list the core ethical guidance documents that have been referred to during the completion of this form (including any discipline-specific codes of research ethics, and also any specific ethical guidance relating to the proposed methodology). Please tick to confirm that your research proposal adheres to these codes and guidelines. |  |
| --- | --- | --- |
| 1 | UWTSD Research Ethics & Integrity Code of Practice | ☒ |
| 2 | UWTSD Research Data Management Policy | ☐ |
| 3 |  | ☐ |

SECTION D: External Collaborative Research Activity

| 1 | Does the research activity involve collaborators outside of the University? |  | YES | ☐ | NO | ☒ |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | If Yes, please provide the name of the external organisation and name and contact details for the main contact person and confirmation this person has consented to their personal data being shared.as part of this collaboration. |  |  |  |  |  |  |  |
| 3 | Institution |  |  |  |  |  |  |  |
| 4 | Contact person name |  |  |  |  |  |  |  |
| 5 | Contact person e-mail address |  |  |  |  |  |  |  |
| 6 | Has this individual consented to sharing their details on this form? |  | YES | ☐ | NO |  |  | ☐ |
| 7 | Are you in receipt of a KESS scholarship? |  | YES | ☐ | NO |  |  | ☐ |
| 8 | Is your research externally funded |  | YES | ☐ | NO |  |  | ☐ |
| 9 | Are you specifically employed to undertake this research in either a paid or voluntary capacity? | Voluntary | YES | ☐ | NO |  | ☐ |  |
| 10 |  | Employed | YES | ☐ | NO |  | ☐ |  |
| 11 | Is the research being undertaken within an existing UWTSD Athrofa Professional Learning Partnership (APLP) | If YES then the permission question below does not need to be answered. | YES | ☐ | NO |  |  | ☐ |
| 12 | Permission to undertake the research has been provided by the partner organisation | (If YES attach copy) If NO the application cannot continue | YES | ☐ | NO |  |  | ☐ |

Where research activity is carried out in collaboration with an external organisation

| 13 | Does this organisation have its own ethics approval system? | YES | ☐ | NO | ☐ |
| --- | --- | --- | --- | --- | --- |
| 14 | If Yes, please attach a copy of any final approval (or interim approval) from the organisation |  |  |  |  |

SECTION E: Details of Research Activity

| 1 | Indicative title: | Construction project schedule management system based on particle swarm optimization |  |  |
| --- | --- | --- | --- | --- |
| 2 | Proposed start date: | 10/05/2022 | Proposed end date: | 18/07/2022 |
| 3 | Introduction to the Research (maximum 300 words) Ensure that you write for a Non-Specialist Audience when outlining your response to the three points below: - Purpose of Research Activity - Proposed Research Question - Aims of Research Activity - Objectives of Research Activity Demonstrate, briefly, how Existing Research has informed the proposed activity and explain - What the research activity will add to the body of knowledge - How it addresses an area of importance. |  |  |  |
| 4 | Purpose of Research Activity Project schedule management can improve construction project construction quality, shorten construction cycle and save construction funds. The scheduling of project schedule has always been a difficult point in project management. The automatic scheduling function of the schedule in the project schedule management system can largely simplify the process of schedule development. (this box should expand as you type) |  |  |  |
| 5 | Research Question Most of the research on project schedule management has focused on one of the modules of project schedule planning, project schedule execution and project schedule monitoring, and few of them have systematically integrated the above three modules to form a complete system. In the area of scheduling, the mainstream research direction is the study of single-objective resource-constrained project scheduling problem. Solving this problem can obtain a project execution plan with the shortest duration, but an executable construction plan actually needs to optimize multiple objectives such as resource load balance and cost fluctuation level of the project. Therefore, there is an urgent need for an algorithm to solve the multi-objective resource-constrained project scheduling problem. (this box should expand as you type) |  |  |  |
| 6 | Aims of Research Activity (1) Design and build the construction project schedule management system, including project schedule planning module, project schedule execution module and project schedule monitoring module. These three modules need to interact and depend on each other to form an organic whole. (2) Solve the multi-objective resource-constrained project scheduling problem based on the improved particle swarm algorithm, and apply this function to the project schedule planning module, so that users can easily obtain a schedule with relatively short duration, relatively balanced resource load and relatively small cost fluctuation. (this box should expand as you type) |  |  |  |
| 7 | Objectives of Research Activity Complete the functional design and implementation of construction project schedule management system, w'c improved particle swarm algorithm for resource-constrained project scheduling problem in project schedule management (this box should expand as you type) |  |  |  |
| 8 | Proposed methods (maximum 600 words) Provide a brief summary of all the methods that may be used in the research activity, making it clear what specific techniques may be used. If methods other than those listed in this section are deemed appropriate later, additional ethical approval for those methods will be needed. |  |  |  |
| 9 | Build a system using VUE+Springboot+mybatis+MySQL Solving resource-constrained project scheduling problems using particle swarm algorithm (this box should expand as you type) |  |  |  |

| 10 | Location of research activity Identify all locations where research activity will take place. |
| --- | --- |
| 11 | Wuhan University of Technology (this box should expand as you type) |
| 12 | Research activity outside of the UK If research activity will take place overseas, you are responsible for ensuring that local ethical considerations are complied with and that the relevant permissions are sought. Specify any local guidelines (e.g. from local professional associations/learned societies/universities) that exist and whether these involve any ethical stipulations beyond those usual in the UK (provide details of any licenses or permissions required). Also specify whether there are any specific ethical issues raised by the local context in which the research activity is taking place, for example, particular cultural and/or legal sensitivities or vulnerabilities of participants. |
| 13 | (this box should expand as you type) |

| 14 | Use of documentation not in the public domain: Are any documents NOT publicly available? | NO | ☒ |
| --- | --- | --- | --- |
|  |  | YES | ☐ |
| 15 | If Yes, please provide details here of how you will gain access to specific documentation that is not in the public domain and that this is in accordance with prevailing data protection law of the country in question and England and Wales. (this box should expand as you type) |  |  |

SECTION F: Scope of Research Activity

| 1 | Will the research activity include: | YES | NO |
| --- | --- | --- | --- |
| 2 | Use of a questionnaire or similar research instrument? | ☐ | ☒ |
| 3 | Use of interviews? | ☐ | ☒ |
| 4 | Use of diaries? | ☐ | ☒ |
| 5 | Participant observation with their knowledge? | ☐ | ☒ |
| 6 | Participant observation without their knowledge? | ☐ | ☒ |
| 7 | Use of video or audio recording? | ☐ | ☒ |
| 8 | Access to personal or confidential information without the participants’ specific consent? | ☐ | ☒ |
| 9 | Administration of any questions, test stimuli, presentation that may be experienced as physically, mentally or emotionally harmful / offensive? | ☐ | ☒ |
| 10 | Performance of any acts which may cause embarrassment or affect self-esteem? | ☐ | ☒ |
| 11 | Investigation of participants involved in illegal activities? | ☐ | ☒ |
| 12 | Use of procedures that involve deception? | ☐ | ☒ |
| 13 | Administration of any substance, agent or placebo? | ☐ | ☒ |
| 14 | Working with live vertebrate animals? | ☐ | ☒ |
| 15 | Other primary data collection methods, please explain in this box For example, ‘focus groups’. Please indicate the type of data collection method(s) in this box and tick the accompany box. | ☐ | ☒ |
| 16 | Details of any other primary data collection method: (this box should expand as you type) |  |  |

If NO to every question, then the research activity is (ethically) low risk and may be exempt from some of the following sections (please refer to Guidance Notes).

If YES to any question, then no research activity should be undertaken until full ethical approval has been obtained.

SECTION G: Intended Participants

| 1 | Who are the intended participants: | YES | NO |
| --- | --- | --- | --- |
| 2 | Students or staff at the University? | ☐ | ☒ |
| 3 | Adults (over the age of 18 and competent to give consent)? | ☐ | ☒ |
| 4 | Vulnerable adults? | ☐ | ☒ |
| 5 | Children and Young People under the age of 18? (Consent from Parent, Carer or Guardian will be required) | ☐ | ☒ |
| 6 | Prisoners? | ☐ | ☒ |
| 7 | Young offenders? | ☐ | ☒ |
| 8 | Those who could be considered to have a particularly dependent relationship with the investigator or a gatekeeper? | ☐ | ☒ |
| 9 | People engaged in illegal activities? | ☐ | ☒ |
| 10 | Others (please identify specifically any group who may be unable to give consent) please indicate here and tick the appropriate box. | ☐ | ☒ |
| 11 | Other – please indicate here: (this box should expand as you type) |  |  |

| 12 | Participant numbers and source Provide an estimate of the expected number of participants. How will you identify participants and how will they be recruited? |  |
| --- | --- | --- |
| 13 | How many participants are expected? | (this box should expand as you type) |
| 14 | Who will the participants be? | (this box should expand as you type) |
| 15 | How will you identify the participants? | (this box should expand as you type) |

| 16 | Information for participants: | YES | NO | N/A |
| --- | --- | --- | --- | --- |
| 17 | Will you describe the main research procedures to participants in advance, so that they are informed about what to expect? | ☐ | ☐ | ☐ |
| 18 | Will you tell participants that their participation is voluntary? | ☐ | ☐ | ☐ |
| 19 | Will you obtain written consent for participation? | ☐ | ☐ | ☐ |
| 20 | Will you explain to participants that refusal to participate in the research will not affect their treatment or education (if relevant)? | ☐ | ☐ | ☐ |
| 21 | If the research is observational, will you ask participants for their consent to being observed? | ☐ | ☐ | ☐ |
| 22 | Will you tell participants that they may withdraw from the research at any time and for any reason? | ☐ | ☐ | ☐ |
| 23 | With questionnaires, will you give participants the option of omitting questions they do not want to answer? | ☐ | ☐ | ☐ |
| 24 | Will you tell participants that their data will be treated with full confidentiality and that, if published, it will not be identifiable as theirs? | ☐ | ☐ | ☐ |
| 25 | Will you debrief participants at the end of their participation, in a way appropriate to the type of research undertaken? | ☐ | ☐ | ☐ |
| 26 | If NO to any of above questions, please give an explanation |  |  |  |
| 27 | (this box should expand as you type) |  |  |  |

| 28 | Information for participants: | YES | NO | N/A |
| --- | --- | --- | --- | --- |
| 29 | Will participants be paid? | ☐ | ☐ | ☐ |
| 30 | Is specialist electrical or other equipment to be used with participants? | ☐ | ☐ | ☐ |
| 31 | Are there any financial or other interests to the investigator or University arising from this study? | ☐ | ☐ | ☐ |
| 32 | Will the research activity involve deliberately misleading participants in any way, or the partial or full concealment of the specific study aims? | ☐ | ☐ | ☐ |
| 33 | If YES to any question, please provide full details |  |  |  |
| 34 | (this box should expand as you type) |  |  |  |

SECTION H: Anticipated Risks

| 1 | Outline any anticipated risks that may adversely affect any of the participants, the researchers and/or the University, and the steps that will be taken to address them. If you have completed a full risk assessment (for example as required by a laboratory, or external research collaborator) you may append that to this form. |  |  |  |
| --- | --- | --- | --- | --- |
| 2 | Full risk assessment completed and appended? |  | Yes | ☐ |
|  |  |  | No | ☐ |
| 3 | Risks to participants For example: emotional distress, financial disclosure, physical harm, transfer of personal data, sensitive organisational information |  |  |  |
| 4 | Risk to Participant: (this box should expand as you type) | How will you mitigate the Risk to Participant (this box should expand as you type) |  |  |
| 5 | If research activity may include sensitive, embarrassing or upsetting topics (e.g. sexual activity, drug use) or issues likely to disclose information requiring further action (e.g. criminal activity), give details of the procedures to deal with these issues, including any support/advice (e.g. helpline numbers) to be offered to participants. Note that where applicable, consent procedures should make it clear that if something potentially or actually illegal is discovered in the course of a project, it may need to be disclosed to the proper authorities |  |  |  |
|  | (this box should expand as you type) |  |  |  |
| 6 | Risks to investigator For example: personal safety, physical harm, emotional distress, risk of accusation of harm/impropriety, conflict of interest |  |  |  |
|  | Risk to Investigator: (this box should expand as you type) | How will you mitigate the Risk to Investigator: (this box should expand as you type) |  |  |
| 7 | University/institutional risks For example: adverse publicity, financial loss, data protection |  |  |  |
|  | Risk to University: (this box should expand as you type) | How will you mitigate the Risk to University: (this box should expand as you type) |  |  |

| 8 | Disclosure and Barring Service |  |  |  |
| --- | --- | --- | --- | --- |
| 9 | If the research activity involves children or vulnerable adults, a Disclosure and Barring Service (DBS) certificate must be obtained before any contact with such participants. | YES | NO | N/A |
| 10 | Does your research require you to hold a current DBS Certificate? | ☐ | ☐ | ☐ |

SECTION I: Feedback, Consent and Confidentiality

| 1 | Feedback What de-briefing and feedback will be provided to participants, how will this be done and when? |
| --- | --- |
|  | (this box should expand as you type) |
| 2 | Informed consent Describe the arrangements to inform potential participants, before providing consent, of what is involved in participating. Describe the arrangements for participants to provide full consent before data collection begins. If gaining consent in this way is inappropriate, explain how consent will be obtained and recorded in accordance with prevailing data protection legislation. |
|  | (this box should expand as you type) |
| 3 | Confidentiality / Anonymity Set out how anonymity of participants and confidentiality will be ensured in any outputs. If anonymity is not being offered, explain why this is the case. |
|  | (this box should expand as you type) |

SECTION J: Data Protection and Storage

In completing this section refer to the University’s Research Data Management Policy and the extensive resources on the University’s Research Data Management web pages (http://uwtsd.ac.uk/library/research-data-management/).

| 1 | Does the research activity involve personal data (as defined by the General Data Protection Regulation 2016 “GDPR” and the Data Protection Act 2018 “DPA”)? | YES | NO |
| --- | --- | --- | --- |
|  | “Personal data” means any information relating to an identified or identifiable natural person (‘data subject’). An identifiable natural person is one who can be identified, directly or indirectly, in particular by reference to an identifier such as a name, an identification number, location data, an online identifier or to one or more factors specific to the physical, physiological, genetic, mental, economic, cultural or social identity of that natural person. | ☐ | ☐ |
| 2 | If YES, provide a description of the data and explain why this data needs to be collected: |  |  |
|  | (this box should expand as you type) |  |  |
| 3 | Does it involve special category data (as defined by the GDPR)? | YES | NO |
|  | “Special category data” means sensitive personal data consisting of information as to the data subjects’ – (a) racial or ethnic origin, (b) political opinions, (c ) religious beliefs or other beliefs of a similar nature, (d) membership of a trade union (within the meaning of the Trade Union and Labour Relations (Consolidation) Act 1992), (e) physical or mental health or condition, (f) sexual life, (g) genetics, (h) biometric data (as used for ID purposes), | ☐ | ☐ |
| 4 | If YES, provide a description of the special category data and explain why this data needs to be collected: |  |  |
|  | (this box should expand as you type) |  |  |

| 5 | Will the research activity involve storing personal data and/or special category data on one of the following: | YES | NO |
| --- | --- | --- | --- |
| 6 | Manual files (i.e. in paper form)? | ☐ | ☐ |
| 7 | University computers? | ☐ | ☐ |
| 8 | Private company computers? | ☐ | ☐ |
| 9 | Home or other personal computers? | ☐ | ☐ |
| 10 | Laptop computers/ CDs/ Portable disk-drives/ memory sticks? | ☐ | ☐ |
| 11 | “Cloud” storage or websites? | ☐ | ☐ |
| 12 | Other – specify: | ☐ | ☐ |
| 13 | For all stored data, explain the measures in place to ensure the security of the data collected, data confidentiality, including details of password protection, encryption, anonymisation and pseudonymisation: |  |  |
|  | (this box should expand as you type) |  |  |
| 14 | All Data Storage |  |  |
| 15 | Will the research activity involve any of the following activities: | YES | NO |
| 16 | Electronic transfer of data in any form? | ☐ | ☐ |
| 17 | Sharing of data with others at the University? | ☐ | ☐ |
| 18 | Sharing of data with other organisations? | ☐ | ☐ |
| 19 | Export of data outside the European Union or importing of data from outside the UK? | ☐ | ☐ |
| 20 | Use of personal addresses, postcodes, faxes, emails or telephone numbers? | ☐ | ☐ |
| 21 | Publication of data that might allow identification of individuals? | ☐ | ☐ |
| 22 | Use of data management system? | ☐ | ☐ |
| 23 | Data archiving? | ☐ | ☐ |
| 24 | If YES to any question, please provide full details, explaining how this will be conducted in accordance with the GDPR and DPA (and/or any international equivalent): |  |  |
|  | (this box should expand as you type) |  |  |
| 25 | List all who will have access to the data generated by the research activity: |  |  |
|  | (this box should expand as you type) |  |  |
| 26 | List who will have control of, and act as custodian(s) for, data generated by the research activity: |  |  |
|  | (this box should expand as you type) |  |  |
| 27 | Give details of data storage arrangements, including security measures in place to protect the data, where data will be stored, how long for, and in what form. Will data be archived – if so how and if not why not. |  |  |
|  | (this box should expand as you type) |  |  |
| 28 | Please indicate if your data will be stored in the UWTSD Research Data Repository (see https://researchdata.uwtsd.ac.uk/ ). If so please explain. (Most relevant to academic staff) |  |  |
|  | (this box should expand as you type) |  |  |
| 29 | Confirm that you have read the UWTSD guidance on data management (see https://www.uwtsd.ac.uk/library/research-data-management/) | YES | ☐ |
|  |  | NO | ☐ |
| 30 | Confirm that you are aware that you need to keep all data until after your research has completed or the end of your funding | YES | ☐ |
|  |  | NO | ☐ |

SECTION K: Declaration

| 31 | The information which I have provided is correct and complete to the best of my knowledge. I have attempted to identify any risks and issues related to the research activity and acknowledge my obligations and the rights of the participants. In submitting this application I hereby confirm that I undertake to ensure that the above named research activity will meet the University’s Research Ethics and Integrity Code of Practice which is published on the website: https://www.uwtsd.ac.uk/research/research-ethics/ |  |  |
| --- | --- | --- | --- |
|  | Signature of applicant: |  | Date: |

For STUDENT Submissions:

| 32 | Director of Studies/Supervisor: | Tim Bashford | Date: 07/05/2022 |
| --- | --- | --- | --- |
| 33 | Signature: |  |  |

For STAFF Submissions:

| 34 | Academic Director/ Assistant Dean: |  | Date: |
| --- | --- | --- | --- |
| 35 | Signature: |  |  |

Checklist: Please complete the checklist below to ensure that you have completed the form according to the guidelines and attached any required documentation:

| ☐ | I have read the guidance notes supplied before completing the form. |
| --- | --- |
| ☐ | I have completed ALL RELEVANT sections of the form in full. |
| ☐ | I confirm that the research activity has received approval in principle |
| ☐ | I have attached a copy of final/interim approval from external organisation (where appropriate) |
| ☐ | I have attached a full risk assessment (and have NOT completed Section H of this form) (where appropriate) ONLY TICK IF YOU HAVE ATTACHED A FULL RISK ASSESSMENT |
| ☐ | I understand that it is my responsibility to ensure that the above named research activity will meet the University’s Research Ethics and Integrity Code of Practice. |
| ☐ | I understand that before commencing data collection all documents aimed at respondents (including information sheets, consent forms, questionnaires, interview schedules etc.) must be confirmed by the DoS/Supervisor, module tutor or Academic Director. |
| ☐ | I have deleted the guidance notes before submitting the PG2 for consideration |

RESEARCH STUDENTS AND STAFF ONLY All communications relating to this application during its processing must be in writing and emailed to pgresearch@uwtsd.ac.uk , with the title ‘Ethical Approval’ followed by your name. You will be informed of the outcome of your claim by email; therefore it is important that you check your University and personal email accounts regularly.

STUDENTS ON UNDERGRADUATE OR TAUGHT MASTERS PROGRAMMES should submit this form (and receive the outcome) via systems explained to you by the supervisor/module leader.

This form is available electronically from the Academic Office web pages: https://www.uwtsd.ac.uk/academic-office/appendices-and-forms/

Application Process

All staff research projects and all research students must submit the Ethical Approval Form to the University Research Ethics Committee via the Academic Office (pgresearch@uwtsd.ac.uk).   Staff research directly in relation to personal study for taught undergraduate or Masters programmes should be submitted via the Institute procedures explained below.

Taught masters and taught undergraduate research Ethical Approval Forms are considered within Institutes.  Institutes will provide details of the specific processes for this.  Where the Ethical issues within any single ethical application are of particular concern the Institute will refer these to the University Research Ethics Committee.   Any student activity that involves the collection of primary data needs to undergo Ethical approval, this includes assignment work as well as dissertations.