University of Wales Trinity Saint David (UWTSD)

Problem Solving and Decision Making

Module Code: LCLM4004

Component 2 Individual Report

Basil’s Bakery

Student Name: Oksana Bielova

Student ID: 2526746

Lecturer’s Name: Toyin Adisa

# Table of Contents

Abstract	3

Introduction	4

Task 1: Overview of Case Study and Nature of the Problem	4

Task 2: Proposed Solutions	4

Solution A — Controlled Artisan Development of a Small Owner-Operated Business	4

Solution B — Relocation to a Higher-Footfall Location with Differentiated Artisan Positioning	5

Task 3a: PMI Evaluation of the Two Proposed Solutions	5

Task 3b: Evaluation Results and Justification of the Selected Solution	6

Task 4: Risk Analysis of the Preferred Solution	7

Task 5: Implementation Plan	7

Task 6: KPIs and SMART Objectives	8

Task 7: Key Findings	9

Conclusion	9

References	10

Appendix A — PMI Analysis	12

Appendix B — Risk Analysis Matrix	15

Appendix C — Implementation Action Plan	17

Appendix D — KPI and SMART Objectives	19

# Abstract

This report analyses Basil’s Bakery’s persistent post-2020 sales shortfall and evaluates two development strategies using problem-solving, Adizes’ organisational lifecycle and PAEI frameworks, PMI and risk analysis. The shortfall combines reduced retail-park footfall, changed working patterns and rising costs with strong operational dependence on Basil. Controlled Artisan Development is recommended: widen customer access through selective delegation, pre-ordering and delivery before adding organisational capacity, then use evidence on demand, profitability and workload to decide whether limited production support or relocation is justified.

# Introduction

Basil’s Bakery is an independent artisan bakery in Coventry whose strengths are Basil’s professional baking skills, high-quality organic products and established local reputation. Sales, however, remained about 25% below the 2019 level during 2023–2025 because of lower retail-park footfall, changed working patterns, rising operating costs and limited adaptation of customer access.

This report evaluates how Basil can improve sales without creating organisational complexity before sustainable demand is known. Two alternatives are assessed through PMI and risk analysis, supported by Adizes’ organisational lifecycle and PAEI frameworks. The central argument is to scale access to Basil’s products before scaling the organisation, then translate the preferred strategy into implementation actions, KPIs and SMART objectives.

# Task 1: Overview of Case Study and Nature of the Problem

Basil’s Bakery grew year-on-year before 2020 but has since stabilised about 25% below its 2019 sales level. Lower retail-park footfall, nearby shop closures, home working and higher rent, utilities, business rates, insurance and organic ingredient costs have weakened performance. Customers have requested delivery and pre-ordering, but Basil’s workload limits consistent provision, creating a gap between customer demand and the current access model.

Adizes’ framework suggests characteristics of the Go-Go/Founder’s Trap because key activities remain concentrated around the founder, although the case does not justify a definitive lifecycle diagnosis (Adizes, 1988). Through PAEI, Basil’s strongest role is Producer (P), while Entrepreneur (E) and Integrator (I) capabilities appear less developed from the available evidence (Adizes, 2004).

# Task 2: Proposed Solutions

## Solution A — Controlled Artisan Development of a Small Owner-Operated Business

The first solution is Controlled Artisan Development: retain Basil’s Bakery as a small owner-operated business while reducing Basil’s operational overload. Basil remains the principal artisan baker, while selected non-production activities are delegated or outsourced. This reduces founder dependency without forcing him immediately into managing a larger organisation and protects the product quality and artisan identity on which the bakery’s reputation depends.

Development would proceed in three stages: stabilise and simplify operations, delegate selected functions, and decide on further growth only after evidence is available. Online pre-ordering and third-party delivery directly answer existing customer requests and widen access without permanent recruitment. Before expansion, Basil should establish his preferred role, sustainable production capacity and required profitability. Delivery platforms can create additional sales opportunities, but commissions and other charges must be assessed against their financial benefit (Li, Mirosa and Bremer, 2020). This gradual approach is consistent with research on digital transformation in agrifood SMEs, which emphasises that successful adoption depends on building dynamic capabilities aligned with the firm’s existing resources and identity rather than pursuing rapid technological expansion (Cannas, 2023).

## Solution B — Relocation to a Higher-Footfall Location with Differentiated Artisan Positioning

The second solution is relocation to a stronger-footfall location while retaining differentiated artisan positioning based on high-quality organic products. It directly addresses the structural weakness of the current retail park, where footfall has fallen, shops are closing and office workers visit less frequently.

Porter’s differentiation logic suggests distinctive attributes may support higher-value positioning (Porter, 1985), but customers cannot be assumed to pay premium prices. Relocation could reduce dependence on declining retail-park traffic while allowing Basil to remain primarily a producer. However, it requires substantial financial commitment when operating costs are already rising, demand at a new site is uncertain and some loyal customers could be lost. It should therefore remain a longer-term alternative rather than an immediate move.

# Task 3a: PMI Evaluation of the Two Proposed Solutions

PMI (Plus, Minus, Interesting) was used to compare the benefits, disadvantages and potentially significant consequences of both alternatives, considering practicality, risk and short- and long-term effects. The full comparison is presented in Appendix A (de Bono, 1988).

# Task 3b: Evaluation Results and Justification of the Selected Solution

The PMI favours Solution A because it addresses demonstrated customer needs with lower fixed commitments. Its main disadvantages—platform costs, founder dependence and capacity constraints—can be tested and mitigated through a pilot, whereas relocation involves less reversible costs, uncertain demand and possible loss of loyal customers. Although PMI is qualitative, financial risk, fit with Basil’s managerial capacity, responsiveness to demand and reversibility are the most relevant criteria because customer numbers remain below previous levels while costs have risen.

Solution A also fits the PAEI analysis: Basil’s strongest role is Producer (Adizes, 2004), whereas rapid organisational expansion would require greater entrepreneurship, delegation and integration.

The preferred sequence is therefore to expand customer access through pre-ordering, external delivery and simple digital channels before increasing organisational complexity. This tests whether sales can improve without the higher commitment of relocation and whether profitable demand exceeds Basil’s sustainable capacity. Relocation should be reconsidered only if location remains the principal constraint. Consistent with the Founder’s Trap interpretation, the pilot reduces founder dependency gradually rather than creating a larger structure immediately. Crucially, the pilot also allows Basil to experience selective delegation in practice and to assess whether this way of working is compatible with his preferred role, personal working style and managerial capacity before any permanent staffing decision is made. This measured approach is supported by evidence that SME digitalisation is most effective when proportionate to organisational capabilities and resources (Sinha, Raby and Salari, 2025), while agrifood SME research similarly emphasises building internal capabilities before scaling (Cannas, 2023).

The recommended sequence is therefore: stabilise → delegate selected functions → test demand → assess results → add limited capacity if justified → consider relocation only if necessary.

# Task 4: Risk Analysis of the Preferred Solution

Controlled Artisan Development should begin with a limited pre-ordering and delivery pilot to test demand, profitability and capacity before higher fixed costs are accepted. A Likelihood × Impact matrix prioritises the main risks; the detailed assessment is provided in Appendix B (ISO, 2018; Project Management Institute, 2019).

Profitability is the highest-priority risk because platform commissions and logistics charges may raise revenue while reducing margins (Niu et al., 2021). Basil should therefore monitor contribution margin, not sales alone. Two further high risks are insufficient demand and demand exceeding capacity, which could respectively make the pilot ineffective or overload production and threaten quality. Sales, workload and sustainable capacity should therefore be monitored.

Delivery risk can be reduced through a limited radius, suitable packaging and direct customer communication; packaging logistics can materially affect food quality, customer satisfaction and competitiveness (Silva and Nilsson, 2025). The strategy remains manageable because it is reversible and requires no major irreversible investment. If profitable demand exceeds capacity, limited production support can be considered; if location remains the principal constraint, relocation can then be reassessed.

# Task 5: Implementation Plan

Implementation should be phased so each commitment depends on evidence from the previous stage (Andries, Debackere and Van Looy, 2013). In Weeks 1–2, Basil and the business consultant should define Basil’s preferred future role and establish baseline sales, operating costs and sustainable production capacity. In Weeks 3–4, they should compare direct pre-ordering and third-party delivery on cost, suitability and operational requirements. If the pilot subsequently identifies consistent end-of-day surplus, a surplus-food platform could be evaluated as an optional secondary channel; the case itself does not establish that such surplus currently exists.

During Months 2–3, pre-ordering and external delivery should be piloted without permanent recruitment, using order limits where necessary and retaining Basil’s control over product quality. By testing pre-ordering and delivery within clearly defined limits, the plan deliberately avoids the risk of over-digitalisation, recognising that optimal outcomes for small firms occur when the scope and depth of digital adoption remain matched to available resources (Sinha, Raby and Salari, 2025). Running the pilot without permanent recruitment first also gives Basil the opportunity to test how the delegation of non-production tasks works for him personally, before deciding whether he wishes to expand the team. During Months 4–6, results should be reviewed against sales, contribution margin, demand, workload and capacity. Profitable demand above sustainable capacity would justify considering limited production support; continuing location constraints would justify reassessing relocation. This sequence is appropriate because it resolves the lowest-cost, most reversible questions first and prevents Basil from committing resources before demand and capacity are evidenced. Responsibility also follows capability: Basil retains decisions affecting product quality and sustainable workload; the business consultant provides independent financial and strategic evaluation; and a digital freelancer or external service provider is used only where specialist channel expertise is required. The phased sequence of clarifying capacity before introducing digital channels reflects the need, identified in agrifood SME research, to develop dynamic capabilities progressively rather than imposing large-scale change (Cannas, 2023). Detailed activities, timings and responsibilities are provided in Appendix C.

# Task 6: KPIs and SMART Objectives

Performance should be assessed through financial, customer and operational measures rather than sales growth alone (Parmenter, 2020). As a proposed benchmark, sales should recover to at least 90% of the 2019 level within 12 months, provided this remains profitable and compatible with sustainable production capacity. Contribution margin should be monitored monthly so platform or delivery charges do not create revenue without profit.

New-channel performance should also track the share of sales from pre-orders and delivery, repeat orders/customer retention, and order volume against sustainable capacity. These measures show whether demand is recurring, profitable and operationally manageable. If demand consistently exceeds capacity, limited production support can be considered rather than automatic expansion. The measures create specific, measurable and time-bound decision points consistent with SMART principles (Doran, 1981); Appendix D provides the detailed table.

# Task 7: Key Findings

• Sales remain about 25% below 2019 because reduced footfall and changed working patterns combine with rising costs and limited customer access.

• Basil’s Producer strength is central to product quality, but operational dependence on him constrains delivery, pre-ordering and growth.

• Controlled Artisan Development is preferable to immediate expansion because it responds to demonstrated demand with lower financial and organisational risk.

• Pre-ordering, delivery and selective outsourcing should be piloted and measured before staffing decisions.

• Relocation should be considered only if evidence shows the current location remains the principal constraint.

# Conclusion

Basil’s Bakery requires adaptation rather than immediate large-scale expansion. Its sales shortfall reflects declining retail-park footfall, changing customer behaviour, rising costs and operational dependence on Basil. Adizes/PAEI analysis indicates that Basil’s strongest contribution is as Producer, supporting a strategy that protects his artisan role while reducing bottlenecks around him.

Controlled Artisan Development is therefore recommended: delegate selected non-production functions, pilot pre-ordering and delivery, measure demand, profitability and capacity, and expand only when evidence justifies it. The guiding logic is stabilise → delegate → pilot → measure → learn → only then expand. Limited production support should follow only if profitable demand exceeds sustainable capacity; relocation should be reassessed only if location remains the dominant constraint.

# References

Adizes, I. (1988) Corporate Lifecycles: How and Why Corporations Grow and Die and What to Do About It. Englewood Cliffs, NJ: Prentice Hall.

Adizes, I. (2004) Management/Mismanagement Styles: How to Identify a Style and What to Do About It. Santa Barbara, CA: The Adizes Institute Publishing.

Andries, P., Debackere, K. and Van Looy, B. (2013) ‘Simultaneous experimentation as a learning strategy: Business model development under uncertainty’, Strategic Entrepreneurship Journal, 7(4), pp. 288–310.

Cannas, R. (2023) ‘Exploring digital transformation and dynamic capabilities in agrifood SMEs’, Journal of Small Business Management, 61(4), pp. 1611–1637. doi: 10.1080/00472778.2020.1844494.

de Bono, E. (1988) De Bono’s Thinking Course. London: BBC Books.

Doran, G.T. (1981) ‘There’s a S.M.A.R.T. way to write management’s goals and objectives’, Management Review, 70(11), pp. 35–36.

International Organization for Standardization (ISO) (2018) ISO 31000:2018 Risk Management — Guidelines. Geneva: International Organization for Standardization.

Li, C., Mirosa, M. and Bremer, P. (2020) ‘Review of online food delivery platforms and their impacts on sustainability’, Sustainability, 12(14), 5528.

Niu, B., Li, Q., Mu, Z., Chen, L. and Ji, P. (2021) ‘Platform logistics or self-logistics? Restaurants’ cooperation with online food-delivery platform considering profitability and sustainability’, International Journal of Production Economics, 234, 108064.

Parmenter, D. (2020) Key Performance Indicators: Developing, Implementing, and Using Winning KPIs. 4th edn. Hoboken, NJ: Wiley.

Porter, M.E. (1985) Competitive Advantage: Creating and Sustaining Superior Performance. New York: Free Press.

Project Management Institute (2019) The Standard for Risk Management in Portfolios, Programs, and Projects. Newtown Square, PA: Project Management Institute.

Silva, N. and Nilsson, F. (2025) ‘Enabling competitiveness in home-delivery through sustainable packaging logistics’, International Journal of Retail & Distribution Management, 53(13), pp. 75–89. doi: 10.1108/IJRDM-09-2024-0441.

Sinha, K.K., Raby, S. and Salari, T. (2025) ‘Exploring the scope and depth of digitalisation in times of crisis: Implications for SME resilience’, International Small Business Journal, 43(3), pp. 219–245. doi: 10.1177/02662426241293000.

# Appendix A — PMI Analysis

## Solution A — Controlled Artisan Development of a Small Owner-Operated Business

| Plus | Minus | Interesting |
| --- | --- | --- |
| Basil retains his main role as an artisan baker, consistent with his strong Producer role (Adizes, 2004). | Opportunities for rapid sales growth remain limited by Basil’s personal production capacity. | New sales channels can be tested without immediately creating a larger team. |
| Online pre-ordering and external delivery respond directly to existing customer requests. | External delivery and digital services create additional costs and may reduce margins. | If demand exceeds Basil’s production capacity, this provides evidence to justify considering limited additional production support, initially potentially one production assistant. |
| Selected functions can be outsourced without requiring Basil immediately to manage several employees. | Basil remains a key dependency within production. | The pilot provides an opportunity to test Basil’s ability and willingness to delegate before further organisational development. |
| Financial and organisational exposure is lower than with immediate relocation or substantial expansion. | The solution does not directly remove the underlying problem of declining footfall at the current retail park. | Pilot results can provide evidence about whether the existing location remains viable or whether higher-footfall relocation should subsequently be considered. |

## Solution B — Relocation to a Higher-Footfall Location with Differentiated Artisan Positioning

| Plus | Minus | Interesting |
| --- | --- | --- |
| Makes stronger use of Basil’s competitive advantage in artisan products and high-quality organic ingredients. | Relocation requires substantial initial investment. | The business model could test whether a stronger location and differentiated artisan positioning improve demand without requiring large-scale organisational growth. |
| A more suitable location could provide access to a larger pool of potential customers. | There is no guarantee that a new location would generate sufficient demand. | Basil could remain primarily an artisan producer rather than becoming the manager of a large organisation. |
| Reduces dependence on declining footfall at the current retail park. | Existing increases in rent, utilities, business rates and insurance make additional financial commitments more risky. | If market evidence supports it, differentiated positioning could support higher prices without requiring a proportional increase in production volume. |
| Differentiated artisan positioning is consistent with the quality and character of Basil’s products. | Relocation could result in the loss of part of the existing loyal customer base. | A distinctive bakery environment could strengthen customer experience; any premium positioning would need validation through market evidence. |

Note: PMI analysis adapted from de Bono (1988). PAEI interpretation based on Adizes (2004).

# Appendix B — Risk Analysis Matrix

The selected Controlled Artisan Development strategy was assessed using a 5 × 5 Likelihood × Impact matrix. Each identified risk was rated from 1 (low) to 5 (high) for likelihood and impact, with the overall score calculated by multiplying the two ratings. This enables the principal risks to be prioritised and appropriate mitigation actions identified (ISO, 2018; Project Management Institute, 2019).

| Identified Risk | Likelihood (1–5) | Impact (1–5) | Risk Score | Risk Level | Mitigation Action |
| --- | --- | --- | --- | --- | --- |
| Delivery and online-platform commissions reduce profitability | 4 | 4 | 16 | High | Compare providers and calculate contribution margin before launch |
| New sales channels fail to generate sufficient additional demand | 3 | 4 | 12 | High | Conduct a low-cost pilot before making significant investment |
| Demand exceeds Basil’s personal production capacity | 3 | 4 | 12 | High | Establish sustainable production capacity and introduce a daily order limit |
| Product quality deteriorates during delivery | 2 | 4 | 8 | Medium | Limit the delivery radius, select products suitable for delivery and test packaging |
| Dependence on a third-party digital/delivery platform | 2 | 3 | 6 | Medium | Maintain direct pre-ordering and customer communication alongside external platforms |

## Risk Rating Scale

| Risk Score | Risk Level | Required Response |
| --- | --- | --- |
| 1–4 | Low | Monitor |
| 5–9 | Medium | Monitor and mitigate |
| 10–16 | High | Active mitigation required |
| 17–25 | Very High | Immediate action required |

Note: Risk scores and rating thresholds were developed for this case using a 5 × 5 Likelihood × Impact matrix. The overall risk-management approach was informed by ISO 31000 (ISO, 2018) and the Project Management Institute (2019).

# Appendix C — Implementation Action Plan

The implementation plan translates Controlled Artisan Development into phased actions that test customer demand and financial viability before Basil commits additional permanent resources. The sequence follows controlled experimentation under uncertainty (Andries, Debackere and Van Looy, 2013).

| What | How | When | Who |
| --- | --- | --- | --- |
| 1. Clarify business objectives and capacity | Define Basil’s preferred future role; establish current production capacity, operating costs and baseline sales | Weeks 1–2 | Basil + Business Consultant |
| 2. Select low-risk sales channels | Compare direct pre-ordering and third-party delivery platforms. Assess cost, suitability, platform dependency and operational requirements. If the pilot identifies consistent end-of-day surplus, evaluate a surplus-food platform only as an optional secondary channel; the case does not establish that such surplus currently exists. | Weeks 3–4 | Basil + Business Consultant / Digital Freelancer |
| 3. Run a controlled pilot | Introduce pre-ordering and external delivery without immediate permanent recruitment; establish order limits and monitor demand, costs and workload | Months 2–3 | Basil + External Service Providers |
| 4. Evaluate pilot results | Compare sales, contribution margin, customer demand, workload and actual production capacity against the established baseline | Months 4–6 | Basil + Business Consultant |
| 5. Determine the next development stage | If sustainable demand exceeds Basil’s production capacity while remaining profitable, consider limited additional production support, initially potentially one production/kitchen assistant. If the current location remains the principal constraint, reconsider relocation to a higher-footfall location. | End of Month 6 | Basil + Business Consultant |

# Appendix D — KPI and SMART Objectives

The KPIs and SMART objectives assess whether Controlled Artisan Development produces sustainable financial, customer and operational improvement. They support evidence-based decisions on maintaining the current scale, introducing limited production support or reconsidering relocation. The objectives follow SMART principles (Doran, 1981), while KPIs provide measurable indicators of performance (Parmenter, 2020).

| SMART Objective | KPI | Target | Timeframe |
| --- | --- | --- | --- |
| Restore sales performance | Sales compared with the 2019 baseline | Proposed benchmark: restore sales to ≥90% of the 2019 level, subject to profitability and sustainable production capacity. | Within 12 months |
| Evaluate new sales channels | Percentage of total sales generated through pre-orders and delivery | Establish and monitor a sustainable contribution from the new channels | 3–6 months |
| Protect profitability | Contribution margin after delivery and platform costs | Maintain a positive contribution margin from new sales channels | Monthly |
| Control production capacity | Order volume compared with Basil’s sustainable production capacity | Operate within sustainable capacity; consider limited additional production support, initially potentially one production/kitchen assistant, if demand consistently exceeds capacity and remains profitable. | 3–6 months |
| Retain customers | Repeat orders and customer retention | Monitor retention and repeat purchasing to establish whether new channels support continued customer demand | 6–12 months |