## Slide 1
Notes: Hello my name is paul benbow
Welcome to my presentation of my reflective account as the refinery maintenance scheduler during a refinery maintenance shut down at vale clydach nickel refinery

## Slide 2
Notes: As you can see from the photograph on the left, the refinery is nestled in the Swansea valley of which the community of clydach has been built around.
The picture on the right shows the history associated with, infact this year the refinery celebrates 120 years of production.

## Slide 3
Notes: Our customers use the nickel that is produced at the refinery to manufacture products such as stainless steel surgical instruments and battery cells for electric vehicles

## Slide 4
Notes: The refinery receives raw material which, is nickel ore and is shipped from either Canada or Japan.
Once refined the nickel that is produced is sold to our customers in the form of nickel pellets and nickel powders

## Slide 5
Notes: The process requires natural gas to be reformed in various gas such as carbon dioxide; carbon monoxide; and hydrogen. This is done at the refinerys process gas plant which is shown in the top picture of the slide.
Process gases are either stored in vessels or transported directly to the required plants via interconnecting pipework that has been suspended above roadways such as that shown photograph in the bottom left of the slide.
The extraction plant is where the process begins. It contains 2 production lines; ‘kiln line 1 and kiln line 2. each kiln line has a series of the three rotating kilns (similar to that in the picture on the right) which transformed the ore into a toxic gas called carbonyl.
The carbonyl is transported to the manufacturing plants via interconnecting pipework, where it will be produced into either pellet or powder products.

## Slide 6
Notes: As previously said the process involves the use of highly toxic gas so, it is of the upmost importance for equipment to be maintained to ensure its functionality and safety of those using them.
Middle picture shows a kiln head. This is an end cover that is fixed into position over the rotating part of the kiln to create a gas tight seal
Every 2 years the refinery will undertake a major shutdown on one kiln line that will see the heads being removed from the rotating kiln to complete internal inspections and maintenance
Within the major shutdown of the kiln line a refinery shutdown window will be planned whereby the plant purged clear of gas so that maintenance can be carried out.

## Slide 7
Refinery Scheduler
Mechanical Planner
Electrical & Instrumentation Planner
Maintenance superintendents
Process Superintendents
Notes: To ensure that the completion of work was efficient during both maintenance windows, a team from 3 departments were brought together to form a project team
The departments were; The Process departments, the maintenance planning and control department and the execution teams.
The process departments have historically been seen as the ‘Customer’ but there expertise extend only to the process and not the equipment used.
The maintenance planning and control department are responsible for making sure that instructions, materials and resources are available for maintenance to be completed.
The execution teams are those that carry out the maintenance activities
Individuals within the team had their regular duties to perform on a day to day basis and the involvement with this project team overwhelmed their existing work load
Technics such as SMART and RACI were used to identify and resolve these issues

## Slide 8
Notes: For similar maintenance projects within the industry the workflow on the left of the slide would depict how the project would be executed from initialization through to project completion
The reliability team which consists of an electrical and mechanical engineer, would identify the work scope. This would be done by reviewing equipment failure and assessing the equipment's life cycle on and bathtub hazard rate curve. Then they would meet with equipment owners to risk assess each item requiring maintenance and determine the consequence of the equipment failing.
On agreement between the reliability and the equipment owners a notification of the maintenance request would be submitted via SAP to the mpc department allowing for the sequential process of planning scheduling and execution

## Slide 9
Notes: However, the next slide shows a workflow that is a more accurate depiction for this project.
As said previously, the process department is seen as the customer and believe that they have the required knowledge to decide on the maintenance regimes for their equipment.
This led to notification of maintenance request being issued to the maintenance planning and control department before approval of the reliability department. In some cases, the reliability department rejected some requests for maintenance that had already been planned and scheduled – this created waste for planning resources and for the purchase of materials.

## Slide 10
Notes: To manage the overwhelming notifications being requested for maintenance, The maintenance planning and control departments supervisor brought the team together to discuss their objectives and the time frame that they had to work in. from this SMART goals were devised of which were illustrated by using a gantt chart.
The departments supervisor used both tools to escalate the issue that the department was under resourced, to the next layer of management.
An additional resource was brought into the department, and existing resources were re-organized to allow the department to achieve their goals. The supervisor met with the reshuffled team and discuss how individuals’ roles had changed and then issued a RACI matrix to ensure the change was embedded.

## Slide 11
Notes: Once notifications had been planned with an accurate duration and the resource required, the scheduler would create a schedule using Microsoft project. Each task in the schedule was risk assessed using a priority table, which ranked for the largest impact that would be felt to production if, equipment was returned late to process. The priority associated with each task would determine how soon a task would be executed in the schedule.
Relationships were built between tasks that identified sequential steps in procedures, also for synergies that brought together execution of work in the same area.
The schedule outlined the critical path (seen on the left) according to the available resources that were needed (shown in the top right corner)

## Slide 12
Notes: The schedulers' role during execution was to inform the stakeholders of potential threats to the project timeline.
To do this first, the scheduler received progress reports from the execution teams in a daily meeting. Then the software could be updated and used to reflect on where progress should have been compared to where progress was.
The update to stakeholders would be through monitoring of project milestones (seen on the left) and a sprint burndown chart (seen on the right)
The red arrow on the sprint burndown chart shows an instance where the project completion date was under threat. A decision was made based on this data to add additional resources to the mechanical work group to resolve the threat.

## Slide 13
Conclusion
A sole project manager responsible for the entire project. This role would manage the desired workflow
Agree Key Performance Indictors at project initialisation stage.
Notes: This slide shows the cycle of a project from initialization through to project completion.
It highlights distinct phases project planning; project implementation and project learning
Comparing the phases to this project it was found that;
during the planning phase, waste was created by the equipment owners not following the desired workflow.
consistent project updates allowed for resourcing issues to be identified and resolved effectively
As this project is yet to conclude and has not entered the project learning phase a fair assessment is difficult., however Key performance indicators where not identified and agreed at the project initialization phase so, identifying areas for improvements will be difficult.

## Slide 14: Thanks For Listening