## CashFlow
CONTRACT |  | UWTSD New retail and accomodation development, SA1 Campus |  |  |  | Last/Curr Val No : | 25
Contract Sum / Est FA |  |  | 9119824.26 |  |  | Max.Value | 11999999
Ditto Less 50% of retention |  |  | 8891828.6535 |  |  | Min.Value | 10000
[5 empty] | Min No of Vals |  | 2
No Of Valuations |  | 25 | (during contract period) |  | Max No of Vals |  | 30
Retention |  | 5% |  |  | Start On Site Date |  | 2021-06-21
Remaining Vals |  | 26 |  |  | Contract Period: |  | 109 | wks
Defects Period |  | 12 | MONTHS |  |  | Compl. Date | 2023-07-24
Val | Date | Original Est Gross | Act Gross | Adj Est Gross | Adj Est Retention | Adj Est Nett | Adj Est Prev | Estimated/Actual Cash Flow (Gross) | % | Nett Monthly Cashflow
[8 empty] | CHECK |  | 8891828.6535
1 | 2021-07-21 12:00 | 151002.891 |  |  | 0 | 0 | 0 | 151002.891 | 97% | 146472.8042
2 | 2021-08-23 | 220919.9382 |  |  | 0 | 0 | 0 | 220919.9382 | 95% | 63401.137
3 | 2021-09-20 12:00 | 302964.5002 |  |  | 0 | 0 | 0 | 302964.5002 | 95% | 77942.334
4 | 2021-10-31 | 467159.7158 |  |  | 0 | 0 | 0 | 467159.7158 | 95% | 155985.4548
5 | 2021-11-23 12:00 | 593977.4556 |  |  | 0 | 0 | 0 | 593977.4556 | 95% | 120476.8528
6 | 2021-12-21 | 777776.9361 |  |  | 0 | 0 | 0 | 777776.9361 | 95% | 174609.5065
7 | 2022-01-24 | 1055184.7035 |  |  | 0 | 0 | 0 | 1055184.7035 | 95% | 263537.379
8 | 2022-02-21 | 1339776.7335 |  |  | 0 | 0 | 0 | 1339776.7335 | 95% | 270362.4285
9 | 2022-03-21 | 1570385.2193 |  |  | 0 | 0 | 0 | 1570385.2193 | 95% | 219078.0615
10 | 2022-03-29 | 1605522.1465 |  |  | 0 | 0 | 0 | 1605522.1465 | 95% | 33380.0809
11 | 2022-04-28 12:00 | 2029144.9532 |  |  | 0 | 0 | 0 | 2029144.9532 | 95% | 402441.6664
12 | 2022-05-29 | 2497593.8649 |  |  | 0 | 0 | 0 | 2497593.8649 | 95% | 445026.4661
13 | 2022-06-28 12:00 | 3053752.6006 |  |  | 0 | 0 | 0 | 3053752.6006 | 95% | 528350.799
14 | 2022-07-29 | 3700373.639 |  |  | 0 | 0 | 0 | 3700373.639 | 95% | 614289.9864
15 | 2022-08-28 12:00 | 4307636.0002 |  |  | 0 | 0 | 0 | 4307636.0002 | 95% | 576899.2431
16 | 2022-09-28 | 5042107.8838 |  |  | 0 | 0 | 0 | 5042107.8838 | 95% | 697748.2894
17 | 2022-10-28 12:00 | 5760837.5088 |  |  | 0 | 0 | 0 | 5760837.5088 | 95% | 682793.1437
18 | 2022-11-28 | 6439661.8017 |  |  | 0 | 0 | 0 | 6439661.8017 | 95% | 644883.0783
19 | 2022-12-28 12:00 | 7117898.827 |  |  | 0 | 0 | 0 | 7117898.827 | 95% | 644325.1741
20 | 2023-01-28 | 7735367.0636 |  |  | 0 | 0 | 0 | 7735367.0636 | 95% | 586594.8247
21 | 2023-02-27 12:00 | 8243323.9292 |  |  | 0 | 0 | 0 | 8243323.9292 | 95% | 482559.0224
22 | 2023-03-30 | 8508262.0601 |  |  | 0 | 0 | 0 | 8508262.0601 | 95% | 251691.2244
23 | 2023-04-29 12:00 | 8843115.8659 |  |  | 0 | 0 | 0 | 8843115.8659 | 95% | 318111.1154
24 | 2023-05-30 | 9056819.445 |  |  | 0 | 0 | 0 | 9056819.445 | 95% | 203018.4002
25 | 2023-06-29 12:00 | 9119824.26 |  |  | 0 | 0 | 0 | 9119824.26 | 97.5% | 287850.1807
Formulas:
Date = [Date, row above]+30.5+2
Date = [Date, row above]+30.5-2

## CashFlowARA (hidden)
| CONTRACT |  | #REF! |  |  |  | Last/Current Valuation No : | #REF! | #REF!
| Current Final Account |  |  | 9119824.26 |  |  | Max.Value | 11999999
[7 empty] | Min.Value | 10000
| Contract Prd |  | #REF! | MONTHS |  | Min No of Vals |  | 2
| No Of Valuations |  | 16 |  |  | Max No of Vals |  | 25
| Retention |  | 3% |  |  | Start On Site Date |  | #REF!
| Remaining Vals |  | #REF! |  |  | Contract Period: |  | #REF! | wks
| Defects Period |  | 12 | MONTHS |  |  | Compl. Date | #REF!
| Val | Date | Original Est Gross | Act Gross | Adj Est Gross | Adj Est Retention | Adj Est Nett | Adj Est Prev | Estimated/Actual Cash Flow (Gross) | Actual /Forecast Paymnt LESS Retention
#REF!
| 1 | 2015-05-08 | #REF! | 57914.65 | 57914.65 | 1737.4395 | 56177.2105 | 0 | 57914.65 | 56177.2105 | #REF!
J | 2 | 2015-06-10 | #REF! | 182957.69 | 182957.69 | 5488.7307 | 177468.9593 | 56177.2105 | 182957.69 | 121291.7488 | #REF!
K | 3 | 2015-07-10 | #REF! | 267232.77 | 267232.77 | 8016.9831 | 259215.7869 | 177468.9593 | 267232.77 | 81746.8276 | #REF!
L | 4 | 2015-08-06 | #REF! | 444030.77 | 444030.77 | 13320.9231 | 430709.8469 | 259215.7869 | 444030.77 | 171494.06 | #REF!
M | 5 | 2015-09-10 | #REF! | #REF! | #REF! | #REF! | #REF! | 430709.8469 | #REF! | #REF! | #REF!
N | 6 | 2015-10-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
O | 7 | 2015-11-12 | #REF! |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #REF!
P | 8 | 2015-12-10 | #REF! |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #REF!
Q | 9 | 2016-01-10 | #REF! |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #REF!
R | 10 | 2016-02-10 | #REF! |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #REF!
S | 11 | 2016-03-12 | #REF! |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #REF!
T | 12 | 2016-04-12 | #REF! |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #REF!
U | 13 | 2016-05-13 | #REF! |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #REF!
V | 14 | 2016-06-13 | #REF! |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #REF!
W | 15 | 2016-07-14 | #REF! |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #REF!
X | 16 | 2016-07-31 | #REF! |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #REF!
Y | 17 | 2016-08-31 | #REF! |  | 0 | 0 | #REF! | 0 | #N/A |  | #REF!
Z | 18 | 2016-10-01 | #REF! |  | 0 | 0 | #REF! | 0 | #N/A |  | #REF!
AA | 19 | 2016-11-01 | #REF! |  | 0 | 0 | #REF! | 0 | #N/A |  | #REF!
AB | 20 | 2016-12-02 | #REF! |  | 0 | 0 | #REF! | 0 | #N/A |  | #REF!
AC | 21 | 2017-01-02 | #REF! |  | 0 | 0 | #REF! | 0 | #N/A |  | #REF!
AD | 22 | 2017-02-02 | #REF! |  | 0 | 0 | #REF! | 0 | #N/A |  | #REF!
AE | 23 | 2017-03-05 | #REF! |  | 0 | 0 | #REF! | 0 | #N/A |  | #REF!
AF | 24 | 2017-04-05 | #REF! |  | 0 | 0 | #REF! | 0 | #N/A |  | #REF!
AG | 25 | 2017-05-06 | #REF! |  | 0 | 0 | #REF! | 0 | #N/A |  | #REF!
Formulas:
Date = [Date, row above]+28+5
Date = [Date, row above]+27

## CashFlowCalcs (hidden)
|  |  | Contract Start Date |  |  | 2021-06-21 | Finish Date | 2023-07-24 | Days | 762 |  |  | * based on Normal Distribution Curve
|  |  | Total Contract Length in Days In all periods) |  |  | 763 |  | 505
|  |  | Mobilisation Period in Days |  |  | Start Date | 2021-06-21 | Days | 0
|  |  | Twilight Period |  |  | Start Date | 2021-06-21 | Days | 0 |  |  |  | Complete
|  |  | On Site Period |  |  | Start Date | 2021-06-21 | Days | 505 |  |  |  | Leave !
|  |  | Contract Value (or Final Account) |  |  | 9119824.26 | Current/Last Val & Date | 25 | 2023-06-29 12:00 | 505
|  |  | Less Work Before Main Start (L) |  |  |  |  | Est Val | Act Val |  | Original Est Left | Act Left | %
|  |  | Used In "S" Curve (S) |  |  | 9119824.26 |  | 9119824.26 | 0 |  | 0 | 9119824.26 | #DIV/0!
[8 empty] | Diff | Per Day |  | Diffence | 9119824.26 |  |  |  |  | 2023-06-30 12:00
[8 empty] | -9119824.26 | -372237.7249
|  |  | Amount Outstanding |  | 9119824.26 | 0 | 9119824.26
|  |  | Predicted Outstanding |  | 9119824.26 | #REF! | #REF!
% adjustment
[5 empty] | Difference |  | #REF! | #REF!
[5 empty] | Months Remaining |  | #REF!
|  |  | A | B | C | D = Normdist of C | E = B | F = D / A | G = (F x S) + L | H | I | J | K | L
Day | Val No | Holiday (Y/N) | Day No (On site Period) | Date1 | X axis divided by On Site Period (From 3 to 0)* | Y axis (Normal Distribution) from 3 to 0 | Date | Factor | Original Gross Val at Start | Running Adjustment | Revised Estimated Gross Val | Day No (As Col A) | Difference | No of Days remaining as Fraction | Actual Val | DayNo1 | Factor To Add | Proportion Left
Mon | 0 | N | 1 | 2021-06-21 | -3 | 0.0044318 | 2021-06-21 | 0.01111 | 101319.1908 | 0 | 101319.1908 | 1 | 0 | 0 | 0 | 1 | 0
Tues | 0 | N | 2 | 2021-06-22 | -2.9882 | 0.0045917 | 2021-06-22 | 0.01151 | 104973.5876 | 0 | 104973.5876 | 2 | 0 | 0 | 0 | 2 | 0
Wed | 0 | N | 3 | 2021-06-23 | -2.9822 | 0.0046735 | 2021-06-23 | 0.011716 | 106844.309 | 0 | 106844.309 | 3 | 0 | 0 | 0 | 3 | 0
Thu | 0 | N | 4 | 2021-06-24 | -2.9763 | 0.0047566 | 2021-06-24 | 0.011924 | 108744.5609 | 0 | 108744.5609 | 4 | 0 | 0 | 0 | 4 | 0
Fri | 0 | N | 5 | 2021-06-25 | -2.9704 | 0.0048411 | 2021-06-25 | 0.012136 | 110674.734 | 0 | 110674.734 | 5 | 0 | 0 | 0 | 5 | 0
Sat | 0 | Y | 5 | 2021-06-26 | -2.9704 | 0.0048411 | 2021-06-26 | 0.012136 | 110674.734 | 0 | 110674.734 | 5 | 0 | 0 | 0 | 5 | 0
Sun | 0 | Y | 5 | 2021-06-27 | -2.9704 | 0.0048411 | 2021-06-27 | 0.012136 | 110674.734 | 0 | 110674.734 | 5 | 0 | 0 | 0 | 5 | 0
Mon | 0 | N | 6 | 2021-06-28 | -2.9645 | 0.0049268 | 2021-06-28 | 0.012351 | 112635.2233 | 0 | 112635.2233 | 6 | 0 | 0 | 0 | 6 | 0
Tues | 0 | N | 7 | 2021-06-29 | -2.9586 | 0.0050139 | 2021-06-29 | 0.012569 | 114626.4271 | 0 | 114626.4271 | 7 | 0 | 0 | 0 | 7 | 0
Wed | 0 | N | 8 | 2021-06-30 | -2.9527 | 0.0051024 | 2021-06-30 | 0.012791 | 116648.7478 | 0 | 116648.7478 | 8 | 0 | 0 | 0 | 8 | 0
Thu | 0 | N | 9 | 2021-07-01 | -2.9467 | 0.0051922 | 2021-07-01 | 0.013016 | 118702.5916 | 0 | 118702.5916 | 9 | 0 | 0 | 0 | 9 | 0
Fri | 0 | N | 10 | 2021-07-02 | -2.9408 | 0.0052835 | 2021-07-02 | 0.013245 | 120788.3684 | 0 | 120788.3684 | 10 | 0 | 0 | 0 | 10 | 0
Sat | 0 | Y | 10 | 2021-07-03 | -2.9408 | 0.0052835 | 2021-07-03 | 0.013245 | 120788.3684 | 0 | 120788.3684 | 10 | 0 | 0 | 0 | 10 | 0
Sun | 0 | Y | 10 | 2021-07-04 | -2.9408 | 0.0052835 | 2021-07-04 | 0.013245 | 120788.3684 | 0 | 120788.3684 | 10 | 0 | 0 | 0 | 10 | 0
Mon | 0 | N | 11 | 2021-07-05 | -2.9349 | 0.0053761 | 2021-07-05 | 0.013477 | 122906.4919 | 0 | 122906.4919 | 11 | 0 | 0 | 0 | 11 | 0
Tues | 0 | N | 12 | 2021-07-06 | -2.929 | 0.0054702 | 2021-07-06 | 0.013713 | 125057.3798 | 0 | 125057.3798 | 12 | 0 | 0 | 0 | 12 | 0
Wed | 0 | N | 13 | 2021-07-07 | -2.9231 | 0.0055657 | 2021-07-07 | 0.013952 | 127241.4534 | 0 | 127241.4534 | 13 | 0 | 0 | 0 | 13 | 0
Thu | 0 | N | 14 | 2021-07-08 | -2.9172 | 0.0056627 | 2021-07-08 | 0.014195 | 129459.1382 | 0 | 129459.1382 | 14 | 0 | 0 | 0 | 14 | 0
Fri | 0 | N | 15 | 2021-07-09 | -2.9112 | 0.0057612 | 2021-07-09 | 0.014442 | 131710.8633 | 0 | 131710.8633 | 15 | 0 | 0 | 0 | 15 | 0
Sat | 0 | Y | 15 | 2021-07-10 | -2.9112 | 0.0057612 | 2021-07-10 | 0.014442 | 131710.8633 | 0 | 131710.8633 | 15 | 0 | 0 | 0 | 15 | 0
Sun | 0 | Y | 15 | 2021-07-11 | -2.9112 | 0.0057612 | 2021-07-11 | 0.014442 | 131710.8633 | 0 | 131710.8633 | 15 | 0 | 0 | 0 | 15 | 0
Mon | 0 | N | 16 | 2021-07-12 | -2.9053 | 0.0058612 | 2021-07-12 | 0.014693 | 133997.0616 | 0 | 133997.0616 | 16 | 0 | 0 | 0 | 16 | 0
Tues | 0 | N | 17 | 2021-07-13 | -2.8994 | 0.0059628 | 2021-07-13 | 0.014947 | 136318.1702 | 0 | 136318.1702 | 17 | 0 | 0 | 0 | 17 | 0
Wed | 0 | N | 18 | 2021-07-14 | -2.8935 | 0.0060658 | 2021-07-14 | 0.015206 | 138674.6297 | 0 | 138674.6297 | 18 | 0 | 0 | 0 | 18 | 0
Thu | 0 | N | 19 | 2021-07-15 | -2.8876 | 0.0061705 | 2021-07-15 | 0.015468 | 141066.8848 | 0 | 141066.8848 | 19 | 0 | 0 | 0 | 19 | 0
Fri | 0 | N | 20 | 2021-07-16 | -2.8817 | 0.0062767 | 2021-07-16 | 0.015734 | 143495.3842 | 0 | 143495.3842 | 20 | 0 | 0 | 0 | 20 | 0
Sat | 0 | Y | 20 | 2021-07-17 | -2.8817 | 0.0062767 | 2021-07-17 | 0.015734 | 143495.3842 | 0 | 143495.3842 | 20 | 0 | 0 | 0 | 20 | 0
Sun | 0 | Y | 20 | 2021-07-18 | -2.8817 | 0.0062767 | 2021-07-18 | 0.015734 | 143495.3842 | 0 | 143495.3842 | 20 | 0 | 0 | 0 | 20 | 0
Mon | 0 | N | 21 | 2021-07-19 | -2.8757 | 0.0063845 | 2021-07-19 | 0.016005 | 145960.5801 | 0 | 145960.5801 | 21 | 0 | 0 | 0 | 21 | 0
Tues | 0 | N | 22 | 2021-07-20 | -2.8698 | 0.006494 | 2021-07-20 | 0.016279 | 148462.929 | 0 | 148462.929 | 22 | 0 | 0 | 0 | 22 | 0
Wed | 0 | N | 23 | 2021-07-21 | -2.8639 | 0.0066051 | 2021-07-21 | 0.016558 | 151002.891 | 0 | 151002.891 | 23 | 0 | 0 | 0 | 23 | 0
Thu | 0 | N | 24 | 2021-07-22 | -2.858 | 0.0067179 | 2021-07-22 | 0.01684 | 153580.9303 | 0 | 153580.9303 | 24 | 0 | 0 | 0 | 24 | 0
Fri | 0 | N | 25 | 2021-07-23 | -2.8521 | 0.0068323 | 2021-07-23 | 0.017127 | 156197.5149 | 0 | 156197.5149 | 25 | 0 | 0 | 0 | 25 | 0
Sat | 0 | Y | 25 | 2021-07-24 | -2.8521 | 0.0068323 | 2021-07-24 | 0.017127 | 156197.5149 | 0 | 156197.5149 | 25 | 0 | 0 | 0 | 25 | 0
Sun | 0 | Y | 25 | 2021-07-25 | -2.8521 | 0.0068323 | 2021-07-25 | 0.017127 | 156197.5149 | 0 | 156197.5149 | 25 | 0 | 0 | 0 | 25 | 0
Mon | 0 | N | 26 | 2021-07-26 | -2.8462 | 0.0069485 | 2021-07-26 | 0.017418 | 158853.1167 | 0 | 158853.1167 | 26 | 0 | 0 | 0 | 26 | 0
Tues | 0 | N | 27 | 2021-07-27 | -2.8402 | 0.0070664 | 2021-07-27 | 0.017714 | 161548.2115 | 0 | 161548.2115 | 27 | 0 | 0 | 0 | 27 | 0
Wed | 0 | N | 28 | 2021-07-28 | -2.8343 | 0.007186 | 2021-07-28 | 0.018014 | 164283.2791 | 0 | 164283.2791 | 28 | 0 | 0 | 0 | 28 | 0
Thu | 0 | N | 29 | 2021-07-29 | -2.8284 | 0.0073074 | 2021-07-29 | 0.018318 | 167058.803 | 0 | 167058.803 | 29 | 0 | 0 | 0 | 29 | 0
Fri | 0 | N | 30 | 2021-07-30 | -2.8225 | 0.0074306 | 2021-07-30 | 0.018627 | 169875.2708 | 0 | 169875.2708 | 30 | 0 | 0 | 0 | 30 | 0
Sat | 0 | Y | 30 | 2021-07-31 | -2.8225 | 0.0074306 | 2021-07-31 | 0.018627 | 169875.2708 | 0 | 169875.2708 | 30 | 0 | 0 | 0 | 30 | 0
Sun | 0 | Y | 30 | 2021-08-01 | -2.8225 | 0.0074306 | 2021-08-01 | 0.018627 | 169875.2708 | 0 | 169875.2708 | 30 | 0 | 0 | 0 | 30 | 0
Mon | 0 | N | 31 | 2021-08-02 | -2.8166 | 0.0075556 | 2021-08-02 | 0.01894 | 172733.1738 | 0 | 172733.1738 | 31 | 0 | 0 | 0 | 31 | 0
Tues | 0 | N | 32 | 2021-08-03 | -2.8107 | 0.0076824 | 2021-08-03 | 0.019258 | 175633.0074 | 0 | 175633.0074 | 32 | 0 | 0 | 0 | 32 | 0
Wed | 0 | N | 33 | 2021-08-04 | -2.8047 | 0.0078111 | 2021-08-04 | 0.019581 | 178575.2707 | 0 | 178575.2707 | 33 | 0 | 0 | 0 | 33 | 0
Thu | 0 | N | 34 | 2021-08-05 | -2.7988 | 0.0079417 | 2021-08-05 | 0.019908 | 181560.4667 | 0 | 181560.4667 | 34 | 0 | 0 | 0 | 34 | 0
Fri | 0 | N | 35 | 2021-08-06 | -2.7929 | 0.0080742 | 2021-08-06 | 0.02024 | 184589.1023 | 0 | 184589.1023 | 35 | 0 | 0 | 0 | 35 | 0
Sat | 0 | Y | 35 | 2021-08-07 | -2.7929 | 0.0080742 | 2021-08-07 | 0.02024 | 184589.1023 | 0 | 184589.1023 | 35 | 0 | 0 | 0 | 35 | 0
Sun | 0 | Y | 35 | 2021-08-08 | -2.7929 | 0.0080742 | 2021-08-08 | 0.02024 | 184589.1023 | 0 | 184589.1023 | 35 | 0 | 0 | 0 | 35 | 0
Mon | 0 | N | 36 | 2021-08-09 | -2.787 | 0.0082086 | 2021-08-09 | 0.020577 | 187661.6884 | 0 | 187661.6884 | 36 | 0 | 0 | 0 | 36 | 0
Tues | 0 | N | 37 | 2021-08-10 | -2.7811 | 0.0083449 | 2021-08-10 | 0.020919 | 190778.7395 | 0 | 190778.7395 | 37 | 0 | 0 | 0 | 37 | 0
Wed | 0 | N | 38 | 2021-08-11 | -2.7751 | 0.0084833 | 2021-08-11 | 0.021266 | 193940.7742 | 0 | 193940.7742 | 38 | 0 | 0 | 0 | 38 | 0
Thu | 0 | N | 39 | 2021-08-12 | -2.7692 | 0.0086236 | 2021-08-12 | 0.021618 | 197148.3147 | 0 | 197148.3147 | 39 | 0 | 0 | 0 | 39 | 0
Fri | 0 | N | 40 | 2021-08-13 | -2.7633 | 0.0087659 | 2021-08-13 | 0.021974 | 200401.8872 | 0 | 200401.8872 | 40 | 0 | 0 | 0 | 40 | 0
Sat | 0 | Y | 40 | 2021-08-14 | -2.7633 | 0.0087659 | 2021-08-14 | 0.021974 | 200401.8872 | 0 | 200401.8872 | 40 | 0 | 0 | 0 | 40 | 0
Sun | 0 | Y | 40 | 2021-08-15 | -2.7633 | 0.0087659 | 2021-08-15 | 0.021974 | 200401.8872 | 0 | 200401.8872 | 40 | 0 | 0 | 0 | 40 | 0
Mon | 0 | N | 41 | 2021-08-16 | -2.7574 | 0.0089102 | 2021-08-16 | 0.022336 | 203702.0217 | 0 | 203702.0217 | 41 | 0 | 0 | 0 | 41 | 0
Tues | 0 | N | 42 | 2021-08-17 | -2.7515 | 0.0090566 | 2021-08-17 | 0.022703 | 207049.252 | 0 | 207049.252 | 42 | 0 | 0 | 0 | 42 | 0
Wed | 0 | N | 43 | 2021-08-18 | -2.7456 | 0.0092051 | 2021-08-18 | 0.023075 | 210444.1155 | 0 | 210444.1155 | 43 | 0 | 0 | 0 | 43 | 0
Thu | 0 | N | 44 | 2021-08-19 | -2.7396 | 0.0093557 | 2021-08-19 | 0.023453 | 213887.1537 | 0 | 213887.1537 | 44 | 0 | 0 | 0 | 44 | 0
Fri | 0 | N | 45 | 2021-08-20 | -2.7337 | 0.0095085 | 2021-08-20 | 0.023836 | 217378.9116 | 0 | 217378.9116 | 45 | 0 | 0 | 0 | 45 | 0
Sat | 0 | Y | 45 | 2021-08-21 | -2.7337 | 0.0095085 | 2021-08-21 | 0.023836 | 217378.9116 | 0 | 217378.9116 | 45 | 0 | 0 | 0 | 45 | 0
Sun | 0 | Y | 45 | 2021-08-22 | -2.7337 | 0.0095085 | 2021-08-22 | 0.023836 | 217378.9116 | 0 | 217378.9116 | 45 | 0 | 0 | 0 | 45 | 0
Mon | 2 | N | 46 | 2021-08-23 | -2.7278 | 0.0096634 | 2021-08-23 | 0.024224 | 220919.9382 | 0 | 220919.9382 | 46 | 0 | 0 | 0 | 46 | 0
Tues | 2 | N | 47 | 2021-08-24 | -2.7219 | 0.0098204 | 2021-08-24 | 0.024618 | 224510.7859 | 0 | 224510.7859 | 47 | 0 | 0 | 0 | 47 | 0
Wed | 2 | N | 48 | 2021-08-25 | -2.716 | 0.0099797 | 2021-08-25 | 0.025017 | 228152.0112 | 0 | 228152.0112 | 48 | 0 | 0 | 0 | 48 | 0
Thu | 2 | N | 49 | 2021-08-26 | -2.7101 | 0.010141 | 2021-08-26 | 0.025422 | 231844.1739 | 0 | 231844.1739 | 49 | 0 | 0 | 0 | 49 | 0
Fri | 2 | N | 50 | 2021-08-27 | -2.7041 | 0.010305 | 2021-08-27 | 0.025832 | 235587.8379 | 0 | 235587.8379 | 50 | 0 | 0 | 0 | 50 | 0
Sat | 2 | Y | 50 | 2021-08-28 | -2.7041 | 0.010305 | 2021-08-28 | 0.025832 | 235587.8379 | 0 | 235587.8379 | 50 | 0 | 0 | 0 | 50 | 0
Sun | 2 | Y | 50 | 2021-08-29 | -2.7041 | 0.010305 | 2021-08-29 | 0.025832 | 235587.8379 | 0 | 235587.8379 | 50 | 0 | 0 | 0 | 50 | 0
Mon | 2 | N | 51 | 2021-08-30 | -2.6982 | 0.010471 | 2021-08-30 | 0.026249 | 239383.5704 | 0 | 239383.5704 | 51 | 0 | 0 | 0 | 51 | 0
Tues | 2 | N | 52 | 2021-08-31 | -2.6923 | 0.010639 | 2021-08-31 | 0.026671 | 243231.9424 | 0 | 243231.9424 | 52 | 0 | 0 | 0 | 52 | 0
Wed | 2 | N | 53 | 2021-09-01 | -2.6864 | 0.01081 | 2021-09-01 | 0.027098 | 247133.5286 | 0 | 247133.5286 | 53 | 0 | 0 | 0 | 53 | 0
Thu | 2 | N | 54 | 2021-09-02 | -2.6805 | 0.010983 | 2021-09-02 | 0.027532 | 251088.907 | 0 | 251088.907 | 54 | 0 | 0 | 0 | 54 | 0
Fri | 2 | N | 55 | 2021-09-03 | -2.6746 | 0.011158 | 2021-09-03 | 0.027972 | 255098.6595 | 0 | 255098.6595 | 55 | 0 | 0 | 0 | 55 | 0
Sat | 2 | Y | 55 | 2021-09-04 | -2.6746 | 0.011158 | 2021-09-04 | 0.027972 | 255098.6595 | 0 | 255098.6595 | 55 | 0 | 0 | 0 | 55 | 0
Sun | 2 | Y | 55 | 2021-09-05 | -2.6746 | 0.011158 | 2021-09-05 | 0.027972 | 255098.6595 | 0 | 255098.6595 | 55 | 0 | 0 | 0 | 55 | 0
Mon | 2 | N | 56 | 2021-09-06 | -2.6686 | 0.011336 | 2021-09-06 | 0.028418 | 259163.3714 | 0 | 259163.3714 | 56 | 0 | 0 | 0 | 56 | 0
Tues | 2 | N | 57 | 2021-09-07 | -2.6627 | 0.011516 | 2021-09-07 | 0.028869 | 263283.6315 | 0 | 263283.6315 | 57 | 0 | 0 | 0 | 57 | 0
Wed | 2 | N | 58 | 2021-09-08 | -2.6568 | 0.011699 | 2021-09-08 | 0.029327 | 267460.032 | 0 | 267460.032 | 58 | 0 | 0 | 0 | 58 | 0
Thu | 2 | N | 59 | 2021-09-09 | -2.6509 | 0.011884 | 2021-09-09 | 0.029791 | 271693.1688 | 0 | 271693.1688 | 59 | 0 | 0 | 0 | 59 | 0
Fri | 2 | N | 60 | 2021-09-10 | -2.645 | 0.012072 | 2021-09-10 | 0.030262 | 275983.6411 | 0 | 275983.6411 | 60 | 0 | 0 | 0 | 60 | 0
Sat | 2 | Y | 60 | 2021-09-11 | -2.645 | 0.012072 | 2021-09-11 | 0.030262 | 275983.6411 | 0 | 275983.6411 | 60 | 0 | 0 | 0 | 60 | 0
Sun | 2 | Y | 60 | 2021-09-12 | -2.645 | 0.012072 | 2021-09-12 | 0.030262 | 275983.6411 | 0 | 275983.6411 | 60 | 0 | 0 | 0 | 60 | 0
Mon | 2 | N | 61 | 2021-09-13 | -2.6391 | 0.012262 | 2021-09-13 | 0.030739 | 280332.0515 | 0 | 280332.0515 | 61 | 0 | 0 | 0 | 61 | 0
Tues | 2 | N | 62 | 2021-09-14 | -2.6331 | 0.012455 | 2021-09-14 | 0.031222 | 284739.006 | 0 | 284739.006 | 62 | 0 | 0 | 0 | 62 | 0
Wed | 2 | N | 63 | 2021-09-15 | -2.6272 | 0.01265 | 2021-09-15 | 0.031712 | 289205.1138 | 0 | 289205.1138 | 63 | 0 | 0 | 0 | 63 | 0
Thu | 2 | N | 64 | 2021-09-16 | -2.6213 | 0.012848 | 2021-09-16 | 0.032208 | 293730.9877 | 0 | 293730.9877 | 64 | 0 | 0 | 0 | 64 | 0
Fri | 2 | N | 65 | 2021-09-17 | -2.6154 | 0.013049 | 2021-09-17 | 0.032711 | 298317.2434 | 0 | 298317.2434 | 65 | 0 | 0 | 0 | 65 | 0
Sat | 2 | Y | 65 | 2021-09-18 | -2.6154 | 0.013049 | 2021-09-18 | 0.032711 | 298317.2434 | 0 | 298317.2434 | 65 | 0 | 0 | 0 | 65 | 0
Sun | 2 | Y | 65 | 2021-09-19 | -2.6154 | 0.013049 | 2021-09-19 | 0.032711 | 298317.2434 | 0 | 298317.2434 | 65 | 0 | 0 | 0 | 65 | 0
Mon | 2 | N | 66 | 2021-09-20 | -2.6095 | 0.013252 | 2021-09-20 | 0.03322 | 302964.5002 | 0 | 302964.5002 | 66 | 0 | 0 | 0 | 66 | 0
Tues | 2 | N | 67 | 2021-09-21 | -2.6036 | 0.013458 | 2021-09-21 | 0.033737 | 307673.3804 | 0 | 307673.3804 | 67 | 0 | 0 | 0 | 67 | 0
Wed | 2 | N | 68 | 2021-09-22 | -2.5976 | 0.013667 | 2021-09-22 | 0.03426 | 312444.5095 | 0 | 312444.5095 | 68 | 0 | 0 | 0 | 68 | 0
Thu | 2 | N | 69 | 2021-09-23 | -2.5917 | 0.013878 | 2021-09-23 | 0.03479 | 317278.5161 | 0 | 317278.5161 | 69 | 0 | 0 | 0 | 69 | 0
Fri | 2 | N | 70 | 2021-09-24 | -2.5858 | 0.014092 | 2021-09-24 | 0.035327 | 322176.0318 | 0 | 322176.0318 | 70 | 0 | 0 | 0 | 70 | 0
Sat | 2 | Y | 70 | 2021-09-25 | -2.5858 | 0.014092 | 2021-09-25 | 0.035327 | 322176.0318 | 0 | 322176.0318 | 70 | 0 | 0 | 0 | 70 | 0
Sun | 2 | Y | 70 | 2021-09-26 | -2.5858 | 0.014092 | 2021-09-26 | 0.035327 | 322176.0318 | 0 | 322176.0318 | 70 | 0 | 0 | 0 | 70 | 0
Mon | 2 | N | 71 | 2021-09-27 | -2.5799 | 0.014309 | 2021-09-27 | 0.035871 | 327137.6915 | 0 | 327137.6915 | 71 | 0 | 0 | 0 | 71 | 0
Tues | 2 | N | 72 | 2021-09-28 | -2.574 | 0.014529 | 2021-09-28 | 0.036422 | 332164.1328 | 0 | 332164.1328 | 72 | 0 | 0 | 0 | 72 | 0
Wed | 2 | N | 73 | 2021-09-29 | -2.568 | 0.014752 | 2021-09-29 | 0.036981 | 337255.9965 | 0 | 337255.9965 | 73 | 0 | 0 | 0 | 73 | 0
Thu | 2 | N | 74 | 2021-09-30 | -2.5621 | 0.014978 | 2021-09-30 | 0.037546 | 342413.9261 | 0 | 342413.9261 | 74 | 0 | 0 | 0 | 74 | 0
Fri | 2 | N | 75 | 2021-10-01 | -2.5562 | 0.015206 | 2021-10-01 | 0.038119 | 347638.5681 | 0 | 347638.5681 | 75 | 0 | 0 | 0 | 75 | 0
Sat | 2 | Y | 75 | 2021-10-02 | -2.5562 | 0.015206 | 2021-10-02 | 0.038119 | 347638.5681 | 0 | 347638.5681 | 75 | 0 | 0 | 0 | 75 | 0
Sun | 2 | Y | 75 | 2021-10-03 | -2.5562 | 0.015206 | 2021-10-03 | 0.038119 | 347638.5681 | 0 | 347638.5681 | 75 | 0 | 0 | 0 | 75 | 0
Mon | 2 | N | 76 | 2021-10-04 | -2.5503 | 0.015438 | 2021-10-04 | 0.038699 | 352930.5718 | 0 | 352930.5718 | 76 | 0 | 0 | 0 | 76 | 0
Tues | 2 | N | 77 | 2021-10-05 | -2.5444 | 0.015672 | 2021-10-05 | 0.039287 | 358290.5892 | 0 | 358290.5892 | 77 | 0 | 0 | 0 | 77 | 0
Wed | 2 | N | 78 | 2021-10-06 | -2.5385 | 0.01591 | 2021-10-06 | 0.039882 | 363719.275 | 0 | 363719.275 | 78 | 0 | 0 | 0 | 78 | 0
Thu | 2 | N | 79 | 2021-10-07 | -2.5325 | 0.01615 | 2021-10-07 | 0.040485 | 369217.2867 | 0 | 369217.2867 | 79 | 0 | 0 | 0 | 79 | 0
Fri | 2 | N | 80 | 2021-10-08 | -2.5266 | 0.016394 | 2021-10-08 | 0.041096 | 374785.2844 | 0 | 374785.2844 | 80 | 0 | 0 | 0 | 80 | 0
Sat | 2 | Y | 80 | 2021-10-09 | -2.5266 | 0.016394 | 2021-10-09 | 0.041096 | 374785.2844 | 0 | 374785.2844 | 80 | 0 | 0 | 0 | 80 | 0
Sun | 2 | Y | 80 | 2021-10-10 | -2.5266 | 0.016394 | 2021-10-10 | 0.041096 | 374785.2844 | 0 | 374785.2844 | 80 | 0 | 0 | 0 | 80 | 0
Mon | 2 | N | 81 | 2021-10-11 | -2.5207 | 0.01664 | 2021-10-11 | 0.041714 | 380423.9305 | 0 | 380423.9305 | 81 | 0 | 0 | 0 | 81 | 0
Tues | 2 | N | 82 | 2021-10-12 | -2.5148 | 0.01689 | 2021-10-12 | 0.04234 | 386133.8902 | 0 | 386133.8902 | 82 | 0 | 0 | 0 | 82 | 0
Wed | 2 | N | 83 | 2021-10-13 | -2.5089 | 0.017143 | 2021-10-13 | 0.042974 | 391915.8311 | 0 | 391915.8311 | 83 | 0 | 0 | 0 | 83 | 0
Thu | 2 | N | 84 | 2021-10-14 | -2.503 | 0.017399 | 2021-10-14 | 0.043616 | 397770.4231 | 0 | 397770.4231 | 84 | 0 | 0 | 0 | 84 | 0
Fri | 2 | N | 85 | 2021-10-15 | -2.497 | 0.017658 | 2021-10-15 | 0.044266 | 403698.3384 | 0 | 403698.3384 | 85 | 0 | 0 | 0 | 85 | 0
Sat | 2 | Y | 85 | 2021-10-16 | -2.497 | 0.017658 | 2021-10-16 | 0.044266 | 403698.3384 | 0 | 403698.3384 | 85 | 0 | 0 | 0 | 85 | 0
Sun | 2 | Y | 85 | 2021-10-17 | -2.497 | 0.017658 | 2021-10-17 | 0.044266 | 403698.3384 | 0 | 403698.3384 | 85 | 0 | 0 | 0 | 85 | 0
Mon | 2 | N | 86 | 2021-10-18 | -2.4911 | 0.017921 | 2021-10-18 | 0.044924 | 409700.2515 | 0 | 409700.2515 | 86 | 0 | 0 | 0 | 86 | 0
Tues | 2 | N | 87 | 2021-10-19 | -2.4852 | 0.018187 | 2021-10-19 | 0.04559 | 415776.8393 | 0 | 415776.8393 | 87 | 0 | 0 | 0 | 87 | 0
Wed | 2 | N | 88 | 2021-10-20 | -2.4793 | 0.018456 | 2021-10-20 | 0.046265 | 421928.7806 | 0 | 421928.7806 | 88 | 0 | 0 | 0 | 88 | 0
Thu | 2 | N | 89 | 2021-10-21 | -2.4734 | 0.018728 | 2021-10-21 | 0.046948 | 428156.7563 | 0 | 428156.7563 | 89 | 0 | 0 | 0 | 89 | 0
Fri | 2 | N | 90 | 2021-10-22 | -2.4675 | 0.019004 | 2021-10-22 | 0.047639 | 434461.4496 | 0 | 434461.4496 | 90 | 0 | 0 | 0 | 90 | 0
Sat | 2 | Y | 90 | 2021-10-23 | -2.4675 | 0.019004 | 2021-10-23 | 0.047639 | 434461.4496 | 0 | 434461.4496 | 90 | 0 | 0 | 0 | 90 | 0
Sun | 2 | Y | 90 | 2021-10-24 | -2.4675 | 0.019004 | 2021-10-24 | 0.047639 | 434461.4496 | 0 | 434461.4496 | 90 | 0 | 0 | 0 | 90 | 0
Mon | 2 | N | 91 | 2021-10-25 | -2.4615 | 0.019283 | 2021-10-25 | 0.048339 | 440843.5453 | 0 | 440843.5453 | 91 | 0 | 0 | 0 | 91 | 0
Tues | 2 | N | 92 | 2021-10-26 | -2.4556 | 0.019566 | 2021-10-26 | 0.049047 | 447303.7302 | 0 | 447303.7302 | 92 | 0 | 0 | 0 | 92 | 0
Wed | 2 | N | 93 | 2021-10-27 | -2.4497 | 0.019852 | 2021-10-27 | 0.049764 | 453842.6931 | 0 | 453842.6931 | 93 | 0 | 0 | 0 | 93 | 0
Thu | 2 | N | 94 | 2021-10-28 | -2.4438 | 0.020141 | 2021-10-28 | 0.05049 | 460461.1243 | 0 | 460461.1243 | 94 | 0 | 0 | 0 | 94 | 0
Fri | 2 | N | 95 | 2021-10-29 | -2.4379 | 0.020434 | 2021-10-29 | 0.051225 | 467159.7158 | 0 | 467159.7158 | 95 | 0 | 0 | 0 | 95 | 0
Sat | 2 | Y | 95 | 2021-10-30 | -2.4379 | 0.020434 | 2021-10-30 | 0.051225 | 467159.7158 | 0 | 467159.7158 | 95 | 0 | 0 | 0 | 95 | 0
Sun | 4 | Y | 95 | 2021-10-31 | -2.4379 | 0.020434 | 2021-10-31 | 0.051225 | 467159.7158 | 0 | 467159.7158 | 95 | 0 | 0 | 0 | 95 | 0
Mon | 4 | N | 96 | 2021-11-01 | -2.432 | 0.020731 | 2021-11-01 | 0.051968 | 473939.1613 | 0 | 473939.1613 | 96 | 0 | 0 | 0 | 96 | 0
Tues | 4 | N | 97 | 2021-11-02 | -2.426 | 0.021031 | 2021-11-02 | 0.05272 | 480800.1561 | 0 | 480800.1561 | 97 | 0 | 0 | 0 | 97 | 0
Wed | 4 | N | 98 | 2021-11-03 | -2.4201 | 0.021335 | 2021-11-03 | 0.053482 | 487743.3967 | 0 | 487743.3967 | 98 | 0 | 0 | 0 | 98 | 0
Thu | 4 | N | 99 | 2021-11-04 | -2.4142 | 0.021642 | 2021-11-04 | 0.054252 | 494769.5812 | 0 | 494769.5812 | 99 | 0 | 0 | 0 | 99 | 0
Fri | 4 | N | 100 | 2021-11-05 | -2.4083 | 0.021953 | 2021-11-05 | 0.055032 | 501879.4088 | 0 | 501879.4088 | 100 | 0 | 0 | 0 | 100 | 0
Sat | 4 | Y | 100 | 2021-11-06 | -2.4083 | 0.021953 | 2021-11-06 | 0.055032 | 501879.4088 | 0 | 501879.4088 | 100 | 0 | 0 | 0 | 100 | 0
Sun | 4 | Y | 100 | 2021-11-07 | -2.4083 | 0.021953 | 2021-11-07 | 0.055032 | 501879.4088 | 0 | 501879.4088 | 100 | 0 | 0 | 0 | 100 | 0
Mon | 4 | N | 101 | 2021-11-08 | -2.4024 | 0.022268 | 2021-11-08 | 0.055821 | 509073.5801 | 0 | 509073.5801 | 101 | 0 | 0 | 0 | 101 | 0
Tues | 4 | N | 102 | 2021-11-09 | -2.3964 | 0.022586 | 2021-11-09 | 0.056619 | 516352.7967 | 0 | 516352.7967 | 102 | 0 | 0 | 0 | 102 | 0
Wed | 4 | N | 103 | 2021-11-10 | -2.3905 | 0.022908 | 2021-11-10 | 0.057426 | 523717.7614 | 0 | 523717.7614 | 103 | 0 | 0 | 0 | 103 | 0
Thu | 4 | N | 104 | 2021-11-11 | -2.3846 | 0.023234 | 2021-11-11 | 0.058243 | 531169.1776 | 0 | 531169.1776 | 104 | 0 | 0 | 0 | 104 | 0
Fri | 4 | N | 105 | 2021-11-12 | -2.3787 | 0.023564 | 2021-11-12 | 0.05907 | 538707.7501 | 0 | 538707.7501 | 105 | 0 | 0 | 0 | 105 | 0
Sat | 4 | Y | 105 | 2021-11-13 | -2.3787 | 0.023564 | 2021-11-13 | 0.05907 | 538707.7501 | 0 | 538707.7501 | 105 | 0 | 0 | 0 | 105 | 0
Sun | 4 | Y | 105 | 2021-11-14 | -2.3787 | 0.023564 | 2021-11-14 | 0.05907 | 538707.7501 | 0 | 538707.7501 | 105 | 0 | 0 | 0 | 105 | 0
Mon | 4 | N | 106 | 2021-11-15 | -2.3728 | 0.023897 | 2021-11-15 | 0.059906 | 546334.1841 | 0 | 546334.1841 | 106 | 0 | 0 | 0 | 106 | 0
Tues | 4 | N | 107 | 2021-11-16 | -2.3669 | 0.024235 | 2021-11-16 | 0.060752 | 554049.1856 | 0 | 554049.1856 | 107 | 0 | 0 | 0 | 107 | 0
Wed | 4 | N | 108 | 2021-11-17 | -2.3609 | 0.024576 | 2021-11-17 | 0.061608 | 561853.4614 | 0 | 561853.4614 | 108 | 0 | 0 | 0 | 108 | 0
Thu | 4 | N | 109 | 2021-11-18 | -2.355 | 0.024922 | 2021-11-18 | 0.062474 | 569747.7185 | 0 | 569747.7185 | 109 | 0 | 0 | 0 | 109 | 0
Fri | 4 | N | 110 | 2021-11-19 | -2.3491 | 0.025271 | 2021-11-19 | 0.063349 | 577732.6646 | 0 | 577732.6646 | 110 | 0 | 0 | 0 | 110 | 0
Sat | 4 | Y | 110 | 2021-11-20 | -2.3491 | 0.025271 | 2021-11-20 | 0.063349 | 577732.6646 | 0 | 577732.6646 | 110 | 0 | 0 | 0 | 110 | 0
Sun | 4 | Y | 110 | 2021-11-21 | -2.3491 | 0.025271 | 2021-11-21 | 0.063349 | 577732.6646 | 0 | 577732.6646 | 110 | 0 | 0 | 0 | 110 | 0
Mon | 4 | N | 111 | 2021-11-22 | -2.3432 | 0.025624 | 2021-11-22 | 0.064235 | 585809.0075 | 0 | 585809.0075 | 111 | 0 | 0 | 0 | 111 | 0
Tues | 4 | N | 112 | 2021-11-23 | -2.3373 | 0.025981 | 2021-11-23 | 0.06513 | 593977.4556 | 0 | 593977.4556 | 112 | 0 | 0 | 0 | 112 | 0
Wed | 4 | N | 113 | 2021-11-24 | -2.3314 | 0.026343 | 2021-11-24 | 0.066036 | 602238.7171 | 0 | 602238.7171 | 113 | 0 | 0 | 0 | 113 | 0
Thu | 4 | N | 114 | 2021-11-25 | -2.3254 | 0.026708 | 2021-11-25 | 0.066952 | 610593.5003 | 0 | 610593.5003 | 114 | 0 | 0 | 0 | 114 | 0
Fri | 4 | N | 115 | 2021-11-26 | -2.3195 | 0.027078 | 2021-11-26 | 0.067879 | 619042.5137 | 0 | 619042.5137 | 115 | 0 | 0 | 0 | 115 | 0
Sat | 4 | Y | 115 | 2021-11-27 | -2.3195 | 0.027078 | 2021-11-27 | 0.067879 | 619042.5137 | 0 | 619042.5137 | 115 | 0 | 0 | 0 | 115 | 0
Sun | 4 | Y | 115 | 2021-11-28 | -2.3195 | 0.027078 | 2021-11-28 | 0.067879 | 619042.5137 | 0 | 619042.5137 | 115 | 0 | 0 | 0 | 115 | 0
Mon | 4 | N | 116 | 2021-11-29 | -2.3136 | 0.027452 | 2021-11-29 | 0.068816 | 627586.4653 | 0 | 627586.4653 | 116 | 0 | 0 | 0 | 116 | 0
Tues | 4 | N | 117 | 2021-11-30 | -2.3077 | 0.027829 | 2021-11-30 | 0.069763 | 636226.063 | 0 | 636226.063 | 117 | 0 | 0 | 0 | 117 | 0
Wed | 4 | N | 118 | 2021-12-01 | -2.3018 | 0.028212 | 2021-12-01 | 0.070721 | 644962.0146 | 0 | 644962.0146 | 118 | 0 | 0 | 0 | 118 | 0
Thu | 4 | N | 119 | 2021-12-02 | -2.2959 | 0.028598 | 2021-12-02 | 0.071689 | 653795.0269 | 0 | 653795.0269 | 119 | 0 | 0 | 0 | 119 | 0
Fri | 4 | N | 120 | 2021-12-03 | -2.2899 | 0.028989 | 2021-12-03 | 0.072669 | 662725.8066 | 0 | 662725.8066 | 120 | 0 | 0 | 0 | 120 | 0
Sat | 4 | Y | 120 | 2021-12-04 | -2.2899 | 0.028989 | 2021-12-04 | 0.072669 | 662725.8066 | 0 | 662725.8066 | 120 | 0 | 0 | 0 | 120 | 0
Sun | 4 | Y | 120 | 2021-12-05 | -2.2899 | 0.028989 | 2021-12-05 | 0.072669 | 662725.8066 | 0 | 662725.8066 | 120 | 0 | 0 | 0 | 120 | 0
Mon | 4 | N | 121 | 2021-12-06 | -2.284 | 0.029384 | 2021-12-06 | 0.073659 | 671755.0595 | 0 | 671755.0595 | 121 | 0 | 0 | 0 | 121 | 0
Tues | 4 | N | 122 | 2021-12-07 | -2.2781 | 0.029783 | 2021-12-07 | 0.07466 | 680883.4906 | 0 | 680883.4906 | 122 | 0 | 0 | 0 | 122 | 0
Wed | 4 | N | 123 | 2021-12-08 | -2.2722 | 0.030186 | 2021-12-08 | 0.075672 | 690111.8042 | 0 | 690111.8042 | 123 | 0 | 0 | 0 | 123 | 0
Thu | 4 | N | 124 | 2021-12-09 | -2.2663 | 0.030595 | 2021-12-09 | 0.076695 | 699440.7034 | 0 | 699440.7034 | 124 | 0 | 0 | 0 | 124 | 0
Fri | 4 | N | 125 | 2021-12-10 | -2.2604 | 0.031007 | 2021-12-10 | 0.077729 | 708870.8903 | 0 | 708870.8903 | 125 | 0 | 0 | 0 | 125 | 0
Sat | 4 | Y | 125 | 2021-12-11 | -2.2604 | 0.031007 | 2021-12-11 | 0.077729 | 708870.8903 | 0 | 708870.8903 | 125 | 0 | 0 | 0 | 125 | 0
Sun | 4 | Y | 125 | 2021-12-12 | -2.2604 | 0.031007 | 2021-12-12 | 0.077729 | 708870.8903 | 0 | 708870.8903 | 125 | 0 | 0 | 0 | 125 | 0
Mon | 4 | N | 126 | 2021-12-13 | -2.2544 | 0.031424 | 2021-12-13 | 0.078774 | 718403.0656 | 0 | 718403.0656 | 126 | 0 | 0 | 0 | 126 | 0
Tues | 4 | N | 127 | 2021-12-14 | -2.2485 | 0.031845 | 2021-12-14 | 0.07983 | 728037.9289 | 0 | 728037.9289 | 127 | 0 | 0 | 0 | 127 | 0
Wed | 4 | N | 128 | 2021-12-15 | -2.2426 | 0.032271 | 2021-12-15 | 0.080898 | 737776.178 | 0 | 737776.178 | 128 | 0 | 0 | 0 | 128 | 0
Thu | 4 | N | 129 | 2021-12-16 | -2.2367 | 0.032702 | 2021-12-16 | 0.081977 | 747618.5096 | 0 | 747618.5096 | 129 | 0 | 0 | 0 | 129 | 0
Fri | 4 | N | 130 | 2021-12-17 | -2.2308 | 0.033137 | 2021-12-17 | 0.083068 | 757565.6181 | 0 | 757565.6181 | 130 | 0 | 0 | 0 | 130 | 0
Sat | 4 | Y | 130 | 2021-12-18 | -2.2308 | 0.033137 | 2021-12-18 | 0.083068 | 757565.6181 | 0 | 757565.6181 | 130 | 0 | 0 | 0 | 130 | 0
Sun | 4 | Y | 130 | 2021-12-19 | -2.2308 | 0.033137 | 2021-12-19 | 0.083068 | 757565.6181 | 0 | 757565.6181 | 130 | 0 | 0 | 0 | 130 | 0
Mon | 4 | N | 131 | 2021-12-20 | -2.2249 | 0.033577 | 2021-12-20 | 0.08417 | 767618.1967 | 0 | 767618.1967 | 131 | 0 | 0 | 0 | 131 | 0
Tues | 6 | N | 132 | 2021-12-21 | -2.2189 | 0.034021 | 2021-12-21 | 0.085284 | 777776.9361 | 0 | 777776.9361 | 132 | 0 | 0 | 0 | 132 | 0
Wed | 6 | N | 133 | 2021-12-22 | -2.213 | 0.03447 | 2021-12-22 | 0.08641 | 788042.5253 | 0 | 788042.5253 | 133 | 0 | 0 | 0 | 133 | 0
Thu | 6 | N | 134 | 2021-12-23 | -2.2071 | 0.034924 | 2021-12-23 | 0.087547 | 798415.651 | 0 | 798415.651 | 134 | 0 | 0 | 0 | 134 | 0
Fri | 6 | N | 135 | 2021-12-24 | -2.2012 | 0.035382 | 2021-12-24 | 0.088697 | 808896.9975 | 0 | 808896.9975 | 135 | 0 | 0 | 0 | 135 | 0
Sat | 6 | Y | 135 | 2021-12-25 | -2.2012 | 0.035382 | 2021-12-25 | 0.088697 | 808896.9975 | 0 | 808896.9975 | 135 | 0 | 0 | 0 | 135 | 0
Sun | 6 | Y | 135 | 2021-12-26 | -2.2012 | 0.035382 | 2021-12-26 | 0.088697 | 808896.9975 | 0 | 808896.9975 | 135 | 0 | 0 | 0 | 135 | 0
Mon | 6 | N | 136 | 2021-12-27 | -2.1953 | 0.035846 | 2021-12-27 | 0.089858 | 819487.2467 | 0 | 819487.2467 | 136 | 0 | 0 | 0 | 136 | 0
Tues | 6 | N | 137 | 2021-12-28 | -2.1893 | 0.036314 | 2021-12-28 | 0.091031 | 830187.0781 | 0 | 830187.0781 | 137 | 0 | 0 | 0 | 137 | 0
Wed | 6 | N | 138 | 2021-12-29 | -2.1834 | 0.036786 | 2021-12-29 | 0.092216 | 840997.1682 | 0 | 840997.1682 | 138 | 0 | 0 | 0 | 138 | 0
Thu | 6 | N | 139 | 2021-12-30 | -2.1775 | 0.037264 | 2021-12-30 | 0.093414 | 851918.1908 | 0 | 851918.1908 | 139 | 0 | 0 | 0 | 139 | 0
Fri | 6 | N | 140 | 2021-12-31 | -2.1716 | 0.037747 | 2021-12-31 | 0.094624 | 862950.8169 | 0 | 862950.8169 | 140 | 0 | 0 | 0 | 140 | 0
Sat | 6 | Y | 140 | 2022-01-01 | -2.1716 | 0.037747 | 2022-01-01 | 0.094624 | 862950.8169 | 0 | 862950.8169 | 140 | 0 | 0 | 0 | 140 | 0
Sun | 6 | Y | 140 | 2022-01-02 | -2.1716 | 0.037747 | 2022-01-02 | 0.094624 | 862950.8169 | 0 | 862950.8169 | 140 | 0 | 0 | 0 | 140 | 0
Mon | 6 | N | 141 | 2022-01-03 | -2.1657 | 0.038234 | 2022-01-03 | 0.095846 | 874095.7141 | 0 | 874095.7141 | 141 | 0 | 0 | 0 | 141 | 0
Tues | 6 | N | 142 | 2022-01-04 | -2.1598 | 0.038727 | 2022-01-04 | 0.09708 | 885353.5469 | 0 | 885353.5469 | 142 | 0 | 0 | 0 | 142 | 0
Wed | 6 | N | 143 | 2022-01-05 | -2.1538 | 0.039224 | 2022-01-05 | 0.098327 | 896724.9766 | 0 | 896724.9766 | 143 | 0 | 0 | 0 | 143 | 0
Thu | 6 | N | 144 | 2022-01-06 | -2.1479 | 0.039726 | 2022-01-06 | 0.099586 | 908210.6607 | 0 | 908210.6607 | 144 | 0 | 0 | 0 | 144 | 0
Fri | 6 | N | 145 | 2022-01-07 | -2.142 | 0.040234 | 2022-01-07 | 0.10086 | 919811.2533 | 0 | 919811.2533 | 145 | 0 | 0 | 0 | 145 | 0
Sat | 6 | Y | 145 | 2022-01-08 | -2.142 | 0.040234 | 2022-01-08 | 0.10086 | 919811.2533 | 0 | 919811.2533 | 145 | 0 | 0 | 0 | 145 | 0
Sun | 6 | Y | 145 | 2022-01-09 | -2.142 | 0.040234 | 2022-01-09 | 0.10086 | 919811.2533 | 0 | 919811.2533 | 145 | 0 | 0 | 0 | 145 | 0
Mon | 6 | N | 146 | 2022-01-10 | -2.1361 | 0.040746 | 2022-01-10 | 0.10214 | 931527.4045 | 0 | 931527.4045 | 146 | 0 | 0 | 0 | 146 | 0
Tues | 6 | N | 147 | 2022-01-11 | -2.1302 | 0.041264 | 2022-01-11 | 0.10344 | 943359.7607 | 0 | 943359.7607 | 147 | 0 | 0 | 0 | 147 | 0
Wed | 6 | N | 148 | 2022-01-12 | -2.1243 | 0.041787 | 2022-01-12 | 0.10475 | 955308.9641 | 0 | 955308.9641 | 148 | 0 | 0 | 0 | 148 | 0
Thu | 6 | N | 149 | 2022-01-13 | -2.1183 | 0.042314 | 2022-01-13 | 0.10607 | 967375.6526 | 0 | 967375.6526 | 149 | 0 | 0 | 0 | 149 | 0
Fri | 6 | N | 150 | 2022-01-14 | -2.1124 | 0.042847 | 2022-01-14 | 0.10741 | 979560.4601 | 0 | 979560.4601 | 150 | 0 | 0 | 0 | 150 | 0
Sat | 6 | Y | 150 | 2022-01-15 | -2.1124 | 0.042847 | 2022-01-15 | 0.10741 | 979560.4601 | 0 | 979560.4601 | 150 | 0 | 0 | 0 | 150 | 0
Sun | 6 | Y | 150 | 2022-01-16 | -2.1124 | 0.042847 | 2022-01-16 | 0.10741 | 979560.4601 | 0 | 979560.4601 | 150 | 0 | 0 | 0 | 150 | 0
Mon | 6 | N | 151 | 2022-01-17 | -2.1065 | 0.043386 | 2022-01-17 | 0.10876 | 991864.0157 | 0 | 991864.0157 | 151 | 0 | 0 | 0 | 151 | 0
Tues | 6 | N | 152 | 2022-01-18 | -2.1006 | 0.043929 | 2022-01-18 | 0.11012 | 1004286.9439 | 0 | 1004286.9439 | 152 | 0 | 0 | 0 | 152 | 0
Wed | 6 | N | 153 | 2022-01-19 | -2.0947 | 0.044478 | 2022-01-19 | 0.1115 | 1016829.8645 | 0 | 1016829.8645 | 153 | 0 | 0 | 0 | 153 | 0
Thu | 6 | N | 154 | 2022-01-20 | -2.0888 | 0.045032 | 2022-01-20 | 0.11289 | 1029493.3923 | 0 | 1029493.3923 | 154 | 0 | 0 | 0 | 154 | 0
Fri | 6 | N | 155 | 2022-01-21 | -2.0828 | 0.045591 | 2022-01-21 | 0.11429 | 1042278.1371 | 0 | 1042278.1371 | 155 | 0 | 0 | 0 | 155 | 0
Sat | 6 | Y | 155 | 2022-01-22 | -2.0828 | 0.045591 | 2022-01-22 | 0.11429 | 1042278.1371 | 0 | 1042278.1371 | 155 | 0 | 0 | 0 | 155 | 0
Sun | 6 | Y | 155 | 2022-01-23 | -2.0828 | 0.045591 | 2022-01-23 | 0.11429 | 1042278.1371 | 0 | 1042278.1371 | 155 | 0 | 0 | 0 | 155 | 0
Mon | 7 | N | 156 | 2022-01-24 | -2.0769 | 0.046155 | 2022-01-24 | 0.1157 | 1055184.7035 | 0 | 1055184.7035 | 156 | 0 | 0 | 0 | 156 | 0
Tues | 7 | N | 157 | 2022-01-25 | -2.071 | 0.046725 | 2022-01-25 | 0.11713 | 1068213.6905 | 0 | 1068213.6905 | 157 | 0 | 0 | 0 | 157 | 0
Wed | 7 | N | 158 | 2022-01-26 | -2.0651 | 0.047301 | 2022-01-26 | 0.11857 | 1081365.6918 | 0 | 1081365.6918 | 158 | 0 | 0 | 0 | 158 | 0
Thu | 7 | N | 159 | 2022-01-27 | -2.0592 | 0.047881 | 2022-01-27 | 0.12003 | 1094641.2954 | 0 | 1094641.2954 | 159 | 0 | 0 | 0 | 159 | 0
Fri | 7 | N | 160 | 2022-01-28 | -2.0533 | 0.048467 | 2022-01-28 | 0.1215 | 1108041.0833 | 0 | 1108041.0833 | 160 | 0 | 0 | 0 | 160 | 0
Sat | 7 | Y | 160 | 2022-01-29 | -2.0533 | 0.048467 | 2022-01-29 | 0.1215 | 1108041.0833 | 0 | 1108041.0833 | 160 | 0 | 0 | 0 | 160 | 0
Sun | 7 | Y | 160 | 2022-01-30 | -2.0533 | 0.048467 | 2022-01-30 | 0.1215 | 1108041.0833 | 0 | 1108041.0833 | 160 | 0 | 0 | 0 | 160 | 0
Mon | 7 | N | 161 | 2022-01-31 | -2.0473 | 0.049059 | 2022-01-31 | 0.12298 | 1121565.6316 | 0 | 1121565.6316 | 161 | 0 | 0 | 0 | 161 | 0
Tues | 7 | N | 162 | 2022-02-01 | -2.0414 | 0.049656 | 2022-02-01 | 0.12448 | 1135215.5104 | 0 | 1135215.5104 | 162 | 0 | 0 | 0 | 162 | 0
Wed | 7 | N | 163 | 2022-02-02 | -2.0355 | 0.050259 | 2022-02-02 | 0.12599 | 1148991.2833 | 0 | 1148991.2833 | 163 | 0 | 0 | 0 | 163 | 0
Thu | 7 | N | 164 | 2022-02-03 | -2.0296 | 0.050867 | 2022-02-03 | 0.12751 | 1162893.5076 | 0 | 1162893.5076 | 164 | 0 | 0 | 0 | 164 | 0
Fri | 7 | N | 165 | 2022-02-04 | -2.0237 | 0.05148 | 2022-02-04 | 0.12905 | 1176922.7338 | 0 | 1176922.7338 | 165 | 0 | 0 | 0 | 165 | 0
Sat | 7 | Y | 165 | 2022-02-05 | -2.0237 | 0.05148 | 2022-02-05 | 0.12905 | 1176922.7338 | 0 | 1176922.7338 | 165 | 0 | 0 | 0 | 165 | 0
Sun | 7 | Y | 165 | 2022-02-06 | -2.0237 | 0.05148 | 2022-02-06 | 0.12905 | 1176922.7338 | 0 | 1176922.7338 | 165 | 0 | 0 | 0 | 165 | 0
Mon | 7 | N | 166 | 2022-02-07 | -2.0178 | 0.0521 | 2022-02-07 | 0.1306 | 1191079.5058 | 0 | 1191079.5058 | 166 | 0 | 0 | 0 | 166 | 0
Tues | 7 | N | 167 | 2022-02-08 | -2.0118 | 0.052724 | 2022-02-08 | 0.13217 | 1205364.3605 | 0 | 1205364.3605 | 167 | 0 | 0 | 0 | 167 | 0
Wed | 7 | N | 168 | 2022-02-09 | -2.0059 | 0.053355 | 2022-02-09 | 0.13375 | 1219777.8278 | 0 | 1219777.8278 | 168 | 0 | 0 | 0 | 168 | 0
Thu | 7 | N | 169 | 2022-02-10 | -2 | 0.053991 | 2022-02-10 | 0.13534 | 1234320.4302 | 0 | 1234320.4302 | 169 | 0 | 0 | 0 | 169 | 0
Fri | 7 | N | 170 | 2022-02-11 | -1.9941 | 0.054633 | 2022-02-11 | 0.13695 | 1248992.683 | 0 | 1248992.683 | 170 | 0 | 0 | 0 | 170 | 0
Sat | 7 | Y | 170 | 2022-02-12 | -1.9941 | 0.054633 | 2022-02-12 | 0.13695 | 1248992.683 | 0 | 1248992.683 | 170 | 0 | 0 | 0 | 170 | 0
Sun | 7 | Y | 170 | 2022-02-13 | -1.9941 | 0.054633 | 2022-02-13 | 0.13695 | 1248992.683 | 0 | 1248992.683 | 170 | 0 | 0 | 0 | 170 | 0
Mon | 7 | N | 171 | 2022-02-14 | -1.9882 | 0.05528 | 2022-02-14 | 0.13858 | 1263795.0938 | 0 | 1263795.0938 | 171 | 0 | 0 | 0 | 171 | 0
Tues | 7 | N | 172 | 2022-02-15 | -1.9822 | 0.055933 | 2022-02-15 | 0.14021 | 1278728.1623 | 0 | 1278728.1623 | 172 | 0 | 0 | 0 | 172 | 0
Wed | 7 | N | 173 | 2022-02-16 | -1.9763 | 0.056592 | 2022-02-16 | 0.14187 | 1293792.3808 | 0 | 1293792.3808 | 173 | 0 | 0 | 0 | 173 | 0
Thu | 7 | N | 174 | 2022-02-17 | -1.9704 | 0.057257 | 2022-02-17 | 0.14353 | 1308988.233 | 0 | 1308988.233 | 174 | 0 | 0 | 0 | 174 | 0
Fri | 7 | N | 175 | 2022-02-18 | -1.9645 | 0.057928 | 2022-02-18 | 0.14521 | 1324316.1948 | 0 | 1324316.1948 | 175 | 0 | 0 | 0 | 175 | 0
Sat | 7 | Y | 175 | 2022-02-19 | -1.9645 | 0.057928 | 2022-02-19 | 0.14521 | 1324316.1948 | 0 | 1324316.1948 | 175 | 0 | 0 | 0 | 175 | 0
Sun | 7 | Y | 175 | 2022-02-20 | -1.9645 | 0.057928 | 2022-02-20 | 0.14521 | 1324316.1948 | 0 | 1324316.1948 | 175 | 0 | 0 | 0 | 175 | 0
Mon | 8 | N | 176 | 2022-02-21 | -1.9586 | 0.058604 | 2022-02-21 | 0.14691 | 1339776.7335 | 0 | 1339776.7335 | 176 | 0 | 0 | 0 | 176 | 0
Tues | 8 | N | 177 | 2022-02-22 | -1.9527 | 0.059286 | 2022-02-22 | 0.14862 | 1355370.3079 | 0 | 1355370.3079 | 177 | 0 | 0 | 0 | 177 | 0
Wed | 8 | N | 178 | 2022-02-23 | -1.9467 | 0.059974 | 2022-02-23 | 0.15034 | 1371097.3682 | 0 | 1371097.3682 | 178 | 0 | 0 | 0 | 178 | 0
Thu | 8 | N | 179 | 2022-02-24 | -1.9408 | 0.060668 | 2022-02-24 | 0.15208 | 1386958.3555 | 0 | 1386958.3555 | 179 | 0 | 0 | 0 | 179 | 0
Fri | 8 | N | 180 | 2022-02-25 | -1.9349 | 0.061367 | 2022-02-25 | 0.15384 | 1402953.7021 | 0 | 1402953.7021 | 180 | 0 | 0 | 0 | 180 | 0
Sat | 8 | Y | 180 | 2022-02-26 | -1.9349 | 0.061367 | 2022-02-26 | 0.15384 | 1402953.7021 | 0 | 1402953.7021 | 180 | 0 | 0 | 0 | 180 | 0
Sun | 8 | Y | 180 | 2022-02-27 | -1.9349 | 0.061367 | 2022-02-27 | 0.15384 | 1402953.7021 | 0 | 1402953.7021 | 180 | 0 | 0 | 0 | 180 | 0
Mon | 8 | N | 181 | 2022-02-28 | -1.929 | 0.062073 | 2022-02-28 | 0.1556 | 1419083.8309 | 0 | 1419083.8309 | 181 | 0 | 0 | 0 | 181 | 0
Tues | 8 | N | 182 | 2022-03-01 | -1.9231 | 0.062784 | 2022-03-01 | 0.15739 | 1435349.1557 | 0 | 1435349.1557 | 182 | 0 | 0 | 0 | 182 | 0
Wed | 8 | N | 183 | 2022-03-02 | -1.9172 | 0.063502 | 2022-03-02 | 0.15919 | 1451750.0805 | 0 | 1451750.0805 | 183 | 0 | 0 | 0 | 183 | 0
Thu | 8 | N | 184 | 2022-03-03 | -1.9112 | 0.064225 | 2022-03-03 | 0.161 | 1468286.9996 | 0 | 1468286.9996 | 184 | 0 | 0 | 0 | 184 | 0
Fri | 8 | N | 185 | 2022-03-04 | -1.9053 | 0.064954 | 2022-03-04 | 0.16283 | 1484960.2977 | 0 | 1484960.2977 | 185 | 0 | 0 | 0 | 185 | 0
Sat | 8 | Y | 185 | 2022-03-05 | -1.9053 | 0.064954 | 2022-03-05 | 0.16283 | 1484960.2977 | 0 | 1484960.2977 | 185 | 0 | 0 | 0 | 185 | 0
Sun | 8 | Y | 185 | 2022-03-06 | -1.9053 | 0.064954 | 2022-03-06 | 0.16283 | 1484960.2977 | 0 | 1484960.2977 | 185 | 0 | 0 | 0 | 185 | 0
Mon | 8 | N | 186 | 2022-03-07 | -1.8994 | 0.06569 | 2022-03-07 | 0.16467 | 1501770.3492 | 0 | 1501770.3492 | 186 | 0 | 0 | 0 | 186 | 0
Tues | 8 | N | 187 | 2022-03-08 | -1.8935 | 0.066431 | 2022-03-08 | 0.16653 | 1518717.5185 | 0 | 1518717.5185 | 187 | 0 | 0 | 0 | 187 | 0
Wed | 8 | N | 188 | 2022-03-09 | -1.8876 | 0.067178 | 2022-03-09 | 0.1684 | 1535802.1595 | 0 | 1535802.1595 | 188 | 0 | 0 | 0 | 188 | 0
Thu | 8 | N | 189 | 2022-03-10 | -1.8817 | 0.067932 | 2022-03-10 | 0.17029 | 1553024.6155 | 0 | 1553024.6155 | 189 | 0 | 0 | 0 | 189 | 0
Fri | 8 | N | 190 | 2022-03-11 | -1.8757 | 0.068691 | 2022-03-11 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Sat | 8 | Y | 190 | 2022-03-12 | -1.8757 | 0.068691 | 2022-03-12 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Sun | 8 | Y | 190 | 2022-03-13 | -1.8757 | 0.068691 | 2022-03-13 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Mon | 8 | Y | 190 | 2022-03-14 | -1.8757 | 0.068691 | 2022-03-14 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Tues | 8 | Y | 190 | 2022-03-15 | -1.8757 | 0.068691 | 2022-03-15 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Wed | 8 | Y | 190 | 2022-03-16 | -1.8757 | 0.068691 | 2022-03-16 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Thu | 8 | Y | 190 | 2022-03-17 | -1.8757 | 0.068691 | 2022-03-17 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Fri | 8 | Y | 190 | 2022-03-18 | -1.8757 | 0.068691 | 2022-03-18 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Sat | 8 | Y | 190 | 2022-03-19 | -1.8757 | 0.068691 | 2022-03-19 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Sun | 8 | Y | 190 | 2022-03-20 | -1.8757 | 0.068691 | 2022-03-20 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Mon | 9 | Y | 190 | 2022-03-21 | -1.8757 | 0.068691 | 2022-03-21 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Tues | 9 | Y | 190 | 2022-03-22 | -1.8757 | 0.068691 | 2022-03-22 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Wed | 9 | Y | 190 | 2022-03-23 | -1.8757 | 0.068691 | 2022-03-23 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Thu | 9 | Y | 190 | 2022-03-24 | -1.8757 | 0.068691 | 2022-03-24 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Fri | 9 | Y | 190 | 2022-03-25 | -1.8757 | 0.068691 | 2022-03-25 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Sat | 9 | Y | 190 | 2022-03-26 | -1.8757 | 0.068691 | 2022-03-26 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Sun | 9 | Y | 190 | 2022-03-27 | -1.8757 | 0.068691 | 2022-03-27 | 0.17219 | 1570385.2193 | 0 | 1570385.2193 | 190 | 0 | 0 | 0 | 190 | 0
Mon | 9 | N | 191 | 2022-03-28 | -1.8698 | 0.069456 | 2022-03-28 | 0.17411 | 1587884.2927 | 0 | 1587884.2927 | 191 | 0 | 0 | 0 | 191 | 0 | 1
Tues | 10 | N | 192 | 2022-03-29 | -1.8639 | 0.070228 | 2022-03-29 | 0.17605 | 1605522.1465 | 0 | 1605522.1465 | 192 | 0 | 0 | 0 | 192 | 0 | 1
Wed | 10 | N | 193 | 2022-03-30 | -1.858 | 0.071005 | 2022-03-30 | 0.178 | 1623299.0804 | 0 | 1623299.0804 | 193 | 0 | 0 | 0 | 193 | 0 | 1
Thu | 10 | N | 194 | 2022-03-31 | -1.8521 | 0.071789 | 2022-03-31 | 0.17996 | 1641215.3825 | 0 | 1641215.3825 | 194 | 0 | 0 | 0 | 194 | 0 | 1
Fri | 10 | N | 195 | 2022-04-01 | -1.8462 | 0.072579 | 2022-04-01 | 0.18194 | 1659271.3295 | 0 | 1659271.3295 | 195 | 0 | 0 | 0 | 195 | 0 | 1
Sat | 10 | Y | 195 | 2022-04-02 | -1.8462 | 0.072579 | 2022-04-02 | 0.18194 | 1659271.3295 | 0 | 1659271.3295 | 195 | 0 | 0 | 0 | 195 | 0 | 1
Sun | 10 | Y | 195 | 2022-04-03 | -1.8462 | 0.072579 | 2022-04-03 | 0.18194 | 1659271.3295 | 0 | 1659271.3295 | 195 | 0 | 0 | 0 | 195 | 0 | 1
Mon | 10 | N | 196 | 2022-04-04 | -1.8402 | 0.073375 | 2022-04-04 | 0.18394 | 1677467.1866 | 0 | 1677467.1866 | 196 | 0 | 0 | 0 | 196 | 0 | 1
Tues | 10 | N | 197 | 2022-04-05 | -1.8343 | 0.074177 | 2022-04-05 | 0.18595 | 1695803.2067 | 0 | 1695803.2067 | 197 | 0 | 0 | 0 | 197 | 0 | 9119824.26
Wed | 10 | N | 198 | 2022-04-06 | -1.8284 | 0.074985 | 2022-04-06 | 0.18797 | 1714279.631 | 0 | 1714279.631 | 198 | 0 | 0 | 0 | 198 | 0 | 9119824.26
Thu | 10 | N | 199 | 2022-04-07 | -1.8225 | 0.075799 | 2022-04-07 | 0.19001 | 1732896.6884 | 0 | 1732896.6884 | 199 | 0 | 0 | 0 | 199 | 0 | 9119824.26
Fri | 10 | N | 200 | 2022-04-08 | -1.8166 | 0.07662 | 2022-04-08 | 0.19207 | 1751654.5956 | 0 | 1751654.5956 | 200 | 0 | 0 | 0 | 200 | 0 | 9119824.26
Sat | 10 | Y | 200 | 2022-04-09 | -1.8166 | 0.07662 | 2022-04-09 | 0.19207 | 1751654.5956 | 0 | 1751654.5956 | 200 | 0 | 0 | 0 | 200 | 0 | 9119824.26
Sun | 10 | Y | 200 | 2022-04-10 | -1.8166 | 0.07662 | 2022-04-10 | 0.19207 | 1751654.5956 | 0 | 1751654.5956 | 200 | 0 | 0 | 0 | 200 | 0 | 9119824.26
Mon | 10 | N | 201 | 2022-04-11 | -1.8107 | 0.077447 | 2022-04-11 | 0.19414 | 1770553.5563 | 0 | 1770553.5563 | 201 | 0 | 0 | 0 | 201 | 0 | 9119824.26
Tues | 10 | N | 202 | 2022-04-12 | -1.8047 | 0.078279 | 2022-04-12 | 0.19623 | 1789593.7621 | 0 | 1789593.7621 | 202 | 0 | 0 | 0 | 202 | 0 | 9119824.26
Wed | 10 | N | 203 | 2022-04-13 | -1.7988 | 0.079118 | 2022-04-13 | 0.19833 | 1808775.3914 | 0 | 1808775.3914 | 203 | 0 | 0 | 0 | 203 | 0 | 9119824.26
Thu | 10 | N | 204 | 2022-04-14 | -1.7929 | 0.079964 | 2022-04-14 | 0.20045 | 1828098.6097 | 0 | 1828098.6097 | 204 | 0 | 0 | 0 | 204 | 0 | 9119824.26
Fri | 10 | N | 205 | 2022-04-15 | -1.787 | 0.080815 | 2022-04-15 | 0.20259 | 1847563.5692 | 0 | 1847563.5692 | 205 | 0 | 0 | 0 | 205 | 0 | 9119824.26
Sat | 10 | Y | 205 | 2022-04-16 | -1.787 | 0.080815 | 2022-04-16 | 0.20259 | 1847563.5692 | 0 | 1847563.5692 | 205 | 0 | 0 | 0 | 205 | 0 | 9119824.26
Sun | 10 | Y | 205 | 2022-04-17 | -1.787 | 0.080815 | 2022-04-17 | 0.20259 | 1847563.5692 | 0 | 1847563.5692 | 205 | 0 | 0 | 0 | 205 | 0 | 9119824.26
Mon | 10 | N | 206 | 2022-04-18 | -1.7811 | 0.081673 | 2022-04-18 | 0.20474 | 1867170.4088 | 0 | 1867170.4088 | 206 | 0 | 0 | 0 | 206 | 0 | 9119824.26
Tues | 10 | N | 207 | 2022-04-19 | -1.7751 | 0.082537 | 2022-04-19 | 0.2069 | 1886919.254 | 0 | 1886919.254 | 207 | 0 | 0 | 0 | 207 | 0 | 9119824.26
Wed | 10 | N | 208 | 2022-04-20 | -1.7692 | 0.083407 | 2022-04-20 | 0.20908 | 1906810.2166 | 0 | 1906810.2166 | 208 | 0 | 0 | 0 | 208 | 0 | 9119824.26
Thu | 10 | N | 209 | 2022-04-21 | -1.7633 | 0.084283 | 2022-04-21 | 0.21128 | 1926843.3945 | 0 | 1926843.3945 | 209 | 0 | 0 | 0 | 209 | 0 | 9119824.26
Fri | 10 | N | 210 | 2022-04-22 | -1.7574 | 0.085165 | 2022-04-22 | 0.21349 | 1947018.8716 | 0 | 1947018.8716 | 210 | 0 | 0 | 0 | 210 | 0 | 9119824.26
Sat | 10 | Y | 210 | 2022-04-23 | -1.7574 | 0.085165 | 2022-04-23 | 0.21349 | 1947018.8716 | 0 | 1947018.8716 | 210 | 0 | 0 | 0 | 210 | 0 | 9119824.26
Sun | 10 | Y | 210 | 2022-04-24 | -1.7574 | 0.085165 | 2022-04-24 | 0.21349 | 1947018.8716 | 0 | 1947018.8716 | 210 | 0 | 0 | 0 | 210 | 0 | 9119824.26
Mon | 10 | N | 211 | 2022-04-25 | -1.7515 | 0.086054 | 2022-04-25 | 0.21572 | 1967336.7178 | 0 | 1967336.7178 | 211 | 0 | 0 | 0 | 211 | 0 | 9119824.26
Tues | 10 | N | 212 | 2022-04-26 | -1.7456 | 0.086949 | 2022-04-26 | 0.21796 | 1987796.9885 | 0 | 1987796.9885 | 212 | 0 | 0 | 0 | 212 | 0 | 9119824.26
Wed | 10 | N | 213 | 2022-04-27 | -1.7396 | 0.08785 | 2022-04-27 | 0.22022 | 2008399.7249 | 0 | 2008399.7249 | 213 | 0 | 0 | 0 | 213 | 0 | 9119824.26
Thu | 10 | N | 214 | 2022-04-28 | -1.7337 | 0.088758 | 2022-04-28 | 0.2225 | 2029144.9532 | 0 | 2029144.9532 | 214 | 0 | 0 | 0 | 214 | 0 | 9119824.26
Fri | 10 | N | 215 | 2022-04-29 | -1.7278 | 0.089671 | 2022-04-29 | 0.22479 | 2050032.6853 | 0 | 2050032.6853 | 215 | 0 | 0 | 0 | 215 | 0 | 9119824.26
Sat | 10 | Y | 215 | 2022-04-30 | -1.7278 | 0.089671 | 2022-04-30 | 0.22479 | 2050032.6853 | 0 | 2050032.6853 | 215 | 0 | 0 | 0 | 215 | 0 | 9119824.26
Sun | 10 | Y | 215 | 2022-05-01 | -1.7278 | 0.089671 | 2022-05-01 | 0.22479 | 2050032.6853 | 0 | 2050032.6853 | 215 | 0 | 0 | 0 | 215 | 0 | 9119824.26
Mon | 10 | N | 216 | 2022-05-02 | -1.7219 | 0.090591 | 2022-05-02 | 0.22709 | 2071062.9178 | 0 | 2071062.9178 | 216 | 0 | 0 | 0 | 216 | 0 | 9119824.26
Tues | 10 | N | 217 | 2022-05-03 | -1.716 | 0.091517 | 2022-05-03 | 0.22942 | 2092235.6324 | 0 | 2092235.6324 | 217 | 0 | 0 | 0 | 217 | 0 | 9119824.26
Wed | 10 | N | 218 | 2022-05-04 | -1.7101 | 0.09245 | 2022-05-04 | 0.23175 | 2113550.7954 | 0 | 2113550.7954 | 218 | 0 | 0 | 0 | 218 | 0 | 9119824.26
Thu | 10 | N | 219 | 2022-05-05 | -1.7041 | 0.093388 | 2022-05-05 | 0.23411 | 2135008.3581 | 0 | 2135008.3581 | 219 | 0 | 0 | 0 | 219 | 0 | 9119824.26
Fri | 10 | N | 220 | 2022-05-06 | -1.6982 | 0.094333 | 2022-05-06 | 0.23647 | 2156608.2558 | 0 | 2156608.2558 | 220 | 0 | 0 | 0 | 220 | 0 | 9119824.26
Sat | 10 | Y | 220 | 2022-05-07 | -1.6982 | 0.094333 | 2022-05-07 | 0.23647 | 2156608.2558 | 0 | 2156608.2558 | 220 | 0 | 0 | 0 | 220 | 0 | 9119824.26
Sun | 10 | Y | 220 | 2022-05-08 | -1.6982 | 0.094333 | 2022-05-08 | 0.23647 | 2156608.2558 | 0 | 2156608.2558 | 220 | 0 | 0 | 0 | 220 | 0 | 9119824.26
Mon | 10 | N | 221 | 2022-05-09 | -1.6923 | 0.095284 | 2022-05-09 | 0.23886 | 2178350.4085 | 0 | 2178350.4085 | 221 | 0 | 0 | 0 | 221 | 0 | 9119824.26
Tues | 10 | N | 222 | 2022-05-10 | -1.6864 | 0.096241 | 2022-05-10 | 0.24126 | 2200234.72 | 0 | 2200234.72 | 222 | 0 | 0 | 0 | 222 | 0 | 9119824.26
Wed | 10 | N | 223 | 2022-05-11 | -1.6805 | 0.097205 | 2022-05-11 | 0.24367 | 2222261.0785 | 0 | 2222261.0785 | 223 | 0 | 0 | 0 | 223 | 0 | 9119824.26
Thu | 10 | N | 224 | 2022-05-12 | -1.6746 | 0.098175 | 2022-05-12 | 0.2461 | 2244429.3559 | 0 | 2244429.3559 | 224 | 0 | 0 | 0 | 224 | 0 | 9119824.26
Fri | 10 | N | 225 | 2022-05-13 | -1.6686 | 0.09915 | 2022-05-13 | 0.24855 | 2266739.4079 | 0 | 2266739.4079 | 225 | 0 | 0 | 0 | 225 | 0 | 9119824.26
Sat | 10 | Y | 225 | 2022-05-14 | -1.6686 | 0.09915 | 2022-05-14 | 0.24855 | 2266739.4079 | 0 | 2266739.4079 | 225 | 0 | 0 | 0 | 225 | 0 | 9119824.26
Sun | 10 | Y | 225 | 2022-05-15 | -1.6686 | 0.09915 | 2022-05-15 | 0.24855 | 2266739.4079 | 0 | 2266739.4079 | 225 | 0 | 0 | 0 | 225 | 0 | 9119824.26
Mon | 10 | N | 226 | 2022-05-16 | -1.6627 | 0.10013 | 2022-05-16 | 0.25101 | 2289191.0736 | 0 | 2289191.0736 | 226 | 0 | 0 | 0 | 226 | 0 | 9119824.26
Tues | 10 | N | 227 | 2022-05-17 | -1.6568 | 0.10112 | 2022-05-17 | 0.25349 | 2311784.1758 | 0 | 2311784.1758 | 227 | 0 | 0 | 0 | 227 | 0 | 9119824.26
Wed | 10 | N | 228 | 2022-05-18 | -1.6509 | 0.10212 | 2022-05-18 | 0.25598 | 2334518.5205 | 0 | 2334518.5205 | 228 | 0 | 0 | 0 | 228 | 0 | 9119824.26
Thu | 10 | N | 229 | 2022-05-19 | -1.645 | 0.10312 | 2022-05-19 | 0.25849 | 2357393.897 | 0 | 2357393.897 | 229 | 0 | 0 | 0 | 229 | 0 | 9119824.26
Fri | 10 | N | 230 | 2022-05-20 | -1.6391 | 0.10412 | 2022-05-20 | 0.26101 | 2380410.0774 | 0 | 2380410.0774 | 230 | 0 | 0 | 0 | 230 | 0 | 9119824.26
Sat | 10 | Y | 230 | 2022-05-21 | -1.6391 | 0.10412 | 2022-05-21 | 0.26101 | 2380410.0774 | 0 | 2380410.0774 | 230 | 0 | 0 | 0 | 230 | 0 | 9119824.26
Sun | 10 | Y | 230 | 2022-05-22 | -1.6391 | 0.10412 | 2022-05-22 | 0.26101 | 2380410.0774 | 0 | 2380410.0774 | 230 | 0 | 0 | 0 | 230 | 0 | 9119824.26
Mon | 10 | N | 231 | 2022-05-23 | -1.6331 | 0.10514 | 2022-05-23 | 0.26355 | 2403566.817 | 0 | 2403566.817 | 231 | 0 | 0 | 0 | 231 | 0 | 9119824.26
Tues | 10 | N | 232 | 2022-05-24 | -1.6272 | 0.10615 | 2022-05-24 | 0.26611 | 2426863.8538 | 0 | 2426863.8538 | 232 | 0 | 0 | 0 | 232 | 0 | 9119824.26
Wed | 10 | N | 233 | 2022-05-25 | -1.6213 | 0.10718 | 2022-05-25 | 0.26868 | 2450300.9082 | 0 | 2450300.9082 | 233 | 0 | 0 | 0 | 233 | 0 | 9119824.26
Thu | 10 | N | 234 | 2022-05-26 | -1.6154 | 0.10821 | 2022-05-26 | 0.27126 | 2473877.6834 | 0 | 2473877.6834 | 234 | 0 | 0 | 0 | 234 | 0 | 9119824.26
Fri | 10 | N | 235 | 2022-05-27 | -1.6095 | 0.10925 | 2022-05-27 | 0.27386 | 2497593.8649 | 0 | 2497593.8649 | 235 | 0 | 0 | 0 | 235 | 0 | 9119824.26
Sat | 10 | Y | 235 | 2022-05-28 | -1.6095 | 0.10925 | 2022-05-28 | 0.27386 | 2497593.8649 | 0 | 2497593.8649 | 235 | 0 | 0 | 0 | 235 | 0 | 9119824.26
Sun | 12 | Y | 235 | 2022-05-29 | -1.6095 | 0.10925 | 2022-05-29 | 0.27386 | 2497593.8649 | 0 | 2497593.8649 | 235 | 0 | 0 | 0 | 235 | 0 | 9119824.26
Mon | 12 | N | 236 | 2022-05-30 | -1.6036 | 0.11029 | 2022-05-30 | 0.27648 | 2521449.1205 | 0 | 2521449.1205 | 236 | 0 | 0 | 0 | 236 | 0 | 9119824.26
Tues | 12 | N | 237 | 2022-05-31 | -1.5976 | 0.11134 | 2022-05-31 | 0.27911 | 2545443.1 | 0 | 2545443.1 | 237 | 0 | 0 | 0 | 237 | 0 | 9119824.26
Wed | 12 | N | 238 | 2022-06-01 | -1.5917 | 0.1124 | 2022-06-01 | 0.28176 | 2569575.4355 | 0 | 2569575.4355 | 238 | 0 | 0 | 0 | 238 | 0 | 9119824.26
Thu | 12 | N | 239 | 2022-06-02 | -1.5858 | 0.11346 | 2022-06-02 | 0.28442 | 2593845.7407 | 0 | 2593845.7407 | 239 | 0 | 0 | 0 | 239 | 0 | 9119824.26
Fri | 12 | N | 240 | 2022-06-03 | -1.5799 | 0.11453 | 2022-06-03 | 0.28709 | 2618253.6113 | 0 | 2618253.6113 | 240 | 0 | 0 | 0 | 240 | 0 | 9119824.26
Sat | 12 | Y | 240 | 2022-06-04 | -1.5799 | 0.11453 | 2022-06-04 | 0.28709 | 2618253.6113 | 0 | 2618253.6113 | 240 | 0 | 0 | 0 | 240 | 0 | 9119824.26
Sun | 12 | Y | 240 | 2022-06-05 | -1.5799 | 0.11453 | 2022-06-05 | 0.28709 | 2618253.6113 | 0 | 2618253.6113 | 240 | 0 | 0 | 0 | 240 | 0 | 9119824.26
Mon | 12 | N | 241 | 2022-06-06 | -1.574 | 0.1156 | 2022-06-06 | 0.28979 | 2642798.6246 | 0 | 2642798.6246 | 241 | 0 | 0 | 0 | 241 | 0 | 9119824.26
Tues | 12 | N | 242 | 2022-06-07 | -1.568 | 0.11668 | 2022-06-07 | 0.29249 | 2667480.3394 | 0 | 2667480.3394 | 242 | 0 | 0 | 0 | 242 | 0 | 9119824.26
Wed | 12 | N | 243 | 2022-06-08 | -1.5621 | 0.11777 | 2022-06-08 | 0.29521 | 2692298.296 | 0 | 2692298.296 | 243 | 0 | 0 | 0 | 243 | 0 | 9119824.26
Thu | 12 | N | 244 | 2022-06-09 | -1.5562 | 0.11886 | 2022-06-09 | 0.29795 | 2717252.0161 | 0 | 2717252.0161 | 244 | 0 | 0 | 0 | 244 | 0 | 9119824.26
Fri | 12 | N | 245 | 2022-06-10 | -1.5503 | 0.11995 | 2022-06-10 | 0.3007 | 2742341.0024 | 0 | 2742341.0024 | 245 | 0 | 0 | 0 | 245 | 0 | 9119824.26
Sat | 12 | Y | 245 | 2022-06-11 | -1.5503 | 0.11995 | 2022-06-11 | 0.3007 | 2742341.0024 | 0 | 2742341.0024 | 245 | 0 | 0 | 0 | 245 | 0 | 9119824.26
Sun | 12 | Y | 245 | 2022-06-12 | -1.5503 | 0.11995 | 2022-06-12 | 0.3007 | 2742341.0024 | 0 | 2742341.0024 | 245 | 0 | 0 | 0 | 245 | 0 | 9119824.26
Mon | 12 | N | 246 | 2022-06-13 | -1.5444 | 0.12106 | 2022-06-13 | 0.30347 | 2767564.7391 | 0 | 2767564.7391 | 246 | 0 | 0 | 0 | 246 | 0 | 9119824.26
Tues | 12 | N | 247 | 2022-06-14 | -1.5385 | 0.12217 | 2022-06-14 | 0.30625 | 2792922.6911 | 0 | 2792922.6911 | 247 | 0 | 0 | 0 | 247 | 0 | 9119824.26
Wed | 12 | N | 248 | 2022-06-15 | -1.5325 | 0.12328 | 2022-06-15 | 0.30904 | 2818414.3044 | 0 | 2818414.3044 | 248 | 0 | 0 | 0 | 248 | 0 | 9119824.26
Thu | 12 | N | 249 | 2022-06-16 | -1.5266 | 0.1244 | 2022-06-16 | 0.31185 | 2844039.0057 | 0 | 2844039.0057 | 249 | 0 | 0 | 0 | 249 | 0 | 9119824.26
Fri | 12 | N | 250 | 2022-06-17 | -1.5207 | 0.12553 | 2022-06-17 | 0.31468 | 2869796.2026 | 0 | 2869796.2026 | 250 | 0 | 0 | 0 | 250 | 0 | 9119824.26
Sat | 12 | Y | 250 | 2022-06-18 | -1.5207 | 0.12553 | 2022-06-18 | 0.31468 | 2869796.2026 | 0 | 2869796.2026 | 250 | 0 | 0 | 0 | 250 | 0 | 9119824.26
Sun | 12 | Y | 250 | 2022-06-19 | -1.5207 | 0.12553 | 2022-06-19 | 0.31468 | 2869796.2026 | 0 | 2869796.2026 | 250 | 0 | 0 | 0 | 250 | 0 | 9119824.26
Mon | 12 | N | 251 | 2022-06-20 | -1.5148 | 0.12666 | 2022-06-20 | 0.31752 | 2895685.2832 | 0 | 2895685.2832 | 251 | 0 | 0 | 0 | 251 | 0 | 9119824.26
Tues | 12 | N | 252 | 2022-06-21 | -1.5089 | 0.1278 | 2022-06-21 | 0.32037 | 2921705.6162 | 0 | 2921705.6162 | 252 | 0 | 0 | 0 | 252 | 0 | 9119824.26
Wed | 12 | N | 253 | 2022-06-22 | -1.503 | 0.12894 | 2022-06-22 | 0.32324 | 2947856.5508 | 0 | 2947856.5508 | 253 | 0 | 0 | 0 | 253 | 0 | 9119824.26
Thu | 12 | N | 254 | 2022-06-23 | -1.497 | 0.13009 | 2022-06-23 | 0.32612 | 2974137.4166 | 0 | 2974137.4166 | 254 | 0 | 0 | 0 | 254 | 0 | 9119824.26
Fri | 12 | N | 255 | 2022-06-24 | -1.4911 | 0.13125 | 2022-06-24 | 0.32901 | 3000547.5234 | 0 | 3000547.5234 | 255 | 0 | 0 | 0 | 255 | 0 | 9119824.26
Sat | 12 | Y | 255 | 2022-06-25 | -1.4911 | 0.13125 | 2022-06-25 | 0.32901 | 3000547.5234 | 0 | 3000547.5234 | 255 | 0 | 0 | 0 | 255 | 0 | 9119824.26
Sun | 12 | Y | 255 | 2022-06-26 | -1.4911 | 0.13125 | 2022-06-26 | 0.32901 | 3000547.5234 | 0 | 3000547.5234 | 255 | 0 | 0 | 0 | 255 | 0 | 9119824.26
Mon | 12 | N | 256 | 2022-06-27 | -1.4852 | 0.13241 | 2022-06-27 | 0.33192 | 3027086.1613 | 0 | 3027086.1613 | 256 | 0 | 0 | 0 | 256 | 0 | 9119824.26
Tues | 12 | N | 257 | 2022-06-28 | -1.4793 | 0.13358 | 2022-06-28 | 0.33485 | 3053752.6006 | 0 | 3053752.6006 | 257 | 0 | 0 | 0 | 257 | 0 | 9119824.26
Wed | 12 | N | 258 | 2022-06-29 | -1.4734 | 0.13475 | 2022-06-29 | 0.33779 | 3080546.0916 | 0 | 3080546.0916 | 258 | 0 | 0 | 0 | 258 | 0 | 9119824.26
Thu | 12 | N | 259 | 2022-06-30 | -1.4675 | 0.13593 | 2022-06-30 | 0.34074 | 3107465.8645 | 0 | 3107465.8645 | 259 | 0 | 0 | 0 | 259 | 0 | 9119824.26
Fri | 12 | N | 260 | 2022-07-01 | -1.4615 | 0.13711 | 2022-07-01 | 0.3437 | 3134511.1297 | 0 | 3134511.1297 | 260 | 0 | 0 | 0 | 260 | 0 | 9119824.26
Sat | 12 | Y | 260 | 2022-07-02 | -1.4615 | 0.13711 | 2022-07-02 | 0.3437 | 3134511.1297 | 0 | 3134511.1297 | 260 | 0 | 0 | 0 | 260 | 0 | 9119824.26
Sun | 12 | Y | 260 | 2022-07-03 | -1.4615 | 0.13711 | 2022-07-03 | 0.3437 | 3134511.1297 | 0 | 3134511.1297 | 260 | 0 | 0 | 0 | 260 | 0 | 9119824.26
Mon | 12 | N | 261 | 2022-07-04 | -1.4556 | 0.1383 | 2022-07-04 | 0.34668 | 3161681.0773 | 0 | 3161681.0773 | 261 | 0 | 0 | 0 | 261 | 0 | 9119824.26
Tues | 12 | N | 262 | 2022-07-05 | -1.4497 | 0.13949 | 2022-07-05 | 0.34968 | 3188974.8772 | 0 | 3188974.8772 | 262 | 0 | 0 | 0 | 262 | 0 | 9119824.26
Wed | 12 | N | 263 | 2022-07-06 | -1.4438 | 0.14069 | 2022-07-06 | 0.35268 | 3216391.6791 | 0 | 3216391.6791 | 263 | 0 | 0 | 0 | 263 | 0 | 9119824.26
Thu | 12 | N | 264 | 2022-07-07 | -1.4379 | 0.14189 | 2022-07-07 | 0.3557 | 3243930.6124 | 0 | 3243930.6124 | 264 | 0 | 0 | 0 | 264 | 0 | 9119824.26
Fri | 12 | N | 265 | 2022-07-08 | -1.432 | 0.1431 | 2022-07-08 | 0.35873 | 3271590.7862 | 0 | 3271590.7862 | 265 | 0 | 0 | 0 | 265 | 0 | 9119824.26
Sat | 12 | Y | 265 | 2022-07-09 | -1.432 | 0.1431 | 2022-07-09 | 0.35873 | 3271590.7862 | 0 | 3271590.7862 | 265 | 0 | 0 | 0 | 265 | 0 | 9119824.26
Sun | 12 | Y | 265 | 2022-07-10 | -1.432 | 0.1431 | 2022-07-10 | 0.35873 | 3271590.7862 | 0 | 3271590.7862 | 265 | 0 | 0 | 0 | 265 | 0 | 9119824.26
Mon | 12 | N | 266 | 2022-07-11 | -1.426 | 0.14432 | 2022-07-11 | 0.36178 | 3299371.2891 | 0 | 3299371.2891 | 266 | 0 | 0 | 0 | 266 | 0 | 9119824.26
Tues | 12 | N | 267 | 2022-07-12 | -1.4201 | 0.14554 | 2022-07-12 | 0.36484 | 3327271.1893 | 0 | 3327271.1893 | 267 | 0 | 0 | 0 | 267 | 0 | 9119824.26
Wed | 12 | N | 268 | 2022-07-13 | -1.4142 | 0.14677 | 2022-07-13 | 0.36791 | 3355289.5345 | 0 | 3355289.5345 | 268 | 0 | 0 | 0 | 268 | 0 | 9119824.26
Thu | 12 | N | 269 | 2022-07-14 | -1.4083 | 0.148 | 2022-07-14 | 0.371 | 3383425.3519 | 0 | 3383425.3519 | 269 | 0 | 0 | 0 | 269 | 0 | 9119824.26
Fri | 12 | N | 270 | 2022-07-15 | -1.4024 | 0.14923 | 2022-07-15 | 0.37409 | 3411677.6481 | 0 | 3411677.6481 | 270 | 0 | 0 | 0 | 270 | 0 | 9119824.26
Sat | 12 | Y | 270 | 2022-07-16 | -1.4024 | 0.14923 | 2022-07-16 | 0.37409 | 3411677.6481 | 0 | 3411677.6481 | 270 | 0 | 0 | 0 | 270 | 0 | 9119824.26
Sun | 12 | Y | 270 | 2022-07-17 | -1.4024 | 0.14923 | 2022-07-17 | 0.37409 | 3411677.6481 | 0 | 3411677.6481 | 270 | 0 | 0 | 0 | 270 | 0 | 9119824.26
Mon | 12 | N | 271 | 2022-07-18 | -1.3964 | 0.15047 | 2022-07-18 | 0.37721 | 3440045.4091 | 0 | 3440045.4091 | 271 | 0 | 0 | 0 | 271 | 0 | 9119824.26
Tues | 12 | N | 272 | 2022-07-19 | -1.3905 | 0.15172 | 2022-07-19 | 0.38033 | 3468527.6003 | 0 | 3468527.6003 | 272 | 0 | 0 | 0 | 272 | 0 | 9119824.26
Wed | 12 | N | 273 | 2022-07-20 | -1.3846 | 0.15297 | 2022-07-20 | 0.38346 | 3497123.1665 | 0 | 3497123.1665 | 273 | 0 | 0 | 0 | 273 | 0 | 9119824.26
Thu | 12 | N | 274 | 2022-07-21 | -1.3787 | 0.15422 | 2022-07-21 | 0.38661 | 3525831.0316 | 0 | 3525831.0316 | 274 | 0 | 0 | 0 | 274 | 0 | 9119824.26
Fri | 12 | N | 275 | 2022-07-22 | -1.3728 | 0.15549 | 2022-07-22 | 0.38977 | 3554650.099 | 0 | 3554650.099 | 275 | 0 | 0 | 0 | 275 | 0 | 9119824.26
Sat | 12 | Y | 275 | 2022-07-23 | -1.3728 | 0.15549 | 2022-07-23 | 0.38977 | 3554650.099 | 0 | 3554650.099 | 275 | 0 | 0 | 0 | 275 | 0 | 9119824.26
Sun | 12 | Y | 275 | 2022-07-24 | -1.3728 | 0.15549 | 2022-07-24 | 0.38977 | 3554650.099 | 0 | 3554650.099 | 275 | 0 | 0 | 0 | 275 | 0 | 9119824.26
Mon | 12 | N | 276 | 2022-07-25 | -1.3669 | 0.15675 | 2022-07-25 | 0.39294 | 3583579.2515 | 0 | 3583579.2515 | 276 | 0 | 0 | 0 | 276 | 0 | 9119824.26
Tues | 12 | N | 277 | 2022-07-26 | -1.3609 | 0.15802 | 2022-07-26 | 0.39613 | 3612617.3509 | 0 | 3612617.3509 | 277 | 0 | 0 | 0 | 277 | 0 | 9119824.26
Wed | 12 | N | 278 | 2022-07-27 | -1.355 | 0.1593 | 2022-07-27 | 0.39932 | 3641763.2384 | 0 | 3641763.2384 | 278 | 0 | 0 | 0 | 278 | 0 | 9119824.26
Thu | 12 | N | 279 | 2022-07-28 | -1.3491 | 0.16058 | 2022-07-28 | 0.40253 | 3671015.7346 | 0 | 3671015.7346 | 279 | 0 | 0 | 0 | 279 | 0 | 9119824.26
Fri | 14 | N | 280 | 2022-07-29 | -1.3432 | 0.16186 | 2022-07-29 | 0.40575 | 3700373.639 | 0 | 3700373.639 | 280 | 0 | 0 | 0 | 280 | 0 | 9119824.26
Sat | 14 | Y | 280 | 2022-07-30 | -1.3432 | 0.16186 | 2022-07-30 | 0.40575 | 3700373.639 | 0 | 3700373.639 | 280 | 0 | 0 | 0 | 280 | 0 | 9119824.26
Sun | 14 | Y | 280 | 2022-07-31 | -1.3432 | 0.16186 | 2022-07-31 | 0.40575 | 3700373.639 | 0 | 3700373.639 | 280 | 0 | 0 | 0 | 280 | 0 | 9119824.26
Mon | 14 | N | 281 | 2022-08-01 | -1.3373 | 0.16315 | 2022-08-01 | 0.40898 | 3729835.7307 | 0 | 3729835.7307 | 281 | 0 | 0 | 0 | 281 | 0 | 9119824.26
Tues | 14 | N | 282 | 2022-08-02 | -1.3314 | 0.16444 | 2022-08-02 | 0.41222 | 3759400.7679 | 0 | 3759400.7679 | 282 | 0 | 0 | 0 | 282 | 0 | 9119824.26
Wed | 14 | N | 283 | 2022-08-03 | -1.3254 | 0.16574 | 2022-08-03 | 0.41548 | 3789067.4882 | 0 | 3789067.4882 | 283 | 0 | 0 | 0 | 283 | 0 | 9119824.26
Thu | 14 | N | 284 | 2022-08-04 | -1.3195 | 0.16704 | 2022-08-04 | 0.41874 | 3818834.6085 | 0 | 3818834.6085 | 284 | 0 | 0 | 0 | 284 | 0 | 9119824.26
Fri | 14 | N | 285 | 2022-08-05 | -1.3136 | 0.16835 | 2022-08-05 | 0.42201 | 3848700.8247 | 0 | 3848700.8247 | 285 | 0 | 0 | 0 | 285 | 0 | 9119824.26
Sat | 14 | Y | 285 | 2022-08-06 | -1.3136 | 0.16835 | 2022-08-06 | 0.42201 | 3848700.8247 | 0 | 3848700.8247 | 285 | 0 | 0 | 0 | 285 | 0 | 9119824.26
Sun | 14 | Y | 285 | 2022-08-07 | -1.3136 | 0.16835 | 2022-08-07 | 0.42201 | 3848700.8247 | 0 | 3848700.8247 | 285 | 0 | 0 | 0 | 285 | 0 | 9119824.26
Mon | 14 | N | 286 | 2022-08-08 | -1.3077 | 0.16966 | 2022-08-08 | 0.4253 | 3878664.8125 | 0 | 3878664.8125 | 286 | 0 | 0 | 0 | 286 | 0 | 9119824.26
Tues | 14 | N | 287 | 2022-08-09 | -1.3018 | 0.17097 | 2022-08-09 | 0.4286 | 3908725.2266 | 0 | 3908725.2266 | 287 | 0 | 0 | 0 | 287 | 0 | 9119824.26
Wed | 14 | N | 288 | 2022-08-10 | -1.2959 | 0.17229 | 2022-08-10 | 0.4319 | 3938880.7013 | 0 | 3938880.7013 | 288 | 0 | 0 | 0 | 288 | 0 | 9119824.26
Thu | 14 | N | 289 | 2022-08-11 | -1.2899 | 0.17362 | 2022-08-11 | 0.43522 | 3969129.8501 | 0 | 3969129.8501 | 289 | 0 | 0 | 0 | 289 | 0 | 9119824.26
Fri | 14 | N | 290 | 2022-08-12 | -1.284 | 0.17494 | 2022-08-12 | 0.43855 | 3999471.2661 | 0 | 3999471.2661 | 290 | 0 | 0 | 0 | 290 | 0 | 9119824.26
Sat | 14 | Y | 290 | 2022-08-13 | -1.284 | 0.17494 | 2022-08-13 | 0.43855 | 3999471.2661 | 0 | 3999471.2661 | 290 | 0 | 0 | 0 | 290 | 0 | 9119824.26
Sun | 14 | Y | 290 | 2022-08-14 | -1.284 | 0.17494 | 2022-08-14 | 0.43855 | 3999471.2661 | 0 | 3999471.2661 | 290 | 0 | 0 | 0 | 290 | 0 | 9119824.26
Mon | 14 | N | 291 | 2022-08-15 | -1.2781 | 0.17627 | 2022-08-15 | 0.44188 | 4029903.5219 | 0 | 4029903.5219 | 291 | 0 | 0 | 0 | 291 | 0 | 9119824.26
Tues | 14 | N | 292 | 2022-08-16 | -1.2722 | 0.17761 | 2022-08-16 | 0.44523 | 4060425.1697 | 0 | 4060425.1697 | 292 | 0 | 0 | 0 | 292 | 0 | 9119824.26
Wed | 14 | N | 293 | 2022-08-17 | -1.2663 | 0.17895 | 2022-08-17 | 0.44859 | 4091034.741 | 0 | 4091034.741 | 293 | 0 | 0 | 0 | 293 | 0 | 9119824.26
Thu | 14 | N | 294 | 2022-08-18 | -1.2604 | 0.18029 | 2022-08-18 | 0.45195 | 4121730.7472 | 0 | 4121730.7472 | 294 | 0 | 0 | 0 | 294 | 0 | 9119824.26
Fri | 14 | N | 295 | 2022-08-19 | -1.2544 | 0.18164 | 2022-08-19 | 0.45533 | 4152511.6793 | 0 | 4152511.6793 | 295 | 0 | 0 | 0 | 295 | 0 | 9119824.26
Sat | 14 | Y | 295 | 2022-08-20 | -1.2544 | 0.18164 | 2022-08-20 | 0.45533 | 4152511.6793 | 0 | 4152511.6793 | 295 | 0 | 0 | 0 | 295 | 0 | 9119824.26
Sun | 14 | Y | 295 | 2022-08-21 | -1.2544 | 0.18164 | 2022-08-21 | 0.45533 | 4152511.6793 | 0 | 4152511.6793 | 295 | 0 | 0 | 0 | 295 | 0 | 9119824.26
Mon | 14 | N | 296 | 2022-08-22 | -1.2485 | 0.18299 | 2022-08-22 | 0.45871 | 4183376.0081 | 0 | 4183376.0081 | 296 | 0 | 0 | 0 | 296 | 0 | 9119824.26
Tues | 14 | N | 297 | 2022-08-23 | -1.2426 | 0.18434 | 2022-08-23 | 0.46211 | 4214322.1842 | 0 | 4214322.1842 | 297 | 0 | 0 | 0 | 297 | 0 | 9119824.26
Wed | 14 | N | 298 | 2022-08-24 | -1.2367 | 0.1857 | 2022-08-24 | 0.46551 | 4245348.6379 | 0 | 4245348.6379 | 298 | 0 | 0 | 0 | 298 | 0 | 9119824.26
Thu | 14 | N | 299 | 2022-08-25 | -1.2308 | 0.18706 | 2022-08-25 | 0.46892 | 4276453.7798 | 0 | 4276453.7798 | 299 | 0 | 0 | 0 | 299 | 0 | 9119824.26
Fri | 14 | N | 300 | 2022-08-26 | -1.2249 | 0.18842 | 2022-08-26 | 0.47234 | 4307636.0002 | 0 | 4307636.0002 | 300 | 0 | 0 | 0 | 300 | 0 | 9119824.26
Sat | 14 | Y | 300 | 2022-08-27 | -1.2249 | 0.18842 | 2022-08-27 | 0.47234 | 4307636.0002 | 0 | 4307636.0002 | 300 | 0 | 0 | 0 | 300 | 0 | 9119824.26
Sun | 14 | Y | 300 | 2022-08-28 | -1.2249 | 0.18842 | 2022-08-28 | 0.47234 | 4307636.0002 | 0 | 4307636.0002 | 300 | 0 | 0 | 0 | 300 | 0 | 9119824.26
Mon | 14 | N | 301 | 2022-08-29 | -1.2189 | 0.18979 | 2022-08-29 | 0.47577 | 4338893.6697 | 0 | 4338893.6697 | 301 | 0 | 0 | 0 | 301 | 0 | 9119824.26
Tues | 14 | N | 302 | 2022-08-30 | -1.213 | 0.19116 | 2022-08-30 | 0.4792 | 4370225.1391 | 0 | 4370225.1391 | 302 | 0 | 0 | 0 | 302 | 0 | 9119824.26
Wed | 14 | N | 303 | 2022-08-31 | -1.2071 | 0.19253 | 2022-08-31 | 0.48264 | 4401628.7393 | 0 | 4401628.7393 | 303 | 0 | 0 | 0 | 303 | 0 | 9119824.26
Thu | 14 | N | 304 | 2022-09-01 | -1.2012 | 0.19391 | 2022-09-01 | 0.4861 | 4433102.7819 | 0 | 4433102.7819 | 304 | 0 | 0 | 0 | 304 | 0 | 9119824.26
Fri | 14 | N | 305 | 2022-09-02 | -1.1953 | 0.19529 | 2022-09-02 | 0.48955 | 4464645.5586 | 0 | 4464645.5586 | 305 | 0 | 0 | 0 | 305 | 0 | 9119824.26
Sat | 14 | Y | 305 | 2022-09-03 | -1.1953 | 0.19529 | 2022-09-03 | 0.48955 | 4464645.5586 | 0 | 4464645.5586 | 305 | 0 | 0 | 0 | 305 | 0 | 9119824.26
Sun | 14 | Y | 305 | 2022-09-04 | -1.1953 | 0.19529 | 2022-09-04 | 0.48955 | 4464645.5586 | 0 | 4464645.5586 | 305 | 0 | 0 | 0 | 305 | 0 | 9119824.26
Mon | 14 | N | 306 | 2022-09-05 | -1.1893 | 0.19667 | 2022-09-05 | 0.49302 | 4496255.3419 | 0 | 4496255.3419 | 306 | 0 | 0 | 0 | 306 | 0 | 9119824.26
Tues | 14 | N | 307 | 2022-09-06 | -1.1834 | 0.19806 | 2022-09-06 | 0.49649 | 4527930.3849 | 0 | 4527930.3849 | 307 | 0 | 0 | 0 | 307 | 0 | 9119824.26
Wed | 14 | N | 308 | 2022-09-07 | -1.1775 | 0.19945 | 2022-09-07 | 0.49997 | 4559668.9216 | 0 | 4559668.9216 | 308 | 0 | 0 | 0 | 308 | 0 | 9119824.26
Thu | 14 | N | 309 | 2022-09-08 | -1.1716 | 0.20084 | 2022-09-08 | 0.50346 | 4591469.1667 | 0 | 4591469.1667 | 309 | 0 | 0 | 0 | 309 | 0 | 9119824.26
Fri | 14 | N | 310 | 2022-09-09 | -1.1657 | 0.20223 | 2022-09-09 | 0.50695 | 4623329.316 | 0 | 4623329.316 | 310 | 0 | 0 | 0 | 310 | 0 | 9119824.26
Sat | 14 | Y | 310 | 2022-09-10 | -1.1657 | 0.20223 | 2022-09-10 | 0.50695 | 4623329.316 | 0 | 4623329.316 | 310 | 0 | 0 | 0 | 310 | 0 | 9119824.26
Sun | 14 | Y | 310 | 2022-09-11 | -1.1657 | 0.20223 | 2022-09-11 | 0.50695 | 4623329.316 | 0 | 4623329.316 | 310 | 0 | 0 | 0 | 310 | 0 | 9119824.26
Mon | 14 | N | 311 | 2022-09-12 | -1.1598 | 0.20363 | 2022-09-12 | 0.51045 | 4655247.5464 | 0 | 4655247.5464 | 311 | 0 | 0 | 0 | 311 | 0 | 9119824.26
Tues | 14 | N | 312 | 2022-09-13 | -1.1538 | 0.20503 | 2022-09-13 | 0.51396 | 4687222.0163 | 0 | 4687222.0163 | 312 | 0 | 0 | 0 | 312 | 0 | 9119824.26
Wed | 14 | N | 313 | 2022-09-14 | -1.1479 | 0.20643 | 2022-09-14 | 0.51747 | 4719250.8652 | 0 | 4719250.8652 | 313 | 0 | 0 | 0 | 313 | 0 | 9119824.26
Thu | 14 | N | 314 | 2022-09-15 | -1.142 | 0.20783 | 2022-09-15 | 0.52099 | 4751332.2142 | 0 | 4751332.2142 | 314 | 0 | 0 | 0 | 314 | 0 | 9119824.26
Fri | 14 | N | 315 | 2022-09-16 | -1.1361 | 0.20924 | 2022-09-16 | 0.52451 | 4783464.166 | 0 | 4783464.166 | 315 | 0 | 0 | 0 | 315 | 0 | 9119824.26
Sat | 14 | Y | 315 | 2022-09-17 | -1.1361 | 0.20924 | 2022-09-17 | 0.52451 | 4783464.166 | 0 | 4783464.166 | 315 | 0 | 0 | 0 | 315 | 0 | 9119824.26
Sun | 14 | Y | 315 | 2022-09-18 | -1.1361 | 0.20924 | 2022-09-18 | 0.52451 | 4783464.166 | 0 | 4783464.166 | 315 | 0 | 0 | 0 | 315 | 0 | 9119824.26
Mon | 14 | N | 316 | 2022-09-19 | -1.1302 | 0.21064 | 2022-09-19 | 0.52804 | 4815644.8054 | 0 | 4815644.8054 | 316 | 0 | 0 | 0 | 316 | 0 | 9119824.26
Tues | 14 | N | 317 | 2022-09-20 | -1.1243 | 0.21205 | 2022-09-20 | 0.53158 | 4847872.1988 | 0 | 4847872.1988 | 317 | 0 | 0 | 0 | 317 | 0 | 9119824.26
Wed | 14 | N | 318 | 2022-09-21 | -1.1183 | 0.21346 | 2022-09-21 | 0.53511 | 4880144.3948 | 0 | 4880144.3948 | 318 | 0 | 0 | 0 | 318 | 0 | 9119824.26
Thu | 14 | N | 319 | 2022-09-22 | -1.1124 | 0.21488 | 2022-09-22 | 0.53866 | 4912459.4244 | 0 | 4912459.4244 | 319 | 0 | 0 | 0 | 319 | 0 | 9119824.26
Fri | 14 | N | 320 | 2022-09-23 | -1.1065 | 0.21629 | 2022-09-23 | 0.54221 | 4944815.3008 | 0 | 4944815.3008 | 320 | 0 | 0 | 0 | 320 | 0 | 9119824.26
Sat | 14 | Y | 320 | 2022-09-24 | -1.1065 | 0.21629 | 2022-09-24 | 0.54221 | 4944815.3008 | 0 | 4944815.3008 | 320 | 0 | 0 | 0 | 320 | 0 | 9119824.26
Sun | 14 | Y | 320 | 2022-09-25 | -1.1065 | 0.21629 | 2022-09-25 | 0.54221 | 4944815.3008 | 0 | 4944815.3008 | 320 | 0 | 0 | 0 | 320 | 0 | 9119824.26
Mon | 14 | N | 321 | 2022-09-26 | -1.1006 | 0.21771 | 2022-09-26 | 0.54576 | 4977210.0199 | 0 | 4977210.0199 | 321 | 0 | 0 | 0 | 321 | 0 | 9119824.26
Tues | 14 | N | 322 | 2022-09-27 | -1.0947 | 0.21913 | 2022-09-27 | 0.54931 | 5009641.5604 | 0 | 5009641.5604 | 322 | 0 | 0 | 0 | 322 | 0 | 9119824.26
Wed | 16 | N | 323 | 2022-09-28 | -1.0888 | 0.22055 | 2022-09-28 | 0.55287 | 5042107.8838 | 0 | 5042107.8838 | 323 | 0 | 0 | 0 | 323 | 0 | 9119824.26
Thu | 16 | N | 324 | 2022-09-29 | -1.0828 | 0.22197 | 2022-09-29 | 0.55644 | 5074606.9347 | 0 | 5074606.9347 | 324 | 0 | 0 | 0 | 324 | 0 | 9119824.26
Fri | 16 | N | 325 | 2022-09-30 | -1.0769 | 0.22339 | 2022-09-30 | 0.56 | 5107136.6409 | 0 | 5107136.6409 | 325 | 0 | 0 | 0 | 325 | 0 | 9119824.26
Sat | 16 | Y | 325 | 2022-10-01 | -1.0769 | 0.22339 | 2022-10-01 | 0.56 | 5107136.6409 | 0 | 5107136.6409 | 325 | 0 | 0 | 0 | 325 | 0 | 9119824.26
Sun | 16 | Y | 325 | 2022-10-02 | -1.0769 | 0.22339 | 2022-10-02 | 0.56 | 5107136.6409 | 0 | 5107136.6409 | 325 | 0 | 0 | 0 | 325 | 0 | 9119824.26
Mon | 16 | N | 326 | 2022-10-03 | -1.071 | 0.22482 | 2022-10-03 | 0.56357 | 5139694.9139 | 0 | 5139694.9139 | 326 | 0 | 0 | 0 | 326 | 0 | 9119824.26
Tues | 16 | N | 327 | 2022-10-04 | -1.0651 | 0.22624 | 2022-10-04 | 0.56715 | 5172279.6485 | 0 | 5172279.6485 | 327 | 0 | 0 | 0 | 327 | 0 | 9119824.26
Wed | 16 | N | 328 | 2022-10-05 | -1.0592 | 0.22767 | 2022-10-05 | 0.57072 | 5204888.7237 | 0 | 5204888.7237 | 328 | 0 | 0 | 0 | 328 | 0 | 9119824.26
Thu | 16 | N | 329 | 2022-10-06 | -1.0533 | 0.2291 | 2022-10-06 | 0.5743 | 5237520.0022 | 0 | 5237520.0022 | 329 | 0 | 0 | 0 | 329 | 0 | 9119824.26
Fri | 16 | N | 330 | 2022-10-07 | -1.0473 | 0.23052 | 2022-10-07 | 0.57788 | 5270171.3311 | 0 | 5270171.3311 | 330 | 0 | 0 | 0 | 330 | 0 | 9119824.26
Sat | 16 | Y | 330 | 2022-10-08 | -1.0473 | 0.23052 | 2022-10-08 | 0.57788 | 5270171.3311 | 0 | 5270171.3311 | 330 | 0 | 0 | 0 | 330 | 0 | 9119824.26
Sun | 16 | Y | 330 | 2022-10-09 | -1.0473 | 0.23052 | 2022-10-09 | 0.57788 | 5270171.3311 | 0 | 5270171.3311 | 330 | 0 | 0 | 0 | 330 | 0 | 9119824.26
Mon | 16 | N | 331 | 2022-10-10 | -1.0414 | 0.23195 | 2022-10-10 | 0.58146 | 5302840.5418 | 0 | 5302840.5418 | 331 | 0 | 0 | 0 | 331 | 0 | 9119824.26
Tues | 16 | N | 332 | 2022-10-11 | -1.0355 | 0.23338 | 2022-10-11 | 0.58505 | 5335525.4506 | 0 | 5335525.4506 | 332 | 0 | 0 | 0 | 332 | 0 | 9119824.26
Wed | 16 | N | 333 | 2022-10-12 | -1.0296 | 0.23481 | 2022-10-12 | 0.58863 | 5368223.8583 | 0 | 5368223.8583 | 333 | 0 | 0 | 0 | 333 | 0 | 9119824.26
Thu | 16 | N | 334 | 2022-10-13 | -1.0237 | 0.23624 | 2022-10-13 | 0.59222 | 5400933.5509 | 0 | 5400933.5509 | 334 | 0 | 0 | 0 | 334 | 0 | 9119824.26
Fri | 16 | N | 335 | 2022-10-14 | -1.0178 | 0.23768 | 2022-10-14 | 0.59581 | 5433652.2999 | 0 | 5433652.2999 | 335 | 0 | 0 | 0 | 335 | 0 | 9119824.26
Sat | 16 | Y | 335 | 2022-10-15 | -1.0178 | 0.23768 | 2022-10-15 | 0.59581 | 5433652.2999 | 0 | 5433652.2999 | 335 | 0 | 0 | 0 | 335 | 0 | 9119824.26
Sun | 16 | Y | 335 | 2022-10-16 | -1.0178 | 0.23768 | 2022-10-16 | 0.59581 | 5433652.2999 | 0 | 5433652.2999 | 335 | 0 | 0 | 0 | 335 | 0 | 9119824.26
Mon | 16 | N | 336 | 2022-10-17 | -1.0118 | 0.23911 | 2022-10-17 | 0.5994 | 5466377.862 | 0 | 5466377.862 | 336 | 0 | 0 | 0 | 336 | 0 | 9119824.26
Tues | 16 | N | 337 | 2022-10-18 | -1.0059 | 0.24054 | 2022-10-18 | 0.60298 | 5499107.9797 | 0 | 5499107.9797 | 337 | 0 | 0 | 0 | 337 | 0 | 9119824.26
Wed | 16 | N | 338 | 2022-10-19 | -1 | 0.24197 | 2022-10-19 | 0.60657 | 5531840.3815 | 0 | 5531840.3815 | 338 | 0 | 0 | 0 | 338 | 0 | 9119824.26
Thu | 16 | N | 339 | 2022-10-20 | -0.99408 | 0.2434 | 2022-10-20 | 0.61016 | 5564572.7823 | 0 | 5564572.7823 | 339 | 0 | 0 | 0 | 339 | 0 | 9119824.26
Fri | 16 | N | 340 | 2022-10-21 | -0.98817 | 0.24483 | 2022-10-21 | 0.61375 | 5597302.883 | 0 | 5597302.883 | 340 | 0 | 0 | 0 | 340 | 0 | 9119824.26
Sat | 16 | Y | 340 | 2022-10-22 | -0.98817 | 0.24483 | 2022-10-22 | 0.61375 | 5597302.883 | 0 | 5597302.883 | 340 | 0 | 0 | 0 | 340 | 0 | 9119824.26
Sun | 16 | Y | 340 | 2022-10-23 | -0.98817 | 0.24483 | 2022-10-23 | 0.61375 | 5597302.883 | 0 | 5597302.883 | 340 | 0 | 0 | 0 | 340 | 0 | 9119824.26
Mon | 16 | N | 341 | 2022-10-24 | -0.98225 | 0.24627 | 2022-10-24 | 0.61734 | 5630028.3716 | 0 | 5630028.3716 | 341 | 0 | 0 | 0 | 341 | 0 | 9119824.26
Tues | 16 | N | 342 | 2022-10-25 | -0.97633 | 0.2477 | 2022-10-25 | 0.62093 | 5662746.9228 | 0 | 5662746.9228 | 342 | 0 | 0 | 0 | 342 | 0 | 9119824.26
Wed | 16 | N | 343 | 2022-10-26 | -0.97041 | 0.24913 | 2022-10-26 | 0.62451 | 5695456.1986 | 0 | 5695456.1986 | 343 | 0 | 0 | 0 | 343 | 0 | 9119824.26
Thu | 16 | N | 344 | 2022-10-27 | -0.9645 | 0.25056 | 2022-10-27 | 0.6281 | 5728153.8482 | 0 | 5728153.8482 | 344 | 0 | 0 | 0 | 344 | 0 | 9119824.26
Fri | 16 | N | 345 | 2022-10-28 | -0.95858 | 0.25199 | 2022-10-28 | 0.63168 | 5760837.5088 | 0 | 5760837.5088 | 345 | 0 | 0 | 0 | 345 | 0 | 9119824.26
Sat | 16 | Y | 345 | 2022-10-29 | -0.95858 | 0.25199 | 2022-10-29 | 0.63168 | 5760837.5088 | 0 | 5760837.5088 | 345 | 0 | 0 | 0 | 345 | 0 | 9119824.26
Sun | 16 | Y | 345 | 2022-10-30 | -0.95858 | 0.25199 | 2022-10-30 | 0.63168 | 5760837.5088 | 0 | 5760837.5088 | 345 | 0 | 0 | 0 | 345 | 0 | 9119824.26
Mon | 16 | N | 346 | 2022-10-31 | -0.95266 | 0.25342 | 2022-10-31 | 0.63526 | 5793504.8053 | 0 | 5793504.8053 | 346 | 0 | 0 | 0 | 346 | 0 | 9119824.26
Tues | 16 | N | 347 | 2022-11-01 | -0.94675 | 0.25484 | 2022-11-01 | 0.63884 | 5826153.351 | 0 | 5826153.351 | 347 | 0 | 0 | 0 | 347 | 0 | 9119824.26
Wed | 16 | N | 348 | 2022-11-02 | -0.94083 | 0.25627 | 2022-11-02 | 0.64242 | 5858780.7475 | 0 | 5858780.7475 | 348 | 0 | 0 | 0 | 348 | 0 | 9119824.26
Thu | 16 | N | 349 | 2022-11-03 | -0.93491 | 0.2577 | 2022-11-03 | 0.646 | 5891384.5853 | 0 | 5891384.5853 | 349 | 0 | 0 | 0 | 349 | 0 | 9119824.26
Fri | 16 | N | 350 | 2022-11-04 | -0.92899 | 0.25912 | 2022-11-04 | 0.64957 | 5923962.444 | 0 | 5923962.444 | 350 | 0 | 0 | 0 | 350 | 0 | 9119824.26
Sat | 16 | Y | 350 | 2022-11-05 | -0.92899 | 0.25912 | 2022-11-05 | 0.64957 | 5923962.444 | 0 | 5923962.444 | 350 | 0 | 0 | 0 | 350 | 0 | 9119824.26
Sun | 16 | Y | 350 | 2022-11-06 | -0.92899 | 0.25912 | 2022-11-06 | 0.64957 | 5923962.444 | 0 | 5923962.444 | 350 | 0 | 0 | 0 | 350 | 0 | 9119824.26
Mon | 16 | N | 351 | 2022-11-07 | -0.92308 | 0.26055 | 2022-11-07 | 0.65314 | 5956511.8922 | 0 | 5956511.8922 | 351 | 0 | 0 | 0 | 351 | 0 | 9119824.26
Tues | 16 | N | 352 | 2022-11-08 | -0.91716 | 0.26197 | 2022-11-08 | 0.6567 | 5989030.4884 | 0 | 5989030.4884 | 352 | 0 | 0 | 0 | 352 | 0 | 9119824.26
Wed | 16 | N | 353 | 2022-11-09 | -0.91124 | 0.26339 | 2022-11-09 | 0.66027 | 6021515.7808 | 0 | 6021515.7808 | 353 | 0 | 0 | 0 | 353 | 0 | 9119824.26
Thu | 16 | N | 354 | 2022-11-10 | -0.90533 | 0.26481 | 2022-11-10 | 0.66382 | 6053965.3079 | 0 | 6053965.3079 | 354 | 0 | 0 | 0 | 354 | 0 | 9119824.26
Fri | 16 | N | 355 | 2022-11-11 | -0.89941 | 0.26623 | 2022-11-11 | 0.66738 | 6086376.5985 | 0 | 6086376.5985 | 355 | 0 | 0 | 0 | 355 | 0 | 9119824.26
Sat | 16 | Y | 355 | 2022-11-12 | -0.89941 | 0.26623 | 2022-11-12 | 0.66738 | 6086376.5985 | 0 | 6086376.5985 | 355 | 0 | 0 | 0 | 355 | 0 | 9119824.26
Sun | 16 | Y | 355 | 2022-11-13 | -0.89941 | 0.26623 | 2022-11-13 | 0.66738 | 6086376.5985 | 0 | 6086376.5985 | 355 | 0 | 0 | 0 | 355 | 0 | 9119824.26
Mon | 16 | N | 356 | 2022-11-14 | -0.89349 | 0.26764 | 2022-11-14 | 0.67093 | 6118747.1723 | 0 | 6118747.1723 | 356 | 0 | 0 | 0 | 356 | 0 | 9119824.26
Tues | 16 | N | 357 | 2022-11-15 | -0.88757 | 0.26906 | 2022-11-15 | 0.67447 | 6151074.5399 | 0 | 6151074.5399 | 357 | 0 | 0 | 0 | 357 | 0 | 9119824.26
Wed | 16 | N | 358 | 2022-11-16 | -0.88166 | 0.27047 | 2022-11-16 | 0.67801 | 6183356.2035 | 0 | 6183356.2035 | 358 | 0 | 0 | 0 | 358 | 0 | 9119824.26
Thu | 16 | N | 359 | 2022-11-17 | -0.87574 | 0.27188 | 2022-11-17 | 0.68155 | 6215589.6567 | 0 | 6215589.6567 | 359 | 0 | 0 | 0 | 359 | 0 | 9119824.26
Fri | 16 | N | 360 | 2022-11-18 | -0.86982 | 0.27329 | 2022-11-18 | 0.68508 | 6247772.3851 | 0 | 6247772.3851 | 360 | 0 | 0 | 0 | 360 | 0 | 9119824.26
Sat | 16 | Y | 360 | 2022-11-19 | -0.86982 | 0.27329 | 2022-11-19 | 0.68508 | 6247772.3851 | 0 | 6247772.3851 | 360 | 0 | 0 | 0 | 360 | 0 | 9119824.26
Sun | 16 | Y | 360 | 2022-11-20 | -0.86982 | 0.27329 | 2022-11-20 | 0.68508 | 6247772.3851 | 0 | 6247772.3851 | 360 | 0 | 0 | 0 | 360 | 0 | 9119824.26
Mon | 16 | N | 361 | 2022-11-21 | -0.86391 | 0.27469 | 2022-11-21 | 0.6886 | 6279901.8668 | 0 | 6279901.8668 | 361 | 0 | 0 | 0 | 361 | 0 | 9119824.26
Tues | 16 | N | 362 | 2022-11-22 | -0.85799 | 0.27609 | 2022-11-22 | 0.69212 | 6311975.5723 | 0 | 6311975.5723 | 362 | 0 | 0 | 0 | 362 | 0 | 9119824.26
Wed | 16 | N | 363 | 2022-11-23 | -0.85207 | 0.2775 | 2022-11-23 | 0.69563 | 6343990.9651 | 0 | 6343990.9651 | 363 | 0 | 0 | 0 | 363 | 0 | 9119824.26
Thu | 16 | N | 364 | 2022-11-24 | -0.84615 | 0.27889 | 2022-11-24 | 0.69913 | 6375945.5017 | 0 | 6375945.5017 | 364 | 0 | 0 | 0 | 364 | 0 | 9119824.26
Fri | 16 | N | 365 | 2022-11-25 | -0.84024 | 0.28029 | 2022-11-25 | 0.70263 | 6407836.6325 | 0 | 6407836.6325 | 365 | 0 | 0 | 0 | 365 | 0 | 9119824.26
Sat | 16 | Y | 365 | 2022-11-26 | -0.84024 | 0.28029 | 2022-11-26 | 0.70263 | 6407836.6325 | 0 | 6407836.6325 | 365 | 0 | 0 | 0 | 365 | 0 | 9119824.26
Sun | 16 | Y | 365 | 2022-11-27 | -0.84024 | 0.28029 | 2022-11-27 | 0.70263 | 6407836.6325 | 0 | 6407836.6325 | 365 | 0 | 0 | 0 | 365 | 0 | 9119824.26
Mon | 18 | N | 366 | 2022-11-28 | -0.83432 | 0.28168 | 2022-11-28 | 0.70612 | 6439661.8017 | 0 | 6439661.8017 | 366 | 0 | 0 | 0 | 366 | 0 | 9119824.26
Tues | 18 | N | 367 | 2022-11-29 | -0.8284 | 0.28307 | 2022-11-29 | 0.7096 | 6471418.4474 | 0 | 6471418.4474 | 367 | 0 | 0 | 0 | 367 | 0 | 9119824.26
Wed | 18 | N | 368 | 2022-11-30 | -0.82249 | 0.28446 | 2022-11-30 | 0.71307 | 6503104.0026 | 0 | 6503104.0026 | 368 | 0 | 0 | 0 | 368 | 0 | 9119824.26
Thu | 18 | N | 369 | 2022-12-01 | -0.81657 | 0.28584 | 2022-12-01 | 0.71654 | 6534715.895 | 0 | 6534715.895 | 369 | 0 | 0 | 0 | 369 | 0 | 9119824.26
Fri | 18 | N | 370 | 2022-12-02 | -0.81065 | 0.28722 | 2022-12-02 | 0.72 | 6566251.5475 | 0 | 6566251.5475 | 370 | 0 | 0 | 0 | 370 | 0 | 9119824.26
Sat | 18 | Y | 370 | 2022-12-03 | -0.81065 | 0.28722 | 2022-12-03 | 0.72 | 6566251.5475 | 0 | 6566251.5475 | 370 | 0 | 0 | 0 | 370 | 0 | 9119824.26
Sun | 18 | Y | 370 | 2022-12-04 | -0.81065 | 0.28722 | 2022-12-04 | 0.72 | 6566251.5475 | 0 | 6566251.5475 | 370 | 0 | 0 | 0 | 370 | 0 | 9119824.26
Mon | 18 | N | 371 | 2022-12-05 | -0.80473 | 0.28859 | 2022-12-05 | 0.72345 | 6597708.3787 | 0 | 6597708.3787 | 371 | 0 | 0 | 0 | 371 | 0 | 9119824.26
Tues | 18 | N | 372 | 2022-12-06 | -0.79882 | 0.28997 | 2022-12-06 | 0.72689 | 6629083.8028 | 0 | 6629083.8028 | 372 | 0 | 0 | 0 | 372 | 0 | 9119824.26
Wed | 18 | N | 373 | 2022-12-07 | -0.7929 | 0.29133 | 2022-12-07 | 0.73032 | 6660375.2306 | 0 | 6660375.2306 | 373 | 0 | 0 | 0 | 373 | 0 | 9119824.26
Thu | 18 | N | 374 | 2022-12-08 | -0.78698 | 0.2927 | 2022-12-08 | 0.73374 | 6691580.0691 | 0 | 6691580.0691 | 374 | 0 | 0 | 0 | 374 | 0 | 9119824.26
Fri | 18 | N | 375 | 2022-12-09 | -0.78107 | 0.29406 | 2022-12-09 | 0.73715 | 6722695.7226 | 0 | 6722695.7226 | 375 | 0 | 0 | 0 | 375 | 0 | 9119824.26
Sat | 18 | Y | 375 | 2022-12-10 | -0.78107 | 0.29406 | 2022-12-10 | 0.73715 | 6722695.7226 | 0 | 6722695.7226 | 375 | 0 | 0 | 0 | 375 | 0 | 9119824.26
Sun | 18 | Y | 375 | 2022-12-11 | -0.78107 | 0.29406 | 2022-12-11 | 0.73715 | 6722695.7226 | 0 | 6722695.7226 | 375 | 0 | 0 | 0 | 375 | 0 | 9119824.26
Mon | 18 | N | 376 | 2022-12-12 | -0.77515 | 0.29542 | 2022-12-12 | 0.74055 | 6753719.5922 | 0 | 6753719.5922 | 376 | 0 | 0 | 0 | 376 | 0 | 9119824.26
Tues | 18 | N | 377 | 2022-12-13 | -0.76923 | 0.29677 | 2022-12-13 | 0.74395 | 6784649.0771 | 0 | 6784649.0771 | 377 | 0 | 0 | 0 | 377 | 0 | 9119824.26
Wed | 18 | N | 378 | 2022-12-14 | -0.76331 | 0.29812 | 2022-12-14 | 0.74733 | 6815481.5743 | 0 | 6815481.5743 | 378 | 0 | 0 | 0 | 378 | 0 | 9119824.26
Thu | 18 | N | 379 | 2022-12-15 | -0.7574 | 0.29946 | 2022-12-15 | 0.7507 | 6846214.479 | 0 | 6846214.479 | 379 | 0 | 0 | 0 | 379 | 0 | 9119824.26
Fri | 18 | N | 380 | 2022-12-16 | -0.75148 | 0.3008 | 2022-12-16 | 0.75405 | 6876845.1852 | 0 | 6876845.1852 | 380 | 0 | 0 | 0 | 380 | 0 | 9119824.26
Sat | 18 | Y | 380 | 2022-12-17 | -0.75148 | 0.3008 | 2022-12-17 | 0.75405 | 6876845.1852 | 0 | 6876845.1852 | 380 | 0 | 0 | 0 | 380 | 0 | 9119824.26
Sun | 18 | Y | 380 | 2022-12-18 | -0.75148 | 0.3008 | 2022-12-18 | 0.75405 | 6876845.1852 | 0 | 6876845.1852 | 380 | 0 | 0 | 0 | 380 | 0 | 9119824.26
Mon | 18 | N | 381 | 2022-12-19 | -0.74556 | 0.30214 | 2022-12-19 | 0.7574 | 6907371.086 | 0 | 6907371.086 | 381 | 0 | 0 | 0 | 381 | 0 | 9119824.26
Tues | 18 | N | 382 | 2022-12-20 | -0.73964 | 0.30347 | 2022-12-20 | 0.76074 | 6937789.574 | 0 | 6937789.574 | 382 | 0 | 0 | 0 | 382 | 0 | 9119824.26
Wed | 18 | N | 383 | 2022-12-21 | -0.73373 | 0.30479 | 2022-12-21 | 0.76406 | 6968098.0412 | 0 | 6968098.0412 | 383 | 0 | 0 | 0 | 383 | 0 | 9119824.26
Thu | 18 | N | 384 | 2022-12-22 | -0.72781 | 0.30612 | 2022-12-22 | 0.76737 | 6998293.8802 | 0 | 6998293.8802 | 384 | 0 | 0 | 0 | 384 | 0 | 9119824.26
Fri | 18 | N | 385 | 2022-12-23 | -0.72189 | 0.30743 | 2022-12-23 | 0.77067 | 7028374.4838 | 0 | 7028374.4838 | 385 | 0 | 0 | 0 | 385 | 0 | 9119824.26
Sat | 18 | Y | 385 | 2022-12-24 | -0.72189 | 0.30743 | 2022-12-24 | 0.77067 | 7028374.4838 | 0 | 7028374.4838 | 385 | 0 | 0 | 0 | 385 | 0 | 9119824.26
Sun | 18 | Y | 385 | 2022-12-25 | -0.72189 | 0.30743 | 2022-12-25 | 0.77067 | 7028374.4838 | 0 | 7028374.4838 | 385 | 0 | 0 | 0 | 385 | 0 | 9119824.26
Mon | 18 | N | 386 | 2022-12-26 | -0.71598 | 0.30874 | 2022-12-26 | 0.77396 | 7058337.2459 | 0 | 7058337.2459 | 386 | 0 | 0 | 0 | 386 | 0 | 9119824.26
Tues | 18 | N | 387 | 2022-12-27 | -0.71006 | 0.31005 | 2022-12-27 | 0.77723 | 7088179.5614 | 0 | 7088179.5614 | 387 | 0 | 0 | 0 | 387 | 0 | 9119824.26
Wed | 18 | N | 388 | 2022-12-28 | -0.70414 | 0.31135 | 2022-12-28 | 0.78049 | 7117898.827 | 0 | 7117898.827 | 388 | 0 | 0 | 0 | 388 | 0 | 9119824.26
Thu | 18 | N | 389 | 2022-12-29 | -0.69822 | 0.31264 | 2022-12-29 | 0.78373 | 7147492.4414 | 0 | 7147492.4414 | 389 | 0 | 0 | 0 | 389 | 0 | 9119824.26
Fri | 18 | N | 390 | 2022-12-30 | -0.69231 | 0.31393 | 2022-12-30 | 0.78696 | 7176957.8055 | 0 | 7176957.8055 | 390 | 0 | 0 | 0 | 390 | 0 | 9119824.26
Sat | 18 | Y | 390 | 2022-12-31 | -0.69231 | 0.31393 | 2022-12-31 | 0.78696 | 7176957.8055 | 0 | 7176957.8055 | 390 | 0 | 0 | 0 | 390 | 0 | 9119824.26
Sun | 18 | Y | 390 | 2023-01-01 | -0.69231 | 0.31393 | 2023-01-01 | 0.78696 | 7176957.8055 | 0 | 7176957.8055 | 390 | 0 | 0 | 0 | 390 | 0 | 9119824.26
Mon | 18 | N | 391 | 2023-01-02 | -0.68639 | 0.31521 | 2023-01-02 | 0.79018 | 7206292.3232 | 0 | 7206292.3232 | 391 | 0 | 0 | 0 | 391 | 0 | 9119824.26
Tues | 18 | N | 392 | 2023-01-03 | -0.68047 | 0.31649 | 2023-01-03 | 0.79338 | 7235493.4012 | 0 | 7235493.4012 | 392 | 0 | 0 | 0 | 392 | 0 | 9119824.26
Wed | 18 | N | 393 | 2023-01-04 | -0.67456 | 0.31776 | 2023-01-04 | 0.79657 | 7264558.4499 | 0 | 7264558.4499 | 393 | 0 | 0 | 0 | 393 | 0 | 9119824.26
Thu | 18 | N | 394 | 2023-01-05 | -0.66864 | 0.31903 | 2023-01-05 | 0.79974 | 7293484.8836 | 0 | 7293484.8836 | 394 | 0 | 0 | 0 | 394 | 0 | 9119824.26
Fri | 18 | N | 395 | 2023-01-06 | -0.66272 | 0.32029 | 2023-01-06 | 0.8029 | 7322270.1207 | 0 | 7322270.1207 | 395 | 0 | 0 | 0 | 395 | 0 | 9119824.26
Sat | 18 | Y | 395 | 2023-01-07 | -0.66272 | 0.32029 | 2023-01-07 | 0.8029 | 7322270.1207 | 0 | 7322270.1207 | 395 | 0 | 0 | 0 | 395 | 0 | 9119824.26
Sun | 18 | Y | 395 | 2023-01-08 | -0.66272 | 0.32029 | 2023-01-08 | 0.8029 | 7322270.1207 | 0 | 7322270.1207 | 395 | 0 | 0 | 0 | 395 | 0 | 9119824.26
Mon | 18 | N | 396 | 2023-01-09 | -0.6568 | 0.32154 | 2023-01-09 | 0.80604 | 7350911.5842 | 0 | 7350911.5842 | 396 | 0 | 0 | 0 | 396 | 0 | 9119824.26
Tues | 18 | N | 397 | 2023-01-10 | -0.65089 | 0.32279 | 2023-01-10 | 0.80916 | 7379406.7024 | 0 | 7379406.7024 | 397 | 0 | 0 | 0 | 397 | 0 | 9119824.26
Wed | 18 | N | 398 | 2023-01-11 | -0.64497 | 0.32403 | 2023-01-11 | 0.81227 | 7407752.9087 | 0 | 7407752.9087 | 398 | 0 | 0 | 0 | 398 | 0 | 9119824.26
Thu | 18 | N | 399 | 2023-01-12 | -0.63905 | 0.32526 | 2023-01-12 | 0.81536 | 7435947.6423 | 0 | 7435947.6423 | 399 | 0 | 0 | 0 | 399 | 0 | 9119824.26
Fri | 18 | N | 400 | 2023-01-13 | -0.63314 | 0.32649 | 2023-01-13 | 0.81844 | 7463988.3486 | 0 | 7463988.3486 | 400 | 0 | 0 | 0 | 400 | 0 | 9119824.26
Sat | 18 | Y | 400 | 2023-01-14 | -0.63314 | 0.32649 | 2023-01-14 | 0.81844 | 7463988.3486 | 0 | 7463988.3486 | 400 | 0 | 0 | 0 | 400 | 0 | 9119824.26
Sun | 18 | Y | 400 | 2023-01-15 | -0.63314 | 0.32649 | 2023-01-15 | 0.81844 | 7463988.3486 | 0 | 7463988.3486 | 400 | 0 | 0 | 0 | 400 | 0 | 9119824.26
Mon | 18 | N | 401 | 2023-01-16 | -0.62722 | 0.32771 | 2023-01-16 | 0.82149 | 7491872.4796 | 0 | 7491872.4796 | 401 | 0 | 0 | 0 | 401 | 0 | 9119824.26
Tues | 18 | N | 402 | 2023-01-17 | -0.6213 | 0.32892 | 2023-01-17 | 0.82453 | 7519597.4942 | 0 | 7519597.4942 | 402 | 0 | 0 | 0 | 402 | 0 | 9119824.26
Wed | 18 | N | 403 | 2023-01-18 | -0.61538 | 0.33012 | 2023-01-18 | 0.82756 | 7547160.8584 | 0 | 7547160.8584 | 403 | 0 | 0 | 0 | 403 | 0 | 9119824.26
Thu | 18 | N | 404 | 2023-01-19 | -0.60947 | 0.33132 | 2023-01-19 | 0.83056 | 7574560.0461 | 0 | 7574560.0461 | 404 | 0 | 0 | 0 | 404 | 0 | 9119824.26
Fri | 18 | N | 405 | 2023-01-20 | -0.60355 | 0.33251 | 2023-01-20 | 0.83355 | 7601792.5392 | 0 | 7601792.5392 | 405 | 0 | 0 | 0 | 405 | 0 | 9119824.26
Sat | 18 | Y | 405 | 2023-01-21 | -0.60355 | 0.33251 | 2023-01-21 | 0.83355 | 7601792.5392 | 0 | 7601792.5392 | 405 | 0 | 0 | 0 | 405 | 0 | 9119824.26
Sun | 18 | Y | 405 | 2023-01-22 | -0.60355 | 0.33251 | 2023-01-22 | 0.83355 | 7601792.5392 | 0 | 7601792.5392 | 405 | 0 | 0 | 0 | 405 | 0 | 9119824.26
Mon | 18 | N | 406 | 2023-01-23 | -0.59763 | 0.3337 | 2023-01-23 | 0.83651 | 7628855.828 | 0 | 7628855.828 | 406 | 0 | 0 | 0 | 406 | 0 | 9119824.26
Tues | 18 | N | 407 | 2023-01-24 | -0.59172 | 0.33487 | 2023-01-24 | 0.83946 | 7655747.4117 | 0 | 7655747.4117 | 407 | 0 | 0 | 0 | 407 | 0 | 9119824.26
Wed | 18 | N | 408 | 2023-01-25 | -0.5858 | 0.33604 | 2023-01-25 | 0.84239 | 7682464.7985 | 0 | 7682464.7985 | 408 | 0 | 0 | 0 | 408 | 0 | 9119824.26
Thu | 18 | N | 409 | 2023-01-26 | -0.57988 | 0.3372 | 2023-01-26 | 0.8453 | 7709005.5065 | 0 | 7709005.5065 | 409 | 0 | 0 | 0 | 409 | 0 | 9119824.26
Fri | 18 | N | 410 | 2023-01-27 | -0.57396 | 0.33836 | 2023-01-27 | 0.84819 | 7735367.0636 | 0 | 7735367.0636 | 410 | 0 | 0 | 0 | 410 | 0 | 9119824.26
Sat | 20 | Y | 410 | 2023-01-28 | -0.57396 | 0.33836 | 2023-01-28 | 0.84819 | 7735367.0636 | 0 | 7735367.0636 | 410 | 0 | 0 | 0 | 410 | 0 | 9119824.26
Sun | 20 | Y | 410 | 2023-01-29 | -0.57396 | 0.33836 | 2023-01-29 | 0.84819 | 7735367.0636 | 0 | 7735367.0636 | 410 | 0 | 0 | 0 | 410 | 0 | 9119824.26
Mon | 20 | N | 411 | 2023-01-30 | -0.56805 | 0.3395 | 2023-01-30 | 0.85106 | 7761547.008 | 0 | 7761547.008 | 411 | 0 | 0 | 0 | 411 | 0 | 9119824.26
Tues | 20 | N | 412 | 2023-01-31 | -0.56213 | 0.34064 | 2023-01-31 | 0.85391 | 7787542.8888 | 0 | 7787542.8888 | 412 | 0 | 0 | 0 | 412 | 0 | 9119824.26
Wed | 20 | N | 413 | 2023-02-01 | -0.55621 | 0.34177 | 2023-02-01 | 0.85674 | 7813352.266 | 0 | 7813352.266 | 413 | 0 | 0 | 0 | 413 | 0 | 9119824.26
Thu | 20 | N | 414 | 2023-02-02 | -0.5503 | 0.34289 | 2023-02-02 | 0.85955 | 7838972.7114 | 0 | 7838972.7114 | 414 | 0 | 0 | 0 | 414 | 0 | 9119824.26
Fri | 20 | N | 415 | 2023-02-03 | -0.54438 | 0.344 | 2023-02-03 | 0.86234 | 7864401.8083 | 0 | 7864401.8083 | 415 | 0 | 0 | 0 | 415 | 0 | 9119824.26
Sat | 20 | Y | 415 | 2023-02-04 | -0.54438 | 0.344 | 2023-02-04 | 0.86234 | 7864401.8083 | 0 | 7864401.8083 | 415 | 0 | 0 | 0 | 415 | 0 | 9119824.26
Sun | 20 | Y | 415 | 2023-02-05 | -0.54438 | 0.344 | 2023-02-05 | 0.86234 | 7864401.8083 | 0 | 7864401.8083 | 415 | 0 | 0 | 0 | 415 | 0 | 9119824.26
Mon | 20 | N | 416 | 2023-02-06 | -0.53846 | 0.3451 | 2023-02-06 | 0.86511 | 7889637.1525 | 0 | 7889637.1525 | 416 | 0 | 0 | 0 | 416 | 0 | 9119824.26
Tues | 20 | N | 417 | 2023-02-07 | -0.53254 | 0.3462 | 2023-02-07 | 0.86785 | 7914676.3524 | 0 | 7914676.3524 | 417 | 0 | 0 | 0 | 417 | 0 | 9119824.26
Wed | 20 | N | 418 | 2023-02-08 | -0.52663 | 0.34729 | 2023-02-08 | 0.87058 | 7939517.0293 | 0 | 7939517.0293 | 418 | 0 | 0 | 0 | 418 | 0 | 9119824.26
Thu | 20 | N | 419 | 2023-02-09 | -0.52071 | 0.34836 | 2023-02-09 | 0.87328 | 7964156.818 | 0 | 7964156.818 | 419 | 0 | 0 | 0 | 419 | 0 | 9119824.26
Fri | 20 | N | 420 | 2023-02-10 | -0.51479 | 0.34943 | 2023-02-10 | 0.87596 | 7988593.3669 | 0 | 7988593.3669 | 420 | 0 | 0 | 0 | 420 | 0 | 9119824.26
Sat | 20 | Y | 420 | 2023-02-11 | -0.51479 | 0.34943 | 2023-02-11 | 0.87596 | 7988593.3669 | 0 | 7988593.3669 | 420 | 0 | 0 | 0 | 420 | 0 | 9119824.26
Sun | 20 | Y | 420 | 2023-02-12 | -0.51479 | 0.34943 | 2023-02-12 | 0.87596 | 7988593.3669 | 0 | 7988593.3669 | 420 | 0 | 0 | 0 | 420 | 0 | 9119824.26
Mon | 20 | N | 421 | 2023-02-13 | -0.50888 | 0.35049 | 2023-02-13 | 0.87862 | 8012824.3388 | 0 | 8012824.3388 | 421 | 0 | 0 | 0 | 421 | 0 | 9119824.26
Tues | 20 | N | 422 | 2023-02-14 | -0.50296 | 0.35154 | 2023-02-14 | 0.88125 | 8036847.4106 | 0 | 8036847.4106 | 422 | 0 | 0 | 0 | 422 | 0 | 9119824.26
Wed | 20 | N | 423 | 2023-02-15 | -0.49704 | 0.35258 | 2023-02-15 | 0.88386 | 8060660.2744 | 0 | 8060660.2744 | 423 | 0 | 0 | 0 | 423 | 0 | 9119824.26
Thu | 20 | N | 424 | 2023-02-16 | -0.49112 | 0.35362 | 2023-02-16 | 0.88645 | 8084260.6374 | 0 | 8084260.6374 | 424 | 0 | 0 | 0 | 424 | 0 | 9119824.26
Fri | 20 | N | 425 | 2023-02-17 | -0.48521 | 0.35464 | 2023-02-17 | 0.88901 | 8107646.2224 | 0 | 8107646.2224 | 425 | 0 | 0 | 0 | 425 | 0 | 9119824.26
Sat | 20 | Y | 425 | 2023-02-18 | -0.48521 | 0.35464 | 2023-02-18 | 0.88901 | 8107646.2224 | 0 | 8107646.2224 | 425 | 0 | 0 | 0 | 425 | 0 | 9119824.26
Sun | 20 | Y | 425 | 2023-02-19 | -0.48521 | 0.35464 | 2023-02-19 | 0.88901 | 8107646.2224 | 0 | 8107646.2224 | 425 | 0 | 0 | 0 | 425 | 0 | 9119824.26
Mon | 20 | N | 426 | 2023-02-20 | -0.47929 | 0.35565 | 2023-02-20 | 0.89155 | 8130814.7682 | 0 | 8130814.7682 | 426 | 0 | 0 | 0 | 426 | 0 | 9119824.26
Tues | 20 | N | 427 | 2023-02-21 | -0.47337 | 0.35666 | 2023-02-21 | 0.89407 | 8153764.0299 | 0 | 8153764.0299 | 427 | 0 | 0 | 0 | 427 | 0 | 9119824.26
Wed | 20 | N | 428 | 2023-02-22 | -0.46746 | 0.35765 | 2023-02-22 | 0.89656 | 8176491.7793 | 0 | 8176491.7793 | 428 | 0 | 0 | 0 | 428 | 0 | 9119824.26
Thu | 20 | N | 429 | 2023-02-23 | -0.46154 | 0.35864 | 2023-02-23 | 0.89903 | 8198995.8051 | 0 | 8198995.8051 | 429 | 0 | 0 | 0 | 429 | 0 | 9119824.26
Fri | 20 | N | 430 | 2023-02-24 | -0.45562 | 0.35961 | 2023-02-24 | 0.90147 | 8221273.9138 | 0 | 8221273.9138 | 430 | 0 | 0 | 0 | 430 | 0 | 9119824.26
Sat | 20 | Y | 430 | 2023-02-25 | -0.45562 | 0.35961 | 2023-02-25 | 0.90147 | 8221273.9138 | 0 | 8221273.9138 | 430 | 0 | 0 | 0 | 430 | 0 | 9119824.26
Sun | 20 | Y | 430 | 2023-02-26 | -0.45562 | 0.35961 | 2023-02-26 | 0.90147 | 8221273.9138 | 0 | 8221273.9138 | 430 | 0 | 0 | 0 | 430 | 0 | 9119824.26
Mon | 20 | N | 431 | 2023-02-27 | -0.4497 | 0.36057 | 2023-02-27 | 0.90389 | 8243323.9292 | 0 | 8243323.9292 | 431 | 0 | 0 | 0 | 431 | 0 | 9119824.26
Tues | 20 | N | 432 | 2023-02-28 | -0.44379 | 0.36153 | 2023-02-28 | 0.90628 | 8265143.6936 | 0 | 8265143.6936 | 432 | 0 | 0 | 0 | 432 | 0 | 9119824.26
Wed | 20 | N | 433 | 2023-03-01 | -0.43787 | 0.36247 | 2023-03-01 | 0.90865 | 8286731.0675 | 0 | 8286731.0675 | 433 | 0 | 0 | 0 | 433 | 0 | 9119824.26
Thu | 20 | N | 434 | 2023-03-02 | -0.43195 | 0.36341 | 2023-03-02 | 0.91099 | 8308083.9303 | 0 | 8308083.9303 | 434 | 0 | 0 | 0 | 434 | 0 | 9119824.26
Fri | 20 | N | 435 | 2023-03-03 | -0.42604 | 0.36433 | 2023-03-03 | 0.91331 | 8329200.1806 | 0 | 8329200.1806 | 435 | 0 | 0 | 0 | 435 | 0 | 9119824.26
Sat | 20 | Y | 435 | 2023-03-04 | -0.42604 | 0.36433 | 2023-03-04 | 0.91331 | 8329200.1806 | 0 | 8329200.1806 | 435 | 0 | 0 | 0 | 435 | 0 | 9119824.26
Sun | 20 | Y | 435 | 2023-03-05 | -0.42604 | 0.36433 | 2023-03-05 | 0.91331 | 8329200.1806 | 0 | 8329200.1806 | 435 | 0 | 0 | 0 | 435 | 0 | 9119824.26
Mon | 20 | N | 436 | 2023-03-06 | -0.42012 | 0.36524 | 2023-03-06 | 0.9156 | 8350077.7365 | 0 | 8350077.7365 | 436 | 0 | 0 | 0 | 436 | 0 | 9119824.26
Tues | 20 | N | 437 | 2023-03-07 | -0.4142 | 0.36615 | 2023-03-07 | 0.91786 | 8370714.5359 | 0 | 8370714.5359 | 437 | 0 | 0 | 0 | 437 | 0 | 9119824.26
Wed | 20 | N | 438 | 2023-03-08 | -0.40828 | 0.36704 | 2023-03-08 | 0.9201 | 8391108.537 | 0 | 8391108.537 | 438 | 0 | 0 | 0 | 438 | 0 | 9119824.26
Thu | 20 | N | 439 | 2023-03-09 | -0.40237 | 0.36792 | 2023-03-09 | 0.9223 | 8411257.7183 | 0 | 8411257.7183 | 439 | 0 | 0 | 0 | 439 | 0 | 9119824.26
Fri | 20 | N | 440 | 2023-03-10 | -0.39645 | 0.36879 | 2023-03-10 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Sat | 20 | Y | 440 | 2023-03-11 | -0.39645 | 0.36879 | 2023-03-11 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Sun | 20 | Y | 440 | 2023-03-12 | -0.39645 | 0.36879 | 2023-03-12 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Mon | 20 | Y | 440 | 2023-03-13 | -0.39645 | 0.36879 | 2023-03-13 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Tues | 20 | Y | 440 | 2023-03-14 | -0.39645 | 0.36879 | 2023-03-14 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Wed | 20 | Y | 440 | 2023-03-15 | -0.39645 | 0.36879 | 2023-03-15 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Thu | 20 | Y | 440 | 2023-03-16 | -0.39645 | 0.36879 | 2023-03-16 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Fri | 20 | Y | 440 | 2023-03-17 | -0.39645 | 0.36879 | 2023-03-17 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Sat | 20 | Y | 440 | 2023-03-18 | -0.39645 | 0.36879 | 2023-03-18 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Sun | 20 | Y | 440 | 2023-03-19 | -0.39645 | 0.36879 | 2023-03-19 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Mon | 20 | Y | 440 | 2023-03-20 | -0.39645 | 0.36879 | 2023-03-20 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Tues | 20 | Y | 440 | 2023-03-21 | -0.39645 | 0.36879 | 2023-03-21 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Wed | 20 | Y | 440 | 2023-03-22 | -0.39645 | 0.36879 | 2023-03-22 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Thu | 20 | Y | 440 | 2023-03-23 | -0.39645 | 0.36879 | 2023-03-23 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Fri | 20 | Y | 440 | 2023-03-24 | -0.39645 | 0.36879 | 2023-03-24 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Sat | 20 | Y | 440 | 2023-03-25 | -0.39645 | 0.36879 | 2023-03-25 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Sun | 20 | Y | 440 | 2023-03-26 | -0.39645 | 0.36879 | 2023-03-26 | 0.92449 | 8431160.0794 | 0 | 8431160.0794 | 440 | 0 | 0 | 0 | 440 | 0 | 9119824.26
Mon | 20 | N | 441 | 2023-03-27 | -0.39053 | 0.36965 | 2023-03-27 | 0.92664 | 8450813.641 | 0 | 8450813.641 | 441 | 0 | 0 | 0 | 441 | 0 | 9119824.26
Tues | 20 | N | 442 | 2023-03-28 | -0.38462 | 0.3705 | 2023-03-28 | 0.92877 | 8470216.4453 | 0 | 8470216.4453 | 442 | 0 | 0 | 0 | 442 | 0 | 9119824.26
Wed | 20 | N | 443 | 2023-03-29 | -0.3787 | 0.37134 | 2023-03-29 | 0.93087 | 8489366.5563 | 0 | 8489366.5563 | 443 | 0 | 0 | 0 | 443 | 0 | 9119824.26
Thu | 22 | N | 444 | 2023-03-30 | -0.37278 | 0.37216 | 2023-03-30 | 0.93294 | 8508262.0601 | 0 | 8508262.0601 | 444 | 0 | 0 | 0 | 444 | 0 | 9119824.26
Fri | 22 | N | 445 | 2023-03-31 | -0.36686 | 0.37298 | 2023-03-31 | 0.93499 | 8526901.0656 | 0 | 8526901.0656 | 445 | 0 | 0 | 0 | 445 | 0 | 9119824.26
Sat | 22 | Y | 445 | 2023-04-01 | -0.36686 | 0.37298 | 2023-04-01 | 0.93499 | 8526901.0656 | 0 | 8526901.0656 | 445 | 0 | 0 | 0 | 445 | 0 | 9119824.26
Sun | 22 | Y | 445 | 2023-04-02 | -0.36686 | 0.37298 | 2023-04-02 | 0.93499 | 8526901.0656 | 0 | 8526901.0656 | 445 | 0 | 0 | 0 | 445 | 0 | 9119824.26
Mon | 22 | N | 446 | 2023-04-03 | -0.36095 | 0.37378 | 2023-04-03 | 0.937 | 8545281.7042 | 0 | 8545281.7042 | 446 | 0 | 0 | 0 | 446 | 0 | 9119824.26
Tues | 22 | N | 447 | 2023-04-04 | -0.35503 | 0.37458 | 2023-04-04 | 0.93899 | 8563402.1303 | 0 | 8563402.1303 | 447 | 0 | 0 | 0 | 447 | 0 | 9119824.26
Wed | 22 | N | 448 | 2023-04-05 | -0.34911 | 0.37536 | 2023-04-05 | 0.94095 | 8581260.5222 | 0 | 8581260.5222 | 448 | 0 | 0 | 0 | 448 | 0 | 9119824.26
Thu | 22 | N | 449 | 2023-04-06 | -0.3432 | 0.37613 | 2023-04-06 | 0.94288 | 8598855.0814 | 0 | 8598855.0814 | 449 | 0 | 0 | 0 | 449 | 0 | 9119824.26
Fri | 22 | N | 450 | 2023-04-07 | -0.33728 | 0.37688 | 2023-04-07 | 0.94478 | 8616184.0337 | 0 | 8616184.0337 | 450 | 0 | 0 | 0 | 450 | 0 | 9119824.26
Sat | 22 | Y | 450 | 2023-04-08 | -0.33728 | 0.37688 | 2023-04-08 | 0.94478 | 8616184.0337 | 0 | 8616184.0337 | 450 | 0 | 0 | 0 | 450 | 0 | 9119824.26
Sun | 22 | Y | 450 | 2023-04-09 | -0.33728 | 0.37688 | 2023-04-09 | 0.94478 | 8616184.0337 | 0 | 8616184.0337 | 450 | 0 | 0 | 0 | 450 | 0 | 9119824.26
Mon | 22 | N | 451 | 2023-04-10 | -0.33136 | 0.37763 | 2023-04-10 | 0.94665 | 8633245.6292 | 0 | 8633245.6292 | 451 | 0 | 0 | 0 | 451 | 0 | 9119824.26
Tues | 22 | N | 452 | 2023-04-11 | -0.32544 | 0.37837 | 2023-04-11 | 0.94849 | 8650038.1426 | 0 | 8650038.1426 | 452 | 0 | 0 | 0 | 452 | 0 | 9119824.26
Wed | 22 | N | 453 | 2023-04-12 | -0.31953 | 0.37909 | 2023-04-12 | 0.9503 | 8666559.8734 | 0 | 8666559.8734 | 453 | 0 | 0 | 0 | 453 | 0 | 9119824.26
Thu | 22 | N | 454 | 2023-04-13 | -0.31361 | 0.3798 | 2023-04-13 | 0.95208 | 8682809.1463 | 0 | 8682809.1463 | 454 | 0 | 0 | 0 | 454 | 0 | 9119824.26
Fri | 22 | N | 455 | 2023-04-14 | -0.30769 | 0.3805 | 2023-04-14 | 0.95383 | 8698784.3118 | 0 | 8698784.3118 | 455 | 0 | 0 | 0 | 455 | 0 | 9119824.26
Sat | 22 | Y | 455 | 2023-04-15 | -0.30769 | 0.3805 | 2023-04-15 | 0.95383 | 8698784.3118 | 0 | 8698784.3118 | 455 | 0 | 0 | 0 | 455 | 0 | 9119824.26
Sun | 22 | Y | 455 | 2023-04-16 | -0.30769 | 0.3805 | 2023-04-16 | 0.95383 | 8698784.3118 | 0 | 8698784.3118 | 455 | 0 | 0 | 0 | 455 | 0 | 9119824.26
Mon | 22 | N | 456 | 2023-04-17 | -0.30178 | 0.38118 | 2023-04-17 | 0.95555 | 8714483.7456 | 0 | 8714483.7456 | 456 | 0 | 0 | 0 | 456 | 0 | 9119824.26
Tues | 22 | N | 457 | 2023-04-18 | -0.29586 | 0.38186 | 2023-04-18 | 0.95724 | 8729905.85 | 0 | 8729905.85 | 457 | 0 | 0 | 0 | 457 | 0 | 9119824.26
Wed | 22 | N | 458 | 2023-04-19 | -0.28994 | 0.38252 | 2023-04-19 | 0.95891 | 8745049.0532 | 0 | 8745049.0532 | 458 | 0 | 0 | 0 | 458 | 0 | 9119824.26
Thu | 22 | N | 459 | 2023-04-20 | -0.28402 | 0.38317 | 2023-04-20 | 0.96054 | 8759911.81 | 0 | 8759911.81 | 459 | 0 | 0 | 0 | 459 | 0 | 9119824.26
Fri | 22 | N | 460 | 2023-04-21 | -0.27811 | 0.38381 | 2023-04-21 | 0.96213 | 8774492.6023 | 0 | 8774492.6023 | 460 | 0 | 0 | 0 | 460 | 0 | 9119824.26
Sat | 22 | Y | 460 | 2023-04-22 | -0.27811 | 0.38381 | 2023-04-22 | 0.96213 | 8774492.6023 | 0 | 8774492.6023 | 460 | 0 | 0 | 0 | 460 | 0 | 9119824.26
Sun | 22 | Y | 460 | 2023-04-23 | -0.27811 | 0.38381 | 2023-04-23 | 0.96213 | 8774492.6023 | 0 | 8774492.6023 | 460 | 0 | 0 | 0 | 460 | 0 | 9119824.26
Mon | 22 | N | 461 | 2023-04-24 | -0.27219 | 0.38443 | 2023-04-24 | 0.9637 | 8788789.9389 | 0 | 8788789.9389 | 461 | 0 | 0 | 0 | 461 | 0 | 9119824.26
Tues | 22 | N | 462 | 2023-04-25 | -0.26627 | 0.38505 | 2023-04-25 | 0.96524 | 8802802.3558 | 0 | 8802802.3558 | 462 | 0 | 0 | 0 | 462 | 0 | 9119824.26
Wed | 22 | N | 463 | 2023-04-26 | -0.26036 | 0.38565 | 2023-04-26 | 0.96674 | 8816528.4169 | 0 | 8816528.4169 | 463 | 0 | 0 | 0 | 463 | 0 | 9119824.26
Thu | 22 | N | 464 | 2023-04-27 | -0.25444 | 0.38624 | 2023-04-27 | 0.96822 | 8829966.7137 | 0 | 8829966.7137 | 464 | 0 | 0 | 0 | 464 | 0 | 9119824.26
Fri | 22 | N | 465 | 2023-04-28 | -0.24852 | 0.38681 | 2023-04-28 | 0.96966 | 8843115.8659 | 0 | 8843115.8659 | 465 | 0 | 0 | 0 | 465 | 0 | 9119824.26
Sat | 22 | Y | 465 | 2023-04-29 | -0.24852 | 0.38681 | 2023-04-29 | 0.96966 | 8843115.8659 | 0 | 8843115.8659 | 465 | 0 | 0 | 0 | 465 | 0 | 9119824.26
Sun | 22 | Y | 465 | 2023-04-30 | -0.24852 | 0.38681 | 2023-04-30 | 0.96966 | 8843115.8659 | 0 | 8843115.8659 | 465 | 0 | 0 | 0 | 465 | 0 | 9119824.26
Mon | 22 | N | 466 | 2023-05-01 | -0.2426 | 0.38737 | 2023-05-01 | 0.97107 | 8855974.5214 | 0 | 8855974.5214 | 466 | 0 | 0 | 0 | 466 | 0 | 9119824.26
Tues | 22 | N | 467 | 2023-05-02 | -0.23669 | 0.38792 | 2023-05-02 | 0.97245 | 8868541.3568 | 0 | 8868541.3568 | 467 | 0 | 0 | 0 | 467 | 0 | 9119824.26
Wed | 22 | N | 468 | 2023-05-03 | -0.23077 | 0.38846 | 2023-05-03 | 0.97379 | 8880815.0774 | 0 | 8880815.0774 | 468 | 0 | 0 | 0 | 468 | 0 | 9119824.26
Thu | 22 | N | 469 | 2023-05-04 | -0.22485 | 0.38898 | 2023-05-04 | 0.97511 | 8892794.4175 | 0 | 8892794.4175 | 469 | 0 | 0 | 0 | 469 | 0 | 9119824.26
Fri | 22 | N | 470 | 2023-05-05 | -0.21893 | 0.38949 | 2023-05-05 | 0.97639 | 8904478.1404 | 0 | 8904478.1404 | 470 | 0 | 0 | 0 | 470 | 0 | 9119824.26
Sat | 22 | Y | 470 | 2023-05-06 | -0.21893 | 0.38949 | 2023-05-06 | 0.97639 | 8904478.1404 | 0 | 8904478.1404 | 470 | 0 | 0 | 0 | 470 | 0 | 9119824.26
Sun | 22 | Y | 470 | 2023-05-07 | -0.21893 | 0.38949 | 2023-05-07 | 0.97639 | 8904478.1404 | 0 | 8904478.1404 | 470 | 0 | 0 | 0 | 470 | 0 | 9119824.26
Mon | 22 | N | 471 | 2023-05-08 | -0.21302 | 0.38999 | 2023-05-08 | 0.97764 | 8915865.0393 | 0 | 8915865.0393 | 471 | 0 | 0 | 0 | 471 | 0 | 9119824.26
Tues | 22 | N | 472 | 2023-05-09 | -0.2071 | 0.39048 | 2023-05-09 | 0.97885 | 8926953.9366 | 0 | 8926953.9366 | 472 | 0 | 0 | 0 | 472 | 0 | 9119824.26
Wed | 22 | N | 473 | 2023-05-10 | -0.20118 | 0.39095 | 2023-05-10 | 0.98003 | 8937743.6848 | 0 | 8937743.6848 | 473 | 0 | 0 | 0 | 473 | 0 | 9119824.26
Thu | 22 | N | 474 | 2023-05-11 | -0.19527 | 0.39141 | 2023-05-11 | 0.98118 | 8948233.1662 | 0 | 8948233.1662 | 474 | 0 | 0 | 0 | 474 | 0 | 9119824.26
Fri | 22 | N | 475 | 2023-05-12 | -0.18935 | 0.39185 | 2023-05-12 | 0.9823 | 8958421.2934 | 0 | 8958421.2934 | 475 | 0 | 0 | 0 | 475 | 0 | 9119824.26
Sat | 22 | Y | 475 | 2023-05-13 | -0.18935 | 0.39185 | 2023-05-13 | 0.9823 | 8958421.2934 | 0 | 8958421.2934 | 475 | 0 | 0 | 0 | 475 | 0 | 9119824.26
Sun | 22 | Y | 475 | 2023-05-14 | -0.18935 | 0.39185 | 2023-05-14 | 0.9823 | 8958421.2934 | 0 | 8958421.2934 | 475 | 0 | 0 | 0 | 475 | 0 | 9119824.26
Mon | 22 | N | 476 | 2023-05-15 | -0.18343 | 0.39229 | 2023-05-15 | 0.98339 | 8968307.0097 | 0 | 8968307.0097 | 476 | 0 | 0 | 0 | 476 | 0 | 9119824.26
Tues | 22 | N | 477 | 2023-05-16 | -0.17751 | 0.39271 | 2023-05-16 | 0.98444 | 8977889.2886 | 0 | 8977889.2886 | 477 | 0 | 0 | 0 | 477 | 0 | 9119824.26
Wed | 22 | N | 478 | 2023-05-17 | -0.1716 | 0.39311 | 2023-05-17 | 0.98545 | 8987167.1346 | 0 | 8987167.1346 | 478 | 0 | 0 | 0 | 478 | 0 | 9119824.26
Thu | 22 | N | 479 | 2023-05-18 | -0.16568 | 0.3935 | 2023-05-18 | 0.98644 | 8996139.583 | 0 | 8996139.583 | 479 | 0 | 0 | 0 | 479 | 0 | 9119824.26
Fri | 22 | N | 480 | 2023-05-19 | -0.15976 | 0.39388 | 2023-05-19 | 0.98739 | 9004805.7004 | 0 | 9004805.7004 | 480 | 0 | 0 | 0 | 480 | 0 | 9119824.26
Sat | 22 | Y | 480 | 2023-05-20 | -0.15976 | 0.39388 | 2023-05-20 | 0.98739 | 9004805.7004 | 0 | 9004805.7004 | 480 | 0 | 0 | 0 | 480 | 0 | 9119824.26
Sun | 22 | Y | 480 | 2023-05-21 | -0.15976 | 0.39388 | 2023-05-21 | 0.98739 | 9004805.7004 | 0 | 9004805.7004 | 480 | 0 | 0 | 0 | 480 | 0 | 9119824.26
Mon | 22 | N | 481 | 2023-05-22 | -0.15385 | 0.39425 | 2023-05-22 | 0.9883 | 9013164.5845 | 0 | 9013164.5845 | 481 | 0 | 0 | 0 | 481 | 0 | 9119824.26
Tues | 22 | N | 482 | 2023-05-23 | -0.14793 | 0.3946 | 2023-05-23 | 0.98919 | 9021215.3645 | 0 | 9021215.3645 | 482 | 0 | 0 | 0 | 482 | 0 | 9119824.26
Wed | 22 | N | 483 | 2023-05-24 | -0.14201 | 0.39494 | 2023-05-24 | 0.99004 | 9028957.2013 | 0 | 9028957.2013 | 483 | 0 | 0 | 0 | 483 | 0 | 9119824.26
Thu | 22 | N | 484 | 2023-05-25 | -0.13609 | 0.39526 | 2023-05-25 | 0.99085 | 9036389.2874 | 0 | 9036389.2874 | 484 | 0 | 0 | 0 | 484 | 0 | 9119824.26
Fri | 22 | N | 485 | 2023-05-26 | -0.13018 | 0.39558 | 2023-05-26 | 0.99163 | 9043510.847 | 0 | 9043510.847 | 485 | 0 | 0 | 0 | 485 | 0 | 9119824.26
Sat | 22 | Y | 485 | 2023-05-27 | -0.13018 | 0.39558 | 2023-05-27 | 0.99163 | 9043510.847 | 0 | 9043510.847 | 485 | 0 | 0 | 0 | 485 | 0 | 9119824.26
Sun | 22 | Y | 485 | 2023-05-28 | -0.13018 | 0.39558 | 2023-05-28 | 0.99163 | 9043510.847 | 0 | 9043510.847 | 485 | 0 | 0 | 0 | 485 | 0 | 9119824.26
Mon | 22 | N | 486 | 2023-05-29 | -0.12426 | 0.39587 | 2023-05-29 | 0.99238 | 9050321.1368 | 0 | 9050321.1368 | 486 | 0 | 0 | 0 | 486 | 0 | 9119824.26
Tues | 24 | N | 487 | 2023-05-30 | -0.11834 | 0.39616 | 2023-05-30 | 0.99309 | 9056819.445 | 0 | 9056819.445 | 487 | 0 | 0 | 0 | 487 | 0 | 9119824.26
Wed | 24 | N | 488 | 2023-05-31 | -0.11243 | 0.39643 | 2023-05-31 | 0.99377 | 9063005.0927 | 0 | 9063005.0927 | 488 | 0 | 0 | 0 | 488 | 0 | 9119824.26
Thu | 24 | N | 489 | 2023-06-01 | -0.10651 | 0.39669 | 2023-06-01 | 0.99441 | 9068877.4329 | 0 | 9068877.4329 | 489 | 0 | 0 | 0 | 489 | 0 | 9119824.26
Fri | 24 | N | 490 | 2023-06-02 | -0.10059 | 0.39693 | 2023-06-02 | 0.99502 | 9074435.8512 | 0 | 9074435.8512 | 490 | 0 | 0 | 0 | 490 | 0 | 9119824.26
Sat | 24 | Y | 490 | 2023-06-03 | -0.10059 | 0.39693 | 2023-06-03 | 0.99502 | 9074435.8512 | 0 | 9074435.8512 | 490 | 0 | 0 | 0 | 490 | 0 | 9119824.26
Sun | 24 | Y | 490 | 2023-06-04 | -0.10059 | 0.39693 | 2023-06-04 | 0.99502 | 9074435.8512 | 0 | 9074435.8512 | 490 | 0 | 0 | 0 | 490 | 0 | 9119824.26
Mon | 24 | N | 491 | 2023-06-05 | -0.094675 | 0.39716 | 2023-06-05 | 0.9956 | 9079679.766 | 0 | 9079679.766 | 491 | 0 | 0 | 0 | 491 | 0 | 9119824.26
Tues | 24 | N | 492 | 2023-06-06 | -0.088757 | 0.39737 | 2023-06-06 | 0.99614 | 9084608.6281 | 0 | 9084608.6281 | 492 | 0 | 0 | 0 | 492 | 0 | 9119824.26
Wed | 24 | N | 493 | 2023-06-07 | -0.08284 | 0.39758 | 2023-06-07 | 0.99664 | 9089221.9214 | 0 | 9089221.9214 | 493 | 0 | 0 | 0 | 493 | 0 | 9119824.26
Thu | 24 | N | 494 | 2023-06-08 | -0.076923 | 0.39776 | 2023-06-08 | 0.99712 | 9093519.1624 | 0 | 9093519.1624 | 494 | 0 | 0 | 0 | 494 | 0 | 9119824.26
Fri | 24 | N | 495 | 2023-06-09 | -0.071006 | 0.39794 | 2023-06-09 | 0.99755 | 9097499.9007 | 0 | 9097499.9007 | 495 | 0 | 0 | 0 | 495 | 0 | 9119824.26
Sat | 24 | Y | 495 | 2023-06-10 | -0.071006 | 0.39794 | 2023-06-10 | 0.99755 | 9097499.9007 | 0 | 9097499.9007 | 495 | 0 | 0 | 0 | 495 | 0 | 9119824.26
Sun | 24 | Y | 495 | 2023-06-11 | -0.071006 | 0.39794 | 2023-06-11 | 0.99755 | 9097499.9007 | 0 | 9097499.9007 | 495 | 0 | 0 | 0 | 495 | 0 | 9119824.26
Mon | 24 | N | 496 | 2023-06-12 | -0.065089 | 0.3981 | 2023-06-12 | 0.99795 | 9101163.719 | 0 | 9101163.719 | 496 | 0 | 0 | 0 | 496 | 0 | 9119824.26
Tues | 24 | N | 497 | 2023-06-13 | -0.059172 | 0.39824 | 2023-06-13 | 0.99832 | 9104510.233 | 0 | 9104510.233 | 497 | 0 | 0 | 0 | 497 | 0 | 9119824.26
Wed | 24 | N | 498 | 2023-06-14 | -0.053254 | 0.39838 | 2023-06-14 | 0.99865 | 9107539.0917 | 0 | 9107539.0917 | 498 | 0 | 0 | 0 | 498 | 0 | 9119824.26
Thu | 24 | N | 499 | 2023-06-15 | -0.047337 | 0.3985 | 2023-06-15 | 0.99895 | 9110249.9773 | 0 | 9110249.9773 | 499 | 0 | 0 | 0 | 499 | 0 | 9119824.26
Fri | 24 | N | 500 | 2023-06-16 | -0.04142 | 0.3986 | 2023-06-16 | 0.99921 | 9112642.6052 | 0 | 9112642.6052 | 500 | 0 | 0 | 0 | 500 | 0 | 9119824.26
Sat | 24 | Y | 500 | 2023-06-17 | -0.04142 | 0.3986 | 2023-06-17 | 0.99921 | 9112642.6052 | 0 | 9112642.6052 | 500 | 0 | 0 | 0 | 500 | 0 | 9119824.26
Sun | 24 | Y | 500 | 2023-06-18 | -0.04142 | 0.3986 | 2023-06-18 | 0.99921 | 9112642.6052 | 0 | 9112642.6052 | 500 | 0 | 0 | 0 | 500 | 0 | 9119824.26
Mon | 24 | N | 501 | 2023-06-19 | -0.035503 | 0.39869 | 2023-06-19 | 0.99944 | 9114716.7244 | 0 | 9114716.7244 | 501 | 0 | 0 | 0 | 501 | 0 | 9119824.26
Tues | 24 | N | 502 | 2023-06-20 | -0.029586 | 0.39877 | 2023-06-20 | 0.99963 | 9116472.117 | 0 | 9116472.117 | 502 | 0 | 0 | 0 | 502 | 0 | 9119824.26
Wed | 24 | N | 503 | 2023-06-21 | -0.023669 | 0.39883 | 2023-06-21 | 0.99979 | 9117908.5988 | 0 | 9117908.5988 | 503 | 0 | 0 | 0 | 503 | 0 | 9119824.26
Thu | 24 | N | 504 | 2023-06-22 | -0.017751 | 0.39888 | 2023-06-22 | 0.99991 | 9119026.0189 | 0 | 9119026.0189 | 504 | 0 | 0 | 0 | 504 | 0 | 9119824.26
Fri | 24 | N | 505 | 2023-06-23 | -0.011834 | 0.39891 | 2023-06-23 | 1 | 9119824.26 | 0 | 9119824.26 | 505 | 0 | 0 | 0 | 505 | 0 | 9119824.26
Formulas:
B = [B, row above]+1
E = B = [E = B, row above]+1

## LevelChange (hidden)
Adjustment For Change in Levels
1 | Substructures of properties (Plots 1,2,24,25,59 - 62) | Orig qty | Revd Qty | Diff | UoM | Rate | Value
a | Excavate to reduce level ne 0.25 deep | 0 | 11.55 | 11.55 | m3 | 3.5 | 40.425
b | Fill to make up levels in selected excavated material ne 0.25m dp | 0 | 5.99 | 5.99 | m3 | 3.5 | 20.965
c | Ditto ne 1m dp | 120.63 | 200.78 | 80.15 | m3 | 3.5 | 280.525
d | Ditto ne 2m dp | 642.24 | 0 | -642.24 | m3 | 3.5 | -2247.84
e | Excavate trench ne 1m deep | 42.93 | 120.63 | 77.7 | m3 | 4.5 | 349.65
f | Ditto not exc 2m deep | 164.6 | 0 | -164.6 | m3 | 4.5 | -740.7
g | Vol of concrete in trenches | 123.62 | 36.71 | -86.91 | m3 | 92.27 | -8019.1857
-10316.1607
Roads
h
i
j
k
l
m
n
o
p

## ADOPTEDROADS (hidden)
Residential Development at Crundale For Millbay Homes | [22 empty] | is incl in FA |  | Needs Checking
Phase 1 | [6 empty] | Assumed to Chain Point 22m into Second Phase |  |  |  |  | Surf | 30 | mm
Adopted Roads | [6 empty] | Site Red Lvl |  | 0.5 | m |  | Binder | 50 | mm | [15 empty] | m2
Tarmac | [11 empty] | wetmix | 150 | mm
[12 empty] | Type 1 | 250 | mm
[12 empty] | Type 3 - Open |  | mm
[13 empty] | 0.48 | m
[7 empty] | 514.1165 |  |  |  | FINISHED LEVELS | [10 empty] | 256.8368 | 1.5009 | 1.5009 | 0 | 42.2278 | 214.609 | 0 | 514.1165 | 506.8125 | 514.1165 | 514.1165 | 514.1165
Loc Ref | Location | Chain From | Chain to | Width | Length | X | Area | Lower Chain Existing Level | Higher Chain Existing Level | Average Existing Level | Surf Lvl (Lower Chain - Side) | Surf Lvl (Lower Chain- Mid) | Surf Lvl (Higher Chain Side) | Surf Lvl (Mid Chain Side) | Av Surf Lvl (Lower) | Av Surf Lvl (Higher) | Average Surface Level | Form Lvl (Lower) | Form Lvl (Higher) | Form Lvl (Average) | Average Exc (+) or Fill (-) | Fill | Cut | Exc to red lvls ne 0.25m | Exc to red lvls ne 1.0m | Fill to make up ne 0.25m | Fill to make up over 0.25 | Check | Compact btms of excns | Comp. Fill. Arising From Exc. | Type 1 as Eng Dwg - Item 10 | GeoTerxtile as Eng Dwg - Item 11 | Wet Mix as dwg - 150 thick
9 | Road 1 | 37 | 40 | 5 | 3 |  | 15 | 41.19 | 41.857 | 41.5235 | 42.025 | 42.091 | 41.742 | 41.805 | 42.058 | 41.7735 | 41.9158 | 41.578 | 41.2935 | 41.4358 | -0.58775 | 8.8162 | 0 | 0 | 0 | 0 | 8.8162 | TRUE | 15 | 15 | 15 | 15 | 15
10 | Road 1 | 40 | 43 | 5 | 3 |  | 15 | 41.857 | 41.718 | 41.7875 | 41.742 | 41.805 | 41.5401 | 41.6052 | 41.7735 | 41.5726 | 41.6731 | 41.2935 | 41.0926 | 41.1931 | -1.0944 | 16.4164 | 0 | 0 | 0 | 0 | 16.4164 | TRUE | 15 | 15 | 15 | 15 | 15
11 | Road 1 | 43 | 50 | 5.25 | 7 |  | 36.75 | 41.718 | 41.3935 | 41.5557 | 41.5401 | 41.6052 | 41.4535 | 41.5195 | 41.5726 | 41.4865 | 41.5296 | 41.0926 | 41.0065 | 41.0496 | -1.0062 | 36.9769 | 0 | 0 | 0 | 0 | 36.9769 | TRUE | 36.75 | 36.75 | 36.75 | 36.75 | 36.75
12 | Road 1 | 50 | 52 | 5.25 | 2 |  | 10.5 | 41.3935 | 41.3008 | 41.3471 | 41.4535 | 41.5195 | 41.3958 | 41.4624 | 41.4865 | 41.4291 | 41.4578 | 41.0065 | 40.9491 | 40.9778 | -0.86935 | 9.1282 | 0 | 0 | 0 | 0 | 9.1282 | TRUE | 10.5 | 10.5 | 10.5 | 10.5 | 10.5
13 | Road 1 | 52 | 60 | 5.5 | 8 |  | 44 | 41.3008 | 40.93 | 41.1154 | 41.3958 | 41.4624 | 41.165 | 41.234 | 41.4291 | 41.1995 | 41.3143 | 40.9491 | 40.7195 | 40.8343 | -0.7811 | 34.3684 | 0 | 0 | 0 | 0 | 34.3684 | TRUE | 44 | 44 | 44 | 44 | 44
14 | Road 1 | 60 | 70 | 5.5 | 10 |  | 55 | 40.93 | 39.981 | 40.4555 | 41.165 | 41.234 | 41.069 | 41.138 | 41.1995 | 41.1035 | 41.1515 | 40.7195 | 40.6235 | 40.6715 | -0.28401 | 15.6207 | 0 | 0 | 0 | 0 | 15.6207 | TRUE | 55 | 55 | 55 | 55 | 55
15 | Road 1 | 70 | 71.328 | 5.5 | 1.328 |  | 7.304 | 39.981 | 39.855 | 39.918 | 41.069 | 41.138 | 41.069 | 41.138 | 41.1035 | 41.1035 | 41.1035 | 40.6235 | 40.6235 | 40.6235 | 0.20549 | 0 | 1.5009 | 1.5009 | 0 | 0 | 0 | TRUE | 7.304 | 0 | 7.304 | 7.304 | 7.304
16 | Road 2 | 2.75 | 20 | 5.5 | 17.25 |  | 94.875 | 39.855 | 40.112 | 39.9835 | 40.8325 | 40.9025 | 40.024 | 40.095 | 40.8675 | 40.0595 | 40.4635 | 40.3875 | 39.5795 | 39.9835 | -0.5 | 47.4375 | 0 | 0 | 0 | 0 | 47.4375 | TRUE | 94.875 | 94.875 | 94.875 | 94.875 | 94.875
17 | Road 2 | 20 | 35 | 5.5 | 15 |  | 82.5 | 40.112 | 38.847 | 39.4795 | 40.024 | 40.095 | 39.137 | 39.206 | 40.0595 | 39.1715 | 39.6155 | 39.5795 | 38.6915 | 39.1355 | -0.844 | 69.63 | 0 | 0 | 0 | 0 | 69.63 | TRUE | 82.5 | 82.5 | 82.5 | 82.5 | 82.5
26 | Road 3 | 2.75 | 20 | 5.75 | 17.25 |  | 99.1875 | 39.855 | 40.542 | 40.1985 | 40.8325 | 40.9025 | 41.028 | 41.103 | 40.8675 | 41.0655 | 40.9665 | 40.3875 | 40.5855 | 40.4865 | -0.212 | 21.0278 | 0 | 0 | 0 | 21.0278 | 0 | TRUE | 99.1875 | 99.1875 | 99.1875 | 99.1875 | 99.1875
27 | Road 3 | 20 | 22 | 6 | 2 |  | 12 | 40.542 | 40.542 | 40.542 | 41.028 | 41.103 | 40.96 | 41.035 | 41.0655 | 40.9975 | 41.0315 | 40.5855 | 40.5175 | 40.5515 | -0.4905 | 5.886 | 0 | 0 | 0 | 0 | 5.886 | TRUE | 12 | 12 | 12 | 12 | 12
28 | Corners at Roads 1 & 2 |  |  | 10 | 10 |  | 100 | 39.855 | 40.542 | 40.1985 | 40.8325 | 40.9025 | 41.028 | 41.103 | 40.8675 | 41.0655 | 40.9665 | 40.3875 | 40.5855 | 40.4865 | -0.212 | 21.2 | 0 | 0 | 0 | 21.2 | 0 | TRUE | 100 | 100 | 100 | 100 | 100
29 | Ditto |  |  | -10 | 10 | 0.79 | -79 | 39.855 | 40.542 | 40.542 | 40.8325 | 41.103 | 40.96 | 41.035 | 40.9677 | 40.9975 | 40.9826 | 40.4877 | 40.5175 | 40.5026 | -0.53937 | -42.6106 | 0 | 0 | 0 | 0 | -42.6106 | TRUE | -79 | -79 | -79 | -79 | -79
30 | Corners at Roads 1 & 2 |  |  | 10 | 10 |  | 100 | 39.855 | 40.542 | 40.542 | 40.8325 | 40.9025 | 41.028 | 41.103 | 40.8675 | 41.0655 | 40.9665 | 40.3875 | 40.5855 | 40.4865 | -0.5555 | 55.55 | 0 | 0 | 0 | 0 | 55.55 | TRUE | 100 | 100 | 100 | 100 | 100
31 | Ditto |  |  | -10 | 10 | 0.79 | -79 | 39.855 | 40.542 | 40.542 | 40.8325 | 41.103 | 40.96 | 41.035 | 40.9677 | 40.9975 | 40.9826 | 40.4877 | 40.5175 | 40.5026 | -0.53937 | -42.6106 | 0 | 0 | 0 | 0 | -42.6106 | TRUE | -79 | -79 | -79 | -79 | -79

## SUBS (hidden)
| Residential Development at Crundale For Millbay Homes | [8 empty] | is incl in FA | [40 empty] | No of Courses | No of Courses | No of Courses | No of Courses | Height in m | Height in m
| Phase 1 | [16 empty] | BeamBlockSlabBuildUp |  | 500 | [10 empty] | Width | Width | [18 empty] | 4 | 4 | 4 | 4 | 1.025 | 1.025
DIFFERENCE | [19 empty] | -556.1043 | 11.5522 | 11.5522 | 0 | 5.986 | 80.1472 | -642.2376 | -2.8422e-14 | [13 empty] | 0 | 18.73 | 0 | 0 | 58.97 | -164.6 | 0 |  |  | -86.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REVISED LEVELS | [19 empty] | 206.7622 | 11.5522 | 11.5522 | 0 | 5.986 | 200.7761 | 0 | -2.8422e-14 | Eng Section A - A | [8 empty] | Btm of Trench 1 | Btm of Trench 2 | Btm of Trench |  | 0 | 18.73 | 0 | 0 | 101.9 | 0 | 654.25 |  |  | 36.71 | 185.148 | 23.3928 | 56.8368 | 172.476 | 205.9348 | 13.3209 | 192.5172 | 205.72
Plot | Type | Det,Semi, Mid Terr. (D , S , M) | Width (side to Side) | Length (Front to Back) | Spr to Front | Spr to Rear | Spr to Left | Spr To Right | Width+ Spr Left & Right | Length + Spr Front And Rear | Max Area | Adj | Act Area | Natural Ground level | Depth Of Topsoil | New reduced Level | Revised FFL | Required formation | Depth of Exc (+) or Fill (-) | Fill | Cut | Exc to red lvls ne 0.25m | Exc to red lvls ne 1.0m | Fill to make up ne 0.25m | Fill to make up ne 1.0m | Fill to make up ne 2.0m | Check | C/L of Perim. Trenches | Adjustments to Perimeter | Act C/L of Perim. Trenches | C/L of Party W. Trenches (Ext Face to Ext Face) | C/L of Internal Trenches | Surface Area of Perim Trenches | Surface Area of Party Wall Trenches x 50% | Surface Area of Internal Trenches | Surface Area of Trenches | Max lvl of trench - based on min dim from FFL to U/S of conc | U/S of fill less 100mm scrape into "virgin" earth | Btm of Trench | Trench depth = Required Formation less Btm of Trench | Exc Trench ne 0.25m dp | Exc Trench ne 1.00m dp | Exc Trench ne 2.00m dp | Exc Trench thru fill ne 0.25m dp | Exc Trench thru fill ne 1.00m dp | Exc Trench thru fill ne 2.00m dp | Compact btms of excns (includes Perimeter Paths) | Top of Concrete in Footing | Thickness of Concrete | Volume of Concrete | C/L of 100mm blockwork to Perim. | C/L of 100mm block to Party Walls | C/L of 100 Block to Int. Walls | C/L of140 Blockwork to Perim. | C/L for Forming Cavity 100wide (Perim) | Ditto Party Wall | C/L of Conc Fill to Hollow Walls | DPC to Outer Skin
1 | A | D | 8.754 | 8.634 | 1 | 1 | 1 | 0.13 | 9.88 | 10.63 | 105.02 | 0 | 105.02 | 41.76 | 0.5 | 41.26 | 41.65 | 41.15 | 0.11 | 0 | 11.5522 | 11.5522 | 0 | 0 | 0 | 0 | TRUE | 33.416 | 0 | 33.416 | 0 | 10.933 | 20.0496 | 0 | 4.9199 | 24.9694 | 40400 | 0 | 40400 | 750 | 0 | 18.73 | 0 | 0 | 0 | 0 | 105.02 | 40625 | 225 | 5.62 | 34.38 | 0 | 8.357 | 32.62 | 33.576 | 0 | 33.576 | 34.38
2 | A | D | 8.754 | 8.634 | 1 | 1 | 1 | 1 | 10.75 | 10.63 | 114.27 | 0 | 114.27 | 41.02 | 0.5 | 40.52 | 41.45 | 40.95 | -0.43 | 49.1361 | 0 | 0 | 0 | 0 | 49.1361 | 0 | TRUE | 33.416 | 0 | 33.416 | 0 | 10.933 | 20.0496 | 0 | 4.9199 | 24.9694 | 40200 | 40420 | 40200 | 750 | 0 | 0 | 0 | 0 | 18.73 | 0 | 114.27 | 40425 | 225 | 5.62 | 34.38 | 0 | 8.357 | 32.62 | 33.576 | 0 | 33.576 | 34.38
24 | A | D | 8.754 | 8.634 | 1 | 1 | 1 | 0.13 | 9.88 | 10.63 | 105.02 | 0 | 105.02 | 39.22 | 0.5 | 38.72 | 39.9 | 39.4 | -0.68 | 71.4136 | 0 | 0 | 0 | 0 | 71.4136 | 0 | TRUE | 33.416 | 0 | 33.416 | 0 | 10.933 | 20.0496 | 0 | 4.9199 | 24.9694 | 38650 | 38620 | 38620 | 780 | 0 | 0 | 0 | 0 | 19.48 | 0 | 105.02 | 38875 | 255 | 6.37 | 34.38 | 0 | 8.357 | 32.62 | 33.576 | 0 | 33.576 | 34.38
25 | A | D | 8.754 | 8.634 | 1 | 1 | 0.13 | 1 | 9.88 | 10.63 | 105.02 | 0 | 105.02 | 39.29 | 0.5 | 38.79 | 39.65 | 39.15 | -0.36 | 37.8072 | 0 | 0 | 0 | 0 | 37.8072 | 0 | TRUE | 33.416 | 0 | 33.416 | 0 | 10.933 | 20.0496 | 0 | 4.9199 | 24.9694 | 38400 | 38690 | 38400 | 750 | 0 | 0 | 0 | 0 | 18.73 | 0 | 105.02 | 38625 | 225 | 5.62 | 34.38 | 0 | 8.357 | 32.62 | 33.576 | 0 | 33.576 | 34.38
59 | G | S | 5.037 | 7.178 | 1 | 1 | 1 | 0 | 6.04 | 9.18 | 55.45 | 0 | 55.45 | 41.01 | 0.5 | 40.51 | 41.5 | 41 | -0.49 | 27.1705 | 0 | 0 | 0 | 0 | 27.1705 | 0 | TRUE | 16.572 | 0 | 16.572 | 7.178 | 7.041 | 9.9432 | 1.8714 | 3.1685 | 14.983 | 40250 | 40410 | 40250 | 750 | 0 | 0 | 0 | 0 | 11.24 | 0 | 55.45 | 40475 | 225 | 3.37 | 17.05 | 6.498 | 7.431 | 15.29 | 16.652 | 3.249 | 19.901 | 17.05
60 | G | S | 5.037 | 7.178 | 1 | 1 | 0 | 1.175 | 6.21 | 9.18 | 57.01 | 0 | 57.01 | 41.49 | 0.5 | 40.99 | 41.5 | 41 | -0.01 | 0.5701 | 0 | 0 | 0 | 0.5701 | 0 | 0 | TRUE | 16.572 | 0 | 16.572 | 7.178 | 7.041 | 9.9432 | 1.8714 | 3.1685 | 14.983 | 40250 | 40890 | 40250 | 750 | 0 | 0 | 0 | 0 | 11.24 | 0 | 57.01 | 40475 | 225 | 3.37 | 17.05 | 6.498 | 7.431 | 15.29 | 16.652 | 3.249 | 19.901 | 17.05
61 | G | S | 5.037 | 7.178 | 1 | 1 | 1.175 | 0 | 6.21 | 9.18 | 57.01 | 0 | 57.01 | 41.53 | 0.5 | 41.03 | 41.625 | 41.125 | -0.095 | 5.4159 | 0 | 0 | 0 | 5.4159 | 0 | 0 | TRUE | 16.572 | 0 | 16.572 | 7.178 | 7.041 | 9.9432 | 1.8714 | 3.1685 | 14.983 | 40375 | 40930 | 40375 | 750 | 0 | 0 | 0 | 0 | 11.24 | 0 | 57.01 | 40600 | 225 | 3.37 | 17.05 | 6.498 | 7.431 | 15.29 | 16.652 | 3.249 | 19.901 | 17.05
62 | G | S | 5.037 | 7.178 | 1 | 1 | 0 | 1 | 6.04 | 9.18 | 55.45 | 0 | 55.45 | 41.35 | 0.5 | 40.85 | 41.625 | 41.125 | -0.275 | 15.2487 | 0 | 0 | 0 | 0 | 15.2487 | 0 | TRUE | 16.572 | 0 | 16.572 | 7.178 | 7.041 | 9.9432 | 1.8714 | 3.1685 | 14.983 | 40375 | 40750 | 40375 | 750 | 0 | 0 | 0 | 0 | 11.24 | 0 | 55.45 | 40600 | 225 | 3.37 | 17.05 | 6.498 | 7.431 | 15.29 | 16.652 | 3.249 | 19.901 | 17.05
ORIGINAL LEVELS | [16 empty] | ORIG FFL |  |  | 762.8665 | 0 | 0 | 0 | 0 | 120.6289 | 642.2376 | 0 | Eng Section A - A | [8 empty] | Btm of Trench 1 | Btm of Trench 2 | Btm of Trench |  | 0 | 0 | 0 | 0 | 42.93 | 164.6 | 654.25 |  |  | 123.62 | 185.148 | 23.3928 | 56.8368 | 172.476 | 205.9348 | 13.3209 | 192.5172 | 205.72
1 | A | D | 8.754 | 8.634 | 1 | 1 | 1 | 0.13 | 9.88 | 10.63 | 105.02 | 0 | 105.02 | 41.76 | 0.5 | 41.26 | 42.35 | 41.85 | -0.59 | 61.9618 | 0 | 0 | 0 | 0 | 61.9618 | 0 | TRUE | 33.416 | 0 | 33.416 | 0 | 10.933 | 20.0496 | 0 | 4.9199 | 24.9694 | 41100 | 41160 | 41100 | 750 | 0 | 0 | 0 | 0 | 18.73 | 0 | 105.02 | 41325 | 225 | 5.62 | 34.38 | 0 | 8.357 | 32.62 | 33.576 | 0 | 33.576 | 34.38
2 | A | D | 8.754 | 8.634 | 1 | 1 | 1 | 1 | 10.75 | 10.63 | 114.27 | 0 | 114.27 | 41.02 | 0.5 | 40.52 | 42.35 | 41.85 | -1.33 | 151.9791 | 0 | 0 | 0 | 0 | 0 | 151.9791 | TRUE | 33.416 | 0 | 33.416 | 0 | 10.933 | 20.0496 | 0 | 4.9199 | 24.9694 | 41100 | 40420 | 40420 | 1430 | 0 | 0 | 0 | 0 | 0 | 35.71 | 114.27 | 41325 | 905 | 22.6 | 34.38 | 0 | 8.357 | 32.62 | 33.576 | 0 | 33.576 | 34.38
24 | A | D | 8.754 | 8.634 | 1 | 1 | 1 | 0.13 | 9.88 | 10.63 | 105.02 | 0 | 105.02 | 39.22 | 0.5 | 38.72 | 41 | 40.5 | -1.78 | 186.9356 | 0 | 0 | 0 | 0 | 0 | 186.9356 | TRUE | 33.416 | 0 | 33.416 | 0 | 10.933 | 20.0496 | 0 | 4.9199 | 24.9694 | 39750 | 38620 | 38620 | 1880 | 0 | 0 | 0 | 0 | 0 | 46.94 | 105.02 | 39975 | 1355 | 33.83 | 34.38 | 0 | 8.357 | 32.62 | 33.576 | 0 | 33.576 | 34.38
25 | A | D | 8.754 | 8.634 | 1 | 1 | 0.13 | 1 | 9.88 | 10.63 | 105.02 | 0 | 105.02 | 39.29 | 0.5 | 38.79 | 40.75 | 40.25 | -1.46 | 153.3292 | 0 | 0 | 0 | 0 | 0 | 153.3292 | TRUE | 33.416 | 0 | 33.416 | 0 | 10.933 | 20.0496 | 0 | 4.9199 | 24.9694 | 39500 | 38690 | 38690 | 1560 | 0 | 0 | 0 | 0 | 0 | 38.95 | 105.02 | 39725 | 1035 | 25.84 | 34.38 | 0 | 8.357 | 32.62 | 33.576 | 0 | 33.576 | 34.38
59 | G | S | 5.037 | 7.178 | 1 | 1 | 1 | 0 | 6.04 | 9.18 | 55.45 | 0 | 55.45 | 41.01 | 0.5 | 40.51 | 41.775 | 41.275 | -0.765 | 42.4193 | 0 | 0 | 0 | 0 | 42.4193 | 0 | TRUE | 16.572 | 0 | 16.572 | 7.178 | 7.041 | 9.9432 | 1.8714 | 3.1685 | 14.983 | 40525 | 40410 | 40410 | 865 | 0 | 0 | 0 | 0 | 12.96 | 0 | 55.45 | 40750 | 340 | 5.09 | 17.05 | 6.498 | 7.431 | 15.29 | 16.652 | 3.249 | 19.901 | 17.05
60 | G | S | 5.037 | 7.178 | 1 | 1 | 0 | 1.175 | 6.21 | 9.18 | 57.01 | 0 | 57.01 | 41.49 | 0.5 | 40.99 | 41.775 | 41.275 | -0.285 | 16.2478 | 0 | 0 | 0 | 0 | 16.2478 | 0 | TRUE | 16.572 | 0 | 16.572 | 7.178 | 7.041 | 9.9432 | 1.8714 | 3.1685 | 14.983 | 40525 | 40890 | 40525 | 750 | 0 | 0 | 0 | 0 | 11.24 | 0 | 57.01 | 40750 | 225 | 3.37 | 17.05 | 6.498 | 7.431 | 15.29 | 16.652 | 3.249 | 19.901 | 17.05
61 | G | S | 5.037 | 7.178 | 1 | 1 | 1.175 | 0 | 6.21 | 9.18 | 57.01 | 0 | 57.01 | 41.53 | 0.5 | 41.03 | 42.775 | 42.275 | -1.245 | 70.9774 | 0 | 0 | 0 | 0 | 0 | 70.9774 | TRUE | 16.572 | 0 | 16.572 | 7.178 | 7.041 | 9.9432 | 1.8714 | 3.1685 | 14.983 | 41525 | 40930 | 40930 | 1345 | 0 | 0 | 0 | 0 | 0 | 20.15 | 57.01 | 41750 | 820 | 12.29 | 17.05 | 6.498 | 7.431 | 15.29 | 16.652 | 3.249 | 19.901 | 17.05
62 | G | S | 5.037 | 7.178 | 1 | 1 | 0 | 1 | 6.04 | 9.18 | 55.45 | 0 | 55.45 | 41.35 | 0.5 | 40.85 | 42.775 | 42.275 | -1.425 | 79.0162 | 0 | 0 | 0 | 0 | 0 | 79.0162 | TRUE | 16.572 | 0 | 16.572 | 7.178 | 7.041 | 9.9432 | 1.8714 | 3.1685 | 14.983 | 41525 | 40750 | 40750 | 1525 | 0 | 0 | 0 | 0 | 0 | 22.85 | 55.45 | 41750 | 1000 | 14.98 | 17.05 | 6.498 | 7.431 | 15.29 | 16.652 | 3.249 | 19.901 | 17.05

## Constants (hidden)
CONSTANTS
Assumed Topsoil Thickness (Extg) | 500 | mm | OR | 0.5 | m
NewTopsoil Thickness | 150 | mm | OR | 0.15 | m
mm
mm
Spread | 130 | mm
Min Dept from EGL to Bot.of Trench | 1000 | mm
Screed | 75 | mm
Insulation | 100 | mm
Beam | 175 | mm
Void | 150 | mm
Total Floor Lab Thickness (from FFL) | 500 | mm
Hieght of Vertical DPM to int face of ext wall | 400 | mm
TRENCH WIDTHS
Perimeter of House Plots | 600 | mm
Party Walls | 600 | mm
Internal Structural Walls | 450 | mm
TRENCH DEPTHS
Facings from FFL to cut block | 225 | mm
cut block depth | 125 | mm
Blocks from cut block to top of conc in ftg | 675 | mm
FFL to top of conc in footing | 1025 | mm
min thickness of conc footing | 225 | mm
Min dim from FFL to U/S of conc footing | 1250 | mm
WALLS |  |  | External Face to C/L
External Skin | 100 | mm | 50
Clear Cavity | 50 | mm | 125
Insulation Thickness | 50 | mm | 175
Internal Skin | 140 | mm | 270
External Wall Build up | 340 | mm
C/L of Ext. Skin to C/L of Int. Skin | 220 | mm
Ext Face to C/L of Cavity | 150 | mm
Height of Conc Fill in Cavity | 675 | mm
Omission from Perimeter for Beam & Block Floor | 200 | mm
mm
mm
mm
mm
mm
Party Wall:
Skin | 100 | mm
Cavity | 150 | mm
Skin | 100 | mm
Party Wall Build up | 350 | mm
Height of Conc Fill in Cavity | 900 | mm
Omission from Perimeter for Beam & Block Floor (from C/L) | 75 | mm
mm
mm
mm
mm