# University of Wales Trinity Saint David

# School of Engineering

# Manufacturing Systems

Six Sigma Green Belt

Undertaking a Green Belt Project AMCB5005

Joseph Lancastle
2214707

29th April 2024

Word Count: 2889

Adjusted Word Count: 4930

Contents

List of Figures	4

Introduction	5

Define	6

Project Charter	6

Voice of the Customer/Critical to Quality	10

Stakeholder Analysis	11

Measure	13

Data Collection Plan	14

Collected Data	15

Camera Subassembly	15

Instrument Test	15

Historical Scrap Data Collection	16

Measurement System Analysis	17

Analyse	18

Normality Anderson Darling Tests	18

Process Capability Analysis (CPK)	19

Subassembly Timings	19

Test Downtime	21

Control Charts	22

Subassembly Timings	22

Test Downtime	23

23

Camera Rejects	24

Pareto	24

Improve	26

Generating Improvement Alternatives	26

Ishikawa Analysis	27

PFMEA	28

Ishikawa/PFMEA Analysis	29

Value Stream Mapping	30

Current State Future State	30

Improvement Opportunities	31

1 Reduce Subjectivity	31

2 Improve Subassembly Procedure	32

3 Improve Test Procedure	33

4 Remove Cardboard	33

5 5S Areas	34

6 Check Incoming Stock	35

7 Review Tooling	35

Control	36

Prevention	36

Detection	39

Cost-Benefit Analysis	40

Control Plan	41

Future Recommendations	42

References	43

Appendices	45

Appendix A	45

Appendix B	46

Appendix C	48

Appendix D	52

# List of Figures

Figure 1: Project Charter 1/3	7

Figure 2: Project Charter 2/3	8

Figure 3: Project Charter 3/3	9

Figure 4: Normal Probability Plot for Subassembly Timings	18

Figure 5: Normal Probability Plot for Testing Downtime	18

Figure 6: Capability Analysis of Subassembly Timings 1	19

Figure 7:Capability Analysis of Subassembly Timings 2	20

Figure 8: Capability Analysis of Test Downtime	21

Figure 9: X Chart for Subassembly Timings	22

Figure 10: mR Chart for Subassembly Timings	22

Figure 11: X Chart for Test Downtime	23

Figure 12: mR Chart for Test Downtime	23

Figure 13: Defects Pareto for Camera Rejects	24

Figure 14: Variable Defects Pareto for Camera Rejects	24

Figure 15: Camera Rejects Variable as Supplied	25

Figure 16: Camera Rejects Variable in House	25

Figure 17: Ishikawa Analysis	27

Figure 18: Ishikawa/PFMEA Analysis	29

Figure 19: Current State Process Map	30

Figure 20: Future State Process Map	30

Figure 21: Camera Contamination Example	31

Figure 22: Technician Presenting Open Camera Lens Outside of Laminar Flow Cabinet	32

Figure 23: Technician Unboxing Camera on Workbench	33

Figure 24: Untidy Laminar Flow Cabinet	34

Figure 25: Dirty Laminar Flow Cabinet Filter	34

Figure 26: Damaged Coating on Camera Thread Reducer	35

Figure 27: Maintained Laminar Flow Cabinet	37

Figure 28: Weekly Technician Check Sheet	37

Figure 29: Stereomicroscope	38

Figure 30: Rubber Tipped Forceps (Buy Beadsmith Haemostats Clamp Coated Jaw, 2023)	38

Figure 31: Old Tightening Tool	39

Figure 32: Redesigned Tightening Tool	39

Figure 33: Positive Pressure Room Proposal	42

Figure 34: Individual Charts Constants (Tables of constants for Control Charts, No Date)	45

Figure 35: Severity Rankings (Ghasemian & Zeeshan, 2017)	46

Figure 36: Occurence Rankings (Ghasemian & Zeeshan, 2017)	46

Figure 37: Detection Rankings (Ghasemian & Zeeshan, 2017)	47

Figure 38: Laminar Flow Quotation	52

# Introduction

The company in question manufacture instruments in the drug discovery pathway. The first step in this pathway is to use microplate readers, used to detect the concentration of a certain compound in a sample. Light is passed through the sample containing a drug and the amount of light absorbed indicates the concentration of the compound in the sample. The next stage is to use Live Cell Imaging equipment to observe the interaction between drug and pathogen.

This project focusses on the Live Cell Imaging instrument, where contamination of the imaging camera represents a risk to the customer from poor image quality and incurs a significant amount of downtime from cleaning operations on site. Using the DMAIC process improvement methodology, the objective of this project is to reduce camera contamination and its associated downtime.

# Define

## Project Charter

Figure 1: Project Charter 1/3

Figure 2: Project Charter 2/3

Figure 3: Project Charter 3/3

## Voice of the Customer/Critical to Quality

Table 1: Voice of the Customer/Critical to Quality

## Stakeholder Analysis

Table 2: Stakeholder Analysis

# Measure

An effective sampling plan will ensure that there are repeatable metrics to compare the results of implemented measures to the original benchmark. Based on the Process Flow Roadmap and Stakeholder Analysis meetings, the Subassembly and Instrument Test phase were defined as areas of importance. This is due to the Cameras being built and sealed in the subassembly phase, meaning that the risk of contamination is likely induced at that point.

The data type for the camera subassembly timings is continuous and quantitative due to it being related to time and can be counted and not in whole integers. The test phase downtime is Binomial, discrete, and quantitative. I.e., it has a pass-fail specification of if there is contamination present or not. Camera contamination rework downtime is also included to capture the extent of the failures and adds a layer to investigate should a 0% First Time Through rate (FTT) occur.

To establish the sampling quantity, Bayes Success Run Theorem was employed with a confidence and reliability level of 80% selected. This was deemed appropriate as the risk of the data being inaccurate, carries a relatively small risk as the consequence of inaccuracies is the timing data being askew. There is no increased risk of the customer as the existing methodology for finding and rejecting cameras due to contamination is robust.

Where:
ln = natural log
n = Sample size
C = Confidence level
R = Reliability

n=ln⁡(1-C)ln⁡(R)

n=ln⁡(1-0.8)ln⁡(0.8)

n=7.21

Using the sample size equation above (Durivage, 2016), the figure should always be rounded up to the nearest whole integer (Luko, 1997). Resulting in a sample size of 8, a feasible timeframe-based instrument production throughput.

Subassembly timings will be taken from fixed points to minimise measurement variation. Instrument contamination during the test phase will be measured by the Technicians using the Quality, Cost, and Delivery (QCD) downtime tracker. To minimise measurement variation, the technicians were informed of the fixed points in which their timing measurements should be taken to ensure data reliability.

## Data Collection Plan

- Subassembly

- The time taken to assemble one camera unit.

- Frame assembly is collected, 45-degree angle block is removed, and mirror is glued to the block (24-hour cure). Once cured, assembly is built then stored in its location in a sealed, plastic box and backflushed.

- Define start/finish for data collection (SOP). Operator training conducted.

- Start time - from the point of materials arriving to technician after mirror gluing and curing time.

- Finish time - Once complete, boxed assembly on shelf and backflushed.

- Sampling plan = 8

- Bayes Success Run Theorem N = 8, 80% reliability and 80% confidence that the results are correct.

- Instrument Test

- The time taken to remove contamination from camera(s) after first detection.

- Instrument is received by test technician; they start instrument test, check for image contamination, contamination is found, source of contamination identified, cameras cleaned, the instrument optical pathway is realigned, and instrument test procedure can be restarted.

- Define start/finish for data collection (SOP). Operator training conducted.

- Start time – When the source of contamination is identified as the camera(s)

- Finish time – Once the technician is ready to re-start instrument test after realignment of instrument optical pathway.

- Sampling plan = 8

- Bayes Success Run Theorem N = 8, 80% reliability and 80% confidence that the results are correct.

## Collected Data

### Camera Subassembly

Table 3: Camera Subassembly Timings

### Instrument Test

Table 4: Instrument Test Downtime

### Historical Scrap Data Collection

Historical scrap data also had to be recorded. As it cannot be planned for when camera

Table 5: Camera Rejects

rejects will occur, a data collection plan cannot be produced Therefore, historical scrap data from 2021-2023 was compiled to gather the reject data.

## Measurement System Analysis

A Measurement System Analysis (MSA) can be undertaken to ensure the methods used for gathering data are suitable. A Kappa is used to evaluate attribute, pass/fail type data, requiring a minimum of 40 sample items Maxey et al. (2004). As there was 0% First Time Through (FTT), the data types are not applicable to this method.

A Gauge R&R (Repeatability and Reproducibility) study is used for continuous data. However, this methodology suits larger sample sizes and is typically used to compare results with different variables applied. Such as, the environment and operators. Since the purpose of this project is to establish the extent of the effect of contamination in terms of downtime, a Gauge R&R does not apply.

# Analyse

## Normality Anderson Darling Tests

Figure 4: Normal Probability Plot for Subassembly Timings

The timings indicate a normal distribution of results as the p value is greater than 0.05. Identifying the data’s Normality type, shows what statistical analysis tools are used as they will differ if the distribution is normal or not normal.

Figure 5: Normal Probability Plot for Testing Downtime

## Process Capability Analysis (CPK)

### Subassembly Timings

The CPK distribution’s nominal was selected from the manufacturing database routing time of 0.96 hours. A USL and LSL (Upper and Lower Specification Limits) were set at +/- 10 times the routing time resolution of 36 seconds.

Figure 6: Capability Analysis of Subassembly Timings 1

Using the routing timings as the nominal far exceeds the actual measured timings giving no process capability insight. A nominal was based on the mean of the measured timings with the same USL and LSL range.

Figure 7:Capability Analysis of Subassembly Timings 2

Figure 8: Capability Analysis of Test Downtime

Test Downtime

## Control Charts

An X-mR chart was selected to visualise continuous, variable data over time from data sets with a subgroup size of 1. The Centre Line, UCL and LCL formulae and Shewhart’s constants that are dependent on the subgroup size were used, as in Appendix A. (Stamatis, 2003; Rahardja, 2014; Grey, 2019; Woolf et al., 2023)

The defined UCL and LCL for X̄-R charts are +/- 3σ from the centreline (Grey, 2019; Hessing, 2023). These were not utilised as a subgroup of 2 – 9 is required to calculate the range of each subgroup which is not applicable to the data collected.

Figure 9: X Chart for Subassembly Timings

Subassembly Timings

Figure 10: mR Chart for Subassembly Timings

It is expected to see narrower Specification Limits as they are user defined. Whereas the Control Limits are calculated from the chart’s data points. Using Control Charts highlight out of control processes by showing timings exceeding the Specified Limits or visible trends, characterised by seven consecutive points on the same side of the centre line or continuously moving positively or negatively (Kiemele et al., 2000). Although, such trends may only become apparent with continuous monitoring and a larger sample size.

Test Downtime

Figure 11: X Chart for Test Downtime

Figure 12: mR Chart for Test Downtime

## Camera Rejects

### Pareto

To visualise the reject data, a Pareto diagram was utilised to identify how many of the camera rejects are due to contamination.

Figure 13: Defects Pareto for Camera Rejects

Figure 14: Variable Defects Pareto for Camera Rejects

The diagrams highlight that the highest frequency failure is contamination. Although, an oversight of the dataset is that: “Marked Window When Cleaning” is a cleaning measure due to contamination. Furthermore, the 8 contamination rejections do not show if the faults are internal or external failures. Therefore, a Variable Pareto diagram was also used to ascertain if rejects are internally or externally borne and who bears the financial onus of repairs.

Figure 15: Camera Rejects Variable as Supplied

Figure 16: Camera Rejects Variable in House

# Improve

## Generating Improvement Alternatives

To generate methods on how to reduce camera contamination occurrences in the test phase, a Brainstorming session with the key stakeholders was conducted where the comments and observations were fed into an Ishikawa Analysis. The points gathered were fed into a Process Failure Mode Effect Analysis. The scoring based on guidance from Chin et al (2009) and Ravi Sankar and Prabhu (2001), Appendix B. For example, point 3 of the PFMEA relates to camera windows being scratched during cleaning, as there was a failure rate of 2 in 25, or 8% this returned an Occurrence score of 7.

### Ishikawa Analysis

Figure 17: Ishikawa Analysis

Table 6: PFMEA

PFMEA

### Ishikawa/PFMEA Analysis

Figure 18: Ishikawa/PFMEA Analysis

## Value Stream Mapping

Value Stream Mapping (VSM) is typically used in the Define phase for scoping a project. It can also be used during the Measure phase to outline the current and future state of processes. These maps will observe the increase in camera subassembly timings from process changes compared to the decrease in instrument test downtime. A SIPOC also provides an overview of a process, as the acronym suggests, Suppliers, Inputs, Process, Outputs and Customers (MacNeil, 2024). However, these methods are too meticulous for this project, requiring significant time investment. Furthermore, items such as Time (C/T), Setup Time (S/T) and Uptime required for a VSM (Nallusamy and Ahamed, 2017), were not measured or in the scope of the data collection plan.  Therefore, a Current State and Future State Process Flow Map was produced to highlight process changes.

Figure 19: Current State Process Map

Current State
Future State

Figure 20: Future State Process Map

## Improvement Opportunities

There were seven key points highlighted from the PFMEA and Ishikawa analysis to focus on:

### 1 Reduce Subjectivity

Missing contamination during testing poses a high risk to the customer, thus scored highly in the PFMEA. In Figure 21, the dark contamination circled in yellow is pronounced and seldom overlooked. However, this is less of a risk to the customer than the contamination circled orange which also fails specification and is in the Region of Interest (ROI) where the customer will conduct their imaging. This contamination type can be missed by using dirty computer monitors that hiding contamination or draw the eye to other areas of the image.

Figure 21: Camera Contamination Example

### 2 Improve Subassembly Procedure

Upon review and the results of the brainstorming sessions and observation of the camera subassembly procedure, the issues of note were:

- Technicians were not using the Laminar Flow cabinets during subassembly, Figure 22.

- The technician was not concentrating air dusting to the camera lens, the area of interest.

- There is no pre-subassembly check of the cameras for contamination.

Figure 22: Technician Presenting Open Camera Lens Outside of Laminar Flow Cabinet

### 3 Improve Test Procedure

Reducing downtime from cleaning contaminated cameras, will be controlled at source during the subassembly procedure. Furthermore, the Reducing Subjectivity opportunity highlights a disparity in technician methods of contamination analysis, due to the variation in technician training

### 4 Remove Cardboard

Cardboard is a key contributor to dust particles in clean manufacturing environment (Munro, 2019; Berestina and Bakhvalov, 2021). The cameras were delivered lineside in cardboard boxes and decanted as in Figure 23.

To benchmark the extent of the issue, environmental particle counts were taken in key areas in the manufacturing area, shown in Appendix C.

Figure 23: Technician Unboxing Camera on Workbench

### 5 5S Areas

Upon visual inspection, the Laminar Flow cabinet was unmaintained as in Figure 24, the air filter was caked in dust, Figure 25, and the build area was cluttered. A particle count test was conducted, that highlighted a failure.

Figure 24: Untidy Laminar Flow Cabinet

Figure 25: Dirty Laminar Flow Cabinet Filter

### 6 Check Incoming Stock

As the Pareto charts highlighted in Figure 15, some contamination rejects are manufacturer borne, and are only identified hours into the test phase. There is no current process defined step to check incoming stock quality.

### 7 Review Tooling

As per Figure 16, 2 rejects in 2023 result from camera windows being scratched by metal forceps, holding lens tissue, used during cleaning.
Observation of the subassembly procedure shows specialised tooling is damaging coated surfaces as in Figure 26, subsequently contaminating the camera lens.

Figure 26: Damaged Coating on Camera Thread Reducer

# Control

To reduce causes of variation, leading to significant downtime during the test phase, a control strategy was developed. Error proofing methods are characterised by prevention and detection.

### Prevention

#### 2 Improve Subassembly Procedure

A revised subassembly SOP will be introduced, detailing the use of Laminar Flow cabinets and detail specific cleaning activities, with the key changes being trained to the technician. The subassembly build time will increase after implementation of additional process steps. This increase will be justified by the reduction in testing downtime and monitored by additional timings and evaluation of its control chart.

#### 3 Improve Test Procedure

AI image analysis of contamination will make the process more robust and increase throughput. The testing procedure improvement will be sustained by monthly QCD evaluations. After the control measures are introduced, a decline in contamination downtime is expected. Should an upward trend or special causes be observed from the Control Charts, the 5-Why root cause analysis tool will be used.

#### 4 Remove Cardboard

To reduce cardboard dust, decanting of components must be done off-line, and the SOP defined use of the Laminar Flow cabinet will filter out environmental particulates creating a segregated environment.

#### 5 5S Areas

The Laminar Flow cabinet was cleared with technician assistance. Unnecessary items were Red Tagged and kept off-line, and the cabinet filter was replaced, Figure 27. A technician was nominated to keep the area clean, focussing on checks including running weekly particle counts, which now have zero particulates of any size. Figure 28.

Figure 27: Maintained Laminar Flow Cabinet

Figure 28: Weekly Technician Check Sheet

#### 6 Check Incoming Stock

An SOP defined process step where the cameras are checked for contamination will be added into subassembly process prior to building activities validated using a stereomicroscope, Figure 29. The microscope will be kept inside the laminar flow cabinet reducing the ingress of contaminants.

Figure 29: Stereomicroscope

#### 7 Review Tooling

Camera windows being scratched from cleaning operations is reduced from replacing the metal forceps with rubber tipped variants. Fig 30.

Figure 30: Rubber Tipped Forceps (Buy Beadsmith Haemostats Clamp Coated Jaw, 2023)

Furthermore, the 3D-Printed Camera tightening tool, was redesigned to ensure that the damage occurring to the coated parts from the protrusion in Figure 31, is removed, as in Figure 32.

Figure 31: Old Tightening Tool

Figure 32: Redesigned Tightening Tool

### Detection

#### 1 Reduce Subjectivity

There is significant awareness around technician subjectivity and its control is encompassed by an ongoing software project due to be delivered in July 2024. The software utilises Artificial Intelligence (AI) for image analysis and detects contamination faster and to a finer degree than the technicians, removing subjectivity.

### Cost-Benefit Analysis

As many of the required parameters of a full cost-benefit analysis are not available. S simplistic calculation of the main potential costs and benefits was produced. Li and Pizer (2021) state that industry used discount rates are either 3% or 7%. As the discount rates are not known for the company, 7% was used demanding higher returns.

Using the calculation methods outlined by Stobierski (2019) and Thakur (2023). The Cost-Benefit analysis produced a ratio of 2.79. A figure higher than 1 indicates that the project is worth undertaking based on the expected returns.

Table 7: Cost Benefit Analysis

Control Plan

Table 8: Control Plan

### Future Recommendations

#### Test Fixtures

The use of the Stereomicroscope has an element of subjectivity and is not able to analyse relative intensity of particles. Using Poka-Yoke error proofing method, a test fixture that takes an image using the camera can utilise the automatic image analysis software and can be fed directly into the test procedure stage, removing the additional non-value-added process step of double handling data. Furthermore, taking an image in this manner will help to error-proof the process by highlighting supply issues of Dark and Hot Pixels.

#### SOP Update Findings

Using the stereomicroscope inside Laminar Flow cabinet and the camera assembly batch size being increased to 4 resulted in the Laminar Flow cabinet not being large enough to conduct subassembly activities. The supplier has provided a quote for a larger, dedicated cabinet, Appendix D, reducing risk of contamination of from other, uncontrolled processes. Its purchase is awaiting the result of Capex funding acceptance.

#### Cardboard Elimination

Figure 33: Positive Pressure Room Proposal

As the environmental particle count is high, a project to eliminate cardboard entering the manufacturing environment is ideal. However, the enormity of the task, including changing how goods are delivered lineside and stored is understood. The recommendation given, is to produce a clean area. This area will house all laminar flow cabinets where no cardboard may enter, and all assemblies are sealed before exiting. Figure 33.

# References

(No date) Tables of constants for Control Charts. Available at: https://web.mit.edu/2.810/www/files/readings/ControlChartConstantsAndFormulae.pdf (Accessed: 20 April 2024).

Berestina, A.V. and Bakhvalov, A.V. (2021) ‘Monitoring of microbial contamination of the Educational and Scientific Cleanroom Facility’, Microbiology Independent Research Journal (MIR Journal), 8(1). doi:10.18527/2500-2236-2021-8-1-18-26.

Buy Beadsmith hemostat clamp coated jaw (2023) Maddisons UK. Available at: https://maddisonsofdurham.co.uk/jewellers-tools/beading-jewellers-tools/view-all-beading/beadsmith-hemostat-clamp-coated-jaw/ (Accessed: 19 April 2024).

Chin, K.-S. et al. (2009) ‘Failure mode and effects analysis using a group-based Evidential Reasoning Approach’, Computers &amp; Operations Research, 36(6), pp. 1768–1779. doi:10.1016/j.cor.2008.05.002.

Cost-benefit analysis (CBA) (2024) Wall Street Prep. Available at: https://www.wallstreetprep.com/knowledge/cost-benefit-analysis/#:~:text=Conceptually%2C%20the%20cost-benefit%20analysis%20ratio%20should%20exceed%201.0,that%20implies%20the%20expected%20benefits%20outweigh%20the%20costs. (Accessed: 21 April 2024).

Durivage, M. (2016) How to establish sample sizes for process validation using the success-run theorem, How To Establish Sample Sizes For Process Validation Using The Success-Run Theorem. Available at: https://www.bioprocessonline.com/doc/how-to-establish-sample-sizes-for-process-validation-using-the-success-run-theorem-0001 (Accessed: 24 March 2024).

Ford Motor Company (2008) Potential failure mode and effects analysis (FMEA): Reference manual. Erscheinungsort nicht ermittelbar: Chrysler LLC.

Ghasemian, H. and Zeeshan, Q. (2017) ‘Failure Mode and Effect Analysis (FMEA) of  Aeronautical Gas Turbine using the Fuzzy Risk  Priority Ranking (FRPR) Approach’, International Journal of Soft Computing and Engineering, 7(1), pp. 81–92. doi:2231-2307.

Grey, K. (2019) XMR chart: Step-by-step guide by hand and with R: R-bar, R-Bar. Available at: https://r-bar.net/xmr-control-chart-tutorial-examples/ (Accessed: 01 April 2024).

Guerriero, C. and Pacelli, A. (2020) ‘Discounting benefits and costs’, Cost-Benefit Analysis of Environmental Health Interventions, pp. 129–143. doi:10.1016/b978-0-12-812885-5.00007-x.

Hessing, T. (2023) Control Charts Study Guide, Six Sigma Study Guide. Available at: https://sixsigmastudyguide.com/control-charts-study-guide/ (Accessed: 08 April 2024).

Kiemele, M.J., Schmidt, S.R. and Berdine, R.J. (2000) ‘Graphical and Measurement Tools’, in Basic statistics: Tools for Continuous Improvement. Colorado Springs, CO: Air Academy Press, pp. 35–35.

Li, Q. and Pizer, W.A. (2021) Discounting for public benefit-cost analysis, Resources for the Future. Available at: https://www.rff.org/publications/issue-briefs/discounting-for-public-benefit-cost-analysis/ (Accessed: 21 April 2024).

Luko, S.N. (1997) ‘Attribute reliability and the success run: A Review’, SAE Technical Paper Series [Preprint]. doi:10.4271/972753.

MacNeil, C. (2024) The secret to Visualizing Your Business Processes, Asana. Available at: https://asana.com/resources/sipoc-diagram (Accessed: 12 April 2024).

Maxey, J. et al. (2004) The lean six sigma pocket toolbox. McGraw-Hill.

McDermott, R.E. (2009) Basics of FMEA.

Munro, D. (2019) ‘Working in a Cleanroom’, in DIY MEMS. Springer, Cham, pp. 21–30.

Nallusamy, S. and Ahamed, A. (2017) ‘Implementation of Lean Tools in an automotive industry for Productivity Enhancement - A case study’, International Journal of Engineering Research in Africa, 29, pp. 175–185. doi:10.4028/www.scientific.net/jera.29.175.

Rahardja, D. (2014) ‘Comparison of individual and moving range chart combinations to individual charts in terms of ARL after designing for a common “all OK” ARL’, Journal of Modern Applied Statistical Methods, 13(2), pp. 364–378. doi:10.22237/jmasm/1414815480.

Ravi Sankar, N. and Prabhu, B.S. (2001) ‘Modified approach for prioritization of failures in a system failure mode and effects analysis’, International Journal of Quality &amp; Reliability Management, 18(3), pp. 324–336. doi:10.1108/02656710110383737.

Stamatis, D.H. (2003) Six sigma and beyond: Statistical process control. Boca Raton, FL: St. Lucie Press.

Stobierski, T. (2019) Cost-benefit analysis: What it is & how to do it, Business Insights Blog. Available at: https://online.hbs.edu/blog/post/cost-benefit-analysis (Accessed: 21 April 2024).

Thakur, M. (2023) Cost benefit analysis formula: Calculator (example with Excel template), EDUCBA. Available at: https://www.educba.com/cost-benefit-analysis-formula/ (Accessed: 21 April 2024).

Woolf, P. et al. (2023) ‘SPC- Basic Control Charts- Theory and Construction, Sample Size, X-Bar, R charts, S charts’, in Chemical Process Dynamics and Controls. Ann Arbor, Michigan: LibreTexts Engineering.

# Appendices

## Appendix A

Figure 34: Individual Charts Constants (Tables of constants for Control Charts, No Date)

## Appendix B

Figure 35: Severity Rankings (Ghasemian & Zeeshan, 2017)

Figure 36: Occurence Rankings (Ghasemian & Zeeshan, 2017)

Figure 37: Detection Rankings (Ghasemian & Zeeshan, 2017)

## Appendix C

Table 9: March Particle Readings

| Date | Time | Particle size | Position 1 | P.P. rack | Position 2 | Centre | Position 3 | Subs rack |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Σ | Δ | Σ | Δ | Σ | Δ |
| 01/03/2024 | 10:45 | 0.5 | 493,347 | 451,322 | 599,997 | 524,777 | 622,599 | 545,260 |
|  |  | 2.5 | 42,025 | 34,962 | 75,220 | 54,737 | 77,339 | 58,975 |
|  |  | 5 | 7,063 | 7,063 | 20,483 | 20,483 | 18,364 | 18,364 |
| 04/03/2024 | 11:20 | 0.5 | 318,539 | 297,703 | 408,945 | 363,063 | 412,123 | 369,039 |
| Monday |  | 2.5 | 20,836 | 16,598 | 45,909 | 40,259 | 43,084 | 37,787 |
|  |  | 5 | 4,238 | 4,238 | 5,650 | 5,650 | 5,297 | 5,297 |
| 05/03/2024 | 10:15 | 0.5 | 515,242 | 483,459 | 506,766 | 466,154 | 507,473 | 472,158 |
|  |  | 2.5 | 31,783 | 25,426 | 40,612 | 31,078 | 35,315 | 28,252 |
|  |  | 5 | 6,357 | 6,357 | 9,575 | 9,575 | 7,063 | 7,063 |
| 06/03/2024 | 10:00 | 0.05 | 897,347 | 827,777 | 862,739 | 797,054 | 888,165 | 840,490 |
|  |  | 2.5 | 69,570 | 53,678 | 65,685 | 51,912 | 47,675 | 39,493 |
|  |  | 5 | 15,892 | 15,892 | 13,773 | 13,773 | 9,182 | 9,182 |
| 07/03/2024 | 10:00 | 0.05 | 783,987 | 746,553 | 563,623 | 515,948 | 840,844 | 785,400 |
|  |  | 2.5 | 37,494 | 30,371 | 47,675 | 37,081 | 55,444 | 46,615 |
|  |  | 5 | 7,063 | 7,063 | 10,594 | 10,594 | 8,829 | 8,829 |
| 08/03/2024 | 13:10 | 0.05 | 993,050 | 946,788 | 1,387,162 | 1,331,718 | 1,397,578 | 1,355,732 |
|  |  | 2.5 | 46,262 | 42,731 | 55,444 | 49,087 | 38,846 | 38,668 |
|  |  | 5 | 3,531 | 3,531 | 6,357 | 6,357 | 3,178 | 3,178 |
| 11/03/2024 | 11:15 | 0.05 | 652,969 | 614,123 | 1,100,760 | 1,027,305 | 999,407 | 927,365 |
| Monday |  | 2.5 | 38,846 | 28,605 | 73,455 | 60,389 | 72,042 | 58,622 |
|  |  | 5 | 10,241 | 10,241 | 13,066 | 13,066 | 13,420 | 13,420 |
| 12/03/2024 | 10:00 | 0.05 | 440,375 | 423,777 | 694,287 | 642,374 | 685,459 | 638,490 |
|  |  | 2.5 | 16,598 | 15,539 | 51,913 | 40,259 | 46,969 | 37,787 |
|  |  | 5 | 1,059 | 1,059 | 11,654 | 11,654 | 9,182 | 9,182 |
| 13/03/2024 | 10:05 | 0.05 | 282,518 | 252,147 | 581,280 | 531,133 | 570,686 | 523,011 |
|  |  | 2.5 | 30,371 | 24,014 | 50,147 | 41,671 | 47,675 | 38,846 |
|  |  | 5 | 6,357 | 6,357 | 8,476 | 8,476 | 8,829 | 8,829 |
| 14/03/2024 | 10:00 | 0.05 | 496,172 | 454,854 | 823,539 | 760,679 | 734,899 | 673,805 |
|  |  | 2.5 | 41,318 | 33,549 | 62,860 | 54,031 | 61,094 | 52,265 |
|  |  | 5 | 7,769 | 7,769 | 8,829 | 8,829 | 8,829 | 8,829 |
| 15/03/2024 | 10:30 | 0.05 | 2,644,367 | 2,575,150 | 2,029,890 | 1,971,621 | 2,298,282 | 2,226,240 |
|  |  | 2.5 | 69,217 | 58,623 | 58,269 | 51,912 | 72,042 | 61,801 |
|  |  | 5 | 10,594 | 10,594 | 6,357 | 6,357 | 10,241 | 10,241 |
| 18/03/2024 | 10:00 | 0.05 | 369,392 | 349,969 | 520,539 | 487,343 | 450,969 | 402,941 |
| Monday |  | 2.5 | 19,423 | 15,185 | 33,196 | 25,780 | 48,028 | 37,080 |
|  |  | 5 | 4,238 | 4,423 | 7,416 | 7,416 | 10,948 | 7,416 |
| 19/03/2024 | 09:55 | 0.05 | 717,595 | 678,043 | 950,672 | 893,462 | 950,319 | 904,763 |
|  |  | 2.5 | 39,552 | 34,255 | 57,210 | 46,616 | 45,556 | 40,259 |
|  |  | 5 | 5,297 | 5,297 | 10,594 | 10,594 | 5,297 | 5,297 |
| 01/01/1900 | 10:10 | 0.05 | 296,644 | 237,668 | 336,549 | 301,587 | 311,829 | 262,742 |
|  |  | 2.5 | 58,976 | 43,438 | 34,962 | 27,899 | 49,087 | 38,493 |
|  |  | 5 | 15,538 | 15,538 | 7,063 | 7,063 | 10,594 | 10,594 |
| 21/03/2024 | 10:00 | 0.05 | 440,021 | 393,406 | 760,326 | 701,350 | 679,455 | 620,479 |
|  |  | 2.5 | 46,615 | 37,433 | 58,976 | 49,441 | 58,976 | 48,382 |
|  |  | 5 | 9,182 | 9,182 | 9,535 | 9,535 | 10,594 | 10,594 |
| 22/03/2024 | 10:30 | 0.05 | 1,161,854 | 1,125,833 | 1,350,435 | 1,293,931 | 1,649,551 | 1,590,222 |
|  |  | 2.5 | 36,021 | 31,430 | 56,504 | 48,028 | 59,329 | 51,209 |
|  |  | 5 | 4,591 | 4,591 | 8,476 | 8,476 | 8,122 | 8,122 |
| 25/03/2024 | 10:05 | 0.05 | 506,413 | 452,028 | 606,001 | 535,372 | 719,008 | 616,948 |
| Monday |  | 2.5 | 54,385 | 40,612 | 70,629 | 57,209 | 102,060 | 78,752 |
|  |  | 5 | 13,773 | 13,773 | 13,420 | 13,420 | 23,308 | 23,308 |
| 26/03/2024 | 11:00 | 0.05 | 756,441 | 713,359 | 776,571 | 716,183 | 586,224 | 527,955 |
|  |  | 2.5 | 43,084 | 38,493 | 60,388 | 50,853 | 58,268 | 49,087 |
|  |  | 5 | 4,591 | 4,591 | 9,535 | 9,535 | 9,182 | 9,182 |
| 27/03/2024 | 10:50 | 0.05 | 240,846 | 211,182 | 353,500 | 324,189 | 383,165 | 351,382 |
|  |  | 2.5 | 29,664 | 24,014 | 29,311 | 21,542 | 31,783 | 24,720 |
|  |  | 5 | 5,650 | 5,650 | 7,769 | 7,769 | 7,063 | 7,063 |
| 28/03/2024 | 10:30 | 0.05 | 289,934 | 258,504 | 278,986 | 245,790 | 288,874 | 256,031 |
|  |  | 2.5 | 31,430 | 24,014 | 33,196 | 25,780 | 32,843 | 25,427 |
|  |  | 5 | 7,416 | 7,416 | 7,416 | 7,416 | 7,416 | 7,416 |

Table 10: April Particle Readings

| Date | Time | Particle size | Position 1 | P.P. rack | Position 2 | Centre | Position 3 | Subs rack |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Σ | Δ | Σ | Δ | Σ | Δ |
| 02/04/2024 | 10:00 | 0.05 | 345,373 | 309,357 | 359,151 | 326,661 | 321,717 | 289,581 |
|  |  | 2.5 | 36,021 | 29,311 | 32,490 | 26,486 | 32,136 | 27,545 |
|  |  | 5 | 6,710 | 6,710 | 6,004 | 6,004 | 4,591 | 4,591 |
| 03/04/2024 | 10:00 | 0.05 | 357,385 | 316,420 | 502,529 | 446,732 | 451,322 | 410,710 |
|  |  | 2.5 | 40,965 | 27,192 | 55,797 | 42,024 | 40,612 | 33,902 |
|  |  | 5 | 13,773 | 13,773 | 13,773 | 13,713 | 6,710 | 6,710 |
| 04/04/2024 | 10:00 | 0.05 | 851,085 | 793,875 | 941,491 | 882,869 | 905,116 | 850,731 |
|  |  | 2.5 | 57,210 | 52,619 | 58,622 | 50,500 | 54,385 | 48,735 |
|  |  | 5 | 4,591 | 4,591 | 8,122 | 8,122 | 5,650 | 5,650 |
| 05/04/2024 | 10:00 | 0.05 | 1,240,253 | 1,192,225 | 1,770,680 | 1,718,414 | 1,981,862 | 1,925,712 |
|  |  | 2.5 | 48,028 | 41,318 | 52,266 | 46,969 | 56,150 | 51,912 |
|  |  | 5 | 6,710 | 6,710 | 5,297 | 5,297 | 4,238 | 4,238 |
| 08/04/2024 | 10:10 | 0.05 | 814,242 | 739,490 | 1,067,211 | 985,987 | 1,024,480 | 969,389 |
| Monday |  | 2.5 | 78,752 | 54,385 | 81,224 | 67,804 | 55,091 | 46,615 |
|  |  | 5 | 24,367 | 24,367 | 13,420 | 13,420 | 8,476 | 8,476 |
| 09/04/2024 | N/A |  |  |  |  |  |  |  |
| 10/04/2024 | 10:00 | 0.05 | 586,378 | 542,081 | 823,893 | 768,802 | 891,364 | 827,777 |
|  |  | 2.5 | 44,497 | 31,431 | 55,091 | 44,143 | 63,567 | 53,328 |
|  |  | 5 | 13,066 | 13,066 | 10,948 | 10,948 | 10,241 | 10,241 |
| 11/04/2024 | 10:00 | 0.05 | 902,291 | 834,487 | 980,690 | 900,526 | 994,110 | 911,120 |
|  |  | 2.5 | 67,804 | 58,975 | 80,164 | 66,038 | 82,490 | 65,686 |
|  |  | 5 | 8,829 | 8,829 | 14,126 | 14,126 | 17,304 | 17,304 |
| 12/04/2024 | 10:00 | 0.05 | 1,215,180 | 1,135,016 | 1,383,984 | 1,203,113 | 1,429,893 | 1,341,606 |
|  |  | 2.5 | 80,164 | 68,510 | 80,871 | 71,689 | 88,287 | 77,693 |
|  |  | 5 | 11,654 | 11,654 | 9,182 | 9,182 | 10,594 | 10,594 |
| 15/04/2024 | 10:00 | 0.05 | 694,641 | 665,683 | 753,616 | 717,948 | 813,298 | 767,036 |
| Monday |  | 2.5 | 28,958 | 22,954 | 35,668 | 29,311 | 46,262 | 38,140 |
|  |  | 5 | 6,004 | 6,004 | 6,357 | 6,357 | 8,122 | 8,122 |
| 16/04/2024 | 10:00 | 0.05 | 631,427 | 591,168 | 662,504 | 577,098 | 744,788 | 701,704 |
|  |  | 2.5 | 40,259 | 28,958 | 90,406 | 69,570 | 43,084 | 35,668 |
|  |  | 5 | 11,301 | 11,301 | 20,830 | 20,836 | 7,416 | 7,416 |
| 17/04/2024 | 10:00 | 0.05 | 423,777 | 392,700 | 461,563 | 404,353 | 528,308 | 478,867 |
|  |  | 2.5 | 31,077 | 20,129 | 57,210 | 40,612 | 49,441 | 40,612 |
|  |  | 5 | 10,948 | 10,948 | 10,948 | 16,598 | 8,829 | 8,829 |
| 18/04/2024 | 10:15 | 0.05 | 247,909 | 218,951 | 300,175 | 262,741 | 327,721 | 292,406 |
|  |  | 2.5 | 28,958 | 23,308 | 37,434 | 30,371 | 35,315 | 29,665 |
|  |  | 5 | 5,650 | 5,650 | 7,063 | 7,063 | 5,650 | 5,650 |
| 19/04/2024 | 10:00 | 0.05 | 156,444 | 133,136 | 417,067 | 346,438 | 501,116 | 422,011 |
|  |  | 2.5 | 23,308 | 19,423 | 70,629 | 60,388 | 79,105 | 68,864 |
|  |  | 5 | 3,885 | 3,885 | 10,241 | 10,241 | 10,241 | 10,241 |
| 22/04/2024 | 10:05 | 0.05 | 997,994 | 892,756 | 1,510,764 | 1,372,683 | 1,367,442 | 1,219,064 |
| Monday |  | 2.5 | 105,238 | 87,934 | 138,081 | 127,840 | 143,378 | 132,077 |
|  |  | 5 | 17,304 | 17,304 | 10,241 | 10,241 | 11,301 | 11,301 |
| 23/04/2024 | 10:50 | 0.05 | 395,172 | 342,553 | 750,791 | 638,137 | 732,781 | 618,714 |
|  |  | 2.5 | 52,619 | 42,025 | 112,654 | 96,056 | 114,067 | 98,882 |
|  |  | 5 | 10,594 | 10,594 | 16,598 | 16,598 | 15,185 | 15,185 |
| 24/04/2024 | 10:00 | 0.05 | 570,333 | 531,134 | 687,225 | 635,812 | 740,903 | 678,749 |
|  |  | 2.5 | 39,199 | 73,195 | 51,913 | 42,025 | 62,154 | 50,147 |
|  |  | 5 | 6,004 | 6,004 | 9,888 | 9,888 | 12,007 | 12,007 |
| 25/04/2024 | 10:00 | 0.05 | 554,441 | 494,053 | 894,875 | 801,291 | 972,214 | 880,396 |
|  |  | 2.5 | 60,388 | 50,147 | 93,584 | 78,399 | 91,818 | 76,633 |
|  |  | 5 | 10,241 | 10,241 | 15,185 | 15,185 | 15,185 | 15,185 |
| 26/04/2024 | 10:40 | 0.05 | 1,060,501 | 882,162 | 953,144 | 773,039 | 932,309 | 757,148 |
|  |  | 2.5 | 178,339 | 143,731 | 180,105 | 150,087 | 175,161 | 146,909 |
|  |  | 5 | 34,608 | 34,608 | 30,018 | 30,018 | 28,252 | 28,252 |

## Appendix D

Figure 38: Laminar Flow Quotation