## Products and Tasks
Stage Number | Stage Description | Products | Individual(s)/Team Responsible for Product | Product Quality Criteria | Tasks | Start date | Duration | Review Point | Tolerance
Stage 1 | Project Start-Up | 1. Project Proposal | 1. PM/PO (Project Team). Project Executive to be involved for final decision-making. | 1.1. Chartered Institute for Archaeologists (CiFA), 2020. Standard and guidance for historic environment desk-based assessment. 1.2. Historic England, 2014. Management of Research Projects in the Historic Environment. 1.3. Headland Archaeology, 2020. Report Production. | 1.1. Document Aims and Objectives of the Business Case. 1.2. Estimate time and resources for the potential project. | 2022-11-21 | 5 days | R1. Start-Up closure. Decision of how and where to allocate resources for Initiation Stage. Assessment of Project Proposals from potential contractors. | Time: +/- one day Cost: +/- £200 Quality: This is an initial assessment; to be kept brief
Stage 2 | Project Design | 2. Written Scheme of Investigation 3. Risk Log 4. Risk Assessment and Health and Safety Statement | 2. Project Team. 3. Project Team. 4. Project Team to liaise with SHEQ team. | 2.1. CiFA 2020. 2.2. Historic England, 2014. 2.3. Headland Archaeology, 2020. 3.1. Historic England, 2014. 4.1. Internal Headland Archaeology Safety, Health, Environment and Quality (SHEQ) documents | 2.1. Identify Aims and Objectives of the project. 2.2. Read associated prior research of site (see evaluation) 3.1. See past research for excavating conditions. 3.1 and 4.1. Conduct site visit. | 2022-11-28 | 10 days | R2. Initiation closure. Decision to be made on whether or not project will proceed on the basis of the Project Design. One week. | Time: +/- three days Cost: +/- £600 Quality: PM to oversee the work of the PO and ensure that Project Design is concise.
Stage 3 | Archaeological Fieldwork | 5. Assembly of site archive begins. 6. Updated Project Design (if applicable) 7. Highlight Report(s) 8. Updated Risk Log (if applicable) | 5. Project and Site Team to liaise with Archive department as led by JF. 6. Project Team to liaise with Site Team. 7. Project Team. 8. Project Team to liaise with Site Team. | 5.1. CiFA, 2020. Standard and guidance for the creation, compilation, transfer and deposition of archaeological archives. 5.1. CiFA, 2019. Codes of Conduct. | 5.1. Site preparation. 5.2 Fieldwork. 6.1 Update Project Design (if applicable). 7.1. Compile Highlight Reportat end of Execution Stage. 8.1 Update Risk Log (if applicable) | 2023-01-04 | 97 days | R3.1 Review of Aims and Objectives and the Business Case, Updated Project Design (if applicable), assessment of resources, issues, progress with archive preparation and deposition, lessons learned. Two weeks. | Time: +/- two weeks Cost: +/- £2000 Quality: appropriate excavation, sampling, finds collection to be undertaken. See Risk Log for potential delays.
Stage 4 | Assessment of Data Potential | 9. Archive accessed. 10. Sampling approach agreed. 11. Materials undertaken/sent out for specialist analysis. | 9. Project Team to liaise with Archive department. 10. Project Team to liaise with Environmental department as led by KT. 11. Project Team to liaise with Finds department as led by JF. | 9. CiFA, 2020. 10. Historic England, 2011. Environmental Archaeology. 11. CiFA, 2019. | 9. Report on potential. Allocation of resources for Analysis stage. 10. Liase with the Environmental team. 11. Communication with internal/external specialists. | 2023-05-24 | 35 days | R3.2. Review of Aims and Objectives and the Business Case, Updated Project Design (if applicable), assessment of resources, issues, progress with archive preparation and deposition, lessons learned. Decide upon further work or project closure. Two weeks. | Time: +/- one week Cost: +/- £1500 Quality: may be some Tolerance on the assessment of later and post-Medieval findings.
Stage 5 | Analysis | 12. Archive accessed. 13. Final report produced. | 12. Project Team to liaise with Archive department. 13. Project Team. | 12. See above. 13. See above. 14. Headland Archaeology, 2020. | 12. Analysis work on site materials undertaken by external and (mostly) internal specialists. 13. Organise data and reports from specialists. 14. Format final report. | 2023-07-10 | 60 days | R3.3. Review of Aims and Objectives and the Business Case, Updated Project Design (if applicable), assessment of resources, issues, progress with archive preparation and deposition, lessons learned. Two weeks. | Time: +/- two weeks Cost: +/- Quality: as above
Stage 6 | Archive Deposition | 14. Data archive deposited with archive holder. 15. Paper archive deposited. 16. Artefact and ecofact archive deposited with archive holder. | 14. Archive team. 15. Archive team. 16. Finds and Environmental teams to liaise with Archive department. | 14-16. Croft et al. 2020. Deposition of Archaeological Archives in Cambridge. Brown, 2011. Archaeological Archives: A guide to best practice in creation, compilation, transfer and curation. | 14. Digital housekeeping of data to current standards. 15. Ensuring appropriate acid-free storage of paper archive. 16. Ensuring artefacts and ecofacts are labelled and stored correctly. | 2023-10-10 | 60 days | R3.4. Review of Aims and Objectives and the Business Case, Updated Project Design (if applicable), assessment of resources, issues, progress with archive preparation and deposition, lessons learned. | Time: +/- two weeks Cost: +/- £1900 Quality: senior archivists to oversee finds bagging and archive storage to ensure standards are being followed. Museum standards not to be sacrificed for time.